## Summery
Reassure-Repairer
Lead Dev: Ajay Kumar
Module | No. of test Written | No. of test executed | Pass | Fail | Deferred
Login | 16 | 8 | 4 | 4 | 0
Complaint Page | 35 | 26 | 17 | 9 | 0
Case Status Update | 12 | 12 | 4 | 8 | 0
Total | 63 | 46 | 25 | 21 | 0

## Bug Report
Bug Report
Project :- |  | Reassure |  |  |  |  | Lead_Devp. :- |  | Ajay Kumar
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 10720
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
10720 | TC_Login_01 | 1 | Website does not get open at first attempt, when entering the url in the address bar and hitting Enter key and system shows blank page. Website gets open when user reload/refreshes the page. | Any particular browser is kept opened on the user's system and the internet connection in on and working. | 1)Type the website's address in the address bar. 2)Click on the "Go" button or press the Enter button of the keyboard. | URL:http://reassure.innov.co.in/ | Please refer to the attachment doc. | High | High | New
10720 | TC_Login_03 | 2 | Validation message for leaving Username field is not specific. It should be "Please Enter Username" | User is on the website's landing page and is registered to the website. | 1)Leave the Username field blank. 2)Enter valid password in the Password field. 3)Click on the "Login" button. | Password: admin | Please refer to the attachment doc. | Mid | Low | New
10720 | TC_Login_04 | 3 | Validation message for leaving Password field is not specific. It should be "Please Enter Password" | User is on the website's landing page and is registered to the website. | 1)Enter the valid username in the field provided. 2)Leave the password field blank. 3)Click on the Login button. | Username: admin | Please refer to the attachment doc. | Mid | Low | New
10720 | TC_Login_05 | 4 | Validation message for entering invalid data in username field is wrong. | User is on the website's landing page and is registered to the website. | 1)Enter invalid username in the field provided 2)Enter valid password in the field provided. 3)Click on the Login button. | Username: #@@@ | Please refer to the attachment doc. | Mid | Low | New
10720 | TC_Complaints_01 | 5 | There should not be an option to create Case Request. | User is already on home page. | 1)Click on Complaints option available under Side Menu. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Complaints_08 | 6 | System does not shows the filtered resulton the basis of searched Program name. | User is already on case requests page. | 1) Enter "Program Name." to be searched in the "Program Name" field. 2) Click on search button. | CPP ACK | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_09 | 7 | System does not shows the filtered resulton the basis of searched Case Number. | User is already on case requests page. | 1) Enter Case No. to be searched in the "Case No." field. 2) Click on search button. | 77865 | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_10 | 8 | System does not shows the filtered resulton the basis of searched Case Creation Date. | User is already on case requests page. | 1) Enter Case Creation Date to be searched in the "Case Creation Date" field. 2) Click on search button. | 01-02-2020 05:30:00 | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_11 | 9 | System does not shows the filtered resulton the basis of searched Ageing. | User is already on case requests page. | 1) Enter Ageing Date to be searched in the "Ageing" field. 2) Click on search button. | 11 | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_12 | 10 | System does not shows the filtered resulton the basis of searched Case Status. | User is already on case requests page. | 1) Enter Case Status to be searched in the "Case Status" field. 2) Click on search button. | Visit Scheduled | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_13 | 11 | System does not shows the filtered resulton the basis of searched Case Status. | User is already on case requests page. | 1) Enter any combination of fields to be searched in the respective fields. 2) Click on search button. | ACK+077865 | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_14 | 12 | Pdf file of selected Case Request is not getting download. | User is already on case requests page. | 1) Select the check box appearing against the Case Request to be downloaded. 2) Click on Download button. |  | Please refer to the attachment doc. | HIGH | HIGH | New
10720 | TC_Complaints_33 | 13 | User doesn't get move to the Approve Invoice section of the Case Request. | User is already on case requests page. | 1) Click on Approve Invoice available under Quick Links section. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Case_Status_Update_03 | 14 | The validation message appearing for leaving all the fields blank while submitting the case status update is wrong. | User is at case status update pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | Please refer to the attachment doc. | High | Low | New
10720 | TC_Case_Status_Update_04 | 15 | The validation message appearing for leaving all the field blank while submitting the case status update is wrong. | User is at case status update pop up. | 1) Leave Case Status field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  | Please refer to the attachment doc. | High | Low | New
10720 | TC_Case_Status_Update_05 | 16 | The validation message appearing for leaving the Reason for Cacellation field blank while submitting the case status update is wrong. | User is at case status update pop up. | 1) Leave Reason for Cancellation field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  | Please refer to the attachment doc. | High | Low | New
10720 | TC_Case_Status_Update_07 | 17 | 1)Duplicate dropdown value is appearing in the dropdown of the Reason for cancellation. 2) The dropdown values coming in Reason list when "Customer Not Available" selected in case status is not as per the Master. As Customer not Contactable should not be in the dropdown. | User is at case status update pop up. | 1) Selct Cancel as the case status 2)Click on the Reason for cancellation Dropdown. 3) Check the values of the dropdown and match it with the data from the master. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Case_Status_Update_08 | 18 | After submitting the case status update form successfully system shows confirmation message as " Successfully Updated" but its response of API has an error as "{"Status": "Case Cancelled", " aiz_claim_number": "06388614", "Cancellation_reason": "Area is out of coverage"}" | User is at case status update pop up. | 1) Enter valid details in all fields. 2)Click on submit button. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Case_Status_Update_09 | 19 | 1)The status should get change to Cancelled by Repairer immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) On refreshing the page after submitting the case status , system shows blank page. | User is at case status update pop up. | 1) Select Cancel as the case status. 2) Select valid reason. 3) Click on submit button. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Case_Status_Update_10 | 20 | 1)The status should get change to Customer Not Contactable immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) User is not able to submit the case status as Customer Not Contactable and system shows an error msg. 3) On refreshing the page after submitting the case status , system shows blank page. | User is at case status update pop up. | 1) Select Customer Not Contactable as the case status. 2) Select valid reason. 3) Click on submit button. |  | Please refer to the attachment doc. | High | High | New
10720 | TC_Case_Status_Update_11 | 21 | 1)The status should get change to Customer Not Available immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) User is not able to submit the case status as Customer Not Available and system shows an error msg. 3) On refreshing the page after submitting the case status , system shows blank page. | User is at case status update pop up. | 1) Select Customer Not Available as the case status. 2) Select valid reason. 3) Click on submit button. |  | Please refer to the attachment doc. | High | High | New
10720 | Suggestion_1 | 22 | Suggestion: There should be an option to reset/change the password. |  |  |  |  | High | High | New
10720 | TC_Visit_Schedule_03 | 23 | The validation message coming for leaving the fields blank has wrong field lables. The field lables appearing are name of the columns in database. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  | High | Low | New
10720 | TC_Visit_Schedule_04 | 24 | The validation message coming for leaving the Appointment date field blank is wrong , As there is a punctuation error. The validation message should be as " Appointment Date :Appointment Date is Required & It can not be empty." | User is already on case requests page. | 1) Leave the Appointment date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  | High | Low | New
10720 | TC_Visit_Schedule_05 | 25 | The validation message coming for leaving the Reason for Resecheduling field blank is wrong , As there is a punctuation error. The validation message should be as "Reason for Resecheduling :Reason for Resecheduling is Required & It can not be empty." | User is already on case requests page. | 1) Leave the Reason for Resecheduling field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  | High | Low | New
10720 | TC_Visit_Schedule_06 | 26 | The validation message coming for leaving the Appointment Time Slot field blank is wrong , As there is a punctuation error. The validation message should be as "Appointment Time Slot :Appointment Time Slot is Required & It can not be empty." | User is already on case requests page. | 1) Leave the Appointment Time Slot field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  | High | Low | New
10720 | TC_Visit_Schedule_07 | 27 | The validation message coming for leaving the Remark field blank is wrong , As there is a punctuation error. The validation message should be as "Remark : Remark is Required & It can not be empty." | User is already on case requests page. | 1) Leave the Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  | High | Low | New
10720 | TC_Visit_Schedule_08 | 28 | 1)The validation message coming for entering invalid data in Appointment date is wrong. 2) User should be able to select the Past date upto three days from current day but currenty this is not happeninig, | User is already on case requests page. | 1) Enter invalid data in Appointment date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. | 1)JHBHB 2)Current date : 02/05/2020 3) Appointment Date: 29/05/2020 |  | High | High | New
10720 | TC_Visit_Schedule_02 | 29 | Visit scheduled date is showing incomplete data in year. | User is already on case requests page. | 1) Click on "Schedule Visit" link available under Quick Links section. |  |  | High | High | New
10720 | TC_Case_Status_Update_01 | 30 | Case Number appearing on the Case detail page of selected case is wrong. Currently Policy Number is appearing instead of case number. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  | High | High | New
When repairer does not want to change the appointment date in visit schedule section and he needs to assign the engineer then the system shows validation message as "Reason for resceduling" is mandatory.

## TC_Login
Project Name:-> Reassure
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Login
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Login_01 | 10720 | 2020-04-29 | Entering in to the website. | Any particular browser is kept opened on the user's system and the internet connection in on and working. | 1)Type the website's address in the address bar. 2)Click on the "Go" button or press the Enter button of the keyboard. | URL:http://reassure.innov.co.in/ | Website does not get open at first attempt, when entering the url in the address bar and hitting Enter key and system shows blank page. Website gets open when user reload/refreshes the page. |  | The website should get opened having the option to login in to the website. The login form should be having the following fields and buttons displayed - 1)User name(Field) 2)Password(Field) 3)Login (Button) 4)Cancel(Button) 5)Remember me(Check Box) 6)Forgot Password(Link/option) | High | High | Fail
TC_Login_02 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by leaving all the mandatory fields blank. | User is on the website's landing page and is registered to the website. | 1)Leave the Username field blank. 2)Leave the Password field blank. 3)Click on the "Login" button. |  | NA |  | Specific & proper Validation messages related to both the blank fields should get displayed. |  |  | Pass
TC_Login_03 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by leaving Username field blank. | User is on the website's landing page and is registered to the website. | 1)Leave the Username field blank. 2)Enter valid password in the Password field. 3)Click on the "Login" button. | Password: admin | Validation message for leaving Username field is not specific. It should be "Please Enter Username" |  | Specific & proper Validationmessage related to the blank field i.e. the username (email address) field should get displayed. | Mid | Low | Fail
TC_Login_04 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by leaving Password field blank. | User is on the website's landing page and is registered to the website. | 1)Enter the valid username in the field provided. 2)Leave the password field blank. 3)Click on the Login button. | Username: admin | Validation message for leaving Password field is not specific. It should be "Please Enter Password" |  | Specific & proper Validation messagerelated to the blank field i.e. password field should get displayed. | Mid | Low | Fail
TC_Login_05 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by entering invalid Username. | User is on the website's landing page and is registered to the website. | 1)Enter invalid username in the field provided 2)Enter valid password in the field provided. 3)Click on the Login button. | Username: #@@@ | Validation message for entering invalid data in username field is wrong. |  | Specific & proper Validation message related to the username field should get displayed. | Mid | Low | Fail
TC_Login_06 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by entering invalid Password. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter invalid password in the field provided. 3)Click on the provided Login button. |  | NA |  | Specific & proper Validation message related to the passwordfield should get displayed. |  |  | Pass
TC_Login_07 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by entering invalid Password and Username. | User is on the website's landing page and is registered to the website. | 1)Enter invalid username and password in the fields provided. 2)Click on the Login button. |  | NA |  | Specific & proper Validation messages related to both the fields should get displayed. |  |  | Pass
TC_Login_08 | 10720 | 2020-04-29 | Verify that the registered user is able to login to the website by entering valid Password and Username. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Click on the Login button. |  | NA |  | User should get logged in to his/her account |  |  | Pass
TC_Login_09 | 10720 | 2020-04-29 | To verify if the system remembers the login credentials if user checks the Remember Me check box. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Select the "Remember me" check box. 3)Click on the Login button. |  | NA |  | User should get logged in to his/her account. Also , the next time when the same user tries to log in and enters his user name(email address) then automatically the password field should get filled the correct password of hisas he checked the Remember me check box when he logged for the first time. |  |  | Not Required
TC_Login_10 | 10720 | 2020-04-29 | Check if the password is masked on the screen i.e., password must be in bullets or asterisks | User is on the website's landing page and is registered to the website. | 1)Enter valid password in the field provided. | some password(can be a registered/unregistered) |  |  | The entered password should be masked/hidden. |  |  | Not Required
TC_Login_11 | 10720 | 2020-04-29 | After logging in try to copy/cut the password and paste it on another screen(passwords are usually in * such that its not visible on the screen) | User is on the website's landing page and is registered to the website. | 1)Enter username and password in the respective fields. Copy the password field’s content(which is in *s) 3)paste the content on another screen | Registered user’s login id and password |  |  | The entered password shouldn't get copied. |  |  | Not Required
TC_Login_12 | 10720 | 2020-04-29 | Verify the url without logging into to the site | User is on the website's landing page and is registered to the website. | 1) Login to the site using registered username and password 2)copy and save the url of the logged in page 3)logout of the site 4)now paste the copied url on the browser | Registered username and password |  |  | User should get redirect o the home/login screen. |  |  | Not Required
TC_Login_13 | 10720 | 2020-04-29 | Verify that the user's password is getting retrieved in case if he has forgotten his password. | Registered user is on the login page having the link of "Forgot Password" and has forgotten his/her password. | Click on the provided "Forgot password" link. |  | NA |  | User should get navigated to the forgot password screen having the following options - 1)Email address (Field) 2)Submit(Button) |  |  | Not Required
TC_Login_14 | 10720 | 2020-04-29 |  |  | 1)Enter invalid email address in the field provided(Invalid email address can be categorized in to two type, first is the email address which is not in correct format and the other one is that which is in correct format but does not exist in the application's data base) 2)Click on the "Submit" button. |  | NA |  | Specific & proper validation message should get displayed related to the email address field. |  |  | Not Required
TC_Login_15 | 10720 | 2020-04-29 |  |  | 1)Enter valid email address in the field provided. 2)Click on the "Submit" button. |  | NA |  | System should reset the password and a mail should get sent to the user's email address havingthe password along with the Log in Link. As Soon as the user enter the correct user name andPassword then he should get navigated to the "Change Password" screen under "My Account" section of the website. |  |  | Not Required
TC_Login_16 | 10720 | 2020-04-29 | Verify that the user is able to get logout. | User is already logged in. | 1) Click on the logout button available underside menu otions. |  |  |  | User should get logged out of the system and should get rediret to the login/landing page. |  |  | Not Required

## TC_Complaints Page
Project Name:-> Reassure
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Complaints Page
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Complaints_01 | 10720 | 2020-04-29 | To verify if the user is able to get navigate to Case Request Page by clicking on Case Requests option available under Side Menu. | User is already on home page. | 1)Click on Complaints option available under Side Menu. |  | 1)There should not be an option to create Case Request. |  | User should get navigate to the Case Request Page with having list of all the case request. | High | High | Fail
TC_Complaints_02 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "Approved" from the Filter by status dropdown. | User is already on Case requests page. | 1) Select "Approved" in the Filter by status dropdown. |  |  |  | System should display the Case requests having status as " Approved". |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_03 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "Closed" from the Filter by status dropdown. | User is already on Case requests page. | 1) Select "Closed" in the Filter by status dropdown. |  |  |  | System should display the Case requests having status as " Closed" |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_04 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "Pending" from the Filter by status dropdown. | User is already on Case requests page. | 1) Select "Pending" in the Filter by status dropdown. |  | System is not displaying the filtered result on the basis of selected status "Pending" |  | System should display the Case requests having status as "Pending". |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_05 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "Rejected" from the Filter by status dropdown. | User is already on Case requests page. | 1) Select "Rejected" in the Filter by status dropdown. |  | System is not displaying the filtered result on the basis of selected status "Rejected" |  | System should display the Case requests having status as "Rejected". |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_06 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "WIP" from the Filter by status dropdown. | User is already on Case requests page. | 1) Select "WIP" in the Filter by status dropdown. |  | System is not displaying the filtered result on the basis of selected status "WIP" |  | System should display the Case requests having status as "WIP". |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_07 | 10720 | 2020-04-29 | To verify if the user is able to filter out the Case Requests by selecting "All" from the Filter by status dropdown. | User is already on Case requests page.dfd | 1) Select "All" in the Filter by status dropdown. |  |  |  | System should display the Case requests having status as "All". |  |  | Cannot execute due to the non availability of case details.
TC_Complaints_08 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering "Program Name." field. | User is already on case requests page. | 1) Enter "Program Name." to be searched in the "Program Name" field. 2) Click on search button. | CPP ACK | System does not shows the filtered resulton the basis of searched Program name. |  | searched result on the basis of entered Program Name should get display. | HIGH | HIGH | Fail
TC_Complaints_09 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering "Case No." field. | User is already on case requests page. | 1) Enter Case No. to be searched in the "Case No." field. 2) Click on search button. | 77865 | System does not shows the filtered resulton the basis of searched Case Number. |  | searched result on the basis of entered Case No. should get display. | HIGH | HIGH | Fail
TC_Complaints_10 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering "Case Creation Date" field. | User is already on case requests page. | 1) Enter Case Creation Date to be searched in the "Case Creation Date" field. 2) Click on search button. | 01-02-2020 05:30:00 | System does not shows the filtered resulton the basis of searched Case Creation Date. |  | searched result on the basis of entered Case Creation Date should get display. | HIGH | HIGH | Fail
TC_Complaints_11 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering "Ageing" field. | User is already on case requests page. | 1) Enter Ageing Date to be searched in the "Ageing" field. 2) Click on search button. | 11 | System does not shows the filtered resulton the basis of searched Ageing. |  | searched result on the basis of entered Ageing should get display. | HIGH | HIGH | Fail
TC_Complaints_12 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering "Case Status" field. | User is already on case requests page. | 1) Enter Case Status to be searched in the "Case Status" field. 2) Click on search button. | Visit Scheduled | System does not shows the filtered resulton the basis of searched Case Status. |  | searched result on the basis of entered Case Status should get display. | HIGH | HIGH | Fail
TC_Complaints_13 | 10720 | 2020-04-29 | To verify if the user is able to Search the Case Request by entering any combination of case requests fields. | User is already on case requests page. | 1) Enter any combination of fields to be searched in the respective fields. 2) Click on search button. | ACK+077865 | System does not shows the filtered resulton the basis of searched Case Status. |  | searched result on the basis of entered fields should get display. | HIGH | HIGH | Fail
TC_Complaints_14 | 10720 | 2020-04-29 | To verify if the user is able to download the selected Case Request or not. | User is already on case requests page. | 1) Select the check box appearing against the Case Request to be downloaded. 2) Click on Download button. |  | Pdf file of selected Case Request is not getting download. |  | Pdf file of selected Case Request should get download. | HIGH | HIGH | Fail
TC_Complaints_15 | 10720 | 2020-04-29 | To verify if the downloaded Case Request is in correct and spacified format. | User is already on case requests page. | 1) Select the check box appearing against the Case Request to be downloaded. 2) Click on Download button. |  |  |  | The downloaded PDF file should be in correct format. |  |  | Cannot verify as the PDF is not getting download.
TC_Complaints_16 | 10720 | 2020-04-29 | To verify if the details of the downloaded Case Request is correct. | User is already on case requests page. | 1) Select the check box appearing against the Case Request to be downloaded. 2) Click on Download button. |  |  |  | The downloaded PDF file should display the correct details as avaialable in the portal. |  |  | Cannot verify as the PDF is not getting download.
TC_Complaints_17 | 10720 | 2020-04-29 | To verify if the user is able to navigate to the Next page of Case Requests list. | User is already on case requests page. | 1) Click on the ">" icon to move to the next page. |  |  |  | User shoulg get navigate to the Next Case Requests page. |  |  | Pass
TC_Complaints_18 | 10720 | 2020-04-29 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass
TC_Complaints_19 | 10720 | 2020-04-29 | To verify if the details appearing in the Case Request Details page is same that has been added while creating the request. | User is already on case requests page. | 1) Note down the details which is being added while creating the request. 2) Click on the View icon appearing against every Case Request. 3) Compare the details of the request with the noted details. |  |  |  | Details appearing in the Case Request Details page is should be same, that has been added while creating the request. |  |  | Need to verify from the API data after inegration.
TC_Complaints_20 | 10720 | 2020-04-29 | To verify if the quick link for "Case Status Update" is clickable/working or not. | User is already on case requests page. | 1) Click on "Case Status Update" link available under Quick Links section. |  |  |  | Case Status Update pop up should get appear. |  |  | Pass
TC_Complaints_21 | 10720 | 2020-04-29 | To verify if the quick link for "Schedule Visit" is clickable/working or not. | User is already on case requests page. | 1) Click on "Schedule Visit" link available under Quick Links section. |  |  |  | User should get move to the "Schedule Visit" section of the Case Request. |  |  | Pass
TC_Complaints_22 | 10720 | 2020-04-29 | To verify if the quick link for "Customer Address" is clickable/working or not. | User is already on case requests page. | 1) Click on "Customer Address" link available under Quick Links section. |  |  |  | User should get move to the "Customer Address" section of the Case Request. |  |  | Pass
TC_Complaints_23 | 10720 | 2020-04-29 | To verify if the quick link for "Add Inspection details" is clickable/working or not. | User is already on case requests page. | 1) Click on "Add Inspection details" link available under Quick Links section. |  |  |  | User should get move to the "Add Inspection Details" section of the Case Request. |  |  | Pass
TC_Complaints_24 | 10720 | 2020-04-29 | To verify if the quick link for "Add Estimation Details" is clickable/working or not. | User is already on case requests page. | 1) Click on "Add Estimation Details" link available under Quick Links section. |  |  |  | User should get move to the "Add Estimation Details" section of the Case Request. |  |  | Pass
TC_Complaints_25 | 10720 | 2020-04-29 | To verify if the quick link for "Generate Invoice" is clickable/working or not. | User is already on case requests page. | 1) Click on "Generate Invoice" available under Quick Links section. |  |  |  | User should get move to the "Generate Invoice" section of the Case Request. |  |  | Pass
TC_Complaints_26 | 10720 | 2020-04-29 | To verify if the quick link for "Submit Invoice" is clickable/working or not. | User is already on case requests page. | 1) Click on "Submit Invoice" available under Quick Links section. |  |  |  | User should get move to the "Submit Invoice" section of the Case Request. |  |  | Pass
TC_Complaints_27 | 10720 | 2020-04-29 | To verify if the quick link for "Contact Details" is clickable/working or not. | User is already on case requests page. | 1) Click on "Contact Details" available under Quick Links section. |  |  |  | User should get move to the "Contact Details" section of the Case Request. |  |  | Pass
TC_Complaints_28 | 10720 | 2020-04-29 | To verify if the quick link for "Customer Details" is clickable/working or not. | User is already on case requests page. | 1) Click on Customer Details" available under Quick Links section. |  |  |  | User should get move to the Customer Details section of the Case Request. |  |  | Pass
TC_Complaints_29 | 10720 | 2020-04-29 | To verify if the quick link for Product Details is clickable/working or not. | User is already on case requests page. | 1) Click on Product Details available under Quick Links section. |  |  |  | User should get move to the Product Details section of the Case Request. |  |  | Pass
TC_Complaints_30 | 10720 | 2020-04-29 | To verify if the quick link for Repair Visit Details is clickable/working or not. | User is already on case requests page. | 1) Click on Repair Visit Details available under Quick Links section. |  |  |  | User should get move to the Repair Visit Details section of the Case Request. |  |  | Pass
TC_Complaints_31 | 10720 | 2020-04-29 | To verify if the quick link for Estimate Details is clickable/working or not. | User is already on case requests page. | 1) Click on Estimate Details available under Quick Links section. |  |  |  | User should get move to the Estimate Details section of the Case Request. |  |  | Pass
TC_Complaints_32 | 10720 | 2020-04-29 | To verify if the quick link for Payment Details is clickable/working or not. | User is already on case requests page. | 1) Click on Payment Details available under Quick Links section. |  |  |  | User should get move to the Payment Details section of the Case Request. |  |  | Pass
TC_Complaints_33 | 10720 | 2020-04-29 | To verify if the quick link for Approve Invoice is clickable/working or not. | User is already on case requests page. | 1) Click on Approve Invoice available under Quick Links section. |  | User doesn't get move to the Approve Invoice section of the Case Request. |  | User should get move to the Approve Invoice section of the Case Request. | High | High | Fail
TC_Complaints_34 | 10720 | 2020-04-29 | To verify if the quick link for Estimate/Invoice History is clickable/working or not. | User is already on case requests page. | 1) Click on Estimate/Invoice History available under Quick Links section. |  |  |  | User should get move to the Estimate/Invoice History section of the Case Request. |  |  | Pass
TC_Complaints_35 | 10720 | 2020-04-29 | To verify if all sections are getting Hidden and scrolled down on clicking on icon. | User is already on service requests page. | 1) Click on scrollup and scroll down icon to hide and display the details. |  |  |  | Selected section should get hide and appear on clickin on scrollup and scroll down icon. |  |  | Pass
Pass

## TC_Case_Status_Update
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Case_Status_Update | [7 empty] | Retesting:2/5/2020
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Status
TC_Case_Status_Update_01 | 10720 | 2020-04-29 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass | 10720 | Pass
TC_Case_Status_Update_02 | 10720 | 2020-04-29 | To verify if the user is able to navigate to case status update pop up by clicking on "Case Status Update" quicl link. | User is already on case requests page. | 1) Click on "Case Status Update" link available under Quick Links section. |  |  |  | Case Status Update pop up should get appear. |  |  | Pass | 10720 | Pass
TC_Case_Status_Update_03 | 10720 | 2020-04-29 | To verify if the user is able to submit the case status update form by leaving all the mandatory fields blank. | User is at case status update pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | The validation message appearing for leaving all the fields blank while submitting the case status update is wrong. |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Fail | 10720 | Fail
TC_Case_Status_Update_04 | 10720 | 2020-04-29 | To verify if the user is able to submit the case status update form by leaving the Case Status field blank. | User is at case status update pop up. | 1) Leave Case Status field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  | The validation message appearing for leaving all the field blank while submitting the case status update is wrong. |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Fail | 10720 | Fail
TC_Case_Status_Update_05 | 10720 | 2020-04-29 | To verify if the user is able to submit the case status update form by leaving the Reason for Cancellation field blank. | User is at case status update pop up. | 1) Leave Reason for Cancellation field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  | The validation message appearing for leaving the Reason for Cacellation field blank while submitting the case status update is wrong. |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Fail | 10720 | Fail
TC_Case_Status_Update_06 | 10720 | 2020-04-29 | To verify if the values of the dropdown is as per the master for Case Status Field. | User is at case status update pop up. | 1)Click on the Case Status Dropdown. 2) Check the values of the dropdown and match it with the data from the master. |  |  |  | The dropdown value should be as per the master. | High | Mid | Pass | 10720 | Pass
TC_Case_Status_Update_07 | 10720 | 2020-04-29 | To verify if the values of the dropdown is as per the master for Reason for cancellation Field. | User is at case status update pop up. | 1)Click on the Reason for cancellation Dropdown. 2) Check the values of the dropdown and match it with the data from the master. |  | 1)Duplicate dropdown value is appearing in the dropdown of the Reason for cancellation. 2) The dropdown values coming in Reason list when "Customer Not Available" selected in case status is not as per the Master. As Customer not Contactable should not be in the dropdown. |  | The dropdown value should be as per the master. | High | High | Fail | 10720 | Fail
TC_Case_Status_Update_08 | 10720 | 2020-04-29 | To verify if the user is able to submit the case status update form by entering valid data in all the mandatory fields. | User is at case status update pop up. | 1) Enter valid details in all fields. 2)Click on submit button. |  | 1) After submitting the case status update form successfully system shows confirmation message as " Successfully Updated" but its response of API has an error as "{"Status": "Case Cancelled", " aiz_claim_number": "06388614", "Cancellation_reason": "Area is out of coverage"}" 2) After Submitting the Case Status Update the Pop-Up form should get auto reset. |  | Case status update should get submitted. | High | High | Fail | 10720 | Fail
TC_Case_Status_Update_09 | 10720 | 2020-04-29 | To verify if the Case Sub Status gets changed to Cancelled by repairer after selecting the case status as cancel. | User is at case status update pop up. | 1) Select Cancel as the case status. 2) Select valid reason. 3) Click on submit button. |  | 1)The status should get change to Cancelled by Repairer immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) On refreshing the page after submitting the case status , system shows blank page. |  | After submitting the case status as cancel, the Case Sub Status should gvet changed to Cancelled by Repairer. | High | High | Fail | 10720 | Fail
TC_Case_Status_Update_10 | 10720 | 2020-04-29 | To verify if the Case Sub Status gets changed to Customer Not Contactable after selecting the case status as Customer Not Contactable. | User is at case status update pop up. | 1) Select Customer Not Contactable as the case status. 2) Select valid reason. 3) Click on submit button. |  | 1)The status should get change to Customer Not Contactable immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) User is not able to submit the case status as Customer Not Contactable and system shows an error msg. 3) On refreshing the page after submitting the case status , system shows blank page. |  | After submitting the case status as Customer Not Contactable the Case Sub Status should get changed to Customer Not Contactable. | High | High | Fail | 10720 | Fail
TC_Case_Status_Update_11 | 10720 | 2020-04-29 | To verify if the Case Sub Status gets changed to Customer Not Available after selecting the case status as Customer Not Available. | User is at case status update pop up. | 1) Select Customer Not Available as the case status. 2) Select valid reason. 3) Click on submit button. |  | 1)The status should get change to Customer Not Available immediately after updating the status but currently user needs to refresh the page in order to view the changed status. 2) User is not able to submit the case status as Customer Not Available and system shows an error msg. 3) On refreshing the page after submitting the case status , system shows blank page. |  | After submitting the case status as Customer Not Available the Case Sub Status should get changed to Customer Not Available. | High | High | Fail | 10720 | Fail
TC_Case_Status_Update_12 | 10720 | 2020-04-29 | To verify if the Cancel button at Case Status Update pop up is functional or not | User is at case status update pop up. | 1)Click on Cancel button. |  |  |  | Case status update should get close. |  |  | Pass | 10720 | Pass

## TC_Visit_Schedule
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Visit_Schedule
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Visit_Schedule_01 | 10720 | 2020-04-30 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass
TC_Visit_Schedule_02 | 10720 | 2020-04-30 | To verify if the user is able to navigate to Repairer visit section by clicking on "Schedule Visit" quick link. | User is already on case requests page. | 1) Click on "Schedule Visit" link available under Quick Links section. |  |  |  | User should get navigate to the Repairer visit section. |  |  | Pass
TC_Visit_Schedule_03 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | The validation message coming for leaving the fields blank has wrong field lables. The field lables appearing are name of the columns in database. |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_04 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by leaving the Appointment date field blank. | User is already on case requests page. | 1) Leave the Appointment date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | The validation message coming for leaving the Appointment date field blank is wrong , As there is a punctuation error. The validation message should be as " Appointment Date :Appointment Date is Required & It can not be empty." |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_05 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by leaving the Reason for Resecheduling field blank. | User is already on case requests page. | 1) Leave the Reason for Resecheduling field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | The validation message coming for leaving the Reason for Resecheduling field blank is wrong , As there is a punctuation error. The validation message should be as "Reason for Resecheduling :Reason for Resecheduling is Required & It can not be empty." |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_06 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by leaving the Appointment Time Slot field blank. | User is already on case requests page. | 1) Leave the Appointment Time Slot field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | 1)The validation message coming for leaving the Appointment Time Slot field blank is wrong , As there is a punctuation error. The validation message should be as "Appointment Time Slot :Appointment Time Slot is Required & It can not be empty." 2) System does not show validation message for leaving Appointment Time SLot blank. It is an mandatory field Visit schedule gets submitted and system picks The time slow as 10:00 AM - 12:30 PM with First Engineer by itself |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_07 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by leaving the Remark field blank. | User is already on case requests page. | 1) Leave the Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | The validation message coming for leaving the Remark field blank is wrong , As there is a punctuation error. The validation message should be as "Remark : Remark is Required & It can not be empty." |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_08 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Appointment date field. | User is already on case requests page. | 1) Enter invalid data in Appointment date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. | 1)JHBHB 2)Current date : 02/05/2020 3) Appointment Date: 29/05/2020 | 1)The validation message coming for entering invalid data in Appointment date is wrong. 2) User should be able to select the Past date upto three days from current day but currenty this is not happeninig, |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | High | Fail
TC_Visit_Schedule_09 | 10720 | 2020-04-30 | To verify if the Repair Schedule form is getting submitted by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all the fields. 3)Click on submit button. |  | 1)After saving the Visit Schedule form the API should get triggeredand the same data should get sent to MetaCube portal but This is not happening currently. 2)[{"field":"aiz_claim_number","error":"invalid_value","description":"aiz_claim_number can not be null/empty."},{"field":"Rescheduled_Date","error":"invalid_date","description":"Invalid Rescheduled_Date"}] |  | Repair schedule form should get submitting. | High | High | Fail
TC_Visit_Schedule_10

## TC_Add_Inspection
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add_Inspection
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Add_Inspection_01 | 10720 | 2020-05-01 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Add_Inspection_02 | 10720 | 2020-05-01 | To verify if the user is able to navigate to Repairer visit section by clicking on "Inspection Details" quick link. | User is already on case requests page. | 1) Click on "Inspection Details" link available under Quick Links section. |  |  |  | User should get navigate to the Inspection Details section. |  |  | pass
TC_Add_Inspection_03 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_04 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving the Visit Completion Date field blank. | User is already on case requests page. | 1) Leave the Visit Completion Date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_05 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving the Appointment date field blank. | User is already on case requests page. | 1) Leave the Inspection Details field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_06 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Visit Sub Status field blank. | User is already on case requests page. | 1) Leave the Visit Sub Status field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Inspection_07 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Problem Diagnosed by Engineer field blank. | User is already on case requests page. | 1) Leave the Problem Diagnosed by Engineer field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_08 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Problem Sub-Category field blank. | User is already on case requests page. | 1) Leave the Problem Sub-Category field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_09 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_10 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_11 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Inspection Remark field blank. | User is already on case requests page. | 1) Leave the Inspection Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_12 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving defect photo field blank. | User is already on case requests page. | 1) Leave the defect photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_13 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving claim form photo field blank. | User is already on case requests page. | 1) Leave the claim form photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_14 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Product No. photo field blank. | User is already on case requests page. | 1) Leave the Product No. photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_15 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Purchase Invoice photo field blank. | User is already on case requests page. | 1) Leave the Purchase Invoice photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_16 | 10720 | 2020-05-01 | To verify if the Inspection Details form is getting submitted by leaving Job Sheet photo field blank. | User is already on case requests page. | 1) Leave the Job Sheet photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_17 | 10720 | 2020-05-01 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Visit Completion date field. | User is already on case requests page. | 1) Enter invalid data in Visit Completion date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Inspection_18 | 10720 | 2020-05-01 | To verify if the Visit Sub Status dropdown values are as per the case master. | User is already on case requests page. | 1) Click on the Visit Sub Status dropdown. 2)Now check the dropdown values with the values in status master. |  |  |  | Visit Sub Status dropdown values should be as per the Case master.
TC_Add_Inspection_19 | 10720 | 2020-05-01 | To verify if the user is able to Add Inspection by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all the fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Added Inspection should get submitting for Approval
TC_Add_Inspection_20 | 10720 | 2020-05-01
TC_Add_Inspection_21 | 10720 | 2020-05-01
TC_Add_Inspection_22 | 10720 | 2020-05-01
TC_Add_Inspection_23 | 10720 | 2020-05-01
TC_Add_Inspection_24 | 10720 | 2020-05-01
TC_Add_Inspection_25 | 10720 | 2020-05-01
TC_Add_Inspection_26 | 10720 | 2020-05-01
TC_Add_Inspection_27 | 10720 | 2020-05-01
TC_Add_Inspection_28 | 10720 | 2020-05-01

## TC_Add_Estimation
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add_Estimation
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Add_Estimation_01 | 10805 | 2020-05-11 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Add_Estimation_02 | 10805 | 2020-05-11 | To verify if the user is able to navigate to Add Estimation section by clicking on "Add Estimation" quick link. | User is already on case requests page. | 1) Click on "Add Estimation Details" link available under Quick Links section. |  |  |  | User should get navigate to the Estimation Details section.
TC_Add_Estimation_03 | 10805 | 2020-05-11 | To verify if the Description section is showing all the "parts" added by the engineer at the time of adding inspection. | User is already on case requests page. | 1)Check the values under description tab and match them with the values entered at the time of adding inspection. |  |  |  | The description values should be same as the of parts/
TC_Add_Estimation_04 | 10805 | 2020-05-11 | To verify if the Estimation Details form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_05 | 10805 | 2020-05-11 | To verify if the Estimation Details form is getting submitted by leaving the QTY field blank. | User is already on case requests page. | 1) Leave the QTY field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_06 | 10805 | 2020-05-11 | To verify if the Estimation Details form is getting submitted by leaving the Unit Price field blank. | User is already on case requests page. | 1) Leave the Unit Price field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_07 | 10805 | 2020-05-11 | To verify if the Estimation Details form is getting submitted by leaving the IGST or SGST+CGST field blank. | User is already on case requests page. | 1) Leave the IGST or SGST+CGST field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
Note: User can only add IGST or CGST+SGST.
TC_Add_Estimation_08 | 10720 | 2020-05-02 | To verify if the Estimation Details form is getting submitted by leaving the Expected Repair Completion Date field blank. | User is already on case requests page. | 1) Leave the Expected Repair Completion Date field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_09 | 10720 | 2020-05-02 | To verify if the Estimation Details form is getting submitted by leaving the Repair Type field blank. | User is already on case requests page. | 1) Leave the Repair Type field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_10 | 10720 | 2020-05-02 | To verify if the Estimation Details form is getting submitted by leaving the Remark field blank. | User is already on case requests page. | 1) Leave the Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_11 | 10720 | 2020-05-02 | To verify if the Repair Schedule form is getting submitted by entering invalid data in QTY field. | User is already on case requests page. | 1) Enter invalid data in QTY field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_12 | 10720 | 2020-05-02 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Unit Price field. | User is already on case requests page. | 1) Enter invalid data in Unit Price field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_13 | 10720 | 2020-05-02 | To verify if the Repair Schedule form is getting submitted by entering invalid data in IGST field. | User is already on case requests page. | 1) Enter invalid data in IGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_14 | 10720 | 2020-05-02 | To verify if the Repair Schedule form is getting submitted by entering invalid data in SGST field. | User is already on case requests page. | 1) Enter invalid data in SGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_15 | 10720 | 2020-05-02 | To verify if the Estimation Details form is getting submitted by entering invalid data in CGST field. | User is already on case requests page. | 1) Enter invalid data in CGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
Note: User can only add IGST or CGST+SGST.
TC_Add_Estimation_16 | 10720 | 2020-05-02 | To verify if there is a validation for entering all three CGST,SGST AND IGST fields | User is already on case requests page. | 1) Enter data in all three fields. |  |  |  | There should be a proper validation msg for it.
TC_Add_Estimation_17 | 10720 | 2020-05-02 | To verify if the user is able to add any Part by clicking on + button. | User is already on case requests page. | 1) Click on + icon appearing on the Add estimation section. |  |  |  | User should be able to Add any missing part/description.
TC_Add_Estimation_18 | 10720 | 2020-05-02 | To verify if the Estimation Details form is getting submitted by entering invalid data in Expected Repair Completion date field. | User is already on case requests page. | 1) Enter invalid data in Expected Repair Completion date field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_19 | 10720 | 2020-05-02 | To verify if the GST Amount of the each part is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in GST Amount fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The GST Amount of each part/description should be correct.
TC_Add_Estimation_20 | 10720 | 2020-05-02 | To verify if the Total of the each part is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in qty, unit price and tax related fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The total of each part/description should be correct.
TC_Add_Estimation_21 | 10720 | 2020-05-02 | To verify if the Sub-Total is showing the Sum of Total parts only. | User is already on case requests page. | 1) Enter valid data in qty, unit price and tax related fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Sub total should only display the summation of parts only.
TC_Add_Estimation_22 | 10720 | 2020-05-02 | To verify if the Total of entire estimation is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Total of entire Estiamtion should be mathematically correct.
TC_Add_Estimation_23 | 10720 | 2020-05-02 | To verify if the Total of entire estimation is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Total of entire Estiamtion should be mathematically correct.
TC_Add_Estimation_24 | 10720 | 2020-05-02 | To verify if the user is able to save estimation as draft by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Save as Draft Button. |  |  |  | The Added submittion should get saved as draft for editing before submitting for approval.
TC_Add_Estimation_25 | 10720 | 2020-05-02 | To verify if the user is able to Submit For Approval the estimation by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Added submittion should get submitting for Approval

## TC_Approve_Estimation
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add_Estimation
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Add_Estimation_01 | 10720 | 2020-05-02 | To verify if the Case Manager is able to get navigate to the Case Request Details page of selected Case Request. | Case Manager is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Add_Estimation_02 | 10720 | 2020-05-02 | To verify if the Case Manager is able to navigate to Approve Estimatio section by clicking on "Approve Estimation" quick link. | Case Manager is already on case requests page. | 1) Click on "Approve Estimation" link available under Quick Links section. |  |  |  | Case Manager should get navigate to the Approve Estimation section.

## TC_Invoice
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Generate Invoice | [7 empty] | Retesting:2/5/2020
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Status
TC_TC_Invoice_01 | 10805 | 2020-05-11 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request.
TC_TC_Invoice_02 | 10805 | 2020-05-11 | To verify if the user is able to navigate to Generate Invoice pop up by clicking on "Generate Invoice" quick link. | User is already on case requests page. | 1) Click on "Generate Invoice" link available under Quick Links section. |  |  |  | Generate Invoice Update pop up should get appear.
TC_TC_Invoice_03 | 10805 | 2020-05-11 | To verify if the user is able to submit the Generate Invoice form by leaving all the mandatory fields blank. | User is at Generate Invoice pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same.
TC_TC_Invoice_04 | 10805 | 2020-05-11 | To verify if the user is able to submit the Generate Invoice form by leaving the Invoice Number field blank. | User is at Generate Invoice pop up. | 1) Leave Invoice Number field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same.
TC_TC_Invoice_05 | 10805 | 2020-05-11 | To verify if the user is able to submit the Generate Invoice form by leaving the Invoice Date field blank. | User is at Generate Invoice pop up. | 1) Invoice Date field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same.
TC_TC_Invoice_06 | 10805 | 2020-05-11 | To verify if the user is able to generate invoice by entering invalid data in Invoice Number field. | User is at Generate Invoice pop up. | 1)Enter Invalid data in Invoice Number field blank. 2) Enter valid details in thenremianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same.
TC_TC_Invoice_07 | 10805 | 2020-05-11 | To verify if the user is able to generate invoice by entering invalid data in Invoice Date field. | User is at Generate Invoice pop up. | 1)Enter Invalid data in Invoice Date field blank. 2) Enter valid details in thenremianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same.
TC_TC_Invoice_08 | 10805 | 2020-05-11 | To verify if the user is able to submit the Generate Invoice form by entering valid data in all the mandatory fields. | User is at Generate Invoice pop up. | 1) Enter valid details in all fields. 2)Click on submit button. |  |  |  | Invoice should get generated and get sent to Case Manager for approval.
TC_TC_Invoice_09 | 10805 | 2020-05-11 | To verify if the Cancel button at Generate Invoice pop up is functional or not | User is at Generate Invoice pop up. | 1)Click on Cancel button. |  |  |  | Generate Invoice should get close.
TC_TC_Invoice_10 | 10805 | 2020-05-11 | To verify if the user is able to navigate to Generate Invoice pop up by clicking on "Submit Invoice" quick link. | User is already on case requests page. | 1) Click on "Submit Invoice" link available under Quick Links section. |  |  |  | User should get navigate to Submit Invoice section.
TC_TC_Invoice_11 | 10805 | 2020-05-11 | To verify if the user is able to submit the invoice by leaving all the fields blank. | User is already on case requests page. | 1) Click on submit button. |  |  |  | Invoice should not get submited and there should be a proper validation message for the same.
TC_TC_Invoice_12 | 10805 | 2020-05-11 | To verify if the user is able to submit the Invoice by uploading invalid file as Invoice. | User is already on case requests page. | 1) Uploading invalid file (Over size/Incorrect file type) 2) Click on Submit Button. |  |  |  | Invoice should not get submited and there should be a proper validation message for the same.
TC_TC_Invoice_13 | 10805 | 2020-05-11 | To verify if the user is able to submit the Invoice by uploading valid file as Invoice. | User is already on case requests page. | 1) Uploading valid file. 2) Click on Submit Button. |  |  |  | Invoice should get submitted for approval.
TC_TC_Invoice_14 | 10805 | 2020-05-11 | To verify if the Cancel button at Submit Invoice is functional or not | User is already on case requests page. | 1)Click on Cancel button. |  |  |  | Invoice submission process should get abort.
TC_TC_Invoice_15 | 10805 | 2020-05-11 | To verify if the Case Manager is able to get navigate to the Approve Invoice secion or not. | Case Manager is already on case requests page. | Click on Approve Invoice link under quick links. |  |  |  | Case Manager should get navigate to the Approve Invoice section.
TC_TC_Invoice_16 | 10805 | 2020-05-11 | To verify if the Case Manager is able to view the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the View Invoice button. |  |  |  | Case Manager should be able to view the Invoice.
TC_TC_Invoice_17 | 10805 | 2020-05-11 | To verify if the Case Manager is able to downloaded the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Download Invoice button. |  |  |  | Case Manager should be able to download the Invoice.
TC_TC_Invoice_18 | 10805 | 2020-05-11 | To verify if the Case Manager is able to Approve the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Approve button. |  |  |  | Case Manager should be able to Approve the Invoice.
TC_TC_Invoice_19 | 10805 | 2020-05-11 | To verify if the Case Manager is able to Reject the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Reject button. |  |  |  | Case Manager should be able to Reject the Invoice.
TC_TC_Invoice_20 | 10805 | 2020-05-11 | To verify if the Case Manager is able to change the status of the invoice to On Hold. | Case Manager is already on case requests page. | 1)Click on the On Hold button. |  |  |  | Case Manager should be able to change the status to On Hold.

## TC_Add_Payment
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add Payment | [7 empty] | Retesting:2/5/2020
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Status
TC_TC_Add_Payment_01 | 10805 | 2020-05-11 | To verify if the Finance User is able to get navigate to the Case Request Details page of selected Case Request. | Finance User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | Finance User should be able to get navigate to the Case Request Details page of selected Case Request.
TC_TC_Add_Payment_02 | 10805 | 2020-05-11 | To verify if the Finance User is able to navigate to Add Payment Details by clicking on "Add Payment Details" quick link. | Finance User is already on case requests page. | 1) Click on "Add Payment Details" link available under Quick Links section. |  |  |  | User should get navigate to the Add Payment Details.
TC_TC_Add_Payment_03 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment details by leaving all the mandatory fields blank. | Finance User is at Generate Invoice pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_04 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by leaving UTR No field blank. | Finance User is at Generate Invoice pop up. | 1) Leave UTR Number field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_05 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by leaving Amount field blank. | Finance User is at Generate Invoice pop up. | 1) Leave Amount field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_06 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by leaving Transection Date field blank. | Finance User is at Generate Invoice pop up. | 1) Leave Transection Date field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_07 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by leaving Status field blank. | Finance User is at Generate Invoice pop up. | 1) Leave Status field blank. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_08 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by entering invalid data in UTR No. | Finance User is at Generate Invoice pop up. | 1) Enter Invalid data in UTR No. field. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_09 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by entering invalid data in Amount field. | Finance User is at Generate Invoice pop up. | 1) Enter Invalid data in Amount field. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_10 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by entering invalid data in Transection Date field. | Finance User is at Generate Invoice pop up. | 1) Enter Invalid data in Transection Date field. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_11 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by entering invalid data in Status field. | Finance User is at Generate Invoice pop up. | 1) Enter Invalid data in Status field. 2) Enter valid details in then remianing fields. 3)Click on submit button. |  |  |  | Payment details should not get submitted and also there should be a proper validation message for the same.
TC_TC_Add_Payment_12 | 10805 | 2020-05-11 | To verify if the Finance User is able to add payment by entering valid data in all fields. | Finance User is at Generate Invoice pop up. | 1 Enter valid details in all fields. 3)Click on submit button. |  |  |  | Payment details should get submitted.

## SIT CPP
Area | Source System | Test Scenarios | Expected Results | Actual Results | Assumptions | Status | Issues | Comment | SIT Date
Claim Creation | SFDC | A case is created on SFDC for CPP Cashless, then Case Creation API will get triggered and Case Details will be sent to ReAssure | Claim should get created successfully on ReAssure system | Claim has been created successfully on ReAssure system. |  | Done | 1.There is issue of leading space in Problem category sending from SFDC and this has benn fixed now by kailash ojha-Fixed | Discussion Point : If there is no value coming in Country from SFDC then it will saving null at ReAssure.This need to be discussed as i remeber shailena thakar suggested it to be saved India always at ReAssure CC Arpit Limba Roohani Deshpande | 5/4/2020
All Mandatory fields data will pass pass from SFDC to ReAssure as per mentioned in Document
|  |  |  | Verfiied it for random 3 products | GLOW-REASSURE API INTEGRATION DOCUMENT |  | 2. If there is no value coming in Country from SFDC then it will saving null at ReAssure.This need to be discussed as i remeber shailena thakar suggested it to be saved India always at ReAssure CC Arpit Limba Roohani Deshpande- Fixed
1. Refirgerator
2. LED TV
3. Air Conditioner
| SFDC | Test case creation for CPP Reimbursement | Reimbursment Claim should not created at ReAssure system | Claim did not created as expected.
Visit ReSchedule | ReAssure | When Appointment Date is not equal to Visit Schedule Date then visit rescheduled API will get triggered and the same should get appear at SFDC. | Due date should be updated on SA on SFDC Sytem as per new date coming from ReAssure end | Due date has been updated on SFDC but time is not updating with current time and updating end time of each slot mentioned in ReAssure. | 1. Visit Reschedule date will always come from Reassure to SFDC(Mandatory field). | Done | 1.ReAssure need to internally handle that Visit Reschedule API will get call only when Appointment date is equal/greater than Schedule date. -Open | 1.Discussion required with both teams. CC Arpit Limba Roohani Deshpande as there is time validation also at SFDC but not at ReAssure | 5/4/2020
|  |  |  | Here are three 3 slots at ReAssure : | 2. Appointment date(Due date) will be always equal/greater than Schedule date. |  | 2. Currently Start time of slot sending from Reassure to SFDC but expected is to send end time of slot.-Fixed | Solution after discussion : Slot end time should come to SFDC instead of start time. cc Jitendra K Roohani Deshpande -Fixed
1. 10:00AM- 12:30 PM -> if Visit rescheduled during this slot time at Reassure then it will update with 12:30PM at SFDC.
[5 empty] | 3. Date Format will be yyyy-MM-dd HH:mm:ss |  |  | 2. At SFDC there is validation that Appointment date(Due date) time can not be less than Schedule date time but ReAssure saves Date only and there can be a situation when ReAssure select Appointment date equal to Schdule date with time slot which is less than schedule date time at SFDC and API will fail because of existing validation at SFDC.
|  |  |  | 2. 12:30 PM - 4:30PM -> if Visit rescheduled during this slot time at Reassure then it will update with 4:30 PM at SFDC. |  |  |  | Discussion required CC Arpit Limba Roohani Deshpande
|  |  |  | 3.4:30 PM - 7:00PM-> if Visit rescheduled during this slot time at Reassure then it will update with 7:00PM at SFDC. |  |  |  | Solution After Discussion : time validation between these fields needs to be removed from SFDC. Only Date validation will be there.
Doument Upload | ReAssure | Document Uploaded by the engineer/repairer should get save to the reassure Database after submitting the Inspection details. | Files uploaded by ReAssure should be visible in 'Approved' folder in Spring CM. |  |  | Pending
Inspection Completed | ReAssure | Inspection completed on mobile: Whenever engineer completes the inspection and submits it then the same details should get stored in the repairer database, then API will get triggered | Status should be updated to
SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done.
and values send in parametrs should get updated to SFDC System
Inspection Completed |  | Inspection completed on Web: Whenever repairer completes the inspection and submits it, the Inspection Completed API will get triggered | 1.Status should be updated to | API called succesfully and Status updated to | 1 . Problem Category and Sub Category is mandatory to pass from ReAssure and it will be from Master data only. | In Progress | 1. Issue in Problem category and Sub category payload value (It sending under [] which need to remove) and Ajay Kumar is taking care of this.-Fixed | ReAssure always passing 00:00:00 UTC time with Visit Completion date (E.g "2020-05-07 00:00:00") and it will save to SFDC and show 5:30 am time(IST) with date on UI. | 5/4/2020
|  |  | SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done. | SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done. |  |  |  | Although there is no validation affecting with this but it seems weird as ideally no once visit at 5:30 am.
|  |  |  | - Visit Compeliton date and Repair age not updating correctly. | 2. Visit Completion date is mandatroy to pass and it will not be future date. |  | 2. Picklist values for Problem Category and Problem Sub Category is not correct/empty for some product categories - to be checked internally at ReAssure | Discussion required CC Arpit Limba Roohani Deshpande
|  |  | 2. Values send in parametrs should get updated to SFDC System |  |  |  | e.g.
[5 empty] | 3.Date Format will be yyyy-MM-dd HH:mm:ss |  | 1. there is no picklist for Vacuum Cleaner product. | Solution After Discussion : ReAssure need to share current UTC time with Visit Completion date instead of 00:00:00 time
2. There is difference in picklist values in LED TV
Product Category names can be multiple for one type of product e.g. LED, LCD for tv.
Open
3. Currently it is passing "00:00:00" with date ib Visit Completion date. this needs to be send current UTC instead of "00:00:00"-Open
4. Currently Reapir agr is handled at ReAssure and taht is why we unable to test thta Scenario. This needs to be take care by ReAssure internally first - Open
Inspection Completed |  | When 'Is Repair Completed' get checked at the time of inspection done. |  |  |  | Pending |  | As per Discussion with Roohani Deshpande she needs to discuss first with Arpit Limba
Estimate submitted by Repairer | ReAssure | After the submission of estaimation for repair the "Estimate submitted by Repairer" API will get triggered | 1.Status should be updated to SDFC System | API called succesfully and Status and other values are updated at SFDC. | 1. Estimate id ,"SAC_or_HSN_Code","QTY","unit_cost" will always pass(mandatory to pass) from ReAssure and QTY will not be 0 in any case. | In Progress | Issue in IGST,CGST,SGST validation which is taking care by Ajay Kumar-Fixed | ReAssure always passing 00:00:00 UTC time with Estimated Repair Completion date (E.g "2020-05-07 00:00:00") and it will save to SFDC and show 5:30 am time(IST) with date on UI. | 5/4/2020
|  |  | WO- Submit For Authorization , Case Sub status - Pending Adjudication. |  |  |  |  | It seems weird to show 5:30 am in time on UI
[5 empty] | 2. Enter Either CGST and SGST Both or Enter IGST Only . |  |  | Discussion required CC Arpit Limba Roohani Deshpande
2. Numberof WOLI should be created as per array passed in API and All details passed in parameters should be saved in glow in WOLI as per respective WOLI details.
[5 empty] | 3. Estimated Repair Completion date will always pass(mandatiry to pass) from ReAssure and it can be future date only. |  |  | Solution After Discussion : ReAssure need to share current UTC time with Estimated Repair Completion date instead of 00:00:00 time - Fixed
3. "Discount" on Work Order should be updated by "Discount" value in API.
4. Date Format will be yyyy-MM-dd HH:mm:ss
4. Calculation of Requested,Authorzed and tax related fields should be done correctly as per values in all WOLIs
Estimate Approved | ReAssure | Repairer's estimate will be approved on ReAssure by Case Manager | 1. Status should be updated to SFDC System | API called succesfully and Status and other values are updated at SFDC. | 1. Estimates (WOLI) would be updated as per matching Estimate id coming in Estimate Submisison API and Estimate Approval APIs. | In Progress | 1. Issue in IGST,CGST,SGST validation which is taking care by Ajay Kumar-Fixed |  | 5/4/2020
WO- Approved , Case Sub status - Repair Approved(For CPP) and Case Sub status - Repair Cost Under Review(For ACKO).
[5 empty] | 2.Estimate ids will come in this API among Ids which was sent in Estimate Submission. |  | 2. Issue in adding new parts and deleting parts and this needs to be take care by ReAssure internally first then only we will able to test this Scenario in SIT - Open
2. WOLIs details (Authorized amount and tax values) should get updated as per new values coming in matching"Estimate_id".
3. Estimate id ,"SAC_or_HSN_Code","QTY","unit_cost" will always pass(mandatory to pass) from ReAssure and QTY will not be 0 in any case.
3. WO details like 'discount' should get updated as per new values coming in API.
4. Enter Either CGST and SGST Both or Enter IGST Only .
4. Calculation of Requested,Authorzed and tax related fields should be done correctly as per updated values in all WOLIs
5. Total Authorized amount at ReAssure will never be 0 and can't be more than Reserve amount on claim.
Estimate Approved | ReAssure | Delete some parts and approved the Estimate | Estimate for deleted ID will be 0 at SFDc after successfull integration |  |  | Pending | One scenario is yet to be tested for deleting any product at the time of estimate approval. Reassure needs to internally handle this as currently part is not getting deleted at reassure end.
Part Pending | ReAssure | When there is some part gets pending after the Estimate approval then repairer updates the status as Repair in progress-Part pending then Part Pending API will get triggered . | WO Sub Status should be updated to 'Pending Parts' at SFDC System | WO Sub Status is updated to 'Pending Parts' at SFDC System | Sub status value will always pass (Mandatory) from ReAssure and value will be 'Pending Parts' always | Done |  |  | 5/5/2020
Doument Upload | ReAssure | Document Uploaded by the engineer/repairer should get save to the reassure Database after submitting the Repairer details. | Files uploaded by ReAssure should be visible in 'Approved' folder in Spring CM. |  |  | Pending
Repair Completed | ReAssure | Repairer completed on mobile: Whenever engineer completes the repair and submits it then the same details should get stored in the repairer database, then API will get triggered | 1.Work Order status should be updated to 'Repair Complete' and Case Status- Sub status should be updated to 'Repair Completed-None'.
2. Field Values should get updated on SFDC as per values mentioned in API.
Repair Completed |  | Repairer completed on Web: Whenever repairer completes the inspection and submits it, the Repairer Completed API should get triggered | 1.Work Order status should be updated to 'Repair Complete' and Case Status- Sub status should be updated to 'Repair Completed-None'. | API called succesfully and Status and other values are updated at SFDC. | 1. Status Value always pass from ReAssure (Mandatory) and it will be 'Repair Complete' always . | Done | Issue in Resolution value (It sending under [] which need to remove) and Ajay Kumar is taking care of this.-Fixed | ReAssure always passing 00:00:00 UTC time with Repair Completion date (E.g "2020-05-07 00:00:00") and it will save to SFDC and show 5:30 am time(IST) with date on UI. | 5/5/2020
And
|  |  | 2. Field Values should get updated on SFDC as per values mentioned in API. |  | 2. Resolution will always pass(Mandatory)and it will be free text. |  |  | there is a existing validation on SFDC system that this date can not be less than start date on SFDC.
Now in case claim creation and Repair is done on same day then it will have start date = 'WO creation date with time' and End date passed by ReAssure will be same date with 5AM and it will fail the API becasue of validtaion error.
[5 empty] | 3. Action type and Repair type will always pass from ReAssure to SDFC and it will be from Master data only (Mandatory fields) |  |  | Also it seems weird to show 5:30 am in time on UI
Discussion required CC Arpit Limba Roohani Deshpande
4. Repair Completion date will always pass(Mandatory) and it will not less than claim created date and will not be future date also.
Solution After Discussion : ReAssure need to share current UTC time with Repair Completion date instead of 00:00:00 time - Fixed
5. Date Format will be yyyy-MM-dd HH:mm:ss
Customer Confirmed | ReAssure | when repairer's invoice gets approved on reassure then Customer Confirmed API will get triggered. | 1.Case Sub status should be updated to 'Customer Confirmed' at SDFC System | 1.Case Sub status is updated to 'Customer Confirmed' at SDFC System | Sub status always pass from ReAssure (Mandatory) and it will be 'Customer Confirmed' always | Done |  |  | 5/5/2020
|  |  | 2. Authorized amount should be deducted from Credit Available and added to Credit Used on CLI. | 2. Authorized amount is deducted from Credit Available and added to Credit Used on CLI.
Repairer Payment | ReAssure | After the submission of Payment details on Reassure portal "Repairer Payment" API will get triggered. | All the field data and status sent from Reassure should be updated at Glow(SFDC) on Work order object. | API called succesfully and Status and other values are updated at SFDC. | 1.Payment status pass from ReAssure to SFDc will be 'Invoice Paid' always | Done | Currently value 'paid' coming from Reassure which should be 'Invoice Paid'. which is taking care by Ajay Kumar-Fixed |  | 5/5/2020
2. Date Format for date fields will be yyyy-MM-dd
Claim Cancellation | ReAssure | When Repairer updates the Case Status as "Cancelled" then Claim Cancellation API will get triggered. | 1.Case status should be updated to 'Closed-Rejected' on SFDC. | Case Status updated to 'Closed - Rejected' and Denial Reason at SFDC get updated by Cancellation Reason selected by ReAssure. | 1. Statua Value will always pass from ReAssure(Mandatory)and it will be 'Case Cancelled' always | Done |  |  | 5/4/2020
|  |  | 2. Denial Reason should be update to SFDC by Cancellation Reason in API. |  | 2.Cancellation Reason will always pass from ReAssure(Mandatory) to SFDC.
Claim Cancellation | SFDC | When CSR marks the Case status to 'Closed - Rejected' | 1.Cancellation API should get called with claim status "Cancelled" and Cancellation Reason. | It has been updated to ReAssure with Case sub status 'Cancelled by Insurer’ | 1.Claim status Value going to API will be "Cancelled" always | Done | On Cancellation ReAssure need to set status 'Cancelled by Insurer' - Fixed | Discussion point : Case sub status 'Cancelled by CSR' and currently cancellation reason not showing on UI but it captured correctly in database. cc Arpit Limba Roohani Deshpande | 5/5/2020
|  |  | 2. It should be updated to ReAssure System. |  | 2.Cancellation Reason will always pass from SFDC to ReAssure.
Case Escalation | SFDC | When CSR Go to Case and check the Escalated Checkbox | 1. ReAssure Escalation API should get called with 'Yes' value in Escalation field. | It has been updated to ReAssure Database but it not showing on UI. | Value in "escalation" will be "Yes" always. | In Progress | It has been updated to ReAssure Database but it not showing on UI. This needs to be handle internally by ReAssure - Open | Discussion Point : It has been updated to ReAssure Database but it not showing on UI. CC Arpit Limba Roohani Deshpande | 5/5/2020
2. It should be updated to ReAssure System.
Repairer Onboarding on ReAssure | ReAssure | After the onboarding of new repairer on reassure portal "Repairer Onboarding on ReAssure' will get triggered.

## SIT ACK
Area | Source System | Test Scenarios | Expected Results | Actual Results (ACKO) | Assumptions | Status | Issues | Comment | SIT Date
Claim Creation | SFDC | A case is created on SFDC for ACKO Cashless, then Case Creation API will get triggered and Case Details will be sent to ReAssure | Claim should get created successfully on ReAssure system | Claim has benn created successfully on ReAssure system. |  | Done |  |  | 5/5/2020
All Mandatory fields data will pass pass from SFDC to ReAssure as per mentioned in Document
|  |  |  | Verfiied it for random 3 products | GLOW-REASSURE API INTEGRATION DOCUMENT
1. Dishwasher
2. Vacuum Cleaner
3. Washing Machine
Visit ReSchedule | ReAssure | When Appointment Date is not equal to Visit Schedule Date then visit rescheduled API will get triggered and the same should get appear at SFDC. | Due date should be updated on SA on SFDC Sytem as per new date coming from ReAssure end | Due date has been updated on SFDC but time is not updating with current time and updating end time of each slot mentioned in ReAssure. | 1. Visit Reschedule date will always come from Reassure to SFDC(Mandatory field). | Done |  |  | 8/5/2020
|  |  |  | Here are three 3 slots at ReAssure : | 2. Appointment date(Due date) will be always equal/greater than Schedule date.
1. 10:00AM- 12:30 PM -> if Visit rescheduled during this slot time at Reassure then it will update with 12:30PM at SFDC.
3. Date Format will be yyyy-MM-dd HH:mm:ss
2. 12:30 PM - 4:30PM -> if Visit rescheduled during this slot time at Reassure then it will update with 4:30 PM at SFDC.
3.4:30 PM - 7:00PM-> if Visit rescheduled during this slot time at Reassure then it will update with 7:00PM at SFDC.
Doument Upload | ReAssure | Document Uploaded by the engineer/repairer should get save to the reassure Database after submitting the Inspection details. | Files uploaded by ReAssure should be visible in 'Approved' folder in Spring CM. |  |  | Pending
Inspection Completed | ReAssure | Inspection completed on mobile: Whenever engineer completes the inspection and submits it then the same details should get stored in the repairer database, then API will get triggered | Status should be updated to |  |  |  | Picklist values for Problem Category and Problem Sub Category is not correct/empty for some product categories - to be checked internally at ReAssure
|  |  | SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done. |  |  |  | e.g.
1. there is no picklist for Vacuum Cleaner product.
|  |  | and values send in parametrs should get updated to SFDC System |  |  |  | 2. There is difference in picklist values in LED TV
Product Category names can be multiple for one type of product e.g. LED, LCD for tv
Inspection Completed |  | Inspection completed on Web: Whenever repairer completes the inspection and submits it, the Inspection Completed API will get triggered | 1.Status should be updated to | API called succesfully and Status updated to | 1 . Problem Category and Sub Category is mandatory to pass from ReAssure and it will be from Master data only. | In Progress |  |  | 8/5/2020
|  |  | SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done. | SA -> Completed , WO- Visit Completed , Case Status sub status -> Repair in Progress,Inspection Done.
|  |  |  | - Visit Compeliton date and Repair age not updating correctly. | 2. Visit Completion date is mandatroy to pass and it will not be future date.
2. Values send in parametrs should get updated to SFDC System
3.Date Format will be yyyy-MM-dd HH:mm:ss
Estimate submitted by Repairer | ReAssure | After the submission of estaimation for repair the "Estimate submitted by Repairer" API will get triggered | 1.Status should be updated to SDFC System | API called succesfully and Status and other values are updated at SFDC. | 1. Estimate id ,"SAC_or_HSN_Code","QTY","unit_cost" will always pass(mandatory to pass) from ReAssure and QTY will not be 0 in any case. | In Progress |  |  | 8/5/2020
WO- Submit For Authorization , Case Sub status - Pending Adjudication.
2. Enter Either CGST and SGST Both or Enter IGST Only .
2. Numberof WOLI should be created as per array passed in API and All details passed in parameters should be saved in glow in WOLI as per respective WOLI details.
3. Estimated Repair Completion date will always pass(mandatiry to pass) from ReAssure and it can be future date only.
3. "Discount" on Work Order should be updated by "Discount" value in API.
4. Date Format will be yyyy-MM-dd HH:mm:ss
4. Calculation of Requested,Authorzed and tax related fields should be done correctly as per values in all WOLIs
Estimate Approved | ReAssure | Repairer's estimate will be approved on ReAssure by Case Manager | 1. Status should be updated to SFDC System | API called succesfully and Status and other values are updated at SFDC. | 1. Estimates (WOLI) would be updated as per matching Estimate id coming in Estimate Submisison API and Estimate Approval APIs. | In Progress |  |  | 8/5/2020
WO- Approved , Case Sub status - Repair Approved(For CPP) and Case Sub status - Repair Cost Under Review(For ACKO).
2.Estimate ids will come in this API among Ids which was sent in Estimate Submission.
2. WOLIs details (Authorized amount and tax values) should get updated as per new values coming in matching"Estimate_id".
3. Estimate id ,"SAC_or_HSN_Code","QTY","unit_cost" will always pass(mandatory to pass) from ReAssure and QTY will not be 0 in any case.
3. WO details like 'discount' should get updated as per new values coming in API.
2. Enter Either CGST and SGST Both or Enter IGST Only .
4. Calculation of Requested,Authorzed and tax related fields should be done correctly as per updated values in all WOLIs
Estimate Approved | ReAssure | Delete some parts and approved the Estimate | Estimate for deleted ID will be 0 at SFDc after successfull integration |  |  | Pending
Client Approval | SFDC | On Hold : ACKO Put the Estimate on Hold | Client Approval API should get called with "On Hold" and it should be updated at ReAssure End. | It has been updated to ReAssure Database but it not showing on UI. | Status value sending in API will be 'On Hold' | In Progress | It has been updated to ReAssure Database but it not showing on UI. |  | 6/5/2020
|  |  |  | This is taking care by Ajay Kumar . |  |  | This is taking care by Ajay Kumar .
|  | Repair Approved : ACKO approves the Estimate | Client Approval API should get called with "Approved" and it should be updated at ReAssure End. | It has been updated to ReAssure Database but it not showing on UI. | Status value sending in API will be 'Approved' | In Progress | It has been updated to ReAssure Database but it not showing on UI. |  | 6/5/2020
|  |  |  | This is taking care by Ajay Kumar . |  |  | This is taking care by Ajay Kumar .
Part Pending | ReAssure | When there is some part gets pending after the Estimate approval then repairer updates the status as Repair in progress-Part pending then Part Pending API will get triggered . | WO Sub Status should be updated to 'Pending Parts' at SFDC System | WO Sub Status is updated to 'Pending Parts' at SFDC System | Sub status value will always pass (Mandatory) from ReAssure and value will be 'Pending Parts' always | Done
Doument Upload | ReAssure | Document Uploaded by the engineer/repairer should get save to the reassure Database after submitting the Repairer details. | Files uploaded by ReAssure should be visible in 'Approved' folder in Spring CM. |  |  | Pending
Repair Completed | ReAssure | Repairer completed on mobile: Whenever engineer completes the repair and submits it then the same details should get stored in the repairer database, then API will get triggered | 1.Work Order status should be updated to 'Repair Complete' and Case Status- Sub status should be updated to 'Repair Completed-None'.
2. Field Values should get updated on SFDC as per values mentioned in API.
Repair Completed |  | Repairer completed on Web: Whenever repairer completes the inspection and submits it, the Repairer Completed API should get triggered | 1.Work Order status should be updated to 'Repair Complete' and Case Status- Sub status should be updated to 'Repair Completed-None'. | API called succesfully and Status and other values are updated at SFDC. | 1. Status Value always pass from ReAssure (Mandatory) and it will be 'Repair Complete' always . | Done |  |  | 8/5/2020
|  |  | 2. Field Values should get updated on SFDC as per values mentioned in API. |  | 2. Resolution will always pass(Mandatory)and it will be free text.
3. Action type and Repair type will always pass from ReAssure to SDFC and it will be from Master data only (Mandatory fields)
4. Repair Completion date will always pass(Mandatory) and it will not less than claim created date and will not be future date also.
5. Date Format will be yyyy-MM-dd HH:mm:ss
Customer Confirmed | ReAssure | when repairer's invoice gets approved on reassure then Customer Confirmed API will get triggered. | 1.Case Sub status should be updated to 'Customer Confirmed' at SDFC System | 1.Case Sub status is updated to 'Customer Confirmed' at SDFC System | Sub status always pass from ReAssure (Mandatory) and it will be 'Customer Confirmed' always | Done |  |  | 8/5/2020
|  |  | 2. Authorized amount should be deducted from Credit Available and added to Credit Used on CLI. | 2. Authorized amount is deducted from Credit Available and added to Credit Used on CLI.
Repairer Payment | ReAssure | After the submission of Payment details on Reassure portal "Repairer Payment" API will get triggered. | All the field data and status sent from Reassure should be updated at Glow(SFDC) on Work order object. | API called succesfully and Status and other values are updated at SFDC. | 1.Payment status pass from ReAssure to SFDc will be 'Invoice Paid' always | Done |  |  | 8/5/2020
2. Date Format for date fields will be yyyy-MM-dd
Claim Cancellation | ReAssure | When Repairer updates the Case Status as "Cancelled" then Claim Cancellation API will get triggered. | 1.Case status should be updated to 'Closed-Rejected' on SFDC. | Case Status updated to 'Closed - Rejected' and Denial Reason at SFDC get updated by Cancellation Reason selected by ReAssure. | 1. Statua Value will always pass from ReAssure(Mandatory)and it will be 'Case Cancelled' always | Done |  |  | 6/5/2020
|  |  | 2. Denial Reason should be update to SFDC by Cancellation Reason in API. |  | 2.Cancellation Reason will always pass from ReAssure(Mandatory) to SFDC.
Claim Cancellation | SFDC | When CSR marks the Case status to 'Closed - Rejected' | 1.Cancellation API should get called with claim status "Cancelled" and Cancellation Reason. | It has been updated to ReAssure with Case sub status 'Cancelled by Insurer’ | 1.Claim status Value going to API will be "Cancelled" always | Done |  |  | 6/5/2020
|  |  | 2. It should be updated to ReAssure System. |  | 2.Cancellation Reason will always pass from SFDC to ReAssure.
|  | When Acko Cancel the claim | 1.Cancellation API should get called with claim status "Cancelled" and Cancellation Reason. | It has been updated to ReAssure with Case sub status 'Cancelled by Insurer’ | 1.Claim status Value going to API will be "Cancelled" always | Done |  |  | 6/5/2020
|  |  | 2. It should be updated to ReAssure System. |  | 2.Cancellation Reason will always pass from SFDC to ReAssure.
|  | When Acko Rejectt the claim during estimate approval. | 1.Cancellation API should get called with claim status "Cancelled" and Cancellation Reason. | It has been updated to ReAssure with Case sub status 'Cancelled by Insurer’ | 1.Claim status Value going to API will be "Cancelled" always | Done |  |  | 6/5/2020
|  |  | 2. It should be updated to ReAssure System. |  | 2.Cancellation Reason will always pass from SFDC to ReAssure.
Case Escalation | SFDC | When CSR Go to Case and check the Escalated Checkbox | 1. ReAssure Escalation API should get called with 'Yes' value in Escalation field. | It has been updated to ReAssure Database but it not showing on UI. | Value in "escalation" will be "Yes" always. | In Progress |  |  | 6/5/2020
2. It should be updated to ReAssure System.
Repairer Onboarding on ReAssure | ReAssure | After the onboarding of new repairer on reassure portal "Repairer Onboarding on ReAssure' will get triggered.

## credentials
http://reassure.innov.co.in/complaints
admin | admin
ajay | ajay
san001 | san001
googledoc: | https://docs.google.com/spreadsheets/d/1pwKJVMrLOqxpsYgbf0Rry7DuS4d4bR2sAWakcFEDU4Q/edit?ts=5ea2dd89#gid=1347446355
wireframe: | https://techfour296418.invisionapp.com/console/ReAssure-ck53oxgz50b7z013r3od0tn3d/ck53wcevn0dze01731ojto508/play
REASSURE Development Tasks | https://docs.google.com/spreadsheets/d/1pwKJVMrLOqxpsYgbf0Rry7DuS4d4bR2sAWakcFEDU4Q/edit?ts=5ea2dd89#gid=369532445
https://docs.google.com/spreadsheets/d/1pwKJVMrLOqxpsYgbf0Rry7DuS4d4bR2sAWakcFEDU4Q/edit#gid=1807645259
https://docs.google.com/spreadsheets/d/1pwKJVMrLOqxpsYgbf0Rry7DuS4d4bR2sAWakcFEDU4Q/edit#gid=1126709398
ReAssure Requirement List | https://docs.google.com/spreadsheets/d/1xQ9izy4awzurQoRV2qG6-nNYluZEo5rloo5fO2ltO-Y/edit?ts=5ea94de8#gid=1234405260

## Sheet1
When Appointment Date is not equal to Visit Schedule Date then visit rescheduled API should get triggered and the same should get appear at SFDC.
Inspection completed on mobile: Whenever engineer completes the inspection and submits it then the same details should get stored in the repairer database, then API will get triggered
Inspection completed on Web: Whenever repairer completes the inspection and submits it, the Inspection Completed API should get triggered
After the submission of estaimation for repair the "Estimate submitted by Repairer" API will get triggered
Repairer's estimate will be approved on ReAssure by Case Manager
When there is some part still pending after the Estimate approval then repairer updates the status as Repair in progress-Part pending then Part Pending API should get triggered .
Inspection completed on mobile: Whenever engineer completes the repair and submits it then the same details should get stored in the repairer database, then API will get triggered
Inspection completed on Web: Whenever repairer completes the inspection and submits it, the Inspection Completed API should get triggered
when repairer's invoice gets approved on reassure then Customer Confirmed API will get triggered.
After the submission of Payment details on Reassure portal "Repairer Payment" API will get triggered.
When Repairer updated the Case Status as "Cancelled" then Claim Cancellation API will get triggered.
After the onboarding of new repairer on reassure portal "Repairer Onboarding on ReAssure' will get triggered.

## Sheet2
{"Discount": "15.50", "Estimate": [{"QTY": 1, "unit_cost": 150.12, "Estimate_id": 128, "CGST_Percentage": null, "IGST_Percentage": 18, "SAC_or_HSN_Code": "1234", "SGST_Percentage": null, "Part_Description": "Headphone"}, {"QTY": 1, "unit_cost": 250, "Estimate_id": 129, "CGST_Percentage": 9, "IGST_Percentage": null, "SAC_or_HSN_Code": "4567", "SGST_Percentage": 9, "Part_Description": "Labour"}, {"QTY": 2, "unit_cost": 150, "Estimate_id": 130, "CGST_Percentage": null, "IGST_Percentage": 9, "SAC_or_HSN_Code": "7890", "SGST_Percentage": null, "Part_Description": "Transportation"}], "Excess_Amount": "15.00", "Repair_Action": "", "aiz_claim_number": "230156", "Estimated_Repair_completion_date": "2020-05-10 12:36:50"}
{"Fault_Category": "", "aiz_claim_number": "78987789", "Repeat_Repair_Age": 0, "Inspection_Completion_Date": "2020-05-12 10:42:01", "Problem_Category_identified": "Distorted Audio", "Problem_SubCategory_identified": "Headphone Faulty"}
{"Status": "Repair Complete", "Resolution": "Test data repair", "Repair_Type": "Major", "Action_Taken": "Electrical Part Repaired", "aiz_claim_number": "78987789", "Repair_Completion_Date": "2020-05-15 11:37:51"}
{"aiz_claim_number":"06418944","Fault_Category":"","Problem_Category_identified":"Leakage from Door","Problem_SubCategory_identified":"Over Loaded","Inspection_Completion_Date":"2020-05-10 06:22:54","Repeat_Repair_Age":0}
{"Discount": "10.00", "Estimate": [{"QTY": null, "unit_cost": 50, "Estimate_id": 115, "CGST_Percentage": null, "IGST_Percentage": null, "SAC_or_HSN_Code": "test1", "SGST_Percentage": null, "Part_Description": "Gasket"}, {"QTY": 5, "unit_cost": null, "Estimate_id": 116, "CGST_Percentage": null, "IGST_Percentage": 10, "SAC_or_HSN_Code": "0", "SGST_Percentage": null, "Part_Description": "PCB"}, {"QTY": null, "unit_cost": null, "Estimate_id": 117, "CGST_Percentage": 2, "IGST_Percentage": null, "SAC_or_HSN_Code": "0", "SGST_Percentage": 3, "Part_Description": "Labour"}, {"QTY": null, "unit_cost": 9, "Estimate_id": 118, "CGST_Percentage": null, "IGST_Percentage": null, "SAC_or_HSN_Code": "0", "SGST_Percentage": null, "Part_Description": "Transportation"}], "Excess_Amount": null, "Repair_Action": "", "aiz_claim_number": "06418944", "Estimated_Repair_completion_date": "2020-05-14 06:52:47"}