## Summery
GIL CSRP
Lead Dev: Rahul Verma
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestions
User_Organisation | 63 | 62 | 50 | 12 | 0
Total | 63 | 62 | 50 | 12 | 0

## Open Bugs
Bug Report
Project :-GIL CSRP | [7 empty] | Lead_Developer: Rahul Verma
Created_By :-Jitendra |  |  |  | Module: User_Organisation
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close
2020-02-29 | NA | 1 | 10220 | The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 2 | 10220 | User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | Fixed
2020-02-29 | NA | 3 | 10220 | All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | Fixed
2020-02-29 | NA | 4 | 10220 | The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 5 | 10220 | The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 6 | 10220 | The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | Fixed
2020-02-29 | NA | 7 | 10220 | Suggestion: There should be a proper and spacific confirmation message before deleting any existing mapping. | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 8 | 10220 | Validation message appears if user user accidentally clicks on edit button againste the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 9 | 10220 | User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 10 | 10220 | User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 11 | 10220 | User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 12 | 10220 | Plant QC: Validation message appearing for leaving all the mandatory fields blank is wrong as " Business Vertical, Country, Zone, Region, Territory are empty" There is no Zone, Region, Territory as the mapping field. It should be "Business Vertical, Plant and Country is empty" | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 13 | 10220 | Plant QC: Validation message appearing for leaving User plant is wrong. Its showing " Zone, Region, Territory are empty" Instead of showing "User Plant is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 14 | 10220 | Plant QC: Validation message appearing for leaving User plant and User Country is wrong. Its showing " Country, Zone, Region, Territory are empty" Instead of showing "User Plant and Country is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-02-29 | NA | 15 | 10220 | Plant QC: User is not able to add mapping for Plant QC as there is no data available in User Plant field. | User is logged in and is on User Organisation Page. | 1) Select any user having role as Plant QC. 2)Select Business Vertical,User Plant and User Country. |  |  | High | High | Fixed
2020-02-29 | NA | 16 | 10220 | Zonal_Head :The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 17 | 10220 | Zonal_Head :User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | Fixed
2020-02-29 | NA | 18 | 10220 | Zonal_Head : All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | Fixed
2020-02-29 | NA | 19 | 10220 | Zonal_Head :The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter valid data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 20 | 10220 | Zonal_Head :The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 21 | 10220 | Zonal_Head :The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | Fixed
2020-02-29 | NA | 22 | 10220 | Zonal_Head :Validation message appears if user user accidentally clicks on edit button against the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 23 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 24 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 25 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 26 | 10220 | BCM :The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 27 | 10220 | BCM :User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | Fixed
2020-02-29 | NA | 28 | 10220 | BCM : All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | Fixed
2020-02-29 | NA | 29 | 10220 | BCM :The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter valid data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 30 | 10220 | BCM :The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | Fixed
2020-02-29 | NA | 31 | 10220 | BCM :The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | Fixed
2020-02-29 | NA | 32 | 10220 | BCM :Validation message appears if user user accidentally clicks on edit button against the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 33 | 10220 | BCM :User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 34 | 10220 | BCM :User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 35 | 10220 | BCM :User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | Fixed
2020-02-29 | NA | 36 | 10220 | Wrong user Role is appearing in the dropdown list of User role as "Organisation" which is not a role. | User is logged in and is on User Organisation Page. | 1) Try to change the role by clicking on the USER ROLE dropdown list. |  |  | High | High | Fixed
2020-02-29 | NA | 37 | 10220 | If user delets any business verticle from business verticle master then there should be a validation message saying " If you delete this verticle then all the mapping against this verticle will get delete." | User is logged in and is on Business verticle Master | 1) Click on Vertical Ellipsis against the business verticle you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | Fixed
2020-02-29 | NA | 38 | 10220 | If user delets any business verticle from business verticle master then the mappings corresponding to the same verticle gets changed to "AFX' business verticle. | User is logged in and is on Business verticle Master | 1) Click on Vertical Ellipsis against the business verticle you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. 4) Now check all the mappings that was previously mapped with the old verticle. |  | https://drive.google.com/open?id=1O1TAJvZnd9aJlTPOucPekXtSBg0zecMQ | High | High | Fixed
2020-02-29 | NA | 39 | 10220 | Deleted Territory is appearing in the dropdown list of Territory while adding any new mapping. |  | 1) Delete any Territory from the Territory master against which there is some mapping. 2) Now add any new mapping and try to select the deleted mapping. |  | https://drive.google.com/open?id=1BVKrUn4ecTK3N9IIm3rqGpG5ywV5NWba | High | High | Not able to execute as the territory is not getting deleted.
2020-02-29 | NA | 40 | 10220 | If user delets any Country from Countrymaster then there should be a validation message saying " If you delete this Country then all the mapping against this Country will get delete." | User is logged in and is on CountryMaster | 1) Click on Vertical Ellipsis against the Country you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | Fixed
2020-02-29 | NA | 41 | 10220 | If user delets any Country from Country master then the mappings corresponding to the same Country gets changed to "Andorra' Country Name. | User is logged in and is on CountryMaster | 1) Click on Vertical Ellipsis against the Country you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. 4) Now check all the mappings that was previously mapped with the old Country. |  | https://drive.google.com/open?id=1d2-h12NyFhiFfW3MlFxBFDLfp4arVSwn | High | High | Fixed
2020-02-29 | NA | 42 | 10220 | If user delets any Region from Region master then there should be a validation message saying " If you delete this Region then all the mapping against this Region will get delete." | User is logged in and is on RegionMaster | 1) Click on Vertical Ellipsis against the Region you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | Fixed
2020-02-29 | NA | 43 | 10220 | Deleted Region is appearing in the dropdown list of Region while adding any new mapping. | User is logged in and is on RegionMaster | 1) Delete any Region from the Region master against which there is some mapping. 2) Now add any new mapping and try to select the deleted mapping. |  | https://drive.google.com/open?id=13iD4iO1uMDtUiqw4r-5M_-h3GGXx_306 | High | High | Not fixed.
2020-03-03 | NA | 44 | 10241 | Territory Master: Option to delete the terrioty is not functional under verticle elipses. |  |  |  |  | High | High | New
2020-03-03 | NA | 45 | 10241 | If user delets any Territory from Territory master then there should be a validation message saying " If you delete this Territory then all the mapping against this Territory will get delete." |  |  |  |  | High | High | New
2020-03-03 | NA | 46 | 10241 | Territory Master: User is not able to delete any territory by clicking on delete icon after selecting a record to delete. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 47 | 10241 | Country Master: Option to delete the Country is not functional under verticle elipses. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 48 | 10241 | Region Master: Option to delete the Region is not functional under verticle elipses. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 49 | 10241 | If user updates any mapping by selecting ALL as Region or Zone then it does not update the mapping with "ALL" instead it shows the previous entry. |  |  |  |  | High | High | New
2020-03-03 | NA | 50 | 10241 | PlantQC: User is not able to add mapping against this user. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 51 | 10241 | If user updates any Business Verticle name from the verticle master then the same update should get appear in the existing mappings corresponding to the updated verticle. But this is not happening the updated record takes the first record from the verticle list. |  |  |  |  | High | High | New
2020-03-03 | NA | 52 | 10241 | Business Verticle should not get delete delete if it is mapped with any user and there should be a message for the same. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 53 | 10241 | If user updates any Territory name from the Territory master then the same update should get appear in the existing mappings corresponding to the updated Territory But his is not happening the updated record takes ALL as the territory name. |  |  |  |  | High | High | New
2020-03-03 | NA | 54 | 10241 | Territory should not get delete if it is mapped with any user and there should be a message for the same. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 55 | 10241 | Updated Region does not get reflectin the user mapping in both new and existing mappings. |  |  |  |  | High | High | New
2020-03-03 | NA | 56 | 10241 | There is no Region , zone and territory available for countries other than india but when user updates any mapping (india as country) to some other country then system updates the mapping by taking ALL in region, zone and territory. |  |  |  |  | High | High | New
2020-03-03 | NA | 57 | 10241 | Plant Head: User is not able to add mapping against this user. |  |  |  |  | High | High | Fixed
2020-03-03 | NA | 58 | 10241 | Plant Head: Validation message appearing for leaving User plant is wrong. Its showing " Zone, Region, Territory are empty" Instead of showing "User Plant is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-03-03 | NA | 59 | 10241 | Plant Head: Validation message appearing for leaving User plant and User Country is wrong. Its showing " Country, Zone, Region, Territory are empty" Instead of showing "User Plant and Country is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | Fixed
2020-04-03 | NA | 60 | 10241 | Grammatically wrong validation message appears for deleting a business vertical. |  |  |  |  | High | High | New
2020-04-03 | NA | 61 | 10241 | Wrong validation message is appearing for deleting a country it sshows a validation for deleting a business vertical instead of country. |  |  |  |  | High | High | New
2020-04-03 | NA | 62 | 10241 | Wrong validation message is appearing for deleting a region it sshows a validation for deleting a business vertical instead of country. |  |  |  |  | High | High | New
2020-04-03 | NA | 63 | 10241 | Region master has no link with the mappings. |  |  |  |  | High | High | New

## Old_User_Organisation
Bug Tracker
|  | Project | Greenlam CSRP
|  | Created By | Jitendra
|  | Module | User Organisation
|  | Task ID | 9970
Date | Bug ID | Bug Description | Severity | Priority | Status | URL/Attachments | Steps To Reproduce | Test Data | Assigned to | Developers Status | Developers Comments | Developers URL | Testers Comments | Open | Close
2020-02-10 | 1 | Creating New User Mapping Master: User is able to create new user without selecting his/her role. That is user role should be mandatory in order to add new User. | High | High | New | https://prnt.sc/r02zds | 1) Click on Add Record button. 2) Enter valid data in Username field. 3)Click Save button without selecting any role. | Test
2020-02-10 | 2 | Creating New User Mapping Master: User Name field is taking spaces as "jitendra k". Username should not take spaces. | High | High | New | https://prnt.sc/r033gy | 1) Click on Add Record button. 2) Enter invalid data in Username field. 3)Click Save button without selecting any role. | Jitendra k
2020-02-10 | 3 | Creating New User Mapping Master: Usernamee field is taking special characters. | Low | Low | New | https://prnt.sc/r0353l | 1) Click on Add Record button. 2) Enter invalid data in Username field. 3)Click Save button without selecting any role. | 1@#$%#%
2020-02-10 | 4 | Creating New User Mapping Master: User is able to add a same username more than one time. Username should be unique and there should not be any duplicacy of username. | High | High | New | https://prnt.sc/r03pi6
2020-02-10 | 5 | User Mapping Master Information: User is able to add user mapping by leaving all the fields blank as its taking first value from the dropdowns of User Business Vertical and User Country. And also its selecting all by default if user submits the form with blank enteries. Note: There should be a proper validation message for each mandatory fields. | High | High | New | https://prnt.sc/r036q7 | 1. Click on Add button without entering any data in the mandatory fields.
2020-02-10 | 6 | User Mapping Master Information: User is able to add user mapping by leaving User Business Vertical blank and also there should be proper validation message for the same. By default its taking AFX as the Business Vertical. | High | High | New |  | 1. Leave the User Business Vertical field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 7 | User Mapping Master Information: User is able to add user mapping by leaving User Country blank and also there should be proper validation message for the same. By default its taking Andorra as the User Country. | High | High | New |  | 1. Leave the User Country field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 8 | User Mapping Master Information: User is able to add user mapping by leaving User Country blank and also there should be proper validation message for the same. By default its taking Andorra as the User Country. | High | High | New |  | 1. Leave the User Country field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 9 | User Mapping Master Information: On clicking on "View All button" new page gets open with details of user which are not present in the user list. | High | High | New | https://prnt.sc/r03r8n https://prnt.sc/r03rot
2020-02-10 | 10 | User Mapping Master Information: Is user is able to map the duplicate entry that is sae user is getting mapped under the same business verticle and same user territory. | High | High | New | https://prnt.sc/r03trx
2020-02-10 | 11 | Suggestion: User Mapping Master Information: View All button should get hide as its showing the same data which is already present on the User Mapping Master Information page. | High | High | New | https://prnt.sc/r03xwy
2020-02-10 | 12 | User Mapping Master Information: If there is only one listing in User territory then there is no point of having "ALL" in the list as both the things are same. For Example: Delhi-Delhi and All | High | High | New | https://prnt.sc/r0427y
2020-02-10 | 13 | User Mapping Master Information: User can map More than one sales executive under same Business verticle and same Territory. | High | High | New | https://prnt.sc/r04c7o https://prnt.sc/r04cdu
2020-02-10 | 14 | Update User Mapping Master: User is able to update with the duplicate data (Already added mapping under the same user) | High | High | New
2020-02-10 | 15 | Update User Mapping Master: When user tries to update the User Territory provided User Country,User Zone and User Region are same then the territory dropdown is showing the territories of different regions. | High | High | New | https://prnt.sc/r04f99
2020-02-10 | 16 | Update User Mapping Master: User is able to update the role by selecting the territory of different region. | High | High | New | https://prnt.sc/r04ler
2020-02-10 | 17 | Update User Mapping Master: User is able to update the role by selecting the Region of different User Zone. | High | High | New | https://prnt.sc/r04o72
2020-02-10 | 18 | Update User Mapping Master: User is able to update the user mapping with blank User Zone, User Region and User Territory details. | High | High | New
2020-02-10 | 19 | Update User Mapping Master: User is able to update the details by clicking on "X" button. | High | High | New
2020-02-10 | 20

## User_Organisation
Bug Report
Project :-GIL CSRP | [7 empty] | Lead_Developer: Rahul Verma
Created_By :-Jitendra |  |  |  | Module: User_Organisation
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close
2020-02-29 | NA | 1 | 10220 | The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 2 | 10220 | User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | New
2020-02-29 | NA | 3 | 10220 | All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | New
2020-02-29 | NA | 4 | 10220 | The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 5 | 10220 | The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 6 | 10220 | The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | New
2020-02-29 | NA | 7 | 10220 | Suggestion: There should be a proper and spacific confirmation message before deleting any existing mapping. | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 8 | 10220 | Validation message appears if user user accidentally clicks on edit button againste the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 9 | 10220 | User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 10 | 10220 | User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 11 | 10220 | User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 12 | 10220 | Plant QC: Validation message appearing for leaving all the mandatory fields blank is wrong as " Business Vertical, Country, Zone, Region, Territory are empty" There is no Zone, Region, Territory as the mapping field. It should be "Business Vertical, Plant and Country is empty" | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 13 | 10220 | Plant QC: Validation message appearing for leaving User plant is wrong. Its showing " Zone, Region, Territory are empty" Instead of showing "User Plant is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 14 | 10220 | Plant QC: Validation message appearing for leaving User plant and User Country is wrong. Its showing " Country, Zone, Region, Territory are empty" Instead of showing "User Plant and Country is empty". | User is logged in and is on User Organisation Page. |  |  |  | High | High | New
2020-02-29 | NA | 15 | 10220 | Plant QC: User is not able to add mapping for Plant QC as there is no data available in User Plant field. | User is logged in and is on User Organisation Page. | 1) Select any user having role as Plant QC. 2)Select Business Vertical,User Plant and User Country. |  |  | High | High | New
2020-02-29 | NA | 16 | 10220 | Zonal_Head :The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 17 | 10220 | Zonal_Head :User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | New
2020-02-29 | NA | 18 | 10220 | Zonal_Head : All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | New
2020-02-29 | NA | 19 | 10220 | Zonal_Head :The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter valid data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 20 | 10220 | Zonal_Head :The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 21 | 10220 | Zonal_Head :The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | New
2020-02-29 | NA | 22 | 10220 | Zonal_Head :Validation message appears if user user accidentally clicks on edit button against the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  |  | High | High
2020-02-29 | NA | 23 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  |  | High | High
2020-02-29 | NA | 24 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  |  | High | High
2020-02-29 | NA | 25 | 10220 | Zonal_Head :User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  |  | High | High
2020-02-29 | NA | 26 | 10220 | BCM :The validation message appearing for leaving Business Verticle blank is grammatically wrong. It should be "Business Vertical is empty" instead of "Business Vertical are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Business Vertical field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 27 | 10220 | BCM :User Zone as "ALL" is getting displayed without even selecting any Country for the same. | User is logged in and is on User Organisation Page. | 1) Leave all the fields blank. 2)Now click on User Zone as ALL. |  |  | Low | Low | New
2020-02-29 | NA | 28 | 10220 | BCM : All the mandatory fields should be (*) marked in order to show them as mandatory fields. | User is logged in and is on User Organisation Page. |  |  |  | High | Low | New
2020-02-29 | NA | 29 | 10220 | BCM :The validation message appearing for leaving Territory blank is grammatically wrong. It should be " Territory is empty" instead of " Territory are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Territory field blank. 3) Enter valid data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 30 | 10220 | BCM :The validation message appearing for leaving Region blank is grammatically wrong. It should be " Region is empty" instead of " Region are empty" | User is logged in and is on User Organisation Page. | 1) Select the User form the list of users. 2) Leave the Region field blank. 3) Enter vali data in the remaining mandatory field. 4) Cliack on ADD button. | NA |  | High | Low | New
2020-02-29 | NA | 31 | 10220 | BCM :The vaidation message coming for entering duplicate entery is grammatically wrong "This combination already exists against a user." it should be "This combination already exists against the same user." | User is logged in and is on User Organisation Page. | 1) Create User Mapping with valid data. 2)Now try to create the same mapping that is with the same data as filled in previous mapping. | NA |  | Low | Low | New
2020-02-29 | NA | 32 | 10220 | BCM :Validation message appears if user user accidentally clicks on edit button against the mpping and then he again clicks on SAVE button without changing anything. There shoul not be any validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | New
2020-02-29 | NA | 33 | 10220 | BCM :User is able to update the mapping without selecting User Territory and by default Its taking "ALL" as Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | New
2020-02-29 | NA | 34 | 10220 | BCM :User is able to update the mapping without selecting User Region and Territory and by default Its taking "ALL" as Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | New
2020-02-29 | NA | 35 | 10220 | BCM :User is able to update the mapping without selecting User Zone, Region and Territory and by default Its taking "ALL" as Zone, Region and Territory value. There should be a proper validation message for the same. | User is logged in and is on User Organisation Page. | User is logged in and is on User Organisation Page. |  |  | High | High | New
2020-02-29 | NA | 36 | 10220 | Wrong user Role is appearing in the dropdown list of User role as "Organisation" which is not a role. | User is logged in and is on User Organisation Page. | 1) Try to change the role by clicking on the USER ROLE dropdown list. |  |  | High | High | New
2020-02-29 | NA | 37 | 10220 | If user delets any business verticle from business verticle master then there should be a validation message saying " If you delete this verticle then all the mapping against this verticle will get delete." | User is logged in and is on Business verticle Master | 1) Click on Vertical Ellipsis against the business verticle you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | New
2020-02-29 | NA | 38 | 10220 | If user delets any business verticle from business verticle master then the mappings corresponding to the same verticle gets changed to "AFX' business verticle. | User is logged in and is on Business verticle Master | 1) Click on Vertical Ellipsis against the business verticle you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. 4) Now check all the mappings that was previously mapped with the old verticle. |  |  | High | High | New
2020-02-29 | NA | 39 | 10220 | Deleted Territory is appearing in the dropdown list of Territory while adding any new mapping. |  | 1) Delete any Territory from the Territory master against which there is some mapping. 2) Now add any new mapping and try to select the deleted mapping. |  |  | High | High | New
2020-02-29 | NA | 40 | 10220 | If user delets any Country from Countrymaster then there should be a validation message saying " If you delete this Country then all the mapping against this Country will get delete." | User is logged in and is on CountryMaster | 1) Click on Vertical Ellipsis against the Country you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | New
2020-02-29 | NA | 41 | 10220 | If user delets any Country from Country master then the mappings corresponding to the same Country gets changed to "Andorra' Country Name. | User is logged in and is on CountryMaster | 1) Click on Vertical Ellipsis against the Country you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. 4) Now check all the mappings that was previously mapped with the old Country. |  |  | High | High | New
2020-02-29 | NA | 42 | 10220 | If user delets any Region from Region master then there should be a validation message saying " If you delete this Region then all the mapping against this Region will get delete." | User is logged in and is on RegionMaster | 1) Click on Vertical Ellipsis against the Region you wish to delete. 2) Click on Delete button. 3) Click on YES button on confirmation message. |  |  | High | High | New
2020-02-29 | NA | 43 | 10220 | Deleted Region is appearing in the dropdown list of Region while adding any new mapping. | User is logged in and is on RegionMaster | 1) Delete any Region from the Region master against which there is some mapping. 2) Now add any new mapping and try to select the deleted mapping. |  |  | High | High | New

## Sheet1
58
59
60