## Bugreport
Bug Report
Project:- |  |  | TOYOTA | [6 empty] | Lead_Devp. :- |  | Vaishali
Created_By :- |  |  | Sakshi Tiwari | [6 empty] | Power_Task_I.D. :- |  | 12620
Created Date: | Power ID | Test Case ID/Module | Task ID | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Attachments/Links | Test Data | Priority | Severaity | Status | Assigned to | Retesting Power ID | Status -15.10.2020 | Testers Comments | Open_Date | Close_Date
2020-10-16 | 12648 | Tc_2 | 12648 | Bug ID_1 | 1)There is a spelling mistake in agreement form. And also 11 digite number accepted. |  | 1)Enter URL 2)click on agreement 3)click on add agreement |  |  | high | high | new

## Summary
TOYOTA
Lead Dev: Vaishali
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestion
Agreement | 3 | 3 | 2 | 1
Total | 3 | 3 | 2 | 1

## TestCases
Project Name:->Toyota
Created By:- |  | Sakshi Tiwari |  | Tested By:- |  | Sakshi Tiwari |  | Pre-condition :-
Creation Date:- |  | 16.20.2020 |  | Module:- |  | AGREEMENT |  | Developed By :- | Vaishali
Version: - |  |  |  | Module:- |  | issue Cerified warranty
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
Tc_1 | 12648 | 2020-10-16 | To verify if dealer is able to loging | dealer is logged into the system. | 1)enter URL 2)enter valid user id and pwd and hit on login | 1) https://toyotanewuat.innov.co.in/ 2) USERNAME= demo-dealer 3) PWD=Welcome@12345 |  |  | home page opend |  |  | pass
Tc_2 | 12648 | 2020-10-16 | To verify if the dealer is able to create a new agreement by selecting TW593/upto 5years or 140,000 Plan in Year with standard price. | dealer is logged into the system with valid vin number | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin 4) fill all mandatory field by selecting TW593/upto 5years or 140,000. and Hit on Save. | Vin=MBJBA3FS700823006 EW=TW593/upto 5years or 140,000 | There is a small spelling mistake in the agreement form word appearing for "Vehicle Chasis Number" and invalid mobile number. |  | vin number should validate and show Aggrement details page |  |  | fail
Tc_3 | 12648 | 2020-10-16 | To verify if the details of the selected EW plan (TW590/UPTO 4 YEARS OR 100,000) is same as that of the details of the same new plan in .uploaded master. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. |  |  |  | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | pass
Fail