## Summery
Bosch
Lead Dev: Vikash Jha/ Ranjeet
Module | No. of test Written | No. of test executed | Pass | Fail
Dealer Tax Invoice | 6 | 6 | 6 | 0
DealerTaxInvoiceClientUAT | 6 | 6 | 6 | 0
Total | 6 | 6 | 6 | 0

## Bug Report
Bug Report
Project :- |  | Bosch |  |  |  |  | Lead_Devp. :- |  | Vikash Jha/ Ranjeet
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 10572
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Status-04/04/2020
10572 | TC_DealerTaxInvoice_05 | 1 | There is an aligmment issue in the downloaded report. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report for. | Februery. |  | High | Low | New | Ranjeet | Done | Fixed
10572 | TC_DealerTaxInvoice_06 | 2 | Only the report downloaded by the dealer -216045-Divya has a data but there is no data in the reports downloaded from other two dealers. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report. 4) Repeat above steps for all three dealers. | 216045-Divya Welcome@123 Service.Advisor1 Welcome@12 Service.Advisor2 Welcome@33 |  | High | High | New | Ranjeet | Done | Fixed

## TC_DealerTaxInvoice
Project Name:-> Bosch
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- | 2020-04-04 |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Dealer Tax Invoice
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Task ID | Status
TC_DealerTaxInvoice_01 | 10572 | 2020-04-03 | To verify if the dealer is able to logged in with valid credentials. | User has a system with an active internet connection. | 1) Enter Url of the portal in the address bar of your browser and hit enter. 2) Enter login credentials. 3) Click on Sign in button. | Service.Advisor1 Welcome@1234 | Dealer is able to login to the portal. |  | Dealer should get logged in. |  |  | Pass | 2020-04-04 | 10582 | Pass
TC_DealerTaxInvoice_02 | 10572 | 2020-04-03 | To verify if the dealer is able to download the Dealer Tax invoice or not. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report for. | Februery. | Report for dealer tax invoice for the selected month is geeting downloaded in to the system. |  | A Dealer Tax Invoice report of the selected month should get downloaded. |  |  | Pass | 2020-04-04 | 10582 | Pass
TC_DealerTaxInvoice_03 | 10572 | 2020-04-03 | To verify if the dealer is able to download the Dealer Tax invoice for last three months if the date of downloading the report lies in 16th to 31 of the month. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) The options to download the report should be available for past three month. | Date of downloading the report is 16th april. |  |  | Option to download the report should be available for March, Feb and Jan. |  |  | Not able to execute. | 2020-04-04 | 10582 | Pass
TC_DealerTaxInvoice_04 | 10572 | 2020-04-03 | To verify if the dealer is able to download the Dealer Tax invoice for last three months if the date of downloading the report lies in 1st to 15th of the month. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) The options to download the report should be available for past three month. | Date of downloading the report is 3rd april. 216045-Divya Welcome@123 |  |  | Option to download the report should be available for March, Feb, Jan and Dec. |  |  | Pass | 2020-04-04 | 10582 | Pass
TC_DealerTaxInvoice_05 | 10572 | 2020-04-03 | To verify if the downloaded report is as per the proper and spacified format. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report for. | Februery. | There is an aligmment issue in the downloaded report. |  | Downloaded report should be as per the specified format. | High | Low | Fail | 2020-04-04 | 10582 | Pass
TC_DealerTaxInvoice_06 | 10572 | 2020-04-03 | To verify if the Same report is getting downloaded in all the dealers login or not. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report. 4) Repeat above steps for all three dealers. | 216045-Divya Welcome@123 Service.Advisor1 Welcome@1234 Service.Advisor2 Welcome@33 Service.Advisor3 Welcome@11 | Only the report downloaded by the dealer -216045-Divya has a data but there is no data in the reports downloaded from other two dealers. |  | Same report for dealer tax invoice should get download in all the three dealers login. | High | High | Fail | 2020-04-04 | 10582 | Pass

## TC_DealerTaxInvoiceClientUAT
Project Name:-> Bosch
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- | 2020-04-06 |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Dealer Tax Invoice- Client UAT
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Task ID | Status
TC_DealerTaxInvoice_01 | 10585 | 2020-04-06 | To verify if the dealer is able to logged in with valid credentials. | User has a system with an active internet connection. | 1) Enter Url of the portal in the address bar of your browser and hit enter. 2) Enter login credentials. 3) Click on Sign in button. | Service.Advisor1 Welcome@1234 | Dealer is able to login to the portal. |  | Dealer should get logged in. |  |  | Pass
TC_DealerTaxInvoice_02 | 10585 | 2020-04-06 | To verify if the dealer is able to download the Dealer Tax invoice or not. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report for. | Februery. | Report for dealer tax invoice for the selected month is geeting downloaded in to the system. |  | A Dealer Tax Invoice report of the selected month should get downloaded. |  |  | Pass
TC_DealerTaxInvoice_03 | 10585 | 2020-04-06 | To verify if the dealer is able to download the Dealer Tax invoice for last three months if the date of downloading the report lies in 16th to 31 of the month. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) The options to download the report should be available for past three month. | Date of downloading the report is 16th april. bhavya-123 M5G9FUQZ42 Service.Advisor1 Welcome@1234 |  |  | Option to download the report should be available for March, Feb and Jan. |  |  | Pass
TC_DealerTaxInvoice_04 | 10585 | 2020-04-06 | To verify if the dealer is able to download the Dealer Tax invoice for last three months if the date of downloading the report lies in 1st to 15th of the month. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) The options to download the report should be available for past three month. | Date of downloading the report is 6rd april. 216045-Divya Welcome@123 |  |  | Option to download the report should be available for March, Feb, Jan and Dec. |  |  | Pass
TC_DealerTaxInvoice_05 | 10585 | 2020-04-06 | To verify if the downloaded report is as per the proper and spacified format. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report for. | Februery. |  |  | Downloaded report should be as per the specified format. | High | Low | Pass
TC_DealerTaxInvoice_06 | 10585 | 2020-04-06 | To verify if the Same report is getting downloaded in all the dealers login or not. | Dealer is already logged in. | 1) Click on SP - Sales. 2)Click on Dealer Tax Invoice button. 3) Clickon the month you wish to download the report. 4) Repeat above steps for all three dealers. | bhavya-123 M5G9FUQZ42 Service.Advisor1 Welcome@1234 Service.Advisor2 Welcome@33 |  |  | Same report for dealer tax invoice should get download in all the three dealers login. | High | High | Pass

## Sheet1
Project Name:-> Mercedes_Benz
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- | 2020-04-04 |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Dealer Tax Invoice
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Task ID | Status