## BugReport
Project :- |  | Renault RSA |  |  |  |  | Lead_Developer. :- |  | Alok Srivastava
Created_By :- |  | Sakshi
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Attachments/Links | Priority | Severaity | Status | Assigned To | Retesting Status | Retesting Power ID
2021-05-19 | RSA_TC_28 | Bug ID_1 |  | "Please Enter First Odometer reading" can be written as "Please Enter Odometer reading" | User is already logged in and is on New RSA page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Medium | Medium | New | Alok Srivastava
2021-05-19 | RSA_TC_31 | Bug ID_2 |  | User is able to save RSA by entering invalid First name | User is already logged in and is on New RSA page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | High | High | New | Alok Srivastava
2021-05-19 | RSA_TC_32 | Bug ID_3 |  | User is able to save RSA by entering invalid Last name | User is already logged in and is on New RSA page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | High | High | New | Alok Srivastava
2021-05-19 | RSA_TC_34 | Bug ID_4 |  | User is able to save RSA by entering invalid data in the Home Phone Field | User is already logged in and is on New RSA page. | 1) Enter invalid data in Home Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | High | High | New | Alok Srivastava
2021-05-19 | RSA_TC_40 | Bug ID_5 |  | There is no validation for Odometer Redaing, User is able to save by entering unlimited value is the odometerReading | User is already logged in and is on New RSA page. | 1) Enter Unlimited Odometer Reading 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | High | High | New | Alok Srivastava
2021-05-19 | RSA_TC_43 | Bug ID_6 |  | RSA End Date is not capturing the date as per the logic | User is already logged in and is on New RSA page. | 1)Select RSA Plan 2)check the RSA end Date |  | High | High | New | Alok Srivastava
2021-05-19 | RSA_TC_51 | Bug ID_7 |  | User is able to change RSA Sale Date | User is already logged in and is on New RSA page. | 1)Select RSA58998 2)Selecting previous date from the current date for RSA Sale Date |  | High | High | New | Alok Srivastava
| RSA_TC_23 | Bug ID_8 |  | Star mark is not having if Registration Type is mandatory and also Please Select First Registration Type can be written as "Please Select Registration Type" | User is already logged in and is on New RSA page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Medium | Medium | New | Alok Srivastava

## Agreement
Project Name:-Renault EW
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 19.05.2021 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok sriwashtava
Version: - |  |  |  | Module:- |  | RSA
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
RSA_TC_1 |  | 2021-05-19 | To verify by clicking on RSA | dealer is already logged |  |  |  |  | RSA page should displays |  |  | pass
RSA_TC_2 |  | 2021-05-19 | To verify RSA page | dealer is already logged | click on RSA module |  |  |  | should display the users detail with proper |  |  | pass
RSA_TC_3 |  | 2021-05-19 | To Verify Refresh button for all the sections | Dealer in on home page |  |  |  |  | button should be clickable and refresh the section |  |  | pass
RSA_TC_4 |  | 2021-05-19 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on RSA link under menu item. 2)Click on Add RSA button. |  |  |  | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button) |  |  | pass
RSA_TC_5 |  | 2021-05-19 | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. | NA |  |  | System should display a validation message as "Vehicle Chassis No. is required." |  |  | pass
RSA_TC_6 |  | 2021-05-19 | To verify if the user is able to validate Vehicle Chassis No. by entering invalid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)@@@@######12345 2)01A8A369B45QWERTY 3)ABCD8KGH7JH123456 4)Blank spaces |  |  | Chassis no. not avaliable msg. should be displayed |  |  | pass
RSA_TC_7 |  | 2021-05-19 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)MEEBBA000G9413910 |  |  | It should get validate successfully and Check list page open with Submit button and and Cancel button. |  |  | pass
RSA_TC_8 |  | 2021-05-19 | Check List page To Verify Check list Page | User is on Check list page | 1)Enter valid data in Chassis No. 2)Click on Validate button. |  |  |  | Page should contain with all the fields with cancel nad submit button as per the requirement |  |  | pass
RSA_TC_9 |  | 2021-05-19 | to verify if all the mandatory fields marked with asterisk(*) | Dealer is on Creating New RSA page |  |  |  |  | all the mandatory gields should have with asterisk(*). |  |  | pass
RSA_TC_10 |  | 2021-05-19 | To verify if the Cancel button on RSA details pop-up is working or not. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on Cancel button. |  |  |  | Process should get aborted. |  |  | pass
RSA_TC_11 |  | 2021-05-19 | To verify if the User is able to get navigate to the Add RSA page. | User is already logged in | 1)Click on the RSA button from the menu section. 2)Click on Add RSA button. |  |  |  | Creating New RSA page should get open having RSA related fields and Save and Cancel button. |  |  | pass
RSA_TC_12 |  | 2021-05-19 | To verify if the data is getting autopopulated as per the Middleware | User is already logged in |  |  |  |  | All the Autopopulated data should come from the MW |  |  | pass
RSA_TC_13 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving all the mandatory fields blank. | User is already logged in and is on RSA page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to create a new RSA and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
RSA_TC_14 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | pass
RSA_TC_15 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on RSA page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care RSA and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | pass
RSA_TC_16 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New RSA page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." |  |  | pass
RSA_TC_17 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | pass
RSA_TC_18 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering leaving in Office Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter leaving in Office Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Office Phone No. field as "Invalid Office Phone No." |  |  | pass
RSA_TC_19 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering Leaving data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "This field is Required." |  |  | pass
RSA_TC_20 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for city field as "City is required." |  |  | pass
RSA_TC_21 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | pass
RSA_TC_22 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving State field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave State field Unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for State field as "State is required." |  |  | pass
RSA_TC_23 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Star mark is not having if Registration Type is mandatory and also Please Select First Registration Type can be written as "Please Select Registration Type" |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Registration Type field as "Please Select Registration Type" |  |  | pass
RSA_TC_24 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care RSA page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care RSA and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | pass
RSA_TC_25 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Executive Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Executive Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Executive Name field as "Executive Name is required." |  |  | pass
RSA_TC_26 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Sales Manager Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Sales Manager Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Sales Manager Name field as "Sales Manager Name is required." |  |  | pass
RSA_TC_27 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Registration No field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Registration No field as " Registration No is required." |  |  | pass
RSA_TC_28 |  | 2021-05-19 | To verify if the User is able to create new RSA by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | "Please Enter First Odometer reading" can be written as "Please Enter Odometer reading" |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Odometer Reading field as "Please Enter Odometer reading" |  |  | Fail
RSA_TC_29 |  | 2021-05-19 | To very by not selecting RSA Plan And enter valid details in the remaining fields | User is already logged in and is on New RSA page. | 1)Leave Select RSA Plan Uselected 2) Enter valid detalis in the remianing fields. 3)Click On Save Button |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Select RSA Plan field as "Select RSA Plan is required." |  |  | pass
RSA_TC_30 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Vehicle Chasis No. and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Vehicle Chasis No. field as "Invalid Vehicle Chasis No. " |  |  | pass
RSA_TC_31 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in First Name and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | First Name #3456677!@#$%^& | User is able to save RSA by entering invalid First name |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in First Name field as "Invalid First Name." |  |  | Fail
RSA_TC_32 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Last Name and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Name GH##$%%---- | User is able to save RSA by entering invalid Last name |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Last Name field as "Invalid Last Name." |  |  | Fail
RSA_TC_33 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in GSTIN and enter valid details in the remaining fields. (if YES selected for GSTIN Applicable) | User is already logged in and is on New RSA page. | 1) Enter invalid data in GSTIN field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in GSTIN No. field as "Invalid GSTIN No." |  |  | pass
RSA_TC_34 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Home Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Home Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Home Phone:47587875478 | User is able to save RSA by entering invalid data in the Home Phone Field |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Home Phone No. field as "Invalid Mobile Phone No." |  |  | Fail
RSA_TC_35 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Mobile Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Mobile Phone No. field as "Invalid Mobile Phone No." |  |  | pass
RSA_TC_36 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Office Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Office Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Office Phone:47587875478 |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Office Phone No. field as "Invalid Office Phone No." |  |  | pass
RSA_TC_37 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "Please enter a valid email address." |  |  | pass
RSA_TC_38 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in Address and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in * Address field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in Address field as "Invalid * Address " |  |  | pass
RSA_TC_39 |  | 2021-05-19 | To verify if the User is able to create new RSA by entering invalid data in City and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter invalid data in * City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new RSA and the system must display a proper and specific validation message for entering invalid data in City field as "Invalid City " |  |  | pass
RSA_TC_40 |  | 2021-05-19 | To verify if the User is able to create new RSA by Invalid value Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Enter Unlimited Odometer Reading 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | There is no validation for Odometer Redaing, User is able to save by entering unlimited value is the odometerReading |  | User should not be able to create new RSA and the system must display a proper and specific validation message for Odometer Reading field |  |  | Fail
RSA_TC_41 |  | 2021-05-19 | To verify by selecting RSA Plan and enter valid details in the remaining fields. | User is already logged in and is on New RSA page. | 1) Select RSA Plan 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Select RSA Plan-1 Year Plan |  |  | User should be able to select the Plan in the option available in the dropdown(1, 2, and 3 year Plan) |  |  | pass
RSA_TC_42 |  | 2021-05-19 | To verify the RSA sale Date by selecting the RSA Plan whie Creating New RSA | User is already logged in and is on New RSA page. | 1)Select RSA Plan 2)check the RSA sale Date | Vin number-MEEBBA002G8391494 Select RSA Plan-1 Year Plan |  |  | RSA Sale Date should capture the date after 48 hours from the Creation RSA date |  |  | pass
RSA_TC_43 |  | 2021-05-19 | To verify RSA End Date by selecting RSA Plan | User is already logged in and is on New RSA page. | 1)Select RSA Plan 2)check the RSA end Date | Select RSA Plan-3 Year Plan | RSA End Date is not capturing the date as per the logic |  | RSA End Date should get populate based on the plan selected |  |  | Fail
RSA_TC_44 |  | 2021-05-19 | To verify if the user is able to save the RSA form by entering valid data in all the fields | User is already logged in and is on New RSA page. | 1)Eneter valid details I all the required fields and save |  |  |  | User is able to save the RSA with all the same details which was entered whlie creating |  |  | pass
RSA_TC_45 |  | 2021-05-19 | To verify RSA sale date and Rsa End date in the details page | user is on detail page | check RSA Sale Date and SA End Date all the entered data in the details page |  | RSA End date having the date as per the RSA Sale date |  | All the details should have the same details which was entered whlie creating and status should be ON HOLD |  |  | pass
RSA_TC_46 |  | 2021-05-19 | To verify the RSA Status | user is on detail page |  |  |  |  | RSA Status should be ON HOLD and it should active after 48 hour |  |  | pass
RSA_TC_47 |  | 2021-05-19 | To verify the Status after 48 hours | user is on detail page | Login with same login ID and check the RSA Staus after 48 hours |  |  |  | RSA Status should chenged as Active after 48 hour |  |  | pass
RSA_TC_48 | 0 | 2021-05-19 | To verify if user is able to Create New RSA for the vehicle more than 10 years | User is already logged in and is on New RSA page. | 1)Validate the Vin number which has vehicle delivery date more than 10 years |  |  |  | System should not allow to create RSA which is not under 10 years |  |  | Not able to Execute
RSA_TC_49 |  | 2021-05-19 | To verify if user is able to create new RSA with the same vin number which has the Status is ON HOLD and Active | User is already logged in and is on Vin Validation page | 1)Validate the vin number | Vehicle Chasis No MEEBBA006G8405090 | User is not able to validate once SA is created already |  | System should not allow usres to validate once SA is created already |  |  | pass
RSA_TC_50 |  | 2021-05-19 | To verify if user is able to update the Sale Plan | User is already logged in and is on New RSA page. | 1)Select RSA58998 2)Change RSA Plan | Rsa Plan from 2 to 3 Year plan |  |  | user should able to update the Sale Plan |  |  | pass
RSA_TC_51 |  | 2021-05-19 | To verify if user is able to Update RSA Sale Date | User is already logged in and is on New RSA page. | 1)Select RSA58998 2)Selecting previous date from the current date for RSA Sale Date | RSA Sale Date 12-05-2021 | User is able to change RSA Sale Date |  | User should not be able to update RSA Sale Date |  |  | Fail

## Summary
Lead Dev: Alok Srivastava
Module | No. of test Written | No. of test executed | Pass | Fail
Agreement | 51 | 50 | 52 | 8