## Digital Apk-Bugs
Bug Report
Project :- |  | MPartner-Digital APK |  |  |  |  | Lead_Devp. :- |  | Shalu
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 12567
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
12567 | NA | 1 | App is getting crash when clicking on Add coupon symbol(+) with blank input. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2)Click on "+" icon without entering any input. |  | Video have been shared on hangout | High | High | New | Shalu
12567 | NA | 2 | App is getting crash when clicking on Add coupon symbol(+) with Invalid input. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter invalid data in coupn number field. 3) Click On "+" icon. | 1.5, Alphbets, special charecters etc | Video have been shared on hangout | High | High | New | Shalu
12567 | NA | 3 | Assigned coupons should get deducted from the total eligible coupons and should get added in the "Balance Coupons" bucket. As total eligible coupons before assigning was 50, and after assiging 5 from it. App should have dispyaed balance coupons but App still shows 0 balance coupons. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter valid data in coupn number field. 3) Click On "+" icon. 4) Check the total balance coupons. | 5 |  | High | High | New | Shalu
12567 | NA | 4 | Count of Assigned coupons should get Added in the "Used Coupons" bucket. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter valid data in coupn number field. 3) Click On "+" icon. 4) Check the total eligible coupons. | 5 |  | High | High | New | Shalu
12567 | NA | 5 | App goes into forever "Please Wait" state when clicking on Resend OTP link under Terms and Conditions OTP verification. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  |  | High | High | New | Shalu
12567 | NA | 6 | App goes into forever "Please Wait" state when clicking on Resend OTP link under Terms and Conditions OTP verification. | User is logged in as a dealer. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  |  | High | High | New | Shalu
12567 | NA | 7 | There should be a maximum input character limit in the T&C otp, It should be same as the actual OTP length. | User is logged in as a dealer and distributor. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  | https://prnt.sc/uw2szk | High | High | New | Shalu
12567 | NA | 8 | At Gift Cards screen: There is a duplicacy of coupons appearing under Gift Cards when logged in as dealer. As there are two "Yesterday" headers under which coupns are available. | User is logged in as a dealer. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) check the gift cards screen. |  |  | High | High | New | Shalu
12567 | NA | 9 | App is getting crash when dealer opens Super7 screen. | User is logged in as a dealer. | 1) Click on Super 7 menu option. |  | Video have been shared on hangout | High | High | New | Shalu
12567 | NA | 10 | App is getting crash when distributor opens Super7 screen. | User is logged in as a dealer. | 1) Click on Super 7 menu option. |  | Video have been shared on hangout | High | High | New | Shalu

## Summary
MPartner-Digital Apk
Lead Dev: Shalu
Module | No. of test Written | No. of test executed | Pass | Fail
Digital Apk | NA | NA | NA | 10