## Sheet1
S. No | Task | Status | QA Status
1 | Dealer login - Request Warranty: Customer Phone - rename to Customer Mobile No. | DONE | Fixed
2 | Dealer login - Request Warranty: Dealer Invoice No. - allow alphanumeric and / | DONE | Fixed
3 | UI to be changed - field alignments, blank spaces, pop up error messages, colour etc | DONE | Fixed
4 | BCM Login - Mouse Hover text on Door/Floor: "Click to view list of Warranty Requests" | DONE | Fixed
5 | Dealer login - Request Warranty: Not yet installed option to be removed in Installation menu | DONE | Fixed
6 | Dashboard: Warranty for Approval - height to be increased to reduce blank spaces | DONE | Fixed
7 | Approval Page: Warranty Years - decimals is getting added. Should be only numeric | DONE | Not Fixed-User is still able to copy any decimal number and paste in warranty years however on saving it does not calculate the decimal part.
8 | Non editable fields to be grey in GIL line items (CSS) - request creation page, approval | DONE | Fixed
9 | Dealer login - View Details page: Download PDF option reqd | DONE | Fixed
10 | Warranty Years changed - end date should be (start date - 1) | DONE | Fixed
11 | Email on Approval - only attachment email will go. | DONE | Not Fixed
12 | Customer login case - single PDF. | DONE | Fixed
13 | Email after approval - attachment is not going in Customer case. | DONE | NotFixed
14 | Door PDF: State,Phone to be shown as separate line | DONE | Fixed
15 | BCM should view only his own assigned warranty requests | DONE | Fixed
16 | Floor PDF: project Name, Address - to be checked in Customer login case | DONE | Fixed
17 | Upload CSV: download option for csv template | DONE | Fixed
Bugs Found :
1) | 1010000345: Downloaded PDF report does not show any added details of the warranty that is Customer/Project Details are not visible in the downloaded report.
2)

## Attechments
Bug No | Screenshot
1
1