## Summary
Mercedes Benz
Lead Dev: Ranjeet/Vikash Jha/Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestion
Extended Eligibility | 16 | 16 | 15 | 0 | 1
Total | 16 | 16 | 15 | 0 | 1

## Bug Report
Bug Report
Project :- |  | Mercedes Benz
Created_By :- |  | Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Status on 21-02-2020 | Task ID- Retesting | Open | Close
2020-09-04 | TC_Extended_Eligibility_03 | 1 | 12172 | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during agreement creattion. "then" should get change to "than". | dealer is logged into the system. | 1) Click on create certificate request. 2)enter odometer reading more than 100000kms 3)Click on Sav button. |  | https://prnt.sc/ubjem6 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_04 | 2 | 12172 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  | https://prnt.sc/ubc0v2 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_08 | 3 | 12172 | details of the selected (12 Months/20k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA927 MBCAR118 | https://prnt.sc/ubhsel https://prnt.sc/ubhsuc http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249900 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_10 | 4 | 12172 | details of the selected (6 Months/10k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA929 MBCAR119 | https://prnt.sc/ubi4ys https://prnt.sc/ubi58f http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249841 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_12 | 5 | 12172 | details of the selected (24 Months/40k KM+4 year) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_13 | 6 | 12172 | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | dealer is logged into the system. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | https://prnt.sc/ubg8ji |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_14 | 7 | 12172 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | dealer is logged into the system. |  | Vin number:WDC1569456L005078 | https://prnt.sc/ubc0v2 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_15 | 8 | 12172 | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | dealer is logged into the system. |  | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | https://prnt.sc/ubc71z |  |  | Fixed | Apurwa
Suggestion | TC_Extended_Eligibility_16 | 9 | 12226 | There is no plan available for 5 years , so system should throw a error message at the time of vin validation about the same. |  |  |  | https://prnt.sc/udffgf |  |  | New

## Extended Eligibility
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :-
Creation Date:- | 2020-09-04 |  |  |  | Re-Testing Date:- | 2020-08-09 |  | Developed By :- | Apurwa
Version: - |  |  |  |  | Module:- | Extended Eligibility
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Test Data | Power ID | Retesting Status
TC_Extended_Eligibility_01 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '4' as Plan in Year with Engine and Transmission coverage and standard price. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCA928 MBCAR116 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=250068 |  |  | agreement should get created with 24months/40k and 4 years. |  |  | Pass | WDC1569456L001111 MBCAR121 MBCA932 | 12226 | Pass
TC_Extended_Eligibility_02 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM+4 year) is same as that of the details of the same ew plan in .uploaded master with Engine and Transmission coverage and standard price. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA928 MBCAR116 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=250068 |  |  | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Pass | WDC1569456L001111 MBCAR121 MBCA932 | 12226 | Pass
TC_Extended_Eligibility_03 | 12172 | 2020-09-04 | To verify if the validation of ODOmeter is upto 100000Kms or not. | dealer is logged into the system. | 1) Click on create certificate request. 2)enter odometer reading more than 100000kms 3)Click on Sav button. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during agreement creattion. "then" should get change to "than". | https://prnt.sc/ubjem6 | There should be a validation message for entering odometer reading more than 100000kms. |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_04 | 12172 | 2020-09-04 | To verify if that the * Standard Warranty Start Date is taking input date between 4 years ,11 months , 30 days to 3 years in past from current date. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | https://prnt.sc/ubc0v2 | System should allow dates only in between 5to3 years in past from current date else system should throw an error message. |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_05 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '3' as Plan in Year with Comprehensive coverage and standard price type | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCAR114 MBCA930 |  |  | agreement should get created with 24months/40k and 3 years. | WDC1569456L000001 MBCA933 MBCAR123 |  | Pass | WDC1569456L000004 MBCA935 MBCAR126 | 12226
TC_Extended_Eligibility_06 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM plan with '3' as Plan in Year )is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCAR114 MBCA930 |  |  | Details of the selected plan should be equal to the details of the same plan in EW master. | WDC1569456L000001 MBCA933 MBCAR123 |  | Pass | WDC1569456L000004 MBCA935 MBCAR126 | 12226
TC_Extended_Eligibility_07 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 12 Months/20k KM plan with '5' as Plan in Year with Comprehensive coverage | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  |  |  | agreement should get created with 12months/20k and 5years. |  |  | Pass | WDC1569456L000002 MBCA934 MBCAR124 | 12226 | Pass
TC_Extended_Eligibility_08 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan 12 Months/20k KM plan with '5' as Plan in Year is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA927 MBCAR118 | details of the selected (12 Months/20k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubhsel https://prnt.sc/ubhsuc http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249900 | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | WDC1569456L000002 MBCA934 MBCAR124 | 12226 | Pass
TC_Extended_Eligibility_09 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 6 Months/10k KM plan with '5' as Plan in Year with Engine and Transmission coverage | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  |  |  | agreement should get created with 6 Months/10k KM and 5years. |  |  | Pass | MBCA933 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_10 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (6 Months/10k KM)is same as that of the details of the same ew plan in .uploaded master with Engine and Transmission coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA929 MBCAR119 | details of the selected (6 Months/10k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubi4ys https://prnt.sc/ubi58f http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249841 | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | MBCA933 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_11 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '4' as Plan in Year with Comprehensive coverage. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 |  | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be | agreement should get created with 24months/40k and 4 years. |  |  | Pass | WDC1569456L000003 MBCA936 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_12 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM+4 year) is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 | details of the selected (24 Months/40k KM+4 year) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | WDC1569456L000003 MBCA936 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_13 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | https://prnt.sc/ubg8ji |  |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_14 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | Vin number:WDC1569456L005078 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | https://prnt.sc/ubc0v2 |  |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_15 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | https://prnt.sc/ubc71z |  |  | Fail | Fail |  | 12226 | Pass
[7 empty] | There is no plan available for 5 years , so system should throw a error message at the time of vin validation about the same. | https://prnt.sc/udffgf | [5 empty] | 12226 | New

## Restrict URL access - correctio
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11384 | 2020-01-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=249643 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Edit&record=249643 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Detail&record=249659 http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249659 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11384 | 2020-01-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249454 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Re-purchase Functionality
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Re-purchase Functionality
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Re-purchase_Functionality_01 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Submitted. |  |  | Pass
TC_Re-purchase_Functionality_02 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Answer By Dealer. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Answer By Dealer.. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Query By Assurant. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request Query By Assurant. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Reject. | Dealer is already logged-in |  | WDC1569086L098655 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Reject. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approve. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should be able to create a new certificate request. |  |  | Pass
TC_Re-purchase_Functionality_04 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Rejected. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Rejected.
TC_Re-purchase_Functionality_05 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approved. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Approved.
TC_Re-purchase_Functionality_06 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_07 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_08 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_09 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_10 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Expired. | Dealer is already logged-in |  | WDD2050026L011379 | User is able to validate the vin for a vin number having Certification request status: Submitted and Agreement Status: Expired. |  | Dealer should not be able to create an agreement. |  |  | Fail
TC_Re-purchase_Functionality_11 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_12 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_13 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_14 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_15 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_16 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_17 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_18 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_19 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_20 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_21 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_22 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_23 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Submitted. | Dealer is already logged-in |  | WDD2120036L056714 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_24 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_25 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_26 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_27 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_28 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Expired. | Dealer is already logged-in |  | WDC1569086L002075 MBCA926 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_29 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Alert close Agreement already created. |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_30 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_31 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_32 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_33 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_34 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_35 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_36 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_37 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_38 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_39 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_40 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_41 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_42 |  | 2020-10-06 | Certification Request should not be added when agreement status is not equal to ‘Cancelled’ or ‘Expired’ for the vin. ----or if there is no agreement in the system against that vin. | Dealer is already logged-in
TC_Re-purchase_Functionality_43 |  | 2020-10-06 | Certification Request should not be added when old certificate request status is not equal to ‘Approve’ or ‘Reject’ for the vin. | Dealer is already logged-in | WDD2131046L005346
TC_Re-purchase_Functionality_44 |  | 2020-10-06 | Check expired condition of the Certificate request when approved and there is no agreement for the same. ->'Existing' expired in 20 days after approval. ->'POC' expired in 90 days after approval. | Dealer is already logged-in | For existing=WDD2131046L007226 | WDC2539036L002406- Dealer should be able to create new certificate request againt this WDC2539036L002406 vin because the vin is already expired as its approval againg is more than 20 days.(Approval date was 11-09-2020)
1) Certification Request should not be added when agreement status is not equal to ‘Cancelled’ or ‘Expired’ for the vin. ----or if there is no agreement in the system against that vin.-Fixed
2) Certification Request should not be added when old certificate request status is not equal to ‘Approve’ or ‘Reject’ for the vin. -Not Fixed
Bug: Certification Request should not be created with a vin number for which there is already a certificate request present in the system having status as "Reject".
Vin number: WDD2131046L005346.
3.Check the expired condition of the Certificate request when approved and there is no agreement for the same.
->'Existing' expired in 20 days after approval.
->'POC' expired in 90 days after approval. -Not Fixed
Bug: Dealer should be able to create new certificate request against WDC2539036L002406 / WDD2131046L007226(Existing) vins because the vin is already expired as its approval aging is more than 20 days.(Approval date was 11-09-2020) but currently system shows a validation as "VIN Number already exists in the database.".

## Approved_Claim_Amt-Dev
Project Name:-> MB
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- | 2020-03-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Ranjeet
Version: - |  |  | Version: - |  | Module:- | Approved_Claim_Amt-Dev
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Date | Status | Power ID | Date | Status
TC_ApprovedClaimAMT_01 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Part Information. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 | 134852.23 |  | The rejected part amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_02 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Labour Information. | User is already logged in | 1)mark the checkbox against the Labour to be reject, 2)Click on Update Labour Rejection | MBCAC198 |  |  | The rejected Labour amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_03 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Miscellaneous Information. | User is already logged in | 1)mark the checkbox against the Miscellaneous to be reject, 2)Click on Update Miscellaneous Rejection | MBCAC198 |  |  | The rejected Miscellaneous amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_04 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Part Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_05 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for Labour information by selecting check box against Rejection check in Labour information. | User is already logged in | 1)mark the checkbox against the Rejection check for Labour Information. | MBCAC198 |  |  | All Labour should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_06 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Miscellaneous Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_07 | 11417 | 2020-03-07 | To verify if the Net Approval amount is showing the amount equal to Total Amt-Rejected Amount | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 |  |  | Net approval amount should be equal to total amt-rejected amount. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_08 | 11417 | 2020-03-07 | To verify if the Grand Total Calculation is correct or not. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection 3)Check the summary of all the parts and calculate manually | MBCAC198 |  |  | Grand total of all the fields should be correct. |  |  | Pass | 11435 | 2020-06-07 | Pass
30-06-2020

## Sheet10
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-07-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11446 | 2020-07-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11446 | 2020-07-07 | To verify if dealer is able to view Certification Request Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11446 | 2020-07-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | Dealer A:5-AD-Hyderabad Dealer B:demo-dealer http://mbuat.innov.co.in/index.php?module=Faq&view=Detail&record=249645 http://mbuat.innov.co.in/index.php?module=Faq&view=Edit&record=249645 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11446 | 2020-07-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | Dealer A:5-AD-Hyderabad Dealer B:demo-dealer http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=245335 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=249612 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=249661 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Edit&record=244366 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11446 | 2020-07-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Edit&record=244366 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=244366 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass