## Summery
Toyota EW
Lead Dev: Vikash Jha/ Ranjeet
Module | No. of test Written | No. of test executed | Pass | Fail | Deferred
Go paper Less field addition in all EW portal | 22 | 22 | 17 | 0 | 5
Total | 22 | 22 | 17 | 0 | 5

## Bug Report
Bug Report
Project :- |  | Toyota EW |  |  |  |  | Lead_Devp. :- |  | Vikash Jha/ Ranjeet
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 12069
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
12069 | TC_GoPaperLess_04 | 1 | In both Document Received Date ,Document Courier Date date format is YYYY/MM/DD and also date format should be DD/MM/YYYY throught the claim process. | User is logged in as a dealer and already on claims page. | 1) Select the claim whose courier details needs to be update. 2)Click on the Add Courier details button. 3) Enter valid details in all the mandatory fields. 4) Click on Submit button. |  | https://prnt.sc/u7ygmz https://prnt.sc/u7yxri | High | High | Fixed | Ranjeet | Done
12069 | TC_GoPaperLess_09 | 2 | Tax Invoice Date is taking future date and also invoice date can take past date till the claim creation date. | User is logged in as a dealer and already on claims page. | 1) Check the final Tax Invoice up section. |  | https://prnt.sc/u7y6as | High | High | Deferred | Ranjeet | No Need to change
12069 | TC_GoPaperLess_15 | 3 | Alert Message is incomplete, Message should also contain the claim numbers for which the status is "Incorrect FINAL SERVICE REQUEST UPLOADED." | User is logged in as a dealer and already on claims page. |  |  | https://prnt.sc/u7yzpy | High | High | Deferred | Ranjeet | No Need to change. Client will provide Alert Message Content.
12069 | TC_GoPaperLess_16 | 4 | There is no option/fields provided to dealer for upload/submit correct Final Service Request. | User is logged in as a dealer and already on claims page. | 1) Open the claim having status "Incorrect FINAL SERVICE REQUEST UPLOADED.". 2) Upload correct final service request . 3)Click on Upload button. | TKIC11514 | https://prnt.sc/u7zoqj | High | High | Fixed | Ranjeet | Done
12069 | TC_GoPaperLess_19 | 5 | By default "Document Courier Date. and Document Received Date." should be current date. | User is logged in as a dealer and already on courier submission page.. | 1) Enter valid data in all the mandatory fields. 2)Click on Save button. |  | https://prnt.sc/u7yauk https://prnt.sc/u7yf2t | Mid | Mid | Fixed | Ranjeet | Done
12069 | TC_GoPaperLess_20 | 6 | Document Courier Date and Document Received Date cannot take future dates. | User is logged in as a dealer and already on courier submission page.. | 1) Enter invalid data in Document Courier Date and Document Received Date fields. 2)1) Enter valid data in all the remaining fields. 3)Click on Save button. | Document Courier Date 2021-08-12 Document Received Date 2022-08-18 | https://prnt.sc/u7ybwe | High | High | Deferred | Ranjeet | No need to change
12069 | TC_GoPaperLess_21 | 7 | Dealer is able to submit courier details by entering blank spaces in POD number and Courier Company Name. | User is logged in as a dealer and already on courier submission page.. | 1) Enter invalid data in POD number and Courier Company Name. fields. 2)1) Enter valid data in all the remaining fields. 3)Click on Save button. | Blank spaces | https://prnt.sc/u7ycgi https://prnt.sc/u7yfpj | High | Low | Deferred | Ranjeet | No need to change
12069 | TC_GoPaperLess_22 | 8 | After submitting the courier details system shows cancel button , Button name should get changed to Close. | User is logged in as a dealer and already on courier submission page.. | 1) Enter valid data in all the mandatory fields. 2)Click on Save button. |  | https://prnt.sc/u7ydrr | High | Low | Deferred | Ranjeet | No need to change

## GoPaperLess
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 29/8/2020 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Claims-Go paper Less field addition in all EW portal
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Status Power ID | Retesting Date | Retesting Status
TC_GoPaperLess_01 | 12069 | 29/8/2020 | To verify if the Labour Operation Time field name have been renamed as “Operation Time in Hours” or not. | User is logged in as a dealer and already on claims page. | 1) Click on Add Service Request button. 2) Create a new claim or open any exisiting claim. 3) Click on the Add Labout Information button. 4)Check the operation time in field name, |  |  |  | Field name should get changed to “Operation Time in Hours” |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_02 | 12069 | 29/8/2020 | To verify that dealer is able to add courier details only when the status is "Doc Verified And Processed For Payment", | User is logged in as a dealer and already on claims page. | 1) Select the claim whose courier details needs to be update. 2)Click on the Add Courier details button. 3) Enter valid details in all the mandatory fields. 4) Click on Submit button. |  |  |  | Dealer should be able to add courier details. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_03 | 12069 | 29/8/2020 | To verify that dealer is able to add courier details only when the status is other than "Doc Verified And Processed For Payment", | User is logged in as a dealer and already on claims page. | 1) Select the claim whose courier details needs to be update. 2)Click on the Add Courier details button. 3) Enter valid details in all the mandatory fields. 4) Click on Submit button. |  | "Courier details will be update on 'Doc Verified And Processed For Payment' status " is coming. |  | Dealer should not be able to add courier details. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_04 | 12069 | 29/8/2020 | To verify if the date format have been changed to DD/MM/YYYY for Document Courier Date field. | User is logged in as a dealer and already on claims page. | 1) Select the claim whose courier details needs to be update. 2)Click on the Add Courier details button. 3) Enter valid details in all the mandatory fields. 4) Click on Submit button. |  | In both Document Received Date ,Document Courier Date date format is YYYY/MM/DD and also date format should be DD/MM/YYYY throught the claim process. | https://prnt.sc/u7ygmz https://prnt.sc/u7yxri | Date format should get changed to DDMMYYYY for Document Courier Date field. |  |  | Fail |  | 02-09-2020 | Pass
TC_GoPaperLess_05 | 12069 | 29/8/2020 | To verify that the tabs of “Add Parts Information” “Add Labour information” & “Add Misc Exp. have been disabled/hide post Approval of the claim. | User is logged in as a dealer and already on claims page. | 1) Open any claim having status as Approved. 2) Chack “Add Parts Information” “Add Labour information” & “Add Misc Exp. fields if they are open to edit or not. |  | "Permission denied" message is coming. |  | Fields “Add Parts Information” “Add Labour information” & “Add Misc Exp." should get disabled for Approved status. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_06 | 12069 | 29/8/2020 | To verify that the tab of "Add Documents" have been disabled/hide post Approval of the claim. | User is logged in as a dealer and already on claims page. | 1) Open any claim having status as Approved. 2) Chack “Add Documents" fields if they are open to edit or not. |  | "Permission denied" message is coming. |  | Fields “Add Documents" should get disabled for Approved status. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_07 | 12069 | 29/8/2020 | To verify if the newly added status are reflecting under Key Matrix or not. 1)Post Approval Invoice Uploaded. 2)Incorrect Final Service request Invoice Uploaded. 3)Query for invoice uploaded. 4)Doc verified and processed for Payment. | Dealer is alreeady logged in. | 1) Check the Key Matrix section. |  |  |  | New statuses should get added in the key Matrix. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_08 | 12069 | 29/8/2020 | To verify that the Post Approval Documents upload by dealer the status has been changed as – “Doc. Verified and processed for Payment” | User is logged in as a dealer and already on claims page. | 1) Upload the documents . 2) Check the status. |  |  |  | Status should get changed to “Doc. Verified and processed for Payment”. |  |  | Pass-“Doc. Verified and processed for Payment” status have been added |  | 02-09-2020 | Pass
TC_GoPaperLess_09 | 12069 | 29/8/2020 | To verify that new fields (a.Tax Invoice # b. Tax Invoice Date: ) have been added under final Tax Invoice upload or not. | User is logged in as a dealer and already on claims page. | 1) Check the final Tax Invoice up section. |  | Tax Invoice Date is taking future date and also invoice date can take past date till the claim creation date. | https://prnt.sc/u7y6as | New fields (a.Tax Invoice # b. Tax Invoice Date: ) should get added under final Tax Invoice upload. |  |  | Fail |  | 02-09-2020 | Fail
TC_GoPaperLess_10 | 12069 | 29/8/2020 | To verify if the Tax Invoice# and Tax Invoice Date under Final Tax Invoice section has a data type Alphanumeric and DDMMYYYY resp. | User is logged in as a dealer and already on claims page. | 1) Check the final Tax Invoice up section. |  |  |  | DataType for Tax Invoice# and Tax Invoice Date under Final Tax Invoice section should be Alphanumeric and DDMMYYYY. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_11 | 12069 | 29/8/2020 | To verify that the Tax Invoice number and Tax invoice date have been added in the dump report or not. | User is logged in as a dealer and already on claims page. | 1) Download the claims dump report and check for Tax Invoice number and Tax invoice date fields. |  |  |  | Fields Tax Invoice number and Tax invoice date should get added in the claims dump report. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_12 | 12069 | 29/8/2020 | To verify that the Post uploading the final tax invoice by dealer, In Assurant login that documents are getting download or not. | User is logged in as a dealer and already on claims page. |  |  |  |  | Post uploading the final tax invoice by dealer, In Assurant login that document should get download. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_13 | 12069 | 29/8/2020 | To verify that the Reason od Rejection"Others" have been removed from the status list or not. | User is logged in as a dealer and already on claims page. |  |  |  |  | Reason od Rejection"others" should get removed. |  |  | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_14 | 12069 | 29/8/2020 | To verify that option to add/edit the courier details have been provided to the back end team of assurant or not. | User is logged in as a dealer and already on claims page. | [7 empty] | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_15 | 12069 | 29/8/2020 | To verify that the Pop -up is appearing for every action that dealer performs when the status is "Incorrect FINAL SERVICE REQUEST UPLOADED." | User is logged in as a dealer and already on claims page. |  |  | Alert Message is incomplete, Message should also contain the claim numbers for which the status is "Incorrect FINAL SERVICE REQUEST UPLOADED." | https://prnt.sc/u7yzpy |  |  |  | Fail |  | 02-09-2020 | Fail
TC_GoPaperLess_16 | 12069 | 29/8/2020 | To verify if the dealer is able to Final service request when the status of the claim is "Incorrect FINAL SERVICE REQUEST UPLOADED.". | User is logged in as a dealer and already on claims page. | 1) Open the claim having status "Incorrect FINAL SERVICE REQUEST UPLOADED.". 2) Upload correct final service request . 3)Click on Upload button. | TKIC11514 | There is no option/fields provided to dealer for upload/submit correct Final Service Request. | https://prnt.sc/u7zoqj |  |  |  | Fail |  | 02-09-2020 | Pass
TC_GoPaperLess_17 | 12069 | 29/8/2020 | To verify that the dealer is not allowed to add new claims when the status is "Incorrect FINAL SERVICE REQUEST UPLOADED." | User is logged in as a dealer and already on claims page. | [7 empty] | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_18 | 12069 | 29/8/2020 | To verify that the New option to add attachments under Miscellaneous Invoice field or not. | User is logged in as a dealer and already on claims page. | [7 empty] | Pass |  | 02-09-2020 | Pass
TC_GoPaperLess_19 | 12069 | 29/8/2020 | To verify if the dealer is able to Add courier details or not. | User is logged in as a dealer and already on courier submission page.. | 1) Enter valid data in all the mandatory fields. 2)Click on Save button. |  | By default "Document Courier Date. and Document Received Date." should be current date. | https://prnt.sc/u7yauk https://prnt.sc/u7yf2t |  |  |  | Fail |  | 02-09-2020 | Pass
TC_GoPaperLess_20 | 12069 | 29/8/2020 | To verify if the dealer is able to add courier details by entering invalid data in Document Courier Date and Document Received Date. | User is logged in as a dealer and already on courier submission page.. | 1) Enter invalid data in Document Courier Date and Document Received Date fields. 2)1) Enter valid data in all the remaining fields. 3)Click on Save button. | Document Courier Date 2021-08-12 Document Received Date 2022-08-18 | Document Courier Date and Document Received Date cannot take future dates. | https://prnt.sc/u7ybwe |  |  |  | Fail |  | 02-09-2020 | Fail
TC_GoPaperLess_21 | 12069 | 29/8/2020 | To verify if the dealer is able to add courier details by entering invalid data in POD number and Courier Company Name. | User is logged in as a dealer and already on courier submission page.. | 1) Enter invalid data in POD number and Courier Company Name. fields. 2)1) Enter valid data in all the remaining fields. 3)Click on Save button. | Blank spaces | Dealer is able to submit courier details by entering blank spaces in POD number and Courier Company Name. | https://prnt.sc/u7ycgi https://prnt.sc/u7yfpj |  |  |  | Fail |  | 02-09-2020 | Fail
TC_GoPaperLess_22 | 12069 | 29/8/2020 | To verify if the dealer is able to Add courier details or not. | User is logged in as a dealer and already on courier submission page.. | 1) Enter valid data in all the mandatory fields. 2)Click on Save button. |  | After submitting the courier details system shows cancel button , Button name should get changed to Close. | https://prnt.sc/u7ydrr |  |  |  | Fail |  | 02-09-2020 | Fail

## Time Automation
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-04-09 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Time Automation in Claim and Dropdpwn in Part Information.
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Time_Automation_01 | 10611 | 2020-04-09 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | tvs-tkml Welcome@123 | [5 empty] | Pass
TC_Time_Automation_02 | 10611 | 2020-04-09 | To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | [6 empty] | Pass
TC_Time_Automation_03 | 10611 | 2020-04-09 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | [6 empty] | Pass
TC_Time_Automation_04 | 10611 | 2020-04-09 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim | [6 empty] | Pass
TC_Time_Automation_05 | 10611 | 2020-04-09 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | [6 empty] | Pass
TC_Time_Automation_06 | 10611 | 2020-04-09 | To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_07 | 10611 | 2020-04-09 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_08 | 10611 | 2020-04-09 | To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. | [6 empty] | Pass
TC_Time_Automation_09 | 10611 | 2020-04-09 | To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal. | [8 empty] | Pass
aecd

## Time Automation Client UAT
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-04-10 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Time Automation in Claim
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Time_Automation_01 | 10619 | 2020-04-10 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | tvs-tkml Welcome@123 Lexus-Delhi Welcome@123 | [5 empty] | Pass
TC_Time_Automation_02 | 10619 | 2020-04-10 | To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_03 | 10619 | 2020-04-10 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_04 | 10619 | 2020-04-10 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_05 | 10619 | 2020-04-10 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_06 | 10619 | 2020-04-10 | To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided |  | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_07 | 10619 | 2020-04-10 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_08 | 10619 | 2020-04-10 | To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. | TKIC9497 TKIC9498 | [5 empty] | Pass
TC_Time_Automation_09 | 10619 | 2020-04-10 | To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal. | [8 empty] | Pass
aecd

## .Time AutomationNewClient UAT
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-04-10 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Time Automation in Claim
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Time_Automation_01 | 10905 | 2020-05-19 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Assurant-tkml Test@123 Lexus-Delhi Welcome@123 | [5 empty] | Pass
TC_Time_Automation_02 | 10905 | 2020-05-19 | To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_03 | 10905 | 2020-05-19 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_04 | 10905 | 2020-05-19 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_05 | 10905 | 2020-05-19 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_06 | 10905 | 2020-05-19 | To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided | 1)Open claim 2)Enter name in claim manager name field. 3)Click on Save Button | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_07 | 10905 | 2020-05-19 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_08 | 10905 | 2020-05-19 | To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. | TKIC11506 , TKIC11272 | [5 empty] | Pass
TC_Time_Automation_09 | 10905 | 2020-05-19 | To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal. |  |  | TKIC11506 , TKIC11272 | [5 empty] | Pass
TKIC11272
TKI16560
aecd

## Ristric URL access - correction
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-10-06 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Ristric URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: EW Data Master dump Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=27 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: DMA Variant | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: DMA Variant | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_04 | 11218 | 2020-10-06 | To verify if dealer is able to view Dealer EW Report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11218 | 2020-10-06 | To verify if dealer is able to view Toyota EW Service Requests dump Report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11218 | 2020-10-06 | To verify if dealer is able to view Toyota EW cancellation report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=28 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Toyota Service Request Dump For Assurant | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=30 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_08 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Vehicle Model Master | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=31 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Extended Warranty | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=32 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_10 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: EWS Retail | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=33 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Service Request Part Information Report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=34 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_12 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Service Request Miscellaneous Report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=35 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_13 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_14 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Cancellation report | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_15 | 11218 | 2020-10-06 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Cancell | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=Reports&view=Detail&record=40 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_16 | 11218 | 2020-10-06 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | Dealer B:CA01A-Kolkata Dealer A: Lexus-Delhi http://13.127.206.20/toyota_dev/index.php?module=PurchaseOrder&view=Detail&record=864270 http://13.127.206.20/toyota_dev/index.php?module=PurchaseOrder&view=Edit&record=864270 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_17 | 11218 | 2020-10-06 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://13.127.206.20/toyota_dev/index.php?module=PurchaseOrder&view=Detail&record=864270 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Ristric URL access -UAT
Project Name:->Toyota EW
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 16/6/2020 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Ristric URL access - correction-UAT
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrectionUAT_01 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Quick Create EW Data Master dump Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=27 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_02 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Quick Create DMA Variant | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_03 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Quick Create DMA Variant | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_04 | 11218 | 16/6/2020 | To verify if dealer is able to view Dealer EW Report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrectionUAT_05 | 11218 | 16/6/2020 | To verify if dealer is able to view Toyota EW Service Requests dump Report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrectionUAT_06 | 11218 | 16/6/2020 | To verify if dealer is able to view Toyota EW cancellation report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=28 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrectionUAT_07 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Toyota Service Request Dump For Assurant | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=30 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_08 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Vehicle Model Master | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=31 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_09 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Extended Warranty | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=32 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_10 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: EWS Retail | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=33 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_11 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Service Request Part Information Report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=34 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_12 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Service Request Miscellaneous Report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=35 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_13 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_14 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Cancellation report | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_15 | 11218 | 16/6/2020 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Cancell | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=Reports&view=Detail&record=40 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrectionUAT_16 | 11218 | 16/6/2020 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | Dealer A: CA02A-Kolkata Dealer B: Demo Dealer http://toyotanewuat.innov.co.in/index.php?module=PurchaseOrder&view=Edit&record=863934 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrectionUAT_17 | 11218 | 16/6/2020 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://toyotanewuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=864001 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Sheet5
http://13.127.206.20/toyotaew/ | tvs-tkml | Welcome@123 | TVS HO
| Lexus-Delhi | Welcome@123 | Dealer Lexus
http://toyotaphp7.innov.co.in/ | tvs-tkml | Welcome@123 | TVS HO
| Lexus-Delhi | Welcome@123 | Dealer Lexus