## Summary
Mercedes Benz
Lead Dev: Ranjeet/Vikash Jha/Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestion
Extended Eligibility | 16 | 16 | 15 | 0 | 1
Total | 16 | 16 | 15 | 0 | 1

## Bug Report
Bug Report
Project :- |  | Mercedes Benz
Created_By :- |  | Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Status on 21-02-2020 | Task ID- Retesting | Open | Close
2020-09-04 | TC_Extended_Eligibility_03 | 1 | 12172 | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during agreement creattion. "then" should get change to "than". | dealer is logged into the system. | 1) Click on create certificate request. 2)enter odometer reading more than 100000kms 3)Click on Sav button. |  | https://prnt.sc/ubjem6 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_04 | 2 | 12172 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  | https://prnt.sc/ubc0v2 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_08 | 3 | 12172 | details of the selected (12 Months/20k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA927 MBCAR118 | https://prnt.sc/ubhsel https://prnt.sc/ubhsuc http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249900 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_10 | 4 | 12172 | details of the selected (6 Months/10k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA929 MBCAR119 | https://prnt.sc/ubi4ys https://prnt.sc/ubi58f http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249841 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_12 | 5 | 12172 | details of the selected (24 Months/40k KM+4 year) is not same as that of the master data. Please find the screenshot for the same. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_13 | 6 | 12172 | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | dealer is logged into the system. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | https://prnt.sc/ubg8ji |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_14 | 7 | 12172 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | dealer is logged into the system. |  | Vin number:WDC1569456L005078 | https://prnt.sc/ubc0v2 |  |  | Fixed | Apurwa
2020-09-04 | TC_Extended_Eligibility_15 | 8 | 12172 | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | dealer is logged into the system. |  | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | https://prnt.sc/ubc71z |  |  | Fixed | Apurwa
Suggestion | TC_Extended_Eligibility_16 | 9 | 12226 | There is no plan available for 5 years , so system should throw a error message at the time of vin validation about the same. |  |  |  | https://prnt.sc/udffgf |  |  | New

## Extended Eligibility
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :-
Creation Date:- | 2020-09-04 |  |  |  | Re-Testing Date:- | 2020-08-09 |  | Developed By :- | Apurwa
Version: - |  |  |  |  | Module:- | Extended Eligibility
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Test Data | Power ID | Retesting Status
TC_Extended_Eligibility_01 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '4' as Plan in Year with Engine and Transmission coverage and standard price. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCA928 MBCAR116 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=250068 |  |  | agreement should get created with 24months/40k and 4 years. |  |  | Pass | WDC1569456L001111 MBCAR121 MBCA932 | 12226 | Pass
TC_Extended_Eligibility_02 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM+4 year) is same as that of the details of the same ew plan in .uploaded master with Engine and Transmission coverage and standard price. | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA928 MBCAR116 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=250068 |  |  | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Pass | WDC1569456L001111 MBCAR121 MBCA932 | 12226 | Pass
TC_Extended_Eligibility_03 | 12172 | 2020-09-04 | To verify if the validation of ODOmeter is upto 100000Kms or not. | dealer is logged into the system. | 1) Click on create certificate request. 2)enter odometer reading more than 100000kms 3)Click on Sav button. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during agreement creattion. "then" should get change to "than". | https://prnt.sc/ubjem6 | There should be a validation message for entering odometer reading more than 100000kms. |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_04 | 12172 | 2020-09-04 | To verify if that the * Standard Warranty Start Date is taking input date between 4 years ,11 months , 30 days to 3 years in past from current date. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | https://prnt.sc/ubc0v2 | System should allow dates only in between 5to3 years in past from current date else system should throw an error message. |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_05 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '3' as Plan in Year with Comprehensive coverage and standard price type | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCAR114 MBCA930 |  |  | agreement should get created with 24months/40k and 3 years. | WDC1569456L000001 MBCA933 MBCAR123 |  | Pass | WDC1569456L000004 MBCA935 MBCAR126 | 12226
TC_Extended_Eligibility_06 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM plan with '3' as Plan in Year )is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCAR114 MBCA930 |  |  | Details of the selected plan should be equal to the details of the same plan in EW master. | WDC1569456L000001 MBCA933 MBCAR123 |  | Pass | WDC1569456L000004 MBCA935 MBCAR126 | 12226
TC_Extended_Eligibility_07 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 12 Months/20k KM plan with '5' as Plan in Year with Comprehensive coverage | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  |  |  | agreement should get created with 12months/20k and 5years. |  |  | Pass | WDC1569456L000002 MBCA934 MBCAR124 | 12226 | Pass
TC_Extended_Eligibility_08 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan 12 Months/20k KM plan with '5' as Plan in Year is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA927 MBCAR118 | details of the selected (12 Months/20k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubhsel https://prnt.sc/ubhsuc http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249900 | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | WDC1569456L000002 MBCA934 MBCAR124 | 12226 | Pass
TC_Extended_Eligibility_09 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 6 Months/10k KM plan with '5' as Plan in Year with Engine and Transmission coverage | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin |  |  |  | agreement should get created with 6 Months/10k KM and 5years. |  |  | Pass | MBCA933 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_10 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (6 Months/10k KM)is same as that of the details of the same ew plan in .uploaded master with Engine and Transmission coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA929 MBCAR119 | details of the selected (6 Months/10k KM plan with '5' as Plan in Year ) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubi4ys https://prnt.sc/ubi58f http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249841 | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | MBCA933 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_11 | 12172 | 2020-09-04 | To verify if the dealer is able to create a new agreement by selecting 24 Months/40k KM plan with '4' as Plan in Year with Comprehensive coverage. | dealer is logged into the system. | 1) Click on the Agreement button. 1)click on Add Agreement button. 3) Validate the vin | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 |  | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be | agreement should get created with 24months/40k and 4 years. |  |  | Pass | WDC1569456L000003 MBCA936 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_12 | 12172 | 2020-09-04 | To verify if the details of the selected EW plan (24 Months/40k KM+4 year) is same as that of the details of the same ew plan in .uploaded master with Comprehensive coverage | dealer is logged into the system. | 1) Check the details of the selectd plan with the details of the same plan in EW master. | MBCA931 MBCAR115 http://13.127.10.134/mercedes_dev/index.php?module=Products&view=Detail&record=249881 | details of the selected (24 Months/40k KM+4 year) is not same as that of the master data. Please find the screenshot for the same. | https://prnt.sc/ubj7zf https://prnt.sc/ubj8be | Details of the selected plan should be equal to the details of the same plan in EW master. |  |  | Fail | WDC1569456L000003 MBCA936 MBCAR125 | 12226 | Pass
TC_Extended_Eligibility_13 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | There is a small spelling mistake in the alert message appearing for entering odometer reading less than the odometer reading during certification. "then" should get change to "than". | https://prnt.sc/ubg8ji |  |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_14 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | Vin number:WDC1569456L005078 | After creating certificate requst 04/09/2015 as vehicle Standard Warranty Start Date if dealer creates a vehicle against it then system shows validation message as "Vehicle is more then 5 Year old.." | https://prnt.sc/ubc0v2 |  |  |  | Fail |  | 12226 | Pass
TC_Extended_Eligibility_15 | 12172 | 2020-09-04 |  | dealer is logged into the system. |  | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | Validation message while creating a certificate request for odometer should be "Odometer reading value should be less than or equal to 100000." | https://prnt.sc/ubc71z |  |  | Fail | Fail |  | 12226 | Pass
[7 empty] | There is no plan available for 5 years , so system should throw a error message at the time of vin validation about the same. | https://prnt.sc/udffgf | [5 empty] | 12226 | New

## Restrict URL access - correctio
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11384 | 2020-01-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=249643 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Edit&record=249643 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Detail&record=249659 http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249659 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11384 | 2020-01-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249454 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Re-purchase Functionality
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Re-purchase Functionality
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Re-purchase_Functionality_01 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Submitted. |  |  | Pass
TC_Re-purchase_Functionality_02 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Answer By Dealer. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Answer By Dealer.. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Query By Assurant. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request Query By Assurant. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Reject. | Dealer is already logged-in |  | WDC1569086L098655 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Reject. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approve. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should be able to create a new certificate request. |  |  | Pass
TC_Re-purchase_Functionality_04 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Rejected. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Rejected.
TC_Re-purchase_Functionality_05 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approved. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Approved.
TC_Re-purchase_Functionality_06 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_07 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_08 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_09 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_10 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Expired. | Dealer is already logged-in |  | WDD2050026L011379 | User is able to validate the vin for a vin number having Certification request status: Submitted and Agreement Status: Expired. |  | Dealer should not be able to create an agreement. |  |  | Fail
TC_Re-purchase_Functionality_11 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_12 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_13 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_14 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_15 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_16 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_17 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_18 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_19 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_20 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_21 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_22 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_23 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Submitted. | Dealer is already logged-in |  | WDD2120036L056714 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_24 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_25 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_26 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_27 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_28 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Expired. | Dealer is already logged-in |  | WDC1569086L002075 MBCA926 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_29 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Alert close Agreement already created. |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_30 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_31 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_32 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_33 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_34 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_35 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_36 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_37 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_38 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_39 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_40 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_41 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select

## Approved_Claim_Amt-Dev
Project Name:-> MB
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- | 2020-03-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Ranjeet
Version: - |  |  | Version: - |  | Module:- | Approved_Claim_Amt-Dev
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Date | Status | Power ID | Date | Status
TC_ApprovedClaimAMT_01 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Part Information. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 | 134852.23 |  | The rejected part amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_02 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Labour Information. | User is already logged in | 1)mark the checkbox against the Labour to be reject, 2)Click on Update Labour Rejection | MBCAC198 |  |  | The rejected Labour amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_03 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Miscellaneous Information. | User is already logged in | 1)mark the checkbox against the Miscellaneous to be reject, 2)Click on Update Miscellaneous Rejection | MBCAC198 |  |  | The rejected Miscellaneous amount should get appear under the Rejection Amount header in Summary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_04 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Part Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_05 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for Labour information by selecting check box against Rejection check in Labour information. | User is already logged in | 1)mark the checkbox against the Rejection check for Labour Information. | MBCAC198 |  |  | All Labour should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_06 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Miscellaneous Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_07 | 11417 | 2020-03-07 | To verify if the Net Approval amount is showing the amount equal to Total Amt-Rejected Amount | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 |  |  | Net approval amount should be equal to total amt-rejected amount. |  |  | Pass | 11435 | 2020-06-07 | Pass
TC_ApprovedClaimAMT_08 | 11417 | 2020-03-07 | To verify if the Grand Total Calculation is correct or not. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection 3)Check the summary of all the parts and calculate manually | MBCAC198 |  |  | Grand total of all the fields should be correct. |  |  | Pass | 11435 | 2020-06-07 | Pass
30-06-2020

## Sheet10
Project Name:->MB
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-07-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11446 | 2020-07-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11446 | 2020-07-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11446 | 2020-07-07 | To verify if dealer is able to view Certification Request Report | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11446 | 2020-07-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11446 | 2020-07-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | Dealer A:5-AD-Hyderabad Dealer B:demo-dealer http://mbuat.innov.co.in/index.php?module=Faq&view=Detail&record=249645 http://mbuat.innov.co.in/index.php?module=Faq&view=Edit&record=249645 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11446 | 2020-07-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | Dealer A:5-AD-Hyderabad Dealer B:demo-dealer http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=245335 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=249612 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=249661 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Edit&record=244366 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11446 | 2020-07-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Edit&record=244366 http://mbuat.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=244366 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass