## Summery
Greenlam WMS
Lead Dev: Rahul Verma
Module | No. of test Written | No. of test executed | Pass | Fail | Deferred
Dealer- Request for Warranty Card |  | NA | 35 | 0 | 0
Builder- Request for Warranty Card | NA | NA | 31 | 0 | 0
Customer-Request for Warranty Card | NA | NA | 29 | 0 | 0
TC_ClientFeedback | 27 | 27 | 24 | 2 | 1
Total | 27 | 26 | 119 | 2 | 1

## Open Bugs
Bug Report
Project :- |  | Greenlam WMS | [5 empty] | Lead_Developer. :-Rahul Verma
Created_By :- |  | Jitendra |  |  | Module: | [8 empty] | Re-Testing : 2020-04-28 |  | Re-Testing : 2020-04-30
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Power ID | Status | Power ID | Status | Developers Comments | Open | Close
2020-04-01 | NA | 1 | 10527 | Dealer- Request for Warranty Card : Dealer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Dealer is already logged in. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 2 | 10527 | Dealer- Request for Warranty Card :Dealer is able to submit Warranty Card form by leaving "Type of site" field blank. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 3 | 10527 | Dealer-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 4 | 10527 | Dealer-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | All the fields are mandatory | 10580 | Fixed
2020-04-01 | NA | 5 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit warrant card by entering invalid data in Customer Name | Dealer is already logged in and is on Add request warranty page. |  | 6515 |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Not Fixed: P9:P62User can copy invalid data and paste in Name field. | 10626 | Fixed
2020-04-01 | NA | 6 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a form by entering invalid data (More than 10 digits and less than 10 digits) in Customer Phone field. | Dealer is already logged in and is on Add request warranty page. |  | 888955545522115 |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 7 | 10527 | Dealer-Request for Warranty Card : Customer City and Customer State both the fields are disbled (Freezed)to add/edit data. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 8 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the form by entering invalid data in Dealer Invoice No. and also Dealer invoice numberhas maximum length of 10 digits . | Dealer is already logged in and is on Add request warranty page. |  | #REF! |  | Mid | High | New | Rahul Verma | Done | 10580 | Not Fixed: User can copy invalid data and paste in invoice number field. | 10626 | Fixed
2020-04-01 | NA | 9 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the form by entering invalid data in Dealer Invoice Date. | Dealer is already logged in and is on Add request warranty page. |  | 2006-02-22 and 2027-11-24 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed: Dealer is able to submit the form by entering invalid data in Dealer Invoice Date.(2009-02-10) | 10626 | Fixed-As discussed
2020-04-01 | NA | 10 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving GIL Invoice field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 11 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Product Name field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 12 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Available Quantity field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 13 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Issue Quantity field blank by default system takes 0 as issue qty. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-01 | NA | 14 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Total Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -8988 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 15 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Issue Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -214748364 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-01 | NA | 16 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Available Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -2147483648 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 17 | 10527 | Dealer-Request for Warranty Card : Available qty cannot be more than the Total qty. | Dealer is already logged in and is on Add request warranty page. |  | Total Quantity: -8988 Available Quantity: 21474836 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-01 | NA | 18 | 10527 | Dealer-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-01 | NA | 19 | 10527 | Dealer-Request for Warranty Card : GIL Invoice and Product Name both dropdowns does not have any data to be select to submit the form. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | invoice and products will related to user business vertical and territory | 10580 | Fixed
2020-04-01 | NA | 20 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 21 | 10527 | Dealer-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 22 | 10527 | Dealer-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 23 | 10527 | Dealer-Request for Warranty Card : Installed By field should not be available to select if dealer have selected "Not yet Installed" as Installation Status. | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-01 | NA | 24 | 10527 | Dealer-Request for Warranty Card : Even after entering valid Pin Code number, system shows a validation message for invalid pin code. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 25 | 10527 | Dealer-Request for Warranty Card : Dealer is not able to edit the form as the form is not editable once it gets submitted. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Dealer only creates the form and then only bcm level user can edit the form | 10580 | Fixed
2020-04-01 | NA | 26 | 10527 | Dealer-Request for Warranty Card : Option for to select Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 27 | 10527 | Builder-Request for Warranty Card : Builder Dealer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Builder is already logged in and is on Add request warranty page. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 28 | 10527 | Builder- Request for Warranty Card : Builder is able to submit Warranty Card form by leaving "Type of site" field blank. | Builder is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 29 | 10527 | Builder-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Builder is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 30 | 10527 | Builder-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Builder is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Fields under Customer/Project information is mandatory | 10580 | Fixed
2020-04-02 | NA | 31 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving GIL Invoice field blank. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 32 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Product Name field blank. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 33 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Total Quantity field blank and system takes 0 by dafualt. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 34 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Available Quantity field blank and system takes 0 by dafualt. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 35 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Issue Quantity field blank and system takes 0 by dafualt | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 36 | 10527 | Builder-Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Total Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -15 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 37 | 10527 | Builder-Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Issue Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -5 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 38 | 10527 | Builder -Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Available Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -5 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 39 | 10527 | Builder -Request for Builder Card : Available qty cannot be more than the Total qty. | Builder is already logged in and is on Add request warranty page. |  | total qty:10 avail. qty: 20 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 40 | 10527 | Builder-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Builder is already logged in and is on Add request warranty page. |  | total qty:100 avail. qty: -100 issue qty: 250 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 41 | 10527 | Builder-Request for Warranty Card : GIL Invoice and Product Name both dropdowns does not have any data to be select to submit the form. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | invoice and products will related to user business vertical and territory | 10580 | Fixed
2020-04-02 | NA | 42 | 10527 | Builder-Request for Warranty Card : Builder is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Builder is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 43 | 10527 | Builder-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 44 | 10527 | Builder-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 45 | 10527 | Builder-Request for Warranty Card : Installed By field should not be available to select if builder have selected "Not yet Installed" as Installation Status. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 46 | 10527 | Builder-Request for Warranty Card : Builder is not able to edit the form as the form is not editable once it gets submitted. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Form creates on SE level and then only bcm level user can edit the form | 10580 | Fixed
2020-04-02 | NA | 47 | 10527 | Builder-Request for Warranty Card : Option for to select Floor and Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Builder is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 48 | 10527 | Builder-Request for Warranty Card : Option for Type of Surface Treatment and Project Address is not available in warranty form as per the shared document there should be Option for Type of Surface Treatment and Project Address. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 49 | 10527 | Customer- Request for Warranty Card : Customer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Customer is already logged in. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 50 | 10527 | Customer- Request for Warranty Card :Customer is able to submit Warranty Card form by leaving "Type of site" field blank. | Customer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 51 | 10527 | Customer-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Customer is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 52 | 10527 | Customer-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Customer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | All the fields are mandatory | 10580 | Fixed
2020-04-02 | NA | 53 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving GIL Invoice field blank. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 54 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Product Name field blank. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 55 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Total Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 56 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Available Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 57 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Issue Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 58 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Total Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -100 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 59 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Issue Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -150 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 60 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Available Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -250 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 61 | 10527 | Customer-Request for Warranty Card : Available qty cannot be more than the Total qty. | Customer is already logged in and is on Add request warranty page. |  | Toatl qty : 20 Available qty: 40 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 62 | 10527 | Customer-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Customer is already logged in and is on Add request warranty page. |  | Available Quantity: -40 Issue Quantity:80 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 63 | 10527 | Customer-Request for Warranty Card : Customer is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Customer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 64 | 10527 | Customer-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 65 | 10527 | Customer-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 66 | 10527 | Customer-Request for Warranty Card : Installed By field should not be available to select if Customer have selected "Not yet Installed" as Installation Status. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | 10626 | Fixed
2020-04-02 | NA | 67 | 10527 | Customer-Request for Warranty Card : Customer is not able to edit the form as the form is not editable once it gets submitted. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 68 | 10527 | Customer-Request for Warranty Card : Option for to select Floor, Door, Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Customer is already logged in and is on Add request warranty page. |  |  |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Fixed
2020-04-08 | NA | 69 | 10580 | Customer-Request for Warranty Card : If customer selects Floor or Doors from the dropdown of Request for Warranty Card then "Customer/Project Information" fields gets disabled to be edit. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 70 | 10580 | Customer-Request for Warranty Card : Customer can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Customer is already logged in and is on Add request warranty page. |  | Issue Quantity:2.5 Issue Quantity:2.9 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 71 | 10580 | Customer-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 72 | 10580 | Customer-Request for Warranty Card : Customer should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 73 | 10580 | Customer-Request for Warranty Card :Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Customer BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10065 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 74 | 10580 | Customer-Request for Warranty Card :Same Product ID/Code is appearing twice in the Product dropdown list. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 75 | 10580 | Customer-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 76 | 10580 | Customer-Request for Warranty Card : Customer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 77 | 10580 | Dealer-Request for Warranty Card : If Dealer selects Floor or Doors from the dropdown of Request for Warranty Card then Project Name and Project Address fields gets disabled to be edit. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 78 | 10580 | Dealer-Request for Warranty Card : Dealer can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Dealer is already logged in and is on Add request warranty page. |  | Issue Quantity:1.5 Issue Quantity:1.9 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 79 | 10580 | Dealer-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 80 | 10580 | Dealer-Request for Warranty Card : Dealer should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 81 | 10580 | Dealer-Request for Warranty Card : Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Dealer BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10066 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 82 | 10580 | Dealer-Request for Warranty Card : Dealer Same Product ID/Code is appearing twice in the Product dropdown list. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 83 | 10580 | Dealer-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 84 | 10580 | Dealer-Request for Warranty Card : Dealer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 85 | 10580 | Dealer-Request for Warranty Card : There is a spelling errorin the validation message for entering issue qty more than the available qty. "then" should be "than". | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 86 | 10580 | Builder-Request for Warranty Card : If Builder selects Floor or Doors from the dropdown of Request for Warranty Card then Project Name and Project Address fields gets disabled to be edit. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 87 | 10580 | Builder-Request for Warranty Card : Builder can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Builder is already logged in and is on Add request warranty page. |  | Issue Quantity:1.6 Issue Quantity:1.9 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 88 | 10580 | Builder-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 89 | 10580 | Builder-Request for Warranty Card : Builder should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 90 | 10580 | Builder-Request for Warranty Card : Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Builder BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10069 | [6 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 91 | 10580 | Builder-Request for Warranty Card : Builder Same Product ID/Code is appearing twice in the Product dropdown list. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 92 | 10580 | Builder-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 93 |  | Builder-Request for Warranty Card : Dealer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 94 |  | Builder-Request for Warranty Card : There is a spelling in the validation message for entering issue qty more than the available qty. "then" should be "than". | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-08 | NA | 95 |  | Customer-Request for Warranty Card : There is a spelling in the validation message for entering issue qty more than the available qty. "then" should be "than". | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | 10626 | Fixed
2020-04-24 | TC_ClientFeedback01 | 96 | 10686 | Customer is able to create warrany by entering invalid date in dealer invoice date. | User is already login |  |  | Please refer to attachment doc. | High | Low | New | Rahul Verma | DONE | 10709 | Fixed. | 10719 | Pass
2020-04-24 | TC_ClientFeedback07 | 97 | 10686 | Project Name is still appearing in the CSV upload file format and also user is not able to view/change end user. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed. | 10719 | Pass
2020-04-24 | TC_ClientFeedback08 | 98 | 10686 | Warranty Years is not coming from warranty master and be displayed to BCM on approval page. | User is already login |  |  | Please refer to attachment doc. | High | High | Fixed | Rahul Verma | DONE | 10709 | Not Fixed
2020-04-24 | TC_ClientFeedback14 | 99 | 10686 | There is no graph available at the dashboard with Buisness Verticle and Year/month wise requests. (For BCM) | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | Not required now, will implement later | 10709 | Deferred | 10719 | Pending
2020-04-24 | TC_ClientFeedback15 | 100 | 10686 | Warranty End Date is non editable/freezed. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | Logic Change Warranty years Is editable now | 10709 | Fixed | 10719 | Pass
2020-04-24 | TC_ClientFeedback20 | 101 | 10686 | The syntax, alignment and content of the email is not proper and neatly aligned. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Not Fixed- I have tried with both dealer and BCM but in both cases I didn't receive any email. | 10719 | Fail- Email is getting receive but there is an issue as the Project name, project address, installed by, installation status is appearing blank in the email. For both creation and approval.
2020-04-24 | TC_ClientFeedback22 | 102 | 10686 | In Builder login : Warranty For Approval section should not be there, Only BCM have the authority to approve/reject the warranty. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed | 10719 | Pass
2020-04-24 | TC_ClientFeedback21 | 103 | 10686 | In Dealer login : Warranty For Approval section should not be there, Only BCM have the authority to approve/reject the warranty. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed | 10719 | Pass | Pass
2020-04-24 | TC_ClientFeedback05 | 104 | 10686 | Some products under the same invoice having remaining quantity greater tha equal to 1 are not appearing in the invoice, | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed | 10719 | Pass
2020-04-24 | Na | 105 | 10686 | On warranty approval page the product name does not appear instead of product name it shows "Select an Option" | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Not Fixed | 10719 | Pass
2020-04-24 | Na | 106 | 10686 | Dropdown value in Product Type is not according to the Warranty master in case of Floor. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Not Fixed | 10719 | Pass
2020-04-24 | TC_ClientFeedback21 | 107 | 10686 | In Customer login : Warranty For Approval section should not be there, Only BCM have the authority to approve/reject the warranty. | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed | 10719 | Pass
2020-04-24 | Na | 108 | 10686 | Type of surface treatment field is not visible on front end (Checked with customer, dealer) | User is already login |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Fixed | 10719 | Pass
2020-04-24 | TC_ClientFeedback18 | 109 | 10686 | In The downloaded PDF file for both Customer and Company's copy the Custtomer Name, City and address is appearing blank and the same details are appearing in Retailers name, city and address. |  |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma | DONE | 10709 | Unable to execute this : as I am not able to approve any warranty due to an error. | 10719 | Pass
2020-04-24 | TC_ClientFeedback10 | 118 | 10686 | Invoice appearing in the invoice dropdown having blank business vertical. It should not get appear. |  |  |  | Please refer to attachment doc. | High | High | New | Rahul Verma |  | 10709 |  | 10719 | Pass
2020-04-24 |  | 113 | 10709 | Both dealer and BCM is not able to receive any email for warranty creation and approval. Which are mapped with the same BV and Territory. |  |  |  |  | High | High | New | Rahul Verma |  | 10709 |  | 10719 | Fail- Email is getting receive but there is an issue as the Project name, project address, installed by, installation status is appearing blank in the email. For both creation and approval.
2020-04-24 |  | 114 | 10709 | BCM : at the Edit warranty page when BCM enters years as 0 then validation message appears where "then" should get change to "than". |  |  |  |  | Low | Low | New | Rahul Verma |  |  |  | 10719 | Pass
2020-04-24 |  | 115 | 10709 | BCM : End date should be calculated as minus one day . Ex: start date: 2019-06-28 End date : 2020-06-27 |  |  |  |  | High | High | New | Rahul Verma |  |  |  | 10719 | Pass
2020-04-24 |  | 116 | 10709 | BCMis not able to approve or reject the warranty due to some error. System shows validation message as "Line item data is mandatory" |  |  |  |  | High | High | New | Rahul Verma |  |  |  | 10719 | Pass
2020-04-24 |  | 117 | 10709 | BCM : GIL invoice is showing blank at edit warranty page but the same warranty shows gil invoice from customer login |  |  |  |  | High | High | New | Rahul Verma |  |  |  | 10719 | Pass
2020-04-30 | TC_ClientFeedback17 | 118 | 10719 | Fail- As the Quantity (sq. mtr.) field is showing the available qty of the product. In the downloaded PDF. | [11 empty] | 10719 | Fail- As the Quantity (sq. mtr.) field is showing the available qty of the product. In the downloaded PDF.
10719
10719
10719
10719
10719

## TC_ClientFeedback
Project Name: Greenlam WMS
Updated By:- | Jitendra |  | ReTestedBy:- |  |  | Developed By: | Rahul Verma
Creation Date:- |  |  | Retesting Date:-
Version: - |  |  | Module:- |  |  | Power ID:10686 |  |  |  |  | Retesting: 28-04-2020 |  | Retesting: 29-04-2020 |  | Retesting: 30-04-2020
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Status | Power ID | Status | Power ID | Status
TC_ClientFeedback01 | To verify if the validation in the dealer invoice date is only upto last one year from the current date by entering invalid data in dealer invoice date. | User is already login | 1) Click on the Micasa Doors image available under Request for warranty. 2) Select dealer invoice date more than 1 year in past 3) Enter valid datra in remaining mandatory fields. 4) Click on Save button. | 2019-04-24 2020-03-05 | Customer is able to create warrany by entering invalid date in dealer invoice date. |  | Validation in the dealer invoice date should be only upto last one year from the current date. Form should not get saved. | High | High | Fail |  | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback02 | To verify if the "Installed by" field is disabled when installation status is "not yet installed" | User is already login |  |  |  |  | Installed by field should be disabled when installation status is "not yet installed" |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback03 | To verify if the Type of site: Example/description is visible below the dropdown | User is already login |  |  |  |  | Type of site: Example/description should be visible below the dropdown |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback04 | To verify if the Invoice List should is getting shown/selected separately from Product selection | User is already login |  |  |  |  | Invoice List should be shown separately from Product selection |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback05 | To verify if the in the Product Selection - only those products are visible which have Available Qty > 0 | User is already login |  |  |  | Some products under the same invoice having remaining quantity greate tham equal to 1 are not appearing in the invoice, | Product Selection - only those product should be visible which have Available Qty > 0 |  |  | Fail | 10709 |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback06 | To verify if the Invoice Dropdown is searchable or not. | User is already login |  |  |  |  | Searchable Invoice dropdown reqd |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback07 | To verify if the Project Name is getting captured from End user form, Project Name should not be a column in csv upload. | User is already login |  |  | Project Name is still appearing in the CSV upload file format and also user is not able to view/change end user. |  | Project Name must be captured from End user form, Project Name should not be a column in csv upload. |  |  | Fail | 10709 |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback08 | To verify if Warranty Years are coimg from warranty master and be displayed to BCM on approval page. | User is already login |  |  | Warranty Years is not coming from warranty master and be displayed to BCM on approval page. |  | Warranty Years should come from warranty master and be displayed to BCM on approval page. |  |  | Fail | 10709 |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback09 | To verify if Laminate is not included in WMS as no warranty is issued for this product type | User is already login |  |  |  |  | Laminate should not get included in WMS as no warranty is issued for this product type |  |  | It will be nagdled at the time of uploading invoice data. | 10709 | It will be nagdled at the time of uploading invoice data. | 10719 | It will be nagdled at the time of uploading invoice data. | 10719 | It will be nagdled at the time of uploading invoice data.
TC_ClientFeedback10 | To verify if the Invoice List is getting filtered on the basis of business vertical selected from Landing Page | User is already login |  |  | Invoice appearing in the invoice dropdown having blank bsiness vertical. It should not get appear. |  | Invoice List should be filtered on the basis of business vertical selected from Landing Page |  |  | Pass | 10709 | Not fixed | 10719 | Pass | 10719 | Pass
TC_ClientFeedback11 | To verify if the Type of surface treatment is placed on the right side or not. | User is already login |  | Type of surface treatment field is not visible on front end (Checked with customer, dealer) |  |  | Type of surface treatment: can be adjusted on right side (layout to be made compact) |  |  | Fail | 10709 |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback12 | To verify if the Warranty Start Date is appearing is same as the invoice date. | User is already login |  |  |  |  | Warranty Start Date should be the invoice date. |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback13 | To verify if the Dashboard is showing only the Pending Requests for approval by default. For BCM | User is already login |  |  |  |  | For BCM - Dashboard should show only Pending Requests for approval, and graphs at right side showing BV-wise and Year/month-wise requests |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback14 | To verify if the Dashboard is showing only the graphs at right side with Buisness Verticle and Year/month wise requests. For BCM | User is already login |  |  | There is no graph available at the dashboard with Buisness Verticle and Year/month wise requests. (For BCM) |  | Dashboard should be showing only the graphs at right side with Buisness Verticle and Year/month wise requests. For BCM |  |  | Fail | 10709 |  | 10719 | Pending | 10719 | Pending
TC_ClientFeedback15 | To verify if the Warrantyn End Date is editable -that is only Year can be edited and Month, date should not. For BCM | User is already login |  |  | Warranty End Date is non editable/freezed. |  | For BCM - Warranty End Date will be editable, but dd-mm will be fixed as per (Start Date minus 1). Only year can be changed. According to this, Warranty Years will be changed. |  |  | Fail | 10709 |  | 10719 | Pass-only years can be chnaged now | 10719 | Pass-only years can be chnaged now
TC_ClientFeedback16 | To verify if the Product Type field have been added (for dealer, customer and builder) right after "type of surface treatment" having values - Fire Rated, Non Fire Rated, Speciality (only for Floor) | User is already login |  |  |  |  | Product Type field should be added (for dealer, customer and builder) right after "type of surface treatment". Values - Fire Rated, Non Fire Rated, Speciality (only for Floor) |  |  | Pass | 10709 | Pass | 10719 | Pass | 10719 | Pass
TC_ClientFeedback17 | To verify if the Product Description/Name is appearing in the downloaded PDF file. | User is already login |  |  |  |  | Product Description/Name reqd in PDF |  |  | Pass | 10709 | Unable to execute as there is a blocker for it | 10719 | Fail | 10719 | Fail- As the Quantity (sq. mtr.) field is showing the available qty of the product. In the downloaded PDF.
TC_ClientFeedback18 | To verify if the Warranty Certificate of Floor - For Dealer/Customer/Builder, "Customer Copy" page is getting downloaded and for BCM, "Company's copy" is getting downloaded. | User is already login |  |  |  | In The downloaded PDF file for both Customer and Company's copy the Custtomer Name, City and address is appearing blank and the same details are appearing in Retailers name, city and address. | Warranty Certificate of Floor - For Dealer/Customer/Builder, "Customer Copy" page will be downloaded; for BCM, "Company's copy" will be downloaded i.e. 2 PDFs reqd |  |  | Fail |  |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback19 | To verify if the Email is getting sent to Dealer / BCM through the system on request creation and after approval. (PDF will be sent as attachment accordingly ) | [5 empty] | Email should ge to Dealer/BCM) sent on request creation and after approval (PDF will be sent as attachment accordingly |  |  | Pass |  | Email is not getting received | 10719 | Pass but sending PDF as attachment is pending | 10719 | Pass
TC_ClientFeedback20 | To verify if the syntax and content of the email sent to dealer and BCM is properor not. | User is already login |  |  | The syntax, alignment and content of the email is not proper and neatly aligned. |  | The syntax, alignment and content of the email should be proper and neatly aligned. |  |  | Fail |  |  | 10719 | Fixed | 10719 | Fail
TC_ClientFeedback21 | To verify if the dashboard is appearing in Dealer home page. | User is already login |  |  | Dashboard is available in Dealer login. It should be available for BCM only. |  | Dashboard should not be available in Dealer login. It should be available for BCM only. |  |  | Fail |  |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback22 | To verify if the dashboard is appearing in Builder home page. | User is already login |  |  | Dashboard is available in builder login. It should be available for BCM only. |  | Dashboard should not be available in Builder login. It should be available for BCM only. |  |  | Fail |  |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback23 | To verify if the dashboard is appearing in Customer home page. | User is already login |  |  | Dashboard is available in customer login. It should be available for BCM only. |  | Dashboard should not be available in Customer login. It should be available for BCM only. |  |  | Fail |  |  | 10719 | Pass | 10719 | Pass
TC_ClientFeedback24 | To | [5 empty] | Whether to change "available qty" and "issue qty" fields/process - to be confirmed from GIL.
TC_ClientFeedback25
TC_ClientFeedback26
TC_ClientFeedback27

## credentials
URL = http://13.232.233.123/wms_greenlam/
cse01 = Welcome@123
cbcm01 =Welcome@123
dse01 = Welcome@123
dbcm01 = Welcome@123
bse01 = Welcome@123
bbcm01 = Welcome@123
1010001148 = Welcome@123
1010000345 = Welcome@123
Client Feedback 23-04-2020
URL | http://13.232.233.123/wms_greenlam/
Login Credentials |  |  |  | WARRANTY/16525
| Username | Password | Role
1 | admin | Welcome@123 | Admin
2 | bse01 | Welcome@123 | Builder
3 | dse01 | Welcome@123 | Dealer
4 | dbcm01 | Welcome@123 | BCM
5 | 1010000345 | Welcome@123 | Customer

## Dump
API Name | Bug Description | Pay Load | Error/Success Message | Screenshot
Estimation Approval API | 1. Please change “Entity” to “Claim Approval” in the confirmation message of successful claim approval. | { "aiz_claim_number": "07786738985", "approval_status": "On Hold" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Estimation Approval API | 2.Claim status should not get update in case of CPP but this is happening. | { "aiz_claim_number": "07786738985", "approval_status": "On Hold" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Escalated Cases API | 1. Please change “Entity” to “Escalation Status” in the confirmation message of successful escalation. | { "aiz_claim_number": "07786738985", "escalation": "yes" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Claim Cancellation API | 1. User is able to cancel the claim without entering “Cancellation Reason” which is a mandatory field. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
| 2. Please change “Entity” to “Escalation Status” in the confirmation message of successful escalation. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
| 3. Claim status should not get update in case of CPP but this is happening. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "Hi this is dummy text" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }