## Summery
Module | No. of Test Case Executed | Pass | Fail
Part-Dropdowns | 2 | 1 | 1
Total | 2 | 1 | 1

## Open Bugs
Bug Report
Project :- | [6 empty] | Lead_Developer. :-Vikash Jha
Created_By :- |  |  | Jitendra |  |  |  | Power_Task_I.D. :-9992
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close
2020-02-12 | TC_Test Cases-Part-Dropdowns_2 | Buug_ID_1 | Dropdown value is not coming in the downlaoded report. | User is already logged in | 1)Click on the Report available under menu item. 2)Click on EW Claims Dump. 3)Select the valid start date and end date (Present date) 4)Click on Generate Now button. 5)Open the claims dump report and check if the same dropdown and its value is coming or not. |  |  | High | High | New

## Reports
Bug Tracker
|  | Project | TVSAL
|  | Created By | Jitendra
|  | Module | Reports
Date | Bug ID | Bug Description | Steps to Reproduce | Severity | Priority | Status | URL/Attachments | Assigned to | Developers Comments | Developers Status | Developers URL | Testers Comments | Open | Close
2020-01-27 | 1 | EW Sales Master Dump Report: Policy Status coming in downloaded excel report is incorrect. That is Policy status column is showing EW issue/creation date instead of showing the status. | 1)Download the EW sales master dump report by clicking on Reports button. 2)Click on EW sales master dump report link. 3)Enter the valid dates in Start Date and End Date. 4)Click on Generate Now button. 5)Open the downloaded excel file. 7)Check the Policy Status column in excel file. | Mid | Mid | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtbue7 | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 2 | EW Sales Master Dump Report: Customer Name is coming without any space in first name and last name. (If both First and Last name have been added) | 1) Open any agreement having First Name and Last Name added in the agreement. 2)Open the downloaded excel file and check the customer name colum of the same agreement which you have opened in portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtbyni and https://prnt.sc/qtbz4q | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 3 | EW Sales Master Dump Report: There is mismatch in the Extended warranty field that is in the downloaded excel file Selected EW plan is appearing for a particular agreement but the same plan field is appearing blank in the portal. (E.G:Agreement Number : SO94318,SO94400,SO94394 ) | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtcb67 and https://prnt.sc/qtcbhs | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 4 | EW Sales Master Dump Report:Mobile number in the downloaded record is different from the mobile number appearing on the portal for the same agreement number. E.G: Take SO94385 agreement number. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtdiu6 and https://prnt.sc/qtdk3d | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 5 | EW Sales Master Dump Report: There is a speclling mistake in Agreement List as "W out" It should be Without. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Low | Low | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtelck | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 6 | Claim Dump For Assurant: In the downloaded excel fil of claim dump for assurant document number is missing. | 1)Download the excel file of Claim Dump For Assurant available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtes12 and https://prnt.sc/qtesk3 | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 7 | Extended Warranty Report: Fuel Type for Product Number PRO1371 and PRO1370 is incorrct in the extended warranty excel file as DIESEL but it should be CNG. | 1)Download the excel file of Extended Warranty Report available under reports and check it with the entries on the portal. | High | High | Fixed | https://prnt.sc/qtffs5 and https://prnt.sc/qtfg98 https://prnt.sc/qtfgm3
2020-01-27 | 8 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is EWS RetaIl No is " Assests No." in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 9 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Dealer Margin is " Distribution_Commissions" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 10 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is AL Royalty is " Manufacturer Royalty" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 11 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Program Fees is " Program Price" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 12 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Roadside Assistance Fees is " Total Sales Excu Incentive" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 13 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Add: Service Tax (GST) is " Service Tax" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 14 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Basic Price (Excluding GST) is "Final Price W`out Tax" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 15 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Final Price (Including GST) is "Final Price" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 16 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Created Time is "EW Issue Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 17 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty is "EW Plan Selected" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 18 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty Start Period is "EW Start Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 19 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty End Period is "EW End Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 20 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty Start Kms is "EW Start Km" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 21 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty End Kms is "EW End Km" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 22 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Status is "Policy Status" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 23 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Address is "Address 1" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 24 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Postal Code is "Pin Code" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 25 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Mobile Phone is "Customer Contact No. 1" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 26 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Office Phone / Home Phone is "Customer Contact No. 2" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 27 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Primary Email is "Customer Email ID" in excel. 2)Executive Name is Sales Person Name 3)Final Price W out Tax is Sub Total 4)Customer Price is Customer Charge 5)CGST Amount is CGST Amount % 6)Dealer Margin is Dealer Commision 7)Final Price Without Tax is Dealer to pay TVS (incl Tax) 8)AL Royalty is Royalty | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 28 | EW cancellation report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Assigned To is "Dealer name" in excel. 2)Agreement Number is Policy No. 3)Vehicle Chassis No is Chassis# 4)Created Time is EW Policy issue date 5) | 1)Download the excel file of EW cancellation report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-28 | 29 | Part Information Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Vehicle Model is "Remark" in excel. 2)Part Description is Description 3)Unit Price No is Price 4)Created Time is EW Policy issue date 5)Status is Approved by TVS | 1)Download the excel file of Part Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Not clear.
2020-01-28 | 30 | Labour Information Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is "Status" is "Approved by TVS" in excel file. 2)GST Amount is "Tax." | 1)Download the excel file of Labour Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Not clear.
2020-01-28 | 31 | Labour Information Report: Rejection status of Labour Information Claim is not coming in the downloaded excel file for the same. | 1)Download the excel file of Labour Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed | https://prnt.sc/qttrbd and https://prnt.sc/qttsr0 | Ranjeet | Not clear.
2020-01-28 | 32 | Claims : Labour code appearing in the Labour Information Claim section is wrong. It is showing as 26028 instead of RS200VA | 1)Download the excel file of EW cancellation report available under reports and check it with the entries on the portal. | High | High | Deffered | https://prnt.sc/qttt9s and https://prnt.sc/qtttuk | Ranjeet | Not required to change. It is showing RS200VA.

## Test Cases-Part-Dropdowns
Test Cases
Project Name: Ashok Leyland EW
Created By:- | JITENDRA |  | Reviewed By:- |  |  | Developed By: | Vikash Jha
Creation Date:- |  |  | Review Date:- |  |  | Power Task ID: | 9992
Version: - |  |  | Module:- | Test Cases-Part-Dropdowns
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Test Cases-Part-Dropdowns_1 | To verify if the dropdowns in the Part Information is coming or not. | User is already logged in | 1)Click on the Claim under Menu item. 2)Click on add claim button. 3)Submit the claim form by entering valid data. 4)Now go to Part information section. 5)Click and view the dropdown values under Part Location. |  | All the dropdowns are appearing under Part Location in Part Information section. |  | All the dropdowns should get appear under Part Location in Part Information section. |  |  | Pass
TC_Test Cases-Part-Dropdowns_2 | To verify if the selected dropdown value after submitting a claim is appearing in the claim dump report. | User is already logged in | 1)Click on the Report available under menu item. 2)Click on EW Claims Dump. 3)Select the valid start date and end date (Present date) 4)Click on Generate Now button. 5)Open the claims dump report and check if the same dropdown and its value is coming or not. |  | Dropdown value is not coming in the downlaoded report. |  | Dropdown value should be in the downlaoded report. |  |  | Fail