## Summery
Nissan Datsun Care
Lead Dev: Vikash Jha/ Ranjeet
Module | No. of test Written | No. of test executed | Pass | Fail
InactiveDatsunCare | 12 | 12 | 12 | 0
Care Sales-Agreement | NA | NA | NA | 8
Total | 12 | 12 | 12 | 0

## Open Bugs
Bug Report
Project :- | [6 empty] | Lead_Devp. :- |  | Vikash Jha
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 11003
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Open_Date | Close_Date
11003 | NA | Bug_ID_11 | There is no validation applied for entering invalid data in First Name & Last Name Field. | User is already logged in and is on Create Agreement Page. |  | First Name: !@! KJN 54 Last Name: 6845 @RFW |  | Mid | Mid | New
11003 | NA | Bug_ID_12 | User should not be able to enter "0000000000" in mobile number field. | User is already logged in and is on Create Agreement Page. |  | 0 |  | Mid | Mid | New
11003 | NA | Bug_ID_13 | There is no validation applied for entering invalid data in Office Phone, Home Phone Field. | User is already logged in and is on Create Agreement Page. |  | Office Phone: 68hj !@@@@# Home Phone: ^&njk 454 6 |  | Mid | Mid | New
11003 | NA | Bug_ID_14 | There is no validation applied for entering invalid data in GSTIN field | User is already logged in and is on Create Agreement Page. |  | GSTIN: 8 561545 |  | Mid | Mid | New
11003 | NA | Bug_ID_15 | There should be a minimum character limit for Address field as the sysetm shows error message "Record you trying to access is not found" | User is already logged in and is on Create Agreement Page. |  | Address : Lorem Ipsum is simply dummy text of the printing and typesetting industry. Lorem Ipsum has been the industry's standard dummy text ever since the 1500s, when an unknown printer took a galley of type and scrambled it to make a type specimen book. It has survived not only five centuries, but also the leap into electronic typesetting, remaining essentially unchanged. It was popularised in the 1960s with the release of Letraset sheets containing Lorem Ipsum passages, and more recently with desktop publishing software like Aldus PageMaker including versions of Lorem Ipsum. |  | High | High | New
11003 | NA | Bug_ID_16 | There is no validation applied for entering invalid data in Executive Name & Sales Manager Name Field. | User is already logged in and is on Create Agreement Page. |  | Sales Manager Name: 65 @#$ eqe Executive Name :98 @#@ fef |  | Mid | Mid | New
11003 | NA | Bug_ID_17 | Browser Compatibility Issue: In firefox: While creating an agreement for Nissan Care Sales user is getting an error message as "Vehicle Invoice date should be greater than 31 may 2019" but No such issue found in Chrome browser and also there is spelling mistake in the validation as grater instead greater. | User is already logged in and is on Create Agreement Page. |  |  |  | High | Hgh | New
11003 | NA | Bug_ID_18 | Browser Compatibility Issue: In firefox: While creating an agreement for Nissan Care Sales user is getting an error message as "We have Not esxtended warranty found for this vin no," but No such issue found in Chrome browser | User is already logged in and is on Create Agreement Page. |  |  |  | High | Hgh | New

## Closed_Bugs
Bug Report
Project :- |  |  | Nissan Datsun Reports |  |  |  | Lead_Developer. :-Vikash Jha
Created_By :- |  |  | Jitendra |  |  |  | Power_Task_I.D. :-9978
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close
2020-02-11 | TC4_DC _Claim Dump | Bug_ID_1 | Customer name should have a space between first and last name. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  |  | High | Low | Closed | Ranjeet
2020-02-11 | TC5_DC _Claim Dump | Bug_ID_2 | Enhancemnt: Service request should get change to Service Request Number |  |  |  |  | Low | Low | Closed | Ranjeet
2020-02-11 | TC7_DC_Claim Periodic_Maintenance | Bug_ID_3 | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | User is already logged in | 1)Download the DC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  |  | High | High | Closed | Ranjeet
2020-02-11 | TC9_DC_Claim Wear_and_Tear | Bug_ID_4 | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | User is already logged in | 1)Download the DC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  |  | High | High | Closed | Ranjeet
2020-02-11 | TC13_NC _Claim Dump | Bug_ID_5 | Customer name should have a space between first and last name. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  |  | High | Low | Closed | Ranjeet
2020-02-11 | TC14_NC _Claim Dump | Bug_ID_6 | Enhancemnt: Service request should get change to Service Request Number |  |  |  |  | Low | Low | Closed | Ranjeet
2020-02-11 | TC16_NC_Claim Periodic_Maintenance | Bug_ID_7 | Total Mrp after multiplication of mrp and qty is wrong. | User is already logged in | 1)Download the NC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r0orj1 | High | High | Closed | Ranjeet
2020-02-11 | TC18_NC_Optional_Periodic_Maintenance | Bug_ID_8 | Total Mrp after multiplication of mrp and qty is wrong. | User is already logged in | 1)Download the NC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r0otrj | High | High | Closed | Ranjeet
2020-02-11 | Suggestion: | Suggestion_1 | Assigned to should get change to Dealer Name. | [6 empty] | Closed
2020-02-17 | DC Claim Periodic Maintenance-Suggestion: Part number and rate should appear as NA instead of showing it blank and zero resp in the case of "Labour type" | Bug_ID_09 | 1)Download the DC Claim Periodic Maintenance report . 2)Check the details of the report against the details of portal for any selected service request number. | [6 empty] | Closed
2020-02-17 | NC Claim Periodic Maintenance-Suggestion: Part number and rate should appear as NA instead of showing it blank in the case of "Labour type" | Bug_ID_10 | 1)Download the NC Claim Periodic Maintenance report . 2)Check the details of the report against the details of portal for any selected service request number. | [6 empty] | Closed
Closed
Closed
Closed
Closed
Closed

## Test Cases_Reports
Test Cases
Project Name: Nissan Datsun Reports
Created By:- | JITENDRA |  | Reviewed By:- |  |  | Developed By: | Vikash Jha
Creation Date:- | 2020-02-10 |  | Review Date:- |  |  | Power Task ID: | 9978
Version: - |  |  | Module:-
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC1_DC _Claim Dump | To verify if the user is able to download the DC Claim Dump excel file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click on Datsun Care Claim Dump link. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of claims dump report under datsun care. |  | User should be able to download the excel file of claims dump report under datsun care. |  |  | Pass
TC2_DC _Claim Dump | To verify if the downloaded excel file have all the claims within the slectect time slot. | User is already logged in | 1)Count the total number of claims. 2)Check the total count of claims on web-portal. |  | Total count on both excel and portal should is same. |  | Total count on both excel and portal should be same. |  |  | Pass
TC3_DC _Claim Dump | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  | All the entries on portal and excel file are same. |  | All the entries should be same as on the portal. |  |  | Pass
TC4_DC _Claim Dump | Customer name should have a space between first and last name. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  | Customer name should have a space between first and last name. |  |  | High | Low | Pass
TC5_DC _Claim Dump | Enhancemnt: Service request should get change to Service Request Number | [6 empty] | Low | Low | Pass
TC6_DC _Claim Periodic_Maintenance | To verify if the user is able to download the DC Claim Periodic Maintenance file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click on Datsun Care Periodic Maintenance. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of DC Periodic_Maintenance report under datsun care. |  | User should be able to download the excel file of Periodic_Maintenance report under datsun care. |  |  | Pass
TC7_DC_Claim Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | https://prnt.sc/r0oede | All the entries should be same as on the portal. | High | High | Pass
TC8_DC_Claim Wear_and_Tear | To verify if the user is able to download the DC Claim Wear and Teare file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click onDC Claim Wear and Tear. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of DC Claim Wear and Tear report under datsun care. |  | User should be able to download the excel file of DC Claim Wear and Tear report under datsun care. |  |  | Pass
TC9_DC_Claim Wear_and_Tear | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | https://prnt.sc/r0oipc | All the entries should be same as on the portal. | High | High | Pass
TC10_NC _Claim Dump | To verify if the user is able to download the NC Claim Dump excel file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on Nissan Care Claim Dump link. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of claims dump report under Nissan care. |  | User should be able to download the excel file of claims dump report under Nissan care. |  |  | Pass
TC11_NC _Claim Dump | To verify if the downloaded excel file have all the claims within the slectect time slot. | User is already logged in | 1)Count the total number of claims. 2)Check the total count of claims on web-portal. |  | Total count on both excel and portal should is same. |  | Total count on both excel and portal should be same. |  |  | Pass
TC12_NC _Claim Dump | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  | All the entries on portal and excel file are same. |  | All the entries should be same as on the portal. |  |  | Pass
TC13_NC _Claim Dump | Customer name should have a space between first and last name. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  | Customer name should have a space between first and last name. |  |  | High | Low | Pass
TC14_NC _Claim Dump | Enhancemnt: Service request should get change to Service Request Number | [6 empty] | Low | Low | Pass
TC15_NC _Claim Periodic_Maintenance | To verify if the user is able to download the NC Claim Periodic Maintenance file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on Nissan Care Periodic Maintenance. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of NC Periodic_Maintenance report under Nissan care. |  | User should be able to download the excel file of Periodic_Maintenance report under Nissan care. |  |  | Pass
TC16_NC_Claim Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the NC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | Total Mrp after multiplication of mrp and qty is wrong. | https://prnt.sc/r0orj1 | All the entries should be same as on the portal. | High | High | Pass
TC17_NC_Optional_Periodic_Maintenance | To verify if the user is able to download the NC Claim Wear and Teare file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on NC Optional Periodic Maintenance 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | All the entries are same as that of portal but User is able to download the excel file of NC Claim Wear and Tear report under Nissan care. |  | User should be able to download the excel file of NC Claim Wear and Tear report under Nissan care. |  |  | Pass
TC18_NC_Optional_Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download theNC Optional Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total Mrp after multiplication of mrp and qty is wrong. | https://prnt.sc/r0otrj | All the entries should be same as on the portal. | High | High | Pass

## InactiveDatsunCare
Project Name: JLR
Created By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Vikas Jha and Ranjeet
Creation Date:- | 2020-02-25 |  | Review Date:-
Version: - |  |  | Module:- | JLR- PMS CLAIM |  | Power ID:
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_InactiveDatsunCare_01 | To verify if the option to Add Agreement in Datsun Care Sales is available in dealer login or not after making the Datsun Care add agreement inactive. | Dealer is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now View the Sales page. | test_user Welcome@123 |  |  | Option to Add Agreement should not be available in the dealer login. |  |  | Pass
TC_InactiveDatsunCare_02 | To verify if the option to Add Agreement in Datsun Care Sales is available in claim manager login or not after making theDatsun Care add agreement inactive. | Claim Manager is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now View the Sales page. | tvs-nissan Welcome@1234 |  |  | Option to Add Agreement should not be available in the Claim Manager login. |  |  | Pass
TC_InactiveDatsunCare_03 | To verify if the option to Add Agreement in Datsun Care Sales is available in Admin login or not after making the Datsun Care add agreement inactive. | Admin is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now View the Sales page. | Admin Welcome@123 |  |  | Option to Add Agreement should not be available in the Admin login. |  |  | Pass
TC_InactiveDatsunCare_04 | To verify if the option to Add Agreement in Nissan Care Sales is available in Dealer login or not after making the Datsun Care add agreement inactive. | Dealer is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Nissan Care- Sales dropdown. 3) Now View the Sales page. | test_user Welcome@123 |  |  | Option to Add Agreement should be available in the Admin login. |  |  | Pass
TC_InactiveDatsunCare_05 | To verify if the option to Add Agreement in Nissan Care Sales is available in claim manager login or not after making the Datsun Care add agreement inactive. | Claim Manager is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Nissan Care- Sales dropdown. 3) Now View the Sales page. | tvs-nissan Welcome@1234 |  |  | Option to Add Agreement should not be available in the Claim Manager login. |  |  | Pass
TC_InactiveDatsunCare_06 | To verify if the option to Add Agreement in Nissan Care Sales is available in Admin login or not after making the Datsun Care add agreement inactive. | Admin is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Nissan Care- Sales dropdown. 3) Now View the Sales page. | Admin Welcome@123 |  |  | Option to Add Agreement shoulde be available in the Admin login. |  |  | Pass
TC_InactiveDatsunCare_07 | To verify if the option to Add Agreement in Nissan EW Sales is available in Dealer login or not after making the Datsun Care add agreement inactive. | Dealer is logged in. | 1)Click on NissanEW Sales available in menu options. 2) Now View the Sales page. | test_user Welcome@123 |  |  | Option to Add Agreement should be available in the Admin login. |  |  | Pass
TC_InactiveDatsunCare_08 | To verify if the option to Add Agreement in Nissan EW Sales is available in claim manager login or not after making the Datsun Care add agreement inactive. | Claim Manager is logged in. | 1)Click on NissanEW Sales available in menu options. 2)) Now View the Sales page. | tvs-nissan Welcome@1234 |  |  | Option to Add Agreement should not be available in the Claim Manager login. |  |  | Pass
TC_InactiveDatsunCare_09 | To verify if the option to Add Agreement in Nissan EW Sales is available in Admin login or not after making the Datsun Care add agreement inactive. | Admin is logged in. | 1)Click on NissanEW Sales available in menu options. 2) Now View the Sales page. | Admin Welcome@123 |  |  | Option to Add Agreement shoulde be available in the Admin login. |  |  | Pass
TC_InactiveDatsunCare_10 | To verify if the Dealer is able to Edit the previously added DatsunCare Sales agreement after making the Datsun Care add agreement inactive. | Dealer is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now click on agreement to be edit. 4) Edit the agreement and claick on Save button. | test_user Welcome@123 |  |  | Dealer should be able to edit the agreement. |  |  | Pass
TC_InactiveDatsunCare_11 | To verify if the Claim Manager is able to Edit the previously added DatsunCare Sales agreement after making the Datsun Care add agreement inactive. | Claim Manager is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now click on agreement to be edit. 4) Edit the agreement and claick on Save button. | tvs-nissan Welcome@1234 |  |  | Claim Manager should not be able to edit the agreement. |  |  | Pass
TC_InactiveDatsunCare_12 | To verify if the Admin is able to Edit the previously added DatsunCare Sales agreement after making the Datsun Care add agreement inactive. | Admin is logged in. | 1)Click on Care Sales available in menu options. 2) Click on Datsun Care- Sales dropdown. 3) Now click on agreement to be edit. 4) Edit the agreement and claick on Save button. | Admin Welcome@123 | There should not be an option to edit the agreement in and Admin login. |  | Admin should not be able to edit the agreement. |  |  | Fail