## Summery
Severaity | (All)
Row Labels
Fail
Pass
(blank)
Grand Total
Nissan Datsun Reports
|  | Module | No. of Test Case Executed | Pass | Fail
|  | DC _Claim Dump | 6 | 6 | 0
|  | Claim Periodic_Maintenance | 2 | 2 | 0
|  | DC_Claim Wear_and_Tear | 2 | 2 | 0
|  | NC _Claim Dump | 6 | 6 | 0
|  | NC _Claim Periodic_Maintenance | 2 | 2 | 0
|  | NC_Optional_Periodic_Maintenance | 2 | 2 | 0
|  | Total | 20 | 20 | 0

## Closed bugs
Bug Report
Project :- |  |  | Nissan DC |  |  |  | Lead_Developer. :-Vikash Jha
Created_By :- |  |  | Jitendra |  |  |  | Power_Task_I.D. :-9978
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close
2020-02-11 | TC4_DC _Claim Dump | Bug_ID_1 | Customer name should have a space between first and last name. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r121pz | High | Low | Deferred-Its entered like this at the time of submitting the agreement. | Ranjeet | Not Required | Its entered like this at the time of submitting the agreement. |  | 2020-02-12
2020-02-11 | TC5_DC _Claim Dump | Bug_ID_2 | Enhancemnt: Service request should get change to Service Request Number |  |  |  |  | Low | Low | Not Implemented | Ranjeet | Not Required |  |  | 2020-02-12
2020-02-11 | TC7_DC_Claim Periodic_Maintenance | Bug_ID_3 | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | User is already logged in | 1)Download the DC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r12457 | High | High | Fixed-Data is coming from the masters which is shared by the client. | Ranjeet | Not Required | Labour cost I fixed and it cannot be computed on the basis of quantity. Data is coming from the masters which is shared by the client. |  | 2020-02-12
2020-02-11 | TC9_DC_Claim Wear_and_Tear | Bug_ID_4 | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | User is already logged in | 1)Download the DC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r123ie | High | High | Fixed-Data is coming from the masters which is shared by the client. | Ranjeet | Not Required | Data is coming from the masters which is shared by the client. |  | 2020-02-12
2020-02-11 | TC13_NC _Claim Dump | Bug_ID_5 | Customer name should have a space between first and last name. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  |  | High | Low | Deferred-Its entered like this at the time of submitting the agreement. | Ranjeet | Not Required | Its entered like this at the time of submitting the agreement. |  | 2020-02-12
2020-02-11 | TC14_NC _Claim Dump | Bug_ID_6 | Enhancemnt: Service request should get change to Service Request Number |  |  |  |  | Low | Low | Not Implemented | Ranjeet | Not Required |  |  | 2020-02-12
2020-02-11 | TC16_NC_Claim Periodic_Maintenance | Bug_ID_7 | Total Mrp after multiplication of mrp and qty is wrong. | User is already logged in | 1)Download the NC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r0orj1 | High | High | Fixed-Data is coming from the masters which is shared by the client. | Ranjeet | Not Required | Data is coming from the masters which is shared by the client. |  | 2020-02-12
2020-02-11 | TC18_NC_Optional_Periodic_Maintenance | Bug_ID_8 | Total Mrp after multiplication of mrp and qty is wrong. | User is already logged in | 1)Download the NC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  | https://prnt.sc/r0otrj | High | High | Fixed-Data is coming from the masters which is shared by the client. | Ranjeet | Not Required | Data is coming from the masters which is shared by the client. |  | 2020-02-12
2020-02-11 | Suggestion: | Suggestion_1 | Assigned to should get change to Dealer Name. | [6 empty] | Not Implemented |  |  |  |  | 2020-02-12

## Open_Bugs
Bug Report
Project :- |  |  | Nissan DC |  |  |  | Lead_Developer. :-Vikash Jha
Created_By :- |  |  | Jitendra |  |  |  | Power_Task_I.D. :-9978
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Open | Close

## Test Cases_Reports
Test Cases
Project Name: Nissan DC
Created By:- | JITENDRA |  | Reviewed By:- |  |  | Developed By: | Vikash Jha
Creation Date:- | 2020-02-10 |  | Review Date:- |  |  | Power Task ID: | 9978
Version: - |  |  | Module:-
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC1_DC _Claim Dump | To verify if the user is able to download the DC Claim Dump excel file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click on Datsun Care Claim Dump link. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of claims dump report under datsun care. |  | User should be able to download the excel file of claims dump report under datsun care. |  |  | Pass
TC2_DC _Claim Dump | To verify if the downloaded excel file have all the claims within the slectect time slot. | User is already logged in | 1)Count the total number of claims. 2)Check the total count of claims on web-portal. |  | Total count on both excel and portal should is same. |  | Total count on both excel and portal should be same. |  |  | Pass
TC3_DC _Claim Dump | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  | All the entries on portal and excel file are same. |  | All the entries should be same as on the portal. |  |  | Pass
TC4_DC _Claim Dump | Customer name should have a space between first and last name. | User is already logged in | 1)Download the DC Claim Dump excel file available under reports and check it with the entries on the portal. |  | Customer name should have a space between first and last name. | https://prnt.sc/r121pz |  | High | Low | Deferred-Its entered like this at the time of submitting the agreement.
TC5_DC _Claim Dump | Enhancemnt: Service request should get change to Service Request Number | [6 empty] | Low | Low | Not Implemented
TC6_DC _Claim Periodic_Maintenance | To verify if the user is able to download the DC Claim Periodic Maintenance file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click on Datsun Care Periodic Maintenance. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of DC Periodic_Maintenance report under datsun care. |  | User should be able to download the excel file of Periodic_Maintenance report under datsun care. |  |  | Pass
TC7_DC_Claim Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | https://prnt.sc/r0oede | All the entries should be same as on the portal. | High | High | Fixed-Data is coming from the masters which is shared by the client.
TC8_DC_Claim Wear_and_Tear | To verify if the user is able to download the DC Claim Wear and Teare file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Datsun Care Report. 3)Click onDC Claim Wear and Tear. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of DC Claim Wear and Tear report under datsun care. |  | User should be able to download the excel file of DC Claim Wear and Tear report under datsun care. |  |  | Pass
TC9_DC_Claim Wear_and_Tear | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the DC Claim Wear and Tear excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total MRP should be zero if the quantity against any part is "0" that is if the quantity is 0 then total MRP should be 0 but its still getting computed by taking quantity as 1 | https://prnt.sc/r0oipc | All the entries should be same as on the portal. | High | High | Fixed-Data is coming from the masters which is shared by the client.
TC10_NC _Claim Dump | To verify if the user is able to download the NC Claim Dump excel file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on Nissan Care Claim Dump link. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of claims dump report under Nissan care. |  | User should be able to download the excel file of claims dump report under Nissan care. |  |  | Pass
TC11_NC _Claim Dump | To verify if the downloaded excel file have all the claims within the slectect time slot. | User is already logged in | 1)Count the total number of claims. 2)Check the total count of claims on web-portal. |  | Total count on both excel and portal should is same. |  | Total count on both excel and portal should be same. |  |  | Pass
TC12_NC _Claim Dump | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  | All the entries on portal and excel file are same. |  | All the entries should be same as on the portal. |  |  | Pass
TC13_NC _Claim Dump | Customer name should have a space between first and last name. | User is already logged in | 1)Download the NC Claim Dump excel file available under reports and check it with the entries on the portal. |  | Customer name should have a space between first and last name. |  |  | High | Low | Deferred-Its entered like this at the time of submitting the agreement.
TC14_NC _Claim Dump | Enhancemnt: Service request should get change to Service Request Number | [6 empty] | Low | Low | Not Implemented
TC15_NC _Claim Periodic_Maintenance | To verify if the user is able to download the NC Claim Periodic Maintenance file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on Nissan Care Periodic Maintenance. 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | User is able to download the excel file of NC Periodic_Maintenance report under Nissan care. |  | User should be able to download the excel file of Periodic_Maintenance report under Nissan care. |  |  | Pass
TC16_NC_Claim Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download the NC Claim Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | Total Mrp after multiplication of mrp and qty is wrong. | https://prnt.sc/r0orj1 | All the entries should be same as on the portal. | High | High | Fixed-Data is coming from the masters which is shared by the client.
TC17_NC_Optional_Periodic_Maintenance | To verify if the user is able to download the NC Claim Wear and Teare file or not,. | User is already logged in | 1)Click on Reports menu item. 2)Click on Nissan Care Report. 3)Click on NC Optional Periodic Maintenance 4)Select the vallid dates. 5)Click on Generate Now. | Start Date: 01/01/2020 End Date: 29/02/2020 | All the entries are same as that of portal but User is able to download the excel file of NC Claim Wear and Tear report under Nissan care. |  | User should be able to download the excel file of NC Claim Wear and Tear report under Nissan care. |  |  | Pass
TC18_NC_Optional_Periodic_Maintenance | To verify if the field lables and its corresponding data for perticular agreement number and service request number is same as that of portal or not. | User is already logged in | 1)Download theNC Optional Periodic Maintenance excel file available under reports and check it with the entries on the portal. |  | All the entries are same as that of portal but Total Mrp after multiplication of mrp and qty is wrong. | https://prnt.sc/r0otrj | All the entries should be same as on the portal. | High | High | Fixed-Data is coming from the masters which is shared by the client.