## Product BIS certificate
Project Name:->Mpartner Revamp
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2021-01-22 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul/ Shalu/Swetha
Version: - |  |  |  |  | Module:- | Product BIS Certificate
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severity | Status | Power Task ID | Retesting Date | Retesting Status
Product BIS Certificate_TC1 | 13675 | 2021-01-22 | To verify if the user(Dealer) is able to get navigate to the Product BIS Certificate link under side drawer. | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link under side drawer | User code-9716234003 pwd-Test@123 |  |  | User should bet navigate to the Product BIS Certificate link under side drawer screen |  |  | Pass | 13744 | 29-01-2021 | Pass
Product BIS Certificate_TC2 | 13675 | 2021-01-22 | To verify if the UI of the screen is as per the Mock Up screen or not. (for dealer) | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer |  | Header Name is not coming as per mock screen | https://lh3.googleusercontent.com/-5qk0phaYwKY/YBPUoni7l6I/AAAAAAAAF0c/oX3HOX6Znko6JpF_jVL8NtvrVG-pSLeIACK8BGAsYHg/s0/2021-01-29.jpg | UI of the Product BIS Certificate page should be as per the mock up screen have thumbnail and certificate name |  |  | Fail | 13744 | 29-01-2021 | Fail
Product BIS Certificate_TC3 | 13675 | 2021-01-22 | To verify if the user is able to download the PDF file of the selected Product BIS Certificate. | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer. 2.Click on the Thumbnail 2) Click on the menu option(Three dot) icon which you wish to download. |  | There is minor spelling mistake or Certificate | https://lh3.googleusercontent.com/-5qk0phaYwKY/YBPUoni7l6I/AAAAAAAAF0c/oX3HOX6Znko6JpF_jVL8NtvrVG-pSLeIACK8BGAsYHg/s0/2021-01-29.jpg | User should be able to download the selected file in Pdf |  |  | Fail | 13744 | 29-01-2021 | Fail
Product BIS Certificate_TC4 | 13675 | 2021-01-22 | To verify if the user is able to share PDF of the selected Product BIS Certificate. | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer. 2) Click on the menu option(Three dot) icon which you wish to Share. |  |  |  | User should be able to share the selected scheme file. |  |  | pass | 13744 | 29-01-2021 | Pass
Product BIS Certificate_TC5 | 13675 | 2021-01-22 | To verify if the user(Dealer) is able to get navigate to the Product BIS Certificate link under side drawer. | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link under side drawer | User code-8130777653 pwd-Test@123 |  |  | User should bet navigate to the Product BIS Certificate link under side drawer screen |  |  | pass | 13744 | 29-01-2021 | Pass
Product BIS Certificate_TC6 | 13675 | 2021-01-22 | To verify if the user(Distributer) is able to download the PDF file of the selected Product BIS Certificate. | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer. 2.Click on the Thumbnail 2) Click on the menu option(Three dot) icon which you wish to download. |  | There is minor spelling mistake or Certificate |  | User should be able to download the selected file in Pdf |  |  | fail | 13744 | 29-01-2021 | Pass

## Partner Certificate
Project Name:->Mpartner Revamp
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul/ Shalu/Swetha
Version: - |  |  |  |  | Module:- | Partner Certificate
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power Task ID | Retesting Date | Retesting Status
PartnerCertifiate_TC1 | 13675 | 2021-01-22 | To verify if the user(Dealer) is able to get navigate to the Partner Certificate link under side drawer. | User has an active internet connection and device and is already logged-in. | 1) Click on the Partner Certificate link under side drawer | User code-9716234003 pwd-Test@123 |  |  | User should bet navigate to the Partner Certificate link under side drawer screen |  |  | Pass | 13744 | 29-01-2021 | Pass
PartnerCertifiate_TC2 | 13675 | 2021-01-22 | To verify if the UI of the screen is as per the Mock Up screen or not. (for dealer) | User has an active internet connection and device and is already logged-in. | 1) Click on the Partner Certificate link available under side drawer |  | Thumbnail of Partner Certificate is too small it should occupy the screen space as per the mock up screen. | https://lh3.googleusercontent.com/-D7onDaZoyzI/YBPUqYdUKEI/AAAAAAAAF0o/uYHhWe8_91Qgz6n5FEjUU2GDmCW-5vrgwCK8BGAsYHg/s0/2021-01-29.jpg | UI of the Product Partner Certificate page should be as per the mock up screen. |  |  | pass | 13744 | 29-01-2021 | Fail
PartnerCertifiate_TC3 | 13675 | 2021-01-22 | To verify if the user(Distributer) is able to get navigate to the Partner Certificate link under side drawer. | User has an active internet connection and device and is already logged-in. | 1) Click on the Partner Certificate link under side drawer | User code- pwd-Test@123 |  |  | User should bet navigate to the Partner Certificate link under side drawer screen |  |  | pass | 13744 | 29-01-2021 | Pass
PartnerCertifiate_TC4 | 13675 | 2021-01-22 | To verify if the UI of the screen is as per the Mock Up screen or not. (for dealer) | User has an active internet connection and device and is already logged-in. | 1) Click on the Partner Certificate link available under side drawer |  | Thumbnail of Partner Certificate is too small it should occupy the screen space as per the mock up screen. | https://lh3.googleusercontent.com/-D7onDaZoyzI/YBPUqYdUKEI/AAAAAAAAF0o/uYHhWe8_91Qgz6n5FEjUU2GDmCW-5vrgwCK8BGAsYHg/s0/2021-01-29.jpg | UI of the Product Partner Certificate page should be as per the mock up screen. |  |  | pass | 13744 | 29-01-2021 | Fail

## BugReport
Bug Report
Project :- |  | M Partner | [5 empty] | Lead_Developer. :-Alok Srivastava
Created_By :- |  | Sakshi |  |  | Retested By: Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severity | Status | Assigned To
29-01-2021 | Product BIS Certificate_TC2 | 1 | 13744 | Header Name is not coming as per mock screen | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer |  | https://lh3.googleusercontent.com/-5qk0phaYwKY/YBPUoni7l6I/AAAAAAAAF0c/oX3HOX6Znko6JpF_jVL8NtvrVG-pSLeIACK8BGAsYHg/s0/2021-01-29.jpg | High | Low | Not Fixed
29-01-2021 | Product BIS Certificate_TC3 | 2 | 13744 | There is minor spelling mistake or Certificate | User has an active internet connection and device and is already logged-in. | 1) Click on the Product BIS Certificate link available under side drawer. 2.Click on the Thumbnail 2) Click on the menu option(Three dot) icon which you wish to download. |  | https://lh3.googleusercontent.com/-5qk0phaYwKY/YBPUoni7l6I/AAAAAAAAF0c/oX3HOX6Znko6JpF_jVL8NtvrVG-pSLeIACK8BGAsYHg/s0/2021-01-29.jpg | High | Low | Not Fixed
29-01-2022 | PartnerCertifiate_TC2 | 3 | 13744 | Thumbnail of Partner Certificate is too small it should occupy the screen space as per the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Partner Certificate link available under side drawer |  | https://lh3.googleusercontent.com/-D7onDaZoyzI/YBPUqYdUKEI/AAAAAAAAF0o/uYHhWe8_91Qgz6n5FEjUU2GDmCW-5vrgwCK8BGAsYHg/s0/2021-01-29.jpg | High | Low | New
29-01-2022 | FAQs_TC2 | 4 | 13744 | UI is not as per the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the FAQs link available under side drawer |  | https://techfour980143.invisionapp.com/console/share/DR1OIIK3HV/490494408 https://lh3.googleusercontent.com/-yHbB3Z0bLek/YBPUn7HBOGI/AAAAAAAAF0Y/URhLNmXm99Qe9P2sLQVhUM3T-tEp6VA2QCK8BGAsYHg/s0/2021-01-29.jpg | High | High | New
29-01-2023 | FAQs_TC3 | 5 | 13744 | FAQs for product , service and BMHR is missing. | User has an active internet connection and device and is already logged-in. | 1) Click on the FAQs link available under side drawer |  |  | High | High | New
29-01-2023 | FAQs_TC4 | 6 | 13744 | User is not able to expand or close the FAQ of Ewarranty by clicking on +&- icon resp. However the same is happening when user clicks on the header text | User has an active internet connection and device and is already logged-in. | 1.Click on Ewarranty Headers |  |  | High | High | New
29-01-2024 | FAQs_TC5 | 7 | 13744 | User is not able to expand or close the FAQ of Price by clicking on +&- icon resp. However the same is happening when user clicks on the header text | User has an active internet connection and device and is already logged-in. | 1.Click on Price Headers |  |  | High | High | New
29-01-2024 | FAQs_TC6 | 8 | 13744 | User is not able to expand or close the Scheme of Ewarranty by clicking on +&- icon resp. However the same is happening when user clicks on the header text | User has an active internet connection and device and is already logged-in. | 1.Click on Scheme Headers |  |  | High | High | New
29-01-2025 | Survey_TC2 | 9 | 13744 | 1) Edges of the pop up survey should have a curve at edges. 2) There should be space after question number and question text. | User has an active internet connection and device and is already logged-in. | 1) Enter valid data in passowrd field . 2) Click on Submit button. |  | https://techfour980143.invisionapp.com/console/share/DR1OIIK3HV/490494412 https://prnt.sc/xswfhh | High | High | New
29-01-2025 | Survey_TC4 | 10 | 13744 | There should be a confirmation message before closing the survey. | User has an active internet connection and device and is already logged-in. | Click on Cancel Icon |  |  | High | High | New
29-01-2026 | Survey_TC10 | 11 | 13744 | 1)Survey is not getting submitted as “Survey” toast is coming when user submits the survey after answering all the questions. | User has an active internet connection and device and is already logged-in. | 1.Answer all the question and click on submit |  | 2) https://lh3.googleusercontent.com/-6JfAvncbF7c/YBPUpjne43I/AAAAAAAAF0k/Cn0XArj1z34H7ZNhWawAc-byCZuD4G8DgCK8BGAsYHg/s0/2021-01-29.jpg | High | High | New
29-01-2026 | Survey_TC11 | 12 | 13744 | Servey pop up is again coming for the same user | User has an active internet connection and device and is already logged-in. | 1.Click on LUMINOUS |  |  | High | High | New
29-01-2027 | UpperMenuHeader_TC1 | 13 | 13744 | 1) Duplicate upper menu header. 2) Dealer Management, Reports, Service and Check Warranty upper sub headers are missing. | User has an active internet connection and device and is already logged-in. | 1) Enter valid data in passowrd field . 2) Click on Submit button. |  | 2)https://lh3.googleusercontent.com/-qXz_Uu-1WQo/YBPUnGtzyvI/AAAAAAAAF0M/XUIumkYoLd8h6JgHDn8SU8ThQ5kAvJIWgCK8BGAsYHg/s0/2021-01-29.jpg | High | High | New

## FAQ
Project Name:->Mpartner Revamp
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul/ Shalu/Swetha
Version: - |  |  |  |  | Module:- | Survey
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power Task ID | Retesting Date | Retesting Status
FAQs_TC1 | 13675 | 2021-01-22 | To verify if the user is able to get navigate to the FAQs link under side drawer. | User has an active internet connection and device and is already logged-in. | 1) Click on the FAQs link under side drawer | User code-9716234003 pwd-Test@123 |  |  | User should bet navigate to the FAQs link under side drawer screen |  |  | pass | 13744 | 29-01-2021 | Pass
FAQs_TC2 | 13675 | 2021-01-22 | To verify if the UI of the screen is as per the Mock Up screen or not. (for dealer) | User has an active internet connection and device and is already logged-in. | 1) Click on the FAQs link available under side drawer |  | UI is not as per the mock up screen. | https://techfour980143.invisionapp.com/console/share/DR1OIIK3HV/490494408 https://lh3.googleusercontent.com/-yHbB3Z0bLek/YBPUn7HBOGI/AAAAAAAAF0Y/URhLNmXm99Qe9P2sLQVhUM3T-tEp6VA2QCK8BGAsYHg/s0/2021-01-29.jpg | UI of the Product Partner Certificate page should be as per the mock up screen. |  |  | pass | 13744 | 29-01-2021 | Fail
FAQs_TC3 | 13675 | 2021-01-22 | To verify the FAQs page | User has an active internet connection and device and is already logged-in. | 1) Click on the FAQs link available under side drawer |  | FAQs for product , service and BMHR is missing. |  | FAQ page should display with the relative headers: +E-Warranty +Product +Service +Schemes +BMHR as per the mock up screen |  |  | Fail | 13744 | 29-01-2021 | Fail
FAQs_TC4 | 13675 | 2021-01-22 | To verify by clicking on Ewarranty header | User has an active internet connection and device and is already logged-in. | 1.Click on Ewarranty Headers |  | User is not able to expand or close the FAQ of Ewarranty by clicking on +&- icon resp. However the same is happening when user clicks on the header text |  | the questions related to that header should display. |  |  | pass | 13744 | 29-01-2021 | Fail
FAQs_TC5 | 13675 | 2021-01-22 | To verify by clicking on Price header | User has an active internet connection and device and is already logged-in. | 1.Click on Price Headers |  | User is not able to expand or close the FAQ of Price by clicking on +&- icon resp. However the same is happening when user clicks on the header text |  | the questions related to that header should display. |  |  | Pass | 13744 | 29-01-2021 | Fail
FAQs_TC6 | 13675 | 2021-01-22 | To verify by clicking on Scheme header | User has an active internet connection and device and is already logged-in. | 1.Click on Scheme Headers |  | User is not able to expand or close the Scheme of Ewarranty by clicking on +&- icon resp. However the same is happening when user clicks on the header text |  | the questions related to that header should display. |  |  | Pass | 13744 | 29-01-2021 | Fail

## Survey
Project Name:->Mpartner Revamp
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul/ Shalu/Swetha
Version: - |  |  |  |  | Module:- | Survey
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power Task ID | Retesting Date | Retesting Status
Survey_TC1 | 13675 | 2021-01-22 | To verify if the user is able to get navigate to the dashboards after a successfull login. | User has an active internet connection and device and is already logged-in. | 1) Enter valid data in passowrd field . 2) Click on Submit button. |  |  |  | User should get navigate to the Dashboards screen of the app. |  |  | pass | 13744 | 29-01-2021 | Pass
Survey_TC2 | 13675 | 2021-01-22 | To verify the UI of the dashboards pop up. | User has an active internet connection and device and is already logged-in. | 1) Enter valid data in passowrd field . 2) Click on Submit button. |  | 1) Edges of the pop up survey should have a curve at edges. 2) There should be space after question number and question text. | https://techfour980143.invisionapp.com/console/share/DR1OIIK3HV/490494412 https://prnt.sc/xswfhh | UI of the dashboards should be as per the mock up screen and survey should display in the homepage |  |  | pass | 13744 | 29-01-2021 | Fail
Survey_TC3 | 13675 | 2021-01-22 | To verify the Survey Pop up by clicking on Next button without Selecting any | User has an active internet connection and device and is already logged-in. | 1.Click on Next button |  |  |  | User should be able to submit the survey and have proper validation "Please select an option" |  |  | pass | 13744 | 29-01-2021 | Pass
Survey_TC4 | 13675 | 2021-01-22 | To verify by Clicking on Cancel icon for Survey Pop up | User has an active internet connection and device and is already logged-in. | Click on Cancel Icon |  | There should be a confirmation message before closing the survey. |  | Survey Pop up should get closed |  |  | pass | 13744 | 29-01-2021 | Fail
Survey_TC5 | 13675 | 2021-01-22 | To verify by clicking on PREVIOUS button | User has an active internet connection and device and is already logged-in. | Click on Previous button |  |  |  | PREVIOUS button should not be clickable |  |  | pass | 13744 | 29-01-2021 | Pass
Survey_TC6 | 13675 | 2021-01-22 | To verify by the selecting the option | User has an active internet connection and device and is already logged-in. | 1.select the option and click on Next button |  |  |  | User should be able navigate the next question |  |  | pass | 13744 | 29-01-2021 | Pass
Survey_TC7 | 13675 | 2021-01-22 | To verify the by clicking the PREVIOUS button | User has an active internet connection and device and is already logged-in. | 1.Click on PREVIOUS button without selecting any option |  | User is able to move to the previous question |  | User should be able to move to the previous question and should answer should be same as user selected previously |  |  | pass | 13744 | 29-01-2021 | Pass
Survey_TC8 | 13675 | 2021-01-22 | To verify if the user is selecting and unselecting options | User has an active internet connection and device and is already logged-in. | 1.Select any two option 2.Untick the Checkbox 2.Click on NEXT button 3.Click on PREVIOUS button |  | user is able to move to the previous question with the selected option which is unselected by the user previously |  | User is able to move to the previous Question and question should not be selected any option |  |  | Fail | 13744 | 29-01-2021 | Pass
Survey_TC9 | 13675 | 2021-01-22 | To verify by changing the option for the perticular question | User has an active internet connection and device and is already logged-in. | 1.Click on PREVIOUS button without 2.Unselect the option which was previously selected 3.select the option again 4.Click on next button 5.Click on Previous button again |  | previous to previous answer is showing after changing the answer |  | User should go back to the previous question the same answer which he/her selected recently |  |  | Fail | 13744 | 29-01-2021 | Pass
Survey_TC10 | 13675 | 2021-01-22 | To verify if user is able to submit the survey by answering all the question | User has an active internet connection and device and is already logged-in. | 1.Answer all the question and click on submit |  | 1)Survey is not getting submitted as “Survey” toast is coming when user submits the survey after answering all the questions. | 2) https://lh3.googleusercontent.com/-6JfAvncbF7c/YBPUpjne43I/AAAAAAAAF0k/Cn0XArj1z34H7ZNhWawAc-byCZuD4G8DgCK8BGAsYHg/s0/2021-01-29.jpg | After answering all the question pop up should be able to submit the servey |  |  | Pass | 13744 | 29-01-2021 | Fail
Survey_TC11 | 13675 | 2021-01-22 | To verify if User is able to submit the survey again | User has an active internet connection and device and is already logged-in. | 1.Click on LUMINOUS |  | Servey pop up is again coming for the same user |  | User should not have the option to sumit the survey once he/her ahs already submitted |  |  | Fail | 13744 | 29-01-2021 | Fail

## Upper menu header
Project Name:->Mpartner Revamp
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul/ Shalu/Swetha
Version: - |  |  |  |  | Module:- | Upper menu header
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severity | Status | Power Task ID | Retesting Date | Retesting Status
UpperMenuHeader_TC1 | 13675 | 2021-01-21 | To verify the Upper menu header | User has an active internet connection and device and is already logged-in. | 1) Enter valid data in passowrd field . 2) Click on Submit button. |  | 1) Duplicate upper menu header. 2) Dealer Management, Reports, Service and Check Warranty upper sub headers are missing. | 2)https://lh3.googleusercontent.com/-qXz_Uu-1WQo/YBPUnGtzyvI/AAAAAAAAF0M/XUIumkYoLd8h6JgHDn8SU8ThQ5kAvJIWgCK8BGAsYHg/s0/2021-01-29.jpg | Some sub headers are Gallery(rename to Luminous Youtube), Dealer Management, Reports, Service Escalation(rename to Service & it is for all service functionality), FAQs, Check Warranty should be shown in the Upper menu header |  |  | Fail | 13744 | 29-01-2021 | Fail
UpperMenuHeader_TC2 | 13675 | 2021-01-21 | To verify by Clicking on Customer Complaints available in the Upper menu header | User has an active internet connection and device and is already logged-in. | 1.Click on Customer Complaints available in the Upper menu header |  | Upper Menu is not clickable |  | Customer Complaints should be clickable |  |  |  | 13744 | 29-01-2021 | Pass
UpperMenuHeader_TC3 | 13675 | 2021-01-21 | To verify if the upper sub menu is scrolling or not | User has an active internet connection and device and is already logged-in. |  |  |  |  | User should be able to scroll the Upper menu Header |  |  |  | 13744 | 29-01-2021 | could not execute.
UpperMenuHeader_TC4 | 13744 | 29-01-2021 | To verify if the user is getting navigate to the Home page after clicking on Luminous. | User has an active internet connection and device and is already logged-in. | 1) Click on luminous logo. |  |  |  | User should get navigate to the home screen. |  |  |  | 13744 | 29-01-2021 | Pass

## Summary
M-partner Revamp phase 2
Lead Dev: Shalu/Ashu
Module | No. of test Written | No. of test executed | Pass | Fail
Survey | 11 | 11 | 7 | 4
Upper Menu Header | 4 | 3 | 2 | 1
Product BIS Certificate | 6 | 6 | 4 | 2
Partner Certificate | 4 | 4 | 3 | 1 | 2)Upper menu header
FAQs | 6 | 6 | 4 | 2 | 3)Product BIS certificate
Total | 31 | 30 | 20 | 10 | 5)FAQ