## Re-purchase Functionality
Project Name:->Renault EW
Created By:- | Sakshi Tiwari |  |  |  | Re-Tested By:- | Sakshi |  | Pre-condition :-
Creation Date:- | 2020-12-28 |  |  |  | Re-Testing Date:- | 2021-01-07 |  | Developed By :- | Apurwa
Version: - |  |  |  |  | Module:- | Re-purchase Functionality
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power Id | Rtesting date | Retesting Status
Repurchage_TC1 | 13389 | 2020-12-28 | To verify if dealer is able to login with valid credentials | User is already logged-in | 1.Enter URL 2.Login with valid user id and pwd | 1.URL-http://13.127.10.134/renaultnew_dev/index.php?module=Home&view=DashBoard 2.User name-BIJA-Bilaspur pwd-Welcome"789 |  |  | Dealer Should be able to login and home page should display |  |  | Pass |  | 2021-01-07 | pass
Repurchage_TC2 | 13389 | 2020-12-28 | To verify if the Dealer is able to get navigate to the Easy Care Sales page. | User is already logged in | 1)Click on the Easy Care Sales available at the menu section. |  |  |  | Add Easy Care Sales page should get open having Add Easy Care Button, Renew Button and Add Update odometer. |  |  | Pass
Repurchage_TC3 | 13389 | 2020-12-28 | To verify the +Renew Button | User is on Vin Validation page | 1)Click on + Renew Button 2)Enter vin number 3)Click on Validate button | Vin number-MEEHSRCFKG2000087 |  |  | Dealer should not be able to validate the vin number having Satus is Active |  |  | Pass
Repurchage_TC4 | 13389 | 2020-12-28 | To Verify if the dealer is able to renew an REC with an existing vin number having AMC status:Active | User is already logged-in | Pick the vin number having AMC Satus is Active and Validate | Vin number-MEEHSRCFKG2000087 |  |  | User should not be able to Repurchage with a vin number having a AMC status Active. |  |  | Pass
Repurchage_TC5 | 13389 | 2020-12-28 | To Verify if the dealer is able to renew an REC with an existing vin number having AMC status:Cancelled | User is already logged-in | Pick the vin number having AMC Satus is Cancelled and Validate the vin number | Vin number-MEEBBA002GB438865 |  |  | User should not be able to Repurchage with a vin number having a AMC status Cancelled. |  |  | Pass
Repurchage_TC6 | 13389 | 2020-12-28 | To verify if the user is able to Repurchase when Existing policy should have the status is ‘Pending for amendment’ . | User is already logged-in | Pick the vin number having AMC Satus is Pending for amendment and Validate the vin number | Vin number-MEEBBA006G3347401 | vin number is validating |  | User should not be able to Repurchage with a vin number having a AMC status Pending for amendment |  |  | Pass
Repurchage_TC7 | 13389 | 2020-12-28 | To verify if the user is able to Repurchase when Existing policy should have the status is ‘Expired’ . | User is already logged-in | Pick the vin number having AMC Satus is Expired and Validate the vin number | Vin number-EERBC004KC021549 | vin number is validating |  | User should be able to Repurchage with a vin number having a AMC status Expired and & details should flow from already punched old REC Policy. |  |  | Pass
Repurchage_TC8 | 13389 | 2020-12-28 | To verify if Customer & Vehicle details flow from old policy details and will reflect in the Easy-Care sales Form | User is already logged-in |  |  | All the Details are visible from old policy details |  | Customer & Vehicle details should flow from old policy details and will reflect in the Easy-Care sales form |  |  | Pass
Repurchage_TC9 | 13389 | 2020-12-28 | to Verify if all the manadatory fields are having * and auto fetch data are not editable | Dealer is already logged in and is on Add New Easy Care Agreement page. | 1)Enter Url 2)Enter Admin and pwd 3)click on Easy Care Sales click on Add Renew Button Enter VIN number and validate |  | non Editable |  | all the mandatory Fields should have * and Autofetch data should not be editable |  |  | Pass
Repurchage_TC10 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving all the mandatory fields blank. | User is already logged in and is on Creating New Easy Care page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  | As expected |  | User should not be able to create a new Easy Care Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | Pass
Repurchage_TC11 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | Pass
Repurchage_TC12 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | Pass
Repurchage_TC13 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required." |  |  | Pass
Repurchage_TC14 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." |  |  | Pass
Repurchage_TC15 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | Pass
Repurchage_TC16 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required." |  |  | Pass
Repurchage_TC17 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for city field as "City is required." |  |  | Pass
Repurchage_TC18 | 13389 | 2020-12-28 | To verify if the Vehicle Chasis No not be editable | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Vehicle Chasis No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Vehicle Chasis No is autofetched and not editable |  | Vehicle Chasis No should not be editable |  |  | Pass
Repurchage_TC19 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | Pass
Repurchage_TC20 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required." |  |  | Pass
Repurchage_TC21 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | Pass
Repurchage_TC22 | 13389 | 2020-12-28 | to verify by not selecting Does Vehicle belongs to Fleet field | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  |  |  |  | Pass
Repurchage_TC23 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message Please select Fleet status for Odometer Reading. |  |  | Pass
Repurchage_TC24 | 13389 | 2020-12-28 | To verify if the User is able to create new Easy Care Agreement by selecting YES from Does Vehicle belongs to Fleet dropDown | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | pop up with valiadtion message reset amc plan with ok button |  |  | Pass
Repurchage_TC25 |  |  | To verify by entering the data in Current Odometer reading and nter valid details in the remianing fields. | User is already logged in and is on New Easy Care Agreement page. | 1.Enter Data in Cureenet ododmeter reading 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Current ododmeter Reading-9 | user is not able to enter number 9 |  | User should be able to repurchange the policy |  |  | Fail
Repurchage_TC26 | 13389 | 2020-12-28 | To verify by Entering Current Odometer Reading is same as REC Start KM | User is on Creating New Easy Care | 1)Enter Current odometer Reading and enter valid data in remaing fields 2)Hit on save | Current Odometer Reading =20000 REC Start KM=20000 |  |  | It shouldn't get validate successfully and a pop-up of Easy Care Agreement details should get appear with OK & Cancel button. NOTE:The start kilometer will be current odometer +1 as per the BRD Shared |  |  | Pass
Repurchage_TC27 | 13389 | 2020-12-28 | To verify by Entering Current Odometer Reading is same as REC End KM | User is on Creating New Easy Care |  |  |  |  | The end kilometer should current odometer +EW end kilometer. |  |  | Pass
Repurchage_TC28 | 13389 | 2020-12-28 | To Verify Based on the plan selected the pricing will be populated in the 'Price Information' fields. | User is on Creating New Easy Care | Matching the price information with the Master |  |  |  | Based on the plan selected the pricing will be populated in the 'Price Information' fields. |  |  | Pass
Repurchage_TC29 | 13389 | 2020-12-28 | AMENDMENT:To verify if the User is able to Amend his/her plan within 15 days of punching | user is on Editing Easy Care - REC6620 Page | Click on Amendment Button |  | As expected |  | Dealer should be able to amend by selecting the REC Policy which was punched and is within the amendment period (15 Days) |  |  | Pass
Repurchage_TC30 | 13389 | 2020-12-28 | To verify if Dealer will click on the REC Policy button and select the reason for amendment and submit |  | Selecting the |  | As expected |  | Dealer should be able to click on the REC Policy button and select the reason for amendment and submit and the REC Policy get to editable mode. |  |  | Pass
Repurchage_TC31 | 13389 | 2020-12-28 | To verify if the Sales manager can accept or reject the amendment request as per the situation. | Sales manager is logged into the sys | 1)Login with valid user id and pwd 2)Click REC6620 | User name-S00074-Anshu pwd-5A09@ffe221b8 |  |  | Sales manager should accept or reject the amendment request. |  |  | Pass
Repurchage_TC32 | 13389 | 2020-12-28 | To verify if dealer is able to Renew the policy when Current odometer reading is expired | Dealer is loggend into the sys | Selecting the policy number which already Expired | 1.REC Agreement Number- REC6613 2.Enter valid data in all the fields. |  |  | Dealer should be able to renew the policy |  |  | Fail |  |  | pass
Repurchage_TC33 | 13389 | 2020-12-28 | Update Odometer-Upading the Current odometer raeding of REC6613 | User is already logged in and is on Update odometer pop up page | select REC Agreement Number- REC6613 1) Enter Current Odometer fields Equal to the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC006KC022587 Agreement number-REC6613 Current odometer -80000 | Updating Successfully |  | Dealer should be able to Update Current odometer raeding from 40000 to 80000. |  |  | pass
Repurchage_TC34 | 13389 | 2020-12-28 | To verify if data is coming from middleware when Renew the policy REC Agreement Number REC6621 | dealer is on Creating New Easy Care | Selecting the same Vin number which already Expired | 1.Chassis No-MEERBC006KC022587 2.observing the data and match with the middleware |  |  | Data should get computed from MW |  |  | Fail
Repurchage_TC35 | 13389 | 2020-12-28 | To verify if the dealer is able to claim against MEEBBA006J9621037 | Dealer is on Creating New Easy Care Claims | 1.Click on New Easy Care Claim 2.Click on Add Easy Care Claim 3.Select the RECC4792 4. Enter all the valid details and save | 1.Current PMS Visit-30k service 2.Job Card no.ROERJA21001111 3.Plan Name 373/REC-KWID AMT-P373-3Y-30K 4.Odometer Reading-60000 | Policy is not getting expired after Avail of services |  | Dealer should be able to claim and after avail the services the policy should get expired and dealer should renew the policy against same vin number |  |  | Fail
Repurchage_TC36 | 13389 |  | To verify if the user is able to renew the policy REC Agreement number REC6627 | Dealer is on Creating New Easy Care Claims | Selecting the REC6627 which is expired forefully | 1.Enter Last odometer reading and current odometer 2.Enter valid details in all the required fields | Agreeement is created successfully when last and current ododmeter is accepting the value which is less than the Expired value |  | User should be able to repurchange the policy |  |  | Fail
Repurchage_TC37 | 13389 | 2020-12-28 | To verify if the AMC status is getting expired when REC end period surpass | Dealer is logged into the sys and on agreement page | Selcting the agrement REC6628 and check the AMC Status |  | Amc Status is Expired |  | when A. REC end period should surpass, policy should expired and dealer should be able to renew the policy again |  |  | pending from apurwa side
Repurchage_TC38 | 13389 | 2020-12-29 | To verify if the dealer is able to repurchase the policy again | Dealer is on Creating New Easy Care Claims | 1)Click on + Renew Button 2)Enter vin number 3)Click on Validate button 4).Enter valid data in all the required fields and save the agreement | Vin number-MEERBC006KC022587 | Document is not visible in the document details list |  | Dealer should be able to renew the policy and save successfully |  |  | Pass
|  |  | Verify the agreement details page | Dealer is on agreement deatails page | Observing the data
Repurchage_TC39 | 13389 | 2020-12-30 | To verify if the dealer is able to repurchase the policy again | Dealer is on Creating New Easy Care Claims | 1)Click on + Renew Button 2)Enter vin number 3)Click on Validate button | Vin number-MEEBBA006J9621037 | Document is not visible in the document details list |  | Dealer should be able to renew the policy and save successfully |  |  | Pass
Repurchage_TC40 | 13389 | 2020-12-31 | To verify if the dealer is able to repurchase the policy again | Dealer is on Creating New Easy Care Claims | 1)Click on + Renew Button 2)Enter vin number 3)Click on Validate button | Vin number-MEERBC004KC021549 | Document is not visible in the document details list |  | Dealer should be able to renew the policy and save successfully |  |  | pass

## UpdateOdometer
Project Name:->Renault EW
Created By:- | Sakshi Tiwari |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-12-28 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Apurwa
Version: - |  |  |  |  | Module:- | Update Odometer
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
UpdateOdometer_TC1 | 13389 | 2020-12-28 | To verify if the able to update the currect odometer reading for the Existing policy | Dealer is logged | 1)Click on + Update Odometer |  |  |  | ask for Updating the odometer and pop-up should open the Do you want to current odometer reading and status |  |  | Pass
UpdateOdometer_TC2 | 13389 | 2020-12-28 | To verify the page | [5 empty] | pop[-Up having following fields 1.Agreement No 2.Chassis No 3.Current Odometer 4.Update and Close (Button) |  |  | Pass
UpdateOdometer_TC3 | 13389 | 2020-12-28 | To verfiy by clicking on Close button |  |  |  |  | Back to previous page | User should be able to close the pop up. |  |  | Pass
UpdateOdometer_TC4 | 13389 | 2020-12-28 | To verify if the User is able to Update the odometer by leaving all the mandatory fields blank. | User is already logged in and is on Creating New Easy Care page. | 1)Leave all the mandatory fields blank. 2)Click On Update Button. |  |  | Valist | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC5 | 13389 | 2020-12-29 | To verify if the User is able to Update odometer by leaving Agreement number field blank and enter valid details in the remaining fields. | User is already logged in and is on Update odometer pop up page | 1) Leave Agreement No fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Current Odometer-REC6620 | As expected |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC6 | 13389 | 2020-12-30 | To verify if the User is able to Update odometer by leaving Chassis No field blank and enter valid details in the remaining fields. | User is already logged in and is on Update odometer pop up page | 1) Leave Chessis No fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Agreement No-REC6620 Current Odometer-REC6620 | As expected |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC7 | 13389 | 2020-12-31 | To verify if the User is able to Update odometer by leaving Chassis No field blank and enter valid details in the remaining fields. | User is already logged in and is on Update odometer pop up page | 1) Leave Current Odometer fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Agreement number-REC6620 | As expected |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC8 | 13389 | 2021-01-01 | To verify if the User is able to Update Current odometer by entering the Reading less than REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Less than REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Agreement number-REC6620 Current odometer -5000 | Validating message appear Current odometer reading should be greater than Rec end km |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Current odometer reading should be greater than Rec end km" |  |  | Pass
UpdateOdometer_TC9 | 13389 | 2021-01-02 | To verify if the User is able to Update Current odometer by entering the Reading Equal to the REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Equal to the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Agreement number-REC6620 Current odometer -10000 | Validating message appear Current odometer reading should be greater than Rec end km |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Current odometer reading should be greater than Rec end km" |  |  | Pass
UpdateOdometer_TC10 | 13389 | 2021-01-03 | To verify if the user is able to Update Current Odometer by Enetring the data greater than REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Greater than the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Agreement number-REC6620 Current odometer -99999999999999 | Incorrect data is updating |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Less than 80,000 kms" |  |  | Fail
UpdateOdometer_TC11 | 13389 | 2021-01-04 | To verify if the user is able to expire the policy forcefully by updating the odometer reading | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Greater than the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC006KC022587 Agreement number-REC6627 Current odometer -41000(More than Rec end km) | Odometer is updated successfully |  | User should be able to expire the policy forcefully by entering the odometer reading more than the REC End KM

## Summary
Renault EW
Lead Dev: Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail
Re-purchase Functionality | 40 | 40 | 37 | 3
Update Odometer | 10 | 10 | 9 | 1
Total | 50 | 50 | 46 | 4

## BugReport
Bug Report
Project :- |  | Renault EW
Created_By :- |  | Sakshi Tiwari
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments
28.12.2020 | 13389 | BUG_ID1 | UpdateOdometer_TC10 | In Current odometer field accepting the unlimited data | Dealer is logged into the system | 1) Enter Current Odometer fields Greater than the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC004KC021549 Agreement number-REC6620 Current odometer -99999999999999 |  |  |  | New | Apurwa
28.12.2020 | 13389 | BUG_ID2 | Repurchage_TC32 | Current odometer Image and Car Image accepting wrong file | Dealer is loggend into the sys | Selecting the policy number which already Expired | 1.REC Agreement Number- REC6613 2.Enter valid data in all the fields. |  |  |  | Fixed | Apurwa
28.12.2020 | 13389 | BUG_ID3 | Repurchage_TC34 | Data is not Updated from middleware | dealer is on Creating New Easy Care page | Selecting the same Vin number which already Expired | 1.Chassis No-MEERBC006KC022587 2.observing the data and match with the middleware |  |  |  | New | Apurwa
28.12.2020 | 13389 | BUG_ID4 | Repurchage_TC35 | Policy is not getting expired after Avail of services | Dealer is on Creating New Easy Care Claims | 1.Click on New Easy Care Claim 2.Click on Add Easy Care Claim 3.Select the RECC4792 4. Enter all the valid details and save | 1.Current PMS Visit-30k service 2.Job Card no.ROERJA21001111 3.Plan Name 373/REC-KWID AMT-P373-3Y-30K 4.Odometer Reading-60000 |  |  |  |  | Apurwa
28.12.2021 | 13389 | BUG_ID5 | Repurchage_TC25 | user is not able to enter number 9 in Current odometer reading field | User is already logged in and is on New Easy Care Agreement page. | 1.Enter Data in Cureenet ododmeter reading 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Current odometer reading-9 |  |  |  | New | Apurwa
28.12.2022 | 13389 | BUG_ID6 | Repurchage_TC40 | Document is not visible in the document details list | Dealer is on Creating New Easy Care Claims | 1)Click on + Renew Button 2)Enter vin number 3)Click on Validate button |  |  |  |  | New | Apurwa