## Summary
Volvo Eicher
Lead Dev: Vikash Jha/ Ranjeet
Module | No. of test Written | No. of test executed | Pass | On Hold | Fail
ClaimFieldNames | 14 | 13 | 13 | 1 | 0
Eicher Task GST Breakup | NA | NA | NA | NA | 4
Total | 14 | 13 | 13 | 1 | 4

## Bug_Report
Bug Report
Project :- |  | Volvo Eicher |  |  |  |  | Lead_Devp. :- |  | Vikash Jha
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10098
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-21 |  | Bug_ID_54 | Creating New Claim :- when switch from 1 mandatory field to another using TAB Validation appears in LOOP | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1Ra2H_lyv0Gw4Ap3oNGAdgnuMQreAIA8j | High | High | Old | Vikash Jha | need to discuss
2020-02-21 |  | Bug_ID_58 | Creating New Claim :- Endorsement No. and Document No. should be marked as Mandatory field. | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1ZghbrWXDuJuiYDzdBwN8-x5S0gfqsGET | High | High | Old | Vikash Jha
2020-02-21 |  | Bug_ID_60 | Edit Document :- Unable to edit Uploaded document in claim | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  | High | High | Old | Vikash Jha | on Hold & need to discuss
2020-02-25 |  | Bug_ID_61 | Creating New Claim :- Unable to search Agreement No. Manually | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | https://drive.google.com/open?id=1J_Edfi2KmVpFyfmvjSI_LkTHaKGp_4OJ | Low | High | Old | Vikash Jha
2020-02-25 |  | Bug_ID_62 | Creating New Claim :- Fields are not arranged Properly | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | https://drive.google.com/open?id=13dR1Tan5hcr2tcwBicjSxaz7WnWYgP6w | Low | Low | Old | Vikash Jha
2020-02-28 |  | Bug_ID_66 | Surveyor Name :- Should not be able to enter numeric data and special char. | Claim is generated | Login with manager and Edit claim |  |  | High | Low | New | Vikash Jha
2020-11-06 | Eicher Task GST Breakup | Bug_ID_67 | Add Part Information: Discount % is freezed due to which dealer is not able to add discount% in the provided field. | Dealer is logged in and created a claim | 1)Click on Add Part Information option EW details page. 2)Check the Discount % field. |  |  | High | High | New | Ranjeet
2020-11-06 | Eicher Task GST Breakup | Bug_ID_68 | Add Part Information:Fields "NDP + 10%.", Quantity,GST % should take values greater than "0" as currently dealer can add part information by entering 0 in the mentioned fields. | Dealer is logged in and created a claim | 1)Click on Add Part Information option EW details page. 2) Enter 0 in "NDP + 10%.", Quantity,GST %. 3)Click on Save button. |  |  | High | High | New | Ranjeet
2020-11-06 | Eicher Task GST Breakup | Bug_ID_69 | Add Labour Information: System shows validation message as soon as dealer enters first digit in Rate per hour field and the entered value gets remove. Validation Message: Please fill operation time. Note: Its a blocker issue as dealer cant add labour information. | Dealer is logged in and created a claim | 1) Click on add labour information. 2) Enter labour code, Sac Code. 3)Enter Rate paer Hour. |  | https://prnt.sc/sxvzod | High | High | New | Ranjeet
2020-11-06 | Eicher Task GST Breakup | Bug_ID_70 | Query by claim manager should get changed to Quaery by Claim Adjudicator |  |  |  | https://prnt.sc/syg20e https://prnt.sc/syg35w https://prnt.sc/syg3ox | High | High | New | Ranjeet
Bug_ID_71
Bug_ID_72
Bug_ID_73

## Closed_Bug
Bug Report
Project :- |  | Volvo Eicher |  |  |  |  | Lead_Devp. :- |  | Alok Srivastava
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10008
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-05 |  | Bug_ID_10 | When dealer submits a Request for ​S​urveyor ​A​ppointment​ by updating the claim form when its already under Pending with Surveyor status then the status gets changed to "Answered by Dealer" instead it should remain the same. [Status should be update in Answered by Dealer-Surveyor] [DONE] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_11 | Claim Manager: There is no validation for Surveyor contact number. User can enter invalid data in Surveyor contact number. (1234 as contact no.) |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_12 | Claim Manager: User is able to change the status to Payment made without entering payment details. |  |  |  |  | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-06 |  | Bug_ID_13 | New Part Information Claim: Description,Discount, Vat fields should be enable to edit/add data. |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-06 |  | Bug_ID_14 | New Part Information Claim: VAT should get change to GST (%). [Update From DB - DONE] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_15 | Claim should come in header with other main menu [add claim in menu from setting - DONE] | - | - |  | https://prnt.sc/qytajb | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_16 | highlighted fields should not be visible to dealers and this should come under Surveyor Information section [ setting from profile - DONE] |  |  |  | https://prnt.sc/qytt3r | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_17 | highlighted fields not required [DONE] [Field Inactive from setting] |  |  |  | https://prnt.sc/qytutz | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_18 | Use any of the one field from the highlighted |  |  |  | https://prnt.sc/qytvix | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-07 |  | Bug_ID_19 | Length of the field - Dealer Contact No should be equal to 10 and only numeric. Space and or any other character not allowed [Update Contact From Database] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_20 | Field "Description" should be editable |  |  |  | https://prnt.sc/qyutmb | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_21 | Field "Discount %" should be editable |  |  |  | https://prnt.sc/qyv3dm | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_22 | Vat to be removed |  |  |  | https://prnt.sc/qyv3ob | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_23 | filed to be added in part information 1> CGST% 2> SCGS% 3> IGST% 4> CGST Amount 5> SGCT Amount 6< IGST Amount |  |  |  |  | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-07 |  | Bug_ID_24 | Tota will be equal to {(price - discounted amonut) +GST} |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_25 | Creating New Claim: Agreement Number field should be "*" marked in order to represent it as a mandatory field. [CHNAGES-DONE] | User has a working system with an active internet connection. | 1) Login the portal with the correct login credentials. 2)Click on "All" dropdown. 3)Click on "Claim" option. 4)Click on "Add Claim" button. 5) Observe the Agreement Number (It is a mandatory field in order to add claim user needs to enter this) |  | https://prnt.sc/quxugo | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_26 | Creating New Claim: The priority for showing validation message should be from top to bottom. E.g: If user clicks on the Save button without entering any data in the mandatory fields then system first needs to show the validation message for Agreement Number. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave all the mandatory fields blank. 2)Click on the save button. |  |  | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_27 | Creating New Claim: User is able to submit the claim form by entering less than 7 digits Job Card Number. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1) Enter invalid data in Job Card Number (Less than 7 digits) 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  |  | Mid | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_28 | Creating New Claim: Validation message appearing for leaving the Agreement number field blank is wrong. It should be "Please Select Agreement Number First" instead of Please Select SalesOrder First [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave the Agreement number field blank. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quy5su | Low | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_30 | Creating New Claim: The validation message coming after Re-selecting the Aggregate Part List dropdown List is non informative it can be modified to : "Please select Aggregate Part List" instead of "Agreement in OEM warranty" [NO-NEED-TO-CHANGE DISCUSS] | User is on the Creating New Claim page. | 1)Re-Select Aggregate Part List dropdown to "Select Aggregate Part" |  | https://prnt.sc/quymbw | Low | Low | No Need to Change | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_31 | Creating New Claim: The validation message appearing for leaving the Aggregate Part List blank is wrong. It should be "Please select Aggregate Part List" instead of JobCard Date Should be less than or equal to warranty end date. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave theAggregate Part List field blank. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quyqft | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_32 | Claims Page: Date and time of creating a new claim is not correct. That is Its showing a lag of one day and 16 hours from the actual day and time of creation. [Update User Time-Zone in User Details] |  |  |  | https://prnt.sc/quyu4s | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_36 | Claim details page: In the agreement/policy warranty is spacified in EW Start EHS and EW End EHS but after raising the claim its showing in Ext. Warranty Start kms and Ext. Warranty End kms. Please refer to the screenshot for more details. [CHANGES DONE] |  |  |  | https://prnt.sc/quzsjj https://prnt.sc/quztlv | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_37 | Creating New Document: User is not able to save a new document page as the Title of the Jobcard is freezed/non editable which is a mandatory field. [NO NEED TO CHANGE] |  |  |  | https://prnt.sc/qv13o9 | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-05 |  | Bug_ID_38 | Creating Part Information Claim:If user adds qauntity first and then he enters the MRP then system does not counts MRP and shows NAN in price,Discount Amount and Total |  |  |  | https://prnt.sc/qxsevh https://prnt.sc/qxsgg4 | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_39 | Creating New Labour Information Claim: There shouls be a unit for Operation Time as hours or day. |  |  |  | https://prnt.sc/qxsi9v | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_40 | Creating New Labour Information Claim: If user adds Rate first and then he enters the Operation Time then system does not counts Price and shows NAN in price and Total |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_41 | Document Tracking Panel: User is able to submit the document tracking panel by entering future date in Document Courier Date. |  |  |  |  | Mid | Mid | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_42 | Document Tracking Panel: User is able to submit the document tracking panel by entering blank spaces in Document Courier Date. |  |  |  |  | Low | Low | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_43 | TVS Manager: Claim Update- if the claim status is approved then user should not be able to select/enter "Reason of Rejection" but currently this is happening. |  |  |  | https://prnt.sc/qxu2yq | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-05 |  | Bug_ID_44 | Creating New Part Information Claim: Quantity cannot be in decimal value. |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_45 | Creating New Part Information Claim: Calculation of Part information is getting wrongly computed that is if user enters a decimal value in MRP as 200 and quantity in decimal as 1.00 then it does not take decimal into consideration while caluclating and gives the total price as 20000 instead of 200 |  |  |  | https://prnt.sc/qxuz2l | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_46 | Creating New Labour Information Claim: Operation time should be a mandatory field as the Price is getting calculatd on the basis of it and also there should be a proper validation for the same. [DONE mandatory from setting] |  |  |  |  | Mid | Mid | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_48 | Creating New Miscellaneous Expenses: user is able to enter negative integers in the amount field and also if user enters any positive vaue in service tax then the total price compute sit wrongly by taking service tax value as negative even when the enteres value was positive. |  |  |  | https://prnt.sc/qxvcvg | High | High | Fixed | Vikash Jha | Fixed
2020-02-15 | TC_03/Vin-Validation | Bug_ID_49 | Two validation msg. appears | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@######12345 |  |  | Low | Fixed | Alok Srivastava | Fixed
2020-02-15 | TC_04/Vin-Validation | Bug_ID_50 | Once Chassis no. not avaliable msg. displayed field data should be reset | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@####12345 |  |  | Low | Fixed | Alok Srivastava | Fixed
2020-02-19 | TC_03/Vin-Validation | Bug_ID_51 | Two validation msg. appears | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@######12345 (Less than 17) |  |  | Low | Fixed | Alok Srivastava | Fixed
2020-02-19 | TC_04/Vin-Validation | Bug_ID_52 | Once Chassis no. not avaliable msg. displayed field data should be reset | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@####12345 (Less than 17) |  |  | Low | Fixed | Alok Srivastava | Fixed
2020-02-05 |  | Bug_ID_47 | Editing New Labour Information Claim:If user does not changes the rate and only changes the Operation Time then the price does not get updated. |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_34 | Creating New Claim: Validation message appearing for entering wrong EHS HRS-less than EW Start EHS (Engine hours) is wrong it should display "Engine hours should be between 6001 and 10000" instead of \ Agreement is in oem warranty [NEED TO DISCUSS] |  |  |  | https://prnt.sc/quz8eu | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_01 | Part Information Claim Details :- Page data reset on leaving MRP blank and Entering Quantity | User is on the Creating New Claim page. |  | Part Code :- asf Quantity :- 2 | https://drive.google.com/open?id=1McNDMvavbVYGuQ1SK3Yth9Z6ZHlFzwUS |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_02 | Creating New Labour Information Claim :- Page data reset on leaving Operation Time[In Minutes] blank and entering Rate. | User is on the Creating New Claim page. |  | Labour Code :- asd Rate :- 300 | https://drive.google.com/open?id=1df6Xi4taz4fhbDudEVqk9kcOjU9TPxpl |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_03 | Part Information Claim :- Rejection is showing (0 or 1) | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=13ZyRfd8pFie7x1RdCwm31Y9mXUYjB-Iv |  | High | Fixed | Vikash Jha | fixed
2020-02-13 |  | Bug_ID_04 | Unable to upload file name in PDF format of more than 2MB where max. upload size is 5MB (Uploaded Document is not Valid) msg. display | Creating New Document page |  |  | https://drive.google.com/open?id=1e94Y-vvHTBao5bDzoQPa1sAGX52qMqBY |  | High | Fixed | Vikash Jha | need to update in php ini upload_max_filesize
2020-02-13 |  | Bug_ID_05 | Unable to upload ODO Meter Reading Photo of more than 2MB where max. upload size is 5MB (Uploaded Document is not Valid) msg. display | Creating New Document page |  |  | https://drive.google.com/open?id=1eY-opjtTu6toq8yoO8WHIFDcfxrNlekP |  | High | Fixed | Vikash Jha | need to update in php ini upload_max_filesize
2020-02-13 |  | Bug_ID_06 | If unable to Upload document Title automatically disappear | Creating New Document page |  |  | https://drive.google.com/open?id=16yn6kYpGKY6RjqZG6iQv4MMIvmuj8402 |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_07 | search claim by Claim Time but it is searching Claim by Claim Date | Search Claim |  |  | https://drive.google.com/open?id=1KY96HuPX9iFKXKCmnkb6r-Jgi9v9IBvJ |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_08 | There is UI issue on claim view page | view claim |  |  | https://drive.google.com/open?id=1WSFxLqkat13G3EuLkTZSLx8iFEHjyXE_ |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-02-13 |  | Bug_ID_09 | There is UI issue on Status and Reason of Rejection | Edit claim on assurant account |  |  | https://drive.google.com/open?id=1so4ywIm2SKblEKfx4yvrX5UQTRaL74pP |  | Low | No Need to Change | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_29 | Creating New Claim: User is able to submit the claim form by entering Date of job card (29-01-2020) which does not lies between the Ext . Warranty Start Date(Ext . Warranty Start Date) and Ext. Warranty End Date(29-11-2023) [NEED TO DISCUSS] | User is on the Creating New Claim page. | 1) Enter invalid data in Date of Job Card. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quygby | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_33 | Creating New Claim: The details appearing after selecting an Aggregate Part should be non-editable/freezed but few of the fields are still editable like Warranty Admin Name,Dealer Email and Dealer Contact No. [NEED TO DISCUSS] | User is on the Creating New Claim page. |  |  | https://prnt.sc/quyzbe | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_35 | Creating New Claim: There should be a validation message for entering a Date of Job Card less than the Ext . Warranty Start Date as "Date of Job Card should not be less than Ext . Warranty Start Date" [NEED TO DISCUSS] | User is on the Creating New Claim page. | 1)Enter Date of Job Card less than Ext . Warranty Start Date. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quzbf4 | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-21 |  | Bug_ID_53 | Creating New Labour Info. Claim :- GST% is accepting value more than 100% | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1BoM_X5V7OsdBCqTB3xjSRn8NASPvjXol | High | High | Fixed | Vikash Jha | fixed
2020-02-21 |  | Bug_ID_55 | Creating New Miscellaneous Expence :- There is no unit of Service Tax | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1w6aAHdSkVtPSP49JmrnFDFj2O12PVC3V | High | High | Fixed | Vikash Jha | fixed
2020-02-21 |  | Bug_ID_56 | Creating New Miscellaneous Expence :- Service Tax is accepting value more than 100% | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1EsNyRtwJEKqov8GEDHIWaYZEDYtvNrPG | High | High | Fixed | Vikash Jha | fixed
2020-02-21 |  | Bug_ID_57 | Creating New Document :- On uploadin Document Invalid request msg. display | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1s6U1BR340D3ZugttcUKwqOt7jE_TENnA | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-21 |  | Bug_ID_59 | Creating New Claim :- When clicking on Update Part, Labour, Miscellaneous Rejection page gets refresh | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=1cCB7R5wCvZc2eShMbWRLCsoDho3F80-w | High | High | No Need to Change | Vikash Jha | No Need to Change
2020-02-25 |  | Bug_ID_63 | Edit Claim :- On Editing Claim when selecting Agreegate part list No Matches Found shows in drop down and previously entered part didn’t show anything | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim 3) Edit claim |  | https://drive.google.com/open?id=1qUjTSzO1bK5TzzDlTcp70ja0p0W3tUgu | High | High | Fixed | Vikash Jha
2020-02-25 |  | Bug_ID_64 | Creating New Claim :- Vehicle Reported date should be same as date of job card validation appears which is not true for each case. And instead of Vehicle Reported date it is showing failure date | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | https://drive.google.com/open?id=1UCWc1LAiDWWpQmA4ZzUicX6M7QDYEL2T | Low | Low | Fixed | Vikash Jha
2020-02-25 |  | Bug_ID_65 | Creating New Claim :- Without entering EHS HRS new calim is created and able to create new claim even if EW start date is a future date [Need to Discuss] | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | https://drive.google.com/open?id=1aKE4SP5TyR7FP0DHdM8fxRA3DDjNY81Q | Low | Low | Fixed | Vikash Jha

## ClaimFieldName
Project Name: Volvo_Eicher
Created By:- | Jitendra |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-03-26 |  | Review Date:- |  |  | Developed By :- | Alok Srivastava / Ranjeet
Version: - |  |  | Module:- | VECV claims portal field name to be changed |  | Power_ID :- | 10510
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_ClaimFieldName_01 | To verify if the Discount % field in part information field is freezed or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add Part Information button. 5) Check discount % field. | NA |  |  | Discount % field should be freezed/non editable. |  |  | Pass
TC_ClaimFieldName_02 | To verify if the MRP field is replaced with NDP +10 % in Part Information or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add Part Information button. 5) Check Rate field. | NA |  |  | MRP field should get changed to NDP +10 %. |  |  | Pass
TC_ClaimFieldName_03 | To verify if the GST% field in labour information is open or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add labour Information button. 5) Check GST% field. |  |  |  | GST% field should be open to edit. |  |  | Pass
TC_ClaimFieldName_04 | To verify if the HSN code field in Part Information have been added or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add Part Information button. 5) Check HSN code field. | NA |  |  | HSN code field should be added in part Information. |  |  | Pass
TC_ClaimFieldName_05 | To verify if the Rate field is replaced with Rate per Hour in Labour Information or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add labour Information button. 5) Check Rate field. | NA |  |  | Rate field should get changed to Rate per Hour. |  |  | Pass
TC_ClaimFieldName_06 | To verify if the SAC code field in labour Information have been added or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Add Claim button. 3) Create claim by entering valid data in all the mandatory fields. 4) Click on Add labour Information button. 5) Check SAC code field. | NA |  |  | SAC code field should be added in labour Information. |  |  | Pass
TC_ClaimFieldName_07 | To verify if the option to upload the documents is blocked/hidden in the dealer login after claim has approved status. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Claim having status as approved 3) try to uplaod the documents, | NA | System does not allow the dealer to upload the docs after approved status. |  | Sysetm should not allow dealer to upload documents. |  |  | Pass
TC_ClaimFieldName_08 | To verify if the option to upload the Invoice is blocked/hidden in the dealer login after incorrect Invoice is uploaded. | User is logged in | 1) Click on Claim menu Item. 2) Click on the Claim having status as approved 3) try to uplaod the documents, | NA |  |  | Sysetm should not allow dealer to upload documents. |  |  | On Hold
TC_ClaimFieldName_09 | To verify if the Discount % field in edit part information field is freezed or not . | User is logged in | 1) Click on Claim menu Item. 2) Click on the update Claim button. 3) Click on edit Part Information button. 5) Check discount % field. | NA |  |  | Discount % field should be freezed/non editable. |  |  | Pass
TC_ClaimFieldName_10 | To verify if the MRP field is replaced with NDP +10 % in edit Part Information or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the edit Claim button. 3) Click on edit Part Information button. 5) Check Rate field. | NA |  |  | MRP field should get changed to NDP +10 %. |  |  | Pass
TC_ClaimFieldName_11 | To verify if the GST% field in edit labour information is open or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the edit Claim button. 3)Click on edit labour Information button. 5) Check GST% field. |  |  |  | GST% field should be open to edit. |  |  | Pass
TC_ClaimFieldName_12 | To verify if the HSN code field in edit Part Information have been added or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the edit Claim button. 3)Click on edit Part Information button. 5) Check HSN code field. | NA |  |  | HSN code field should be added in part Information. |  |  | Pass
TC_ClaimFieldName_13 | To verify if the Rate field is replaced with Rate per Hour in edit Labour Information or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the edit Claim button. 3) Click on edit labour Information button. 5) Check Rate field. | NA |  |  | Rate field should get changed to Rate per Hour. |  |  | Pass
TC_ClaimFieldName_14 | To verify if the SAC code field in edit labour Information have been added or not. | User is logged in | 1) Click on Claim menu Item. 2) Click on the edit Claim button. 3) Click on edit labour Information button. 5) Check SAC code field. | NA |  |  | SAC code field should be added in labour Information. |  |  | Pass

## Claim
Project Name: Volvo_Eicher
Created By:- | Atyab Alam |  |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-03-02 |  |  | Review Date:- |  |  | Developed By :- | Vikash Jha
Version: - |  |  |  | Module:- | Issue_New_Eicher_Xtend
Test Case ID/Module | Power_ID :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01 | 10210 | To verify that Dealer is able to Login | Login Credential Provided | ID :- demo-dealer Password :- Welcome@12 |  |  |  | Dealer should be able to login and will be redirected to homepage
TC_02 | 10210 | To verify that Dealer is able to go to Claim Page | On Home Page | Click on Claim present on top left of the screen |  |  |  | Will be redirected to Claim Page
TC_03 | 10210 | To Verify that Dealer is able to Open Create new Claim Form | On Claim page | Click on Add Claim |  |  |  | Form to Add new Claim Will be Open
TC_04 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Leave all Mandatory Field Blank and click on Save |  |  | Pop-up notification will display that this field is mandatory will display
TC_05 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Leave Agreement No. blank and try to fill all remaining mandatory field |  |  | Please Select Agreement First validation will appear when entering Odometer Reading
TC_06 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Search Agreement No. manually e.g. :- VECV1166 | No Results Found msg. is displayed in the Pop-Up | https://drive.google.com/open?id=1J_Edfi2KmVpFyfmvjSI_LkTHaKGp_4OJ | Related agreement No. will be Displayed in the Drop-down | High | High | Fail
TC_07 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Search Agreement No. by opening list of Agreement |  |  | Will be able to open and select Agreement No.
TC_08 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Leave Aggregate to be claimed blank and enter Odometer Reading / EHS HRS |  |  | Please Select Aggregate to be claimed Validation will Appear
TC_09 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Leave EHS HRS blank and fill Job Card No |  |  | Please Fill ehs hrs first validation will appear
TC_10 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Enter 6 digit (Numeric) Job Card No |  |  | Job Card No. can only be of 7 digit. Validation will Appear
TC_11 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Enter 8 digit (Numeric) Job Card No |  |  | Unable to enter 8 digit Job card No
TC_12 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Enter 7 digit (Numeric) Job Card No |  |  | Will be able to enter 7 digit job card No.
TC_13 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Enter 6 digit (Alha-Numeric) Job Card No |  |  | Will accept only numeric data
TC_14 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Date of Job Card :- future Date |  |  | JobCard Date can not Accepts future date validation will Appear
TC_15 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Date of Job Card :- 3-days before present date | JobCard Date Should be less than 2 days before date validation Appear. |  | JobCard Date Should be equal to or 2 days before from Today's date validation will Appear | High | High | Fail
TC_16 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Date of Job Card :- Present date |  |  | Will accept todays date
TC_17 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Date of Job Card :- Two days before present date |  |  | Will accept Two days before date
TC_18 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Vehicle Reported Date :- future date from date of job card date | Failure Date Should be equal to or 2 days before from Jobcard date validation appears |  | Vehicle Reported Date Should be equal to or 2 days before from Jobcard date validation will Appear | High | High | Fail
TC_19 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Vehicle Reported Date :- 3-days before from date of job card date |  |  | Vehicle Reported Date Should be equal to or 2 days before from Jobcard date validation will Appear
TC_20 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Vehicle Reported Date :- Same as that of job card date |  |  | Will accept same date date as that of job card date
TC_21 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Select Vehicle Reported Date :- Two days before from date of job card date |  |  | Will accept Two days before date from date of job card
TC_22 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Leave Quotation # blank and fill all the remining mandatory field |  |  | This field is mandatory validation will appear
TC_23 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and leave Warranty Admin Name blank |  |  | New claim will be generated
TC_24 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and Dealer Email blank |  |  | New claim will be generated
TC_25 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and enter invalid Dealer Email e.g. :- akgupta4@VECV |  |  | Please enetr a valid email address popup will display
TC_26 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and enter valid Dealer Email e.g. :- akgupta4@VECV.in |  |  | New claim will be generated
TC_27 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and enter 6-digit Dealer Contact No. e.g. :- 123456 |  |  | Contact No. can only be of 10 digit. Validation will appear
TC_28 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and enter invalid Dealer Contact No. e.g. :- abcdef |  |  | user will not be able to enter numeric data
TC_29 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the mandatory field and leave Dealer Contact No. blank |  |  | Will be able to create new claim
TC_30 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the field and leave Diagnosis Done by Dealer blank |  |  | This field is mandatory validation will appear
TC_31 | 10210 | To Verify that dealer is able create new Claim | On Claim page | Click on Add Claim | Fill all the field and enter (alpha-numeric) data in Diagnosis Done by Dealer blank |  |  | New claim will be generated
TC_32 | 10210 | To verify that dealer is able to switch from 1 mandatory field to another using TAB | On Claim page | Click on Add Claim | Fill invalid data in one mandatory field and click on tab to go to another field | Validation appears in loop | https://drive.google.com/open?id=1Ra2H_lyv0Gw4Ap3oNGAdgnuMQreAIA8j | Will be able to switch from one field to another | High | High | Fail
TC_33 | 10210 | To verify that all Fields are arranged properly | On Claim page | Click on Add Claim |  | Fields are not arranged Properly | https://drive.google.com/open?id=13dR1Tan5hcr2tcwBicjSxaz7WnWYgP6w | All fields will be arranged properly | High | High | Fail
TC_34 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim |  |  |  | Creating New Part Information Claim page will open
TC_35 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Leave all Mandatory Field Blank and click on Save |  |  | This field is mandatory validation will appear on all mandatory field
TC_36 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Leave part code blank and fill all the remaining field. |  |  | This field is required validation will appear on part code
TC_37 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Leave MRP blank and fill all the remaining field. | Please fill MRP validation appears when entering quantity |  | Please enter MRP first validation appears when entering quantity | High | High | Fail
TC_38 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter negative value in MRP |  |  | User will not be able to enter neagtive price
TC_39 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter fraction value in MRP |  |  | User will be able to enter price in fraction value
TC_40 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter +ve integer value in MRP |  |  | User will be able to enter price in +ve integer value
TC_41 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter alphabet and special character in MRP |  |  | User will not be able to enter alphabet and special character in MRP
TC_42 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Leave quantity blank and Fill all the remaining mandatory field |  |  | This field is required validation will appear on Quantity
TC_43 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter alphabet and special character in quantity |  |  | User will not be able to enter alphabet and special character in quantity
TC_44 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter fraction value in Quantity |  |  | User will not be able to enter fraction value in quantity
TC_45 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter negative value in Quantity |  |  | User will not be able to enter negative value in Quantity
TC_46 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Enter +ve integer value in Quantity |  |  | User will be able to enter +ve integer value in Quantity
TC_47 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter -ve discount %age |  |  | User will unable to enter -ve discount %age.
TC_48 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter fraction discount %age |  |  | User will be able to enter fractional discount %age
TC_49 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter +ve integer discount %age |  |  | User will be able to enter +ve integer discount %age
TC_50 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter -ve integer GST %age |  |  | User Will not be able to enter -ve integer GST %age
TC_51 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter alphabet and special character GST %age |  |  | User will not be able to enter alphabet and special character
TC_52 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter Fraction value in GST %age |  |  | User will be able to enter Fraction value in GST %age
TC_53 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and enter +ve integer value in GST %age |  |  | User will be able to enter +ve integer value in GST %age
TC_54 | 10210 | To Verify that dealer is able Add Part Information Claim | Claim is generated | Click on Add Part Information Claim | Fill all the mandatory field and check Boundary value of GST %age | GST %age = 100 validation appears "GST can not be grater then 100" | https://drive.google.com/open?id=1VAF1WbfkWL8wEEwPZlUuDzmo2cojB088 | GST %age will accept all the value between "0 to 100" | High | High | Fail
TC_55 | 10210 | To Verify that dealer is able Edit Part Information Claim | Claim is generated | Click on Edit Part Information Claim |  |  |  | User will be able to edit Claim part information
TC_56 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim |  |  |  | Creating New Labour Information Claim page will open
TC_57 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Leave all Mandatory Field Blank and click on Save |  |  | This field is mandatory validation will appear on all mandatory field
TC_58 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Leave Labour Code blank and fill all the remaining field |  |  | This field is mandatory validation msg. will appear on Labour Code
TC_59 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Leave Operation Time[In Minutes] blank and fill all the remaining field |  |  | This field is mandatory validation msg. will appear on Operation Time[In Minutes]
TC_60 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter -ve integer value in Operation Time[In Minutes] |  |  | User will not be able to enter -ve integer in Operation Time[In Minutes]
TC_61 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter alphabet and special character value in Operation Time[In Minutes] |  |  | User will not be able to enter alphabet and special character value in Operation Time[In Minutes]
TC_62 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter Fraction value in Operation Time[In Minutes] |  |  | User will not be able to enter Fraction in Operation Time[In Minutes]
TC_63 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter +ve integer value in Operation Time[In Minutes] |  |  | User will be able to enter +ve integer in Operation Time[In Minutes]
TC_64 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Leave Rate blank and fill all the remaining field |  |  | This field is mandatory validation msg. will appear on Rate
TC_65 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter -ve integer value in Rate |  |  | User will not be able to enter -ve integer in Rate
TC_66 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter alphabet and special character value in Rate |  |  | User will not be able to enter alphabet and special character value in Rate
TC_67 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter Fraction value in Rate |  |  | User will be able to enter Fraction in Rate
TC_68 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Enter +ve integer value in Rate |  |  | User will be able to enter +ve integer in Rate
TC_69 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Fill all the mandatory field and enter -ve integer GST %age |  |  | User Will not be able to enter -ve integer GST %age
TC_70 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Fill all the mandatory field and enter alphabet and special character in GST %age |  |  | User will not be able to enter alphabet and special character
TC_71 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Fill all the mandatory field and enter Fraction value in GST %age |  |  | User will be able to enter Fraction value in GST %age
TC_72 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Fill all the mandatory field and enter +ve integer value in GST %age |  |  | User will be able to enter +ve integer value in GST %age
TC_73 | 10210 | To Verify that dealer is able Add Labour Information Claim | Claim is generated | Click on Add Labour Information Claim | Fill all the mandatory field and check Boundary value of GST %age | GST %age = 100 validation appears "GST can not be grater then 100" | https://drive.google.com/open?id=1_VVNxS6h-G0mihZi7c9GVoW48YAqDiw7 | GST %age will accept all the value between "0 to 100" | High | High | Fail
TC_74 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses |  |  |  | Creating New Miscellaneous Expenses page will open
TC_75 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter -ve Integer in Amount |  |  | Will not accept -ve Integer
TC_76 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter alphabet and special character in Amount |  |  | Will not accept alphabet and special character in Amount
TC_77 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter Fraction value in Amount |  |  | Will accept Fraction in Amount
TC_78 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter +ve integer value in Amount |  |  | Will accept +ve integer value in Amount
TC_79 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter -ve Integer in Service Tax %age |  |  | Will not accept -ve Integer in Service Tax %age
TC_80 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter alphabet and special character in Service Tax %age |  |  | Will not accept alphabet and special character in Service Tax %age
TC_81 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter Fraction value in Service Tax %age |  |  | Will accept Fraction value in Service Tax %age
TC_82 | 10210 | To Verify that dealer is able Add Miscellaneous Expenses | Claim is generated | Click on Add Miscellaneous Expenses | Enter +ve integer value in Service Tax %age |  |  | Will accept +ve integer value in Service Tax %age
TC_83 | 10210 | To Verify that dealer is able Edit Miscellaneous Expenses | Claim is generated | Click on Edit Miscellaneous Expenses |  |  |  | User will be able to Edit Miscellaneous Expenses
TC_84 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document |  |  |  | Creating New Document page will open
TC_85 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document | Do not choose any document and click on Upload |  |  | This field is Mandatory msg. will display on all mandatory field
TC_86 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document | Leave ODO Meter Reading Photo blank and fill all the remaining field |  |  | This field is Mandatory msg. will display on ODO Meter Reading Photo
TC_87 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document | Leave Vehicle History blank and fill all the remaining field |  |  | This field is Mandatory msg. will display on Vehicle History
TC_88 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document | Leave Photo/Video Of Failed Component blank and fill all the remaining field |  |  | This field is Mandatory msg. will display on Photo/Video Of Failed Component
TC_89 | 10210 | To Verify that dealer is able Add Document | Claim is generated | Click on Add Document | Leave File Name blank and fill all the remaining field |  |  | This field is Mandatory msg. will display on File Name
TC_90 | 10210 | To Verify that dealer is able Edit Document | Claim is generated | Click on Edit Document |  | Unable to edit Uploaded document | https://drive.google.com/open?id=1Ra2H_lyv0Gw4Ap3oNGAdgnuMQreAIA8j | Should be able to edit Uploaded document | High | High | Fail
TC_91 | 10210 | To Verify that dealer is able to Edit Claim | Claim is generated | Click on Edit Claim |  |  |  | Dealer should be able to Edit Claim
TC_92 | 10210 | To verify that Manager is able to Login | Login Credential Provided | ID :- demo-tvs Password :- Welcome@12 |  |  |  | Manager should be able to login and will be redirected to homepage
TC_93 | 10210 | To Verify that Manager is able go to claim page | Claim is generated | Click on the claim present on the top right of the screen |  |  |  | Will be redirected to Claim Page
TC_94 | 10210 | To Verify that Manager is able to open newly generated Claim | Claim is generated | 1) Search Claim be claim No. 2) Click on the result that appear on the screen |  |  |  | Will be able to open desired Claim and validation will appear that Endorsement No and Document No can not be empty.
TC_95 | 10210 | To Verify that Manager is able Edit Claim | Claim is generated | Click on Edit option present on the Top of the Screen |  |  |  | Edit Claim Form will open
TC_96 | 10210 | To verify that Manager is able to edit EHS HRS | Claim is generated | Enter EHS less than EW Start EHS |  |  |  | The selected aggregate is still under Standard Warranty period validation will appear
TC_97 | 10210 | To verify that Manager is able to edit EHS HRS | Claim is generated | Enter EHS greater than EW End EHS |  |  |  | The selected aggregate is not under Extended Warranty period validation will appear
TC_98 | 10210 | To verify that Manager is able to edit EHS HRS | Claim is generated | Enter EHS that comes under EW Start EHS and EW End EHS |  |  |  | Will accept EW EHS
TC_99 | 10210 | To verify that manager is able to Edit Job Card No. | Claim is generated | Enetr alphabet and special character in Job Card No |  |  |  | Will not accept alphabet and special character
TC_100 | 10210 | To verify that manager is able to Edit Job Card No. | Claim is generated | Enter 6 digit Job Card No. |  |  |  | Validation will appear Job Card No. can only be of 7 digit.
TC_101 | 10210 | To verify that manager is able to Edit Job Card No. | Claim is generated | Enter 8 digit Job Card No. |  |  |  | Validation will appear Job Card No. can only be of 7 digit.
TC_102 | 10210 | To verify that manager is able to Edit Job Card No. | Claim is generated | Enter 7 digit Job Card No. |  |  |  | Will accept Job Card No.
TC_103 | 10210 | To Verify that Manager is able to edit Date of Job Card | Claim is generated | Change Date of Job Card | Date of Job Card :- 28-02-2020 |  |  | JobCard Date Should be equal to or 2 days before from Today date validation will appear
TC_104 | 10210 | To Verify that Manager is able to edit Date of Job Card | Claim is generated | Enter future Date of Job Card | Date of Job Card :- 03-03-2020 |  |  | JobCard Date can not Accepts future date validation will appear
TC_105 | 10210 | To Verify that Manager is able to edit Date of Job Card | Claim is generated | Enter Date of Job Card in boundary limit |  |  |  | Should accept Date of Job Card in boundary limit
TC_106 | 10210 | To verify that manager is able to edit Vehicle Reported Date | Claim is generated | Change Vehicle Reported Date | Vehicle Reported Date :- 28-02-2020 |  |  | Failure Date Should be equal to or 2 days before from Jobcard date validation will appear
TC_107 | 10210 | To verify that manager is able to edit Vehicle Reported Date | Claim is generated | Enter future Vehicle Reported Date than Date of job card | Vehicle Reported Date :- 03-03-2020 |  |  | Failure Date Should be equal to or 2 days before from Jobcard date validation will appear
TC_108 | 10210 | To verify that manager is able to edit Vehicle Reported Date | Claim is generated | Enter Vehicle Reported Date in boundary limit |  |  |  | Should accept Vehicle Reported Date in boundary limit
TC_109 | 10210 | To verify that manager is able to edit Quotation | Claim is generated | Enter alpha-numeric data. |  |  |  | Should be able to edit Quotation.
TC_110 | 10210 | To verify that manager is able to Edit Warranty Admin Name | Claim is generated | Enter alpha-numeric data. |  |  |  | Should be able to edit Warranty Admin Name
TC_111 | 10210 | To verify that manager is able to Edit Dealer Email | Claim is generated | Enter Invalid Email | sushilgos2008@gmail |  |  | Please enter a valid email address validation will appear
TC_112 | 10210 | To verify that manager is able to Edit Dealer Email | Claim is generated | Enter alpha-numeric data. | qwertyu@123456 |  |  | Please enter a valid email address validation will appear
TC_113 | 10210 | To verify that manager is able to Edit Dealer Email | Claim is generated | Enter valid Email | sushilgos2008@gmail.com |  |  | Will accept Entered Email ID
TC_114 | 10210 | To verify that manager is able to edit Dealer Contact No | Claim is generated | Enter Alphabet and Special char. | wert!@#$% |  |  | Will not be able to Enter Alphabet and Special char.
TC_115 | 10210 | To verify that manager is able to edit Dealer Contact No | Claim is generated | Enter 9-digit Dealer Contact No | 23456788 |  |  | Contact No. can only be of 10 digit validation will appear
TC_116 | 10210 | To verify that manager is able to edit Dealer Contact No | Claim is generated | Enter 10-digit Dealer Contact No | 234567880 |  |  | Will accept Dealer Contact No
TC_117 | 10210 | To verify that manager is able to edit Diagnosis Done by Dealer | Claim is generated | Enter Alpha-numeric data and special char. | 234qwer!@#$ |  |  | Will be able to edit Diagnosis Done by Dealer
TC_118 | 10210 | To verify that manager is able to enter Endorsement No. | Claim is generated | Enter alpha-numeric data and special char. |  |  |  | Will be able to Enter Endorsement No.
TC_119 | 10210 | To verify that manager is able to enter Document No. | Claim is generated | Enter alpha-numeric data and special char. |  |  |  | Will be able to Enter Document No.
TC_120 | 10210 | To verify that manager is able to enter Claim Manager Name | Claim is generated | Click on Claim Manager Name | Bhola Babu |  |  | Should be able to enter Claim Manager Name
TC_121 | 10210 | To verify that manager is able to enter Surveyor Name | Claim is generated | Enter numeric data and special char. |  | Should be able to enter Surveyor Name |  | Should not be able to enter Surveyor Name | High | Low | Fail
TC_122 | 10210 | To verify that manager is able to enter Surveyor Name | Claim is generated | Enter Alphabet | Bhola shola |  |  | Should be able to enter Surveyor Name
TC_123 | 10210 | To verify that manager is able to enter Surveyor Primary Email | Claim is generated | Enter Invalid Email | wert |  |  | Please enter a valid email address validation will appear
TC_124 | 10210 | To verify that manager is able to enter Surveyor Primary Email | Claim is generated | Enter alpha-numeric data and special char. | asdf1234!@#$ |  |  | Please enter a valid email address validation will appear
TC_125 | 10210 | To verify that manager is able to enter Surveyor Primary Email | Claim is generated | Enter Valid Email | qwerty@asdf.zxc |  |  | Will be able to enter Email
TC_126 | 10210 | To verify that manager is able to enter Surveyor Contact No. | Claim is generated | Enter 9-digit Surveyor Contact No | 987654321 |  |  | Contact No. can only be of 10 digit validation will appear
TC_127 | 10210 | To verify that manager is able to enter Surveyor Contact No. | Claim is generated | Enter 11-digit Surveyor Contact No | 98765432123 |  |  | Unable to Enter 11-digit contact No.
TC_128 | 10210 | To verify that manager is able to enter Surveyor Contact No. | Claim is generated | Enter 10-digit Surveyor Contact No | 9876543212 |  |  | Will be able to enter 10-digit Surveyor Contact No
TC_129 | 10210 | To verify that manager is able to change status of claim | Claim is generated | Click on status | Status :- Pre Approval Document Pending |  |  | Status will be changed to Pre Approval Document Pending
TC_130 | 10210 | To verify that manager is able to change status of claim | Claim is generated | Click on status | Status :- Pending with Surveyor |  |  | Status will be changed to Pending with Surveyor
TC_131 | 10210 | To verify that dealer is able to Add Comment. | Claim is generated | 1) Open Claim 2) Click on Comment present on left side of the screen | Comment :- qwerty |  |  | Will be able to add Comment
TC_132 | 10210 | To verify that on adding comment Status will change to Answered by Dealer-Surveyor | Claim is generated | Refresh the page |  |  |  | Status will change to Answered by Dealer-Surveyor
TC_133 | 10210 | To verify that manager is able to change status of claim | Claim is generated | Click on status | Status :- Rejected |  |  | Status of claim will be change to Rejected
TC_134 | 10210 | To verify that manager is able to change status of claim | Claim is generated | Click on status | Status :- Approved |  |  | Status of claim will be change to Approved
TC_135 | 10210 | To verify that dealer is able to upload Final Tax Invoice when status of claim is Approved | Claim is generated | 1) Login with dealer acount 2) Open claim 3) Click on Choose file Final Tax Invoice | Select Invoice and click on Upload |  |  | Selected Invoice will be Uploaded
TC_136 | 10210 | To verify that dealer is able to Download Uploaded Final Tax Invoice | Claim is generated | Click on Download Final Tax invoice |  |  |  | Final Tax invoice will be downloaded
TC_137 | 10210 | To verify that Mnanger is able to Download Uploaded Final Tax Invoice | Claim is generated | Click on Download Final Tax invoice |  |  |  | Final Tax invoice will be downloaded
TC_138 | 10210 | To verify that Mnanger is able to Remove Final Tax invoice | Claim is generated | Click on Remove Final Tax invoice |  |  |  | Final Tax invoice will be Removed
TC_139 | 10210 | To verify that manager is able to Upload Final Tax invoice | Claim is generated | 1) Login with Manager acount 2) Open claim 3) Click on Choose file Final Tax Invoice | Select Invoice and click on Upload |  |  | Selected Invoice will be Uploaded
TC_140 | 10210 | To verify that manager is able to change EW claim invoice verified | Claim is generated | 1) Login with Manager acount 2) Open claim 3) Click on Choose file EW claim invoice verified | EW claim invoice verified :- Yes |  |  | EW claim invoice verified will be changed to yes
TC_141 | 10210 | To verify that manager is able to change EW claim invoice verified | Claim is generated | 1) Login with Manager acount 2) Open claim 3) Click on Choose file EW claim invoice verified | EW claim invoice verified :- Verification pending |  |  | EW claim invoice verified will be changed to Verification pending
TC_142 | 10210 | To verify that manager is able to change EW claim invoice verified | Claim is generated | 1) Login with Manager acount 2) Open claim 3) Click on Choose file EW claim invoice verified | EW claim invoice verified :- Incorrect invoice uploaded |  |  | EW claim invoice verified will be changed to Incorrect invoice uploaded

## Vin-Validation
Project Name: Volvo_Eicher
Created By:- | Atyab Alam |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-14 |  | Review Date:- |  |  | Developed By :- | Alok Srivastava
Version: - |  |  | Module:- | Issue_New_Eicher_Xtend |  | Power_ID :- | 10026
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/Vin-Validation | To verify that Dealer is able to Login to Claim management Portal | Login Credential Provided | ID :- kiran-bikaner Password :- Welcome@123 |  |  |  | Dealer should be able to login and will be redirected to homepage
TC_02/Vin-Validation | To verify that Dealer is able to open Issue New Eicher Xtend | Login Credential Provided | Click on Issue New Eicher Xtend |  |  |  | Issue New Eicher Xtend page will open
TC_03/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Enter Space in Vehicle Chessis No. | Two validation msg. appears |  | Vehicle Chassis No. can only be of 17 digit. Msg. will be displayed |  | High | Fixed
TC_04/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@######12345 | Once Chassis no. not avaliable msg. displayed fiesld data should be reset |  | Chassis no. not avaliable msg. should be displayed |  | Low | Fixed
TC_05/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- 01A8A369B45QWERTY |  |  | Chassis no. not avaliable msg. should be displayed
TC_06/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- ABCD8KGH7JH123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_07/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- CC090QWE5GH456258 |  |  | Chassis no. not avaliable msg. should be displayed
TC_08/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- VV6DF1AC0GH789852 |  |  | Chassis no. not avaliable msg. should be displayed
TC_09/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- BH1J5ABCDEF123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_10/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- GF0D5FFF544123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_11/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- BB0QWERT9YUABC123 |  |  | Chassis no. not avaliable msg. should be displayed
TC_12/Vin-Validation | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- GH0A0SDE8GH458965 |  |  | Chassis no. not avaliable msg. should be displayed

## Sheet1
Add