## Summary
Mercedes-Benz
Lead Dev: Vikash Jha/ Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail | Deferred
Claim | 82 | 82 | 78 | 0 | 4
CertificateRequestReport | 12 | 12*3=36(For admin,Assurant,Dealer) | 8 | 0 | 1
CertificateRequestReport_Client_Feedback | 6 | 6 | 6 | 0 | 0
Dropdownlist in Part Info. Client Uat | 2 | 2 | 2 | 0 | 0
Time_Auto_ClientUAT | 11 | 11 | 11 | 0 | 0
Certificate Request -Comprehensive-ETG | 5 | 5 | 4 | 0 | 1
Certificate Request -Comprehensive-ETG (Client UAT) | 5 | 5 | 4 | 0 | 1
Total | 123 | 137 | 113 | 0 | 7

## Bug_Report
Bug Report
Project :- |  | Mecedes Benz |  |  |  |  | Lead_Devp. :- |  | Vikash Jha/ Ranjeet
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :-
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
10350 | TC_68/Claim | 31 | User is able to save the claim form by entering invalid data in Service Request Date and also there is no validation message appears for the same. | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Service Request Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. | Service Request Date: 06-02-2013 |  | High | High | Deferred | Ranjeet | on hold
10350 | TC_17/Claim | 51 | Labour Information page: There is an alignment issue as the menu headers are getting mis- aligned from its place. Please refer tp the screenshot for more details. | User is logged in as a dealer and is on Claim page. | 1)Click on Add Labour Information Claim |  |  | High | High | Deferred | Ranjeet | on hold
10350 | TC_41/Claim | 52 | Query by TVS Claim is appearing in the dropdowns to filter the claims. | User is logged in as a dealer and is on Claim page. | 1) Click on Filter 2) Click on Query by Assurant |  |  | High | High | Fixed | Ranjeet | Done
10350 | TC_52/Claim | 53 | Incomplete validation message appears for entering invalid surveyor contact number. It should be Surveyor Contact No. should be of 10 digits only. | User is logged in as a dealer and is on Claim page. | 1)Enter 8 digit in surveyor contact number. |  |  | Low | Low | Fixed | Ranjeet | Done
10350 | TC_52/Claim | 54 | Claim Manager: Status dropdown has an option as " Query By TVS" It should be " Quary By Assurant". | User is logged in as a Claim Manager and is on Claim page. | 1) Click on Claim number to be edit. 2)Click on the Status Dropdown. |  |  | High | High | Fixed | Ranjeet | Done
10350 | TC_69/Claim | 32 | User is able to save the claim form by entering invalid data in Work Order Date and also there is no validation message appears for the same. | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Work Order Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. | Work Order Date: 18-07-2014 |  | High | High | Deferred | Ranjeet | on hold
10350 | TC_52/Claim | 55 | Once the status of the claim changes to Approved/Rejected then it should not get change if dealer updates the comment. Currently on posting any comment the status of the claim gets changed to " Answer By Dealer." | User is logged in as a Claim Manager and is on Claim page. (Status of the clai is either Approved/Rejected) | 1) Post a comment by going to the Comment section. |  |  | High | High | Fixed | Ranjeet | Done
10350 | TC_69/Claim | 56 | User is able to save the claim form by entering invalid data in Work Order Date and also there is no validation message appears for the same.(Date is invalid alert) | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Work Order Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. |  |  | High | High | Fixed | Ranjeet | Done
10350 | TC_69/Claim | 57 | ​​Request for ​S​urveyor ​A​ppointment​ ​Date & Request for ​S​urveyor ​A​ppointment​ Time are not aligned. | User is logged in as a Claim Manager and is on Claim page. | 1) Open any claim. 2)View both ​​Request for ​S​urveyor ​A​ppointment​ ​Date & Request for ​S​urveyor ​A​ppointment​ Time fields. |  |  | High | High | Fixed | Ranjeet | No need to change
10457 | TC_CertificationRequest _05 | 58 | User is able to download the report by entering invalid data in start and also there is no validation message for the same. | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the start date field and enter valid data in the end date. 2)Click on Generate Now button. | Start Date: ijugkjghgh End Date: kjbhkhb |  | High | Mid | Fixed-23-03-2020 | Ranjeet | Done | 10476 | Fixed-23-03-2020
10457 | TC_CertificationRequest _06 | 59 | User is able to download the report by entering invalid data in end date and also there is no validation message for the same. | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the end date field and enter valid data in the start date. 2)Click on Generate Now button. | Start Date: kjhjkhk End Date: kjbhghghghghkg |  | High | Mid | Fixed-23-03-2020 | Ranjeet | Done | 10476 | Fixed-23-03-2020
10457 | TC_CertificationRequest _08 | 60 | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  |  | Mid | Mid | Fixed- As per the format given by the client. | Ranjeet | No need to change. Name is acc. to client format | 10476 | Fixed- As per the format given by the client.
10457 | TC_CertificationRequest _12 | 61 | There is a spelling mistake in the Certificate Request field -Odometer Reading During Certification(Final Xentry | User is logged in as Dealer. | 1)Click on Certificate Request menu item. 2)Click on the certificate request to be open, |  |  | High | Mid | Deferred | Ranjeet | Need to check with client | 10476 | Deferred
10581 | TC_Comprehensive-ETG_02 | 62 | On viewing the added certificate request , "ETG(Engine Transmission Gear Box)" field shows empty data.( when "Y" was selected in the Comprehensive field) | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "Y" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin : WDD2120036L054215 | Please check the attachment doc. | High | High | New | Apurwa | Issue solved | 10601 | Pass
10581 | TC_Comprehensive-ETG_03 | 63 | On viewing the added certificate request , "ETG(Engine Transmission Gear Box)" field shows empty data. (when "N" was selected in the Comprehensive field) | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "N" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin :WDD2050026L011379 | Please check the attachment doc. | High | High | New | Apurwa | Issue solved | 10601 | Pass
10581 | TC_Comprehensive-ETG_04 | 64 | ETG(Engine Transmission Gear Box) field shows "Select an option" on Editing Certification Request page instead of showing N or Y based on the previously selected Comprehensive field. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check ETG(Engine Transmission Gear Box) field. | MBCAR99 | Please check the attachment doc. | High | High | New | Apurwa | Issue solved | 10601 | Pass
10581 | TC_Comprehensive-ETG_05 | 65 | Certificate Request Number is missing from the title of the page. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check Title of the page. | MBCAR99 | Please check the attachment doc. | High | High | New | Apurwa | Not Implemented | 10601 | Not Implemented
[10 empty] | New | Ranjeet

## Closed_Bug_Report
Bug Report
Project :- |  | Mecedes Benz |  |  |  |  | Lead_Devp. :- |  | Vikash Jha/ Ranjeet
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10136
Date | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-19 | TC_03/Claim | 1 | There is allingment Issue in Static Button | Login cridential provided |  |  |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_05/Claim | 2 | There is allingment Issue in new Claim Form | Login cridential provided | Click on Add Claim |  |  |  | Low | Fixed | Ranjeet | No need to change
2020-02-19 | TC_06/Claim | 3 | New Claim :-Two validation Msg. Appear and work order validation appears first which is not serial wise | Login cridential provided | Leave all field blank and click on submit |  |  |  | Low | Fixed | Ranjeet | No need to change
2020-02-19 | TC_07/Claim | 4 | Service Request length is less than 16 char and validation of Work Order Length length is less than 16 char. Is displayed. | Login cridential provided | Fill data and check validation | Service Request :- 1234QW Work Order :- Service Request Date :- Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_08/Claim | 5 | After submitting Wrong Information Creating New Claim page data Unable to reset Data. | Login cridential provided | Fill data and check validation |  |  |  | Low | Fixed | Ranjeet | No need to change
2020-02-19 | TC_09/Claim | 6 | New Claim :-Validation msg. is not serial wise | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | High | Fixed | Ranjeet | Done
2020-02-19 | TC_10/Claim | 7 | Validation msg. should be Please select Certificate No. instead of salesorder | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_11/Claim | 8 | Validation :-Odometer reading should be in between warranty reading | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_14/Claim | 9 | Add part information :- NAN is showing in Total Field. Field should be blank Also Quantity is accepting decimal value | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.2 MRP :- Part Location :- |  |  | High | Fixed | Ranjeet | Done
2020-02-19 | TC_15/Claim | 10 | Add part information claim :- There is calculation mistake (Sugg. :- There should be GST on Total price of Part) | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.1 MRP :- 100 Total :- 110.00000000000001 Part Location :- |  |  | High | Fixed | Ranjeet | No need to change
2020-02-19 | TC_22/Claim | 11 | Unable to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component of 5MB | Login cridential provided | Click on Add Document |  |  |  | Low | Fixed | Ranjeet | Server Issue max_file_upload limit should be increase
2020-02-19 | TC_24/Claim | 12 | Warranty Manager Name is accepting special character and numeric data | Login cridential provided | Click on Add Claim |  |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_33/Claim | 13 | Instead of created time it is searching with created date | Login cridential provided | Created Time |  |  |  | Low | Fixed | Ranjeet | No need to change
2020-02-19 | TC_52/Claim | 15 | accepting Surveyor Contact No. less than 10 digit | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Contact No. :- 222 |  |  | High | Fixed | Ranjeet | Done
2020-02-19 | TC_55/Claim | 16 | There is no option of Entering Claim Manager Name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty |  |  | High | Fixed | Ranjeet | we are using claim manager detail as claim manager name
2020-02-19 | TC_56/Claim | 17 | First Action Date and First Action Time automatically gets captured on adding Claim manager Details instead of Name | Login cridential provided |  |  |  |  | High | Fixed | Ranjeet | we are using claim manager detail as claim manager name
2020-02-19 | TC_63/Claim | 19 | Accepting special character and numeric data in surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- @##$123 |  |  | Low | Fixed | Ranjeet | Done
2020-02-19 | TC_62/Claim | 18 | Total record found in the report will be displayed on screen | Login cridential provided | 1) Login with manager ID 2) Open Report 3) Click on Claim Report | Start Date :- 2020-02-15 End Date :- 2020-02-19 |  |  | High | Fixed | Ranjeet | No need to change | Sugg. :- If possible try to fix this | 2020-02-24
2020-02-24 |  | 20 | Validation :- Instead of Warranty manager contact No. It is showing Dealer Contact No. Length is less than 10 Char. | Login cridential provided | Click on Add Claim |  |  |  | Low | Fixed | Ranjeet | Done | Fixed
2020-02-24 |  | 21 | New Claim :- Service request date and work order date is accepting Invalid Data | Login cridential provided | Click on Add Claim |  |  |  | High | Duplicate | Ranjeet | Hold | Not Fixed
2020-02-24 |  | 22 | New Claim :- Current Odometer Reading is showing NAN, For entering Odometer reading dealer need to delete NAN first | Login cridential provided | Click on Add Claim |  |  |  | Low | Fixed | Ranjeet | Done | Fixed
2020-02-24 |  | 24 | compatibility Issue :- Accepting Surveyor Contact No. Less than 10 digit in Internet Explorer | Login cridential provided | 1) Click Claim 2) Open any Claim 3) Click on edit |  |  |  | Low | deferred | Ranjeet | client side validation working. No need to change | deferred
2020-02-24 |  | 25 | Edit :- Without Clicking on Edit Manager is able to Edit Data | Login cridential provided | 1) Click Claim 2) Open any Claim |  |  |  | High | Fixed | Ranjeet | Admin & Manager Can Edit without click on edit button. (No need to change) | Fixed
2020-02-27 | TC_63/Claim | 26 | Wrong validation message appears for leaving Certificate number blank as "Please Select Agreement First" | User is logged in and is already on creating new claim page. | 1) Leave the Certificate number field blank. 2) Enter data in odometer reading and enter valid data in all the remaining fields.. 3)Click on Save button. |  |  | High | Low | New | Ranjeet | Done
2020-02-27 | TC_04/Claim | 27 | Certificate No should be marked (*) in order to show it as a mandatory fields. | Login cridential provided | Click on Add Claim |  |  | High | Low | New | Ranjeet | Done
2020-02-27 | TC_06/Claim | 28 | There should be a proper validation message for leaving all the mandatory fields blank as " All the mandatory fields marked with * are required. | Login cridential provided | Leave all field blank and click on submit |  |  | High | Mid | New | Ranjeet | No need to change
2020-02-27 | TC_09/Claim | 29 | System should display a validation message for Leaving Certificate No. first and all the validation message should prioritized according to their order of appearance. | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  | High | Mid | New | Ranjeet | Done
TC_65/Claim | 10180 | 30 | The validation message coming should be changed to "Please Select Certificate Number." and also the rest of dependent data should get reset to blank. | User is logged in and is already on creating new claim page. | 1 Select any certificate number you wish to raise claim forr. 2) Enter valid details in other mandatory fields. 3) Now click on X button appearing before Certificate number. 4) Click on Save button. |  |  | High | High | New | Ranjeet | No need to change
TC_66/Claim | 10180 | 33 | Blank spaces in the service request number are not disabled. | To verify if the user is able to submit the claim form by entering invalid data in Service Request Number. | User is logged in and is already on creating new claim page. | 1) Enter any Alphanumeric number in combination with blank spases in Service request.. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | Low | Low | Fixed | Ranjeet | Done
TC_67/Claim | 10180 | 34 | Blank spaces in the Work Order number are not disabled. | To verify if the user is able to submit the claim form by entering invalid data in Work Order Number. | User is logged in and is already on creating new claim page. | 1) Enter any Alphanumeric number in combination with blank spases in Work Order. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | Low | Low | Fixed | Ranjeet | Done
TC_70/Claim | 10180 | 35 | user is able to update the claim by updating the certificate number having the Certified Assurance End Date which is less than the Work Order Date ( Which is already added while creating the claim) and also there is no validation message for the same. | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update other certificate number. | Work Order Date 19-02-2020 with previous certificate number. Certified Assurance End Date 21-10-2019 |  | High | High | Fixed | Ranjeet | Done
TC_71/Claim | 10180 | 37 | User is able to update the claim form by entering invalid Warranty Manager Contact No. | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update with invalid Warranty Manager Contact No. | enter 0 ten times. |  | High | High | Fixed | Ranjeet | No need to change
TC_72/Claim | 10180 | 38 | User is able to update the claim form by entering invalid Repair Cost. | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update with invalid Repair Cost. | 0 |  | High | High | Fixed | Ranjeet | No need to change
Suggestion1 | 10180 | 39 | There should be an option to update the Part Information Claim. |  |  |  |  | High | High | Fixed | Ranjeet | Done
Suggestion2 | 10180 | 40 | There should be an option to update the Miscellaneous Expenses. |  |  |  |  | High | High | Fixed | Ranjeet | Done
Suggestion3 | 10180 | 41 | There should be an option to update theLabours Information Claim. |  |  |  |  | High | High | Fixed | Ranjeet | Done
TC_73/Claim | 10180 | 42 | The calculation in labour information claim is wrong. (Total amount is getting calculate as 41.80 and Amount as 38) | User is logged in and is already on creating new claim page. | 1)After submitting the claim click on the add Labour Information Claim. 2)Enter valid data in all the mandatory fields. 3) Observe the Amount and the total amount. | Rate per Hour -150 Operation Time in Hour-0.25 |  | High | High | Fixed | Ranjeet | Done
TC_74/Claim | 10180 | 43 | GST %: % Value cannot exceed more than 100% in Part Information Claim,Labour Information Claim and Miscellaneous Expenses fields. | User is logged in and is already on creating new claim page. | 1)After submitting the claim click on the add Labour Information Claim. 2)Enter 200 in GST %. 3) Observe the Amount and the total amount. | 200 in GST %. |  | High | High | Fixed | Ranjeet | Done
TC_75/Claim | 10180 | 44 | Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection fields are not clickable. | User is logged in and is already on creating new claim page. | 1)After submitting the part information, Labour Information and Miscellaneous click on Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection resp. |  |  | High | High | Fixed | Ranjeet | Its working fine
TC_76/Claim | 10180 | 45 | To verify if the approval/rejection date & time is getting update when claim manager first approves the claim and then later on due to some reasons he again rejects the claim. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) Change status to Approved. 3) Note down the Approved / Rejected Time and Approved / Rejected Date. 4) After some time or after one day change the status to rejects on the same claim. 5) Note down the Approved / Rejected Time and Approved / Rejected Date. |  |  | High | High | Fixed | Ranjeet | No need to change
TC_55/Claim | 10180 | 47 | Claim Manager Details should get change to Claim Manager Name | User is logged in as a claim manager. | 1)Open any claim which is to be update. 2) Now observe the Claim Manager Details . |  |  | High | Low | Fixed | Ranjeet | No need to change
TC_78/Claim | 10180 | 48 | Claim matured date & time field does not get update when dealer updates the comment prior to change the status “approved/rejected” in portal | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and again go to comment section andd add a comment. |  |  | High | High | Fixed | Ranjeet | done. Check by dealer login
TC_79/Claim | 10180 | 49 | Claim matured date & time field does not get update when dealer upload any new document prior to change the status “approved/rejected” in portal | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. |  |  | High | High | Fixed | Ranjeet | done. Check by dealer login
TC_80/Claim | 10180 | 50 | Claim Manager can update the details of Approve / Rejection Information and Surveyor Information already approved claim to blank, or with any valid and invalid data. | User is logged in as a claim manager. | 1) Open the claim whose status is approved. 2) Double click the fields under Approve / Rejection Information and Surveyor Information and change it to blank. |  |  | High | High | deferred | Ranjeet | No need to change
TC_77/Claim | 10180 | 46 | User isbe able to submit document by uploading invalid file in vehicle history. | User is logged in and is already on creating new claim page. | 1) Upload invalid file in Vehicle History field. | Upload an .exe fiel. |  | High | High | Fixed | Ranjeet | Done
TC_81/Claim | 10180 | 23 | Creating New Labour Information :- There is allingment Issue in Rejection Remark drop down menu. | Login cridential provided | 1) Add Claim 2) Creating New Labour Information |  |  |  | Low | Pass | Ranjeet | No need to change | Please explain why ?
2020-02-19 | TC_49/Claim | 14 | Unable To Delete Filter newly Created filter | Login cridential provided | 1) Click on Filter 2) Click on Delete Filter |  |  |  | High | Please explain why ? | Ranjeet | No need to change | Please explain why ? | 2020-02-24
TC_68/Claim | 10180 | 36 | The validation appears for entering invalid service request date when entering Work Order Open Time which is wrong and also the validation is incomplete. | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Service Request Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. | Service Request Date: 06-02-2013 |  | High | High | Not Fixed | Ranjeet | Done

## Comprehensive-ETG
Project Name:-> Mercedes_Benz
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :- | Login credential
Creation Date:- | 2020-04-04 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Apurwa
Version: - |  |  |  |  | Module:- | Certificate Request -Comprehensive-ETG | [6 empty] | Re-Testing
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power_ID :- | Date :- | Status
TC_Comprehensive-ETG_01 | 10581 | 2020-04-04 | To verify that Dealer is able to login to Mercedes-Benz | User has system with an active internet connection. | 1) Enter URL of the portal in your browser and press enter key. 2)Enter login credentials and click on Login button. | ID :- demo-dealer P.W. :- Welcome@123 | User is able to login to the portal |  | User should be able to login to the portal |  |  | Pass | 10601 | 2020-04-08 | Pass
TC_Comprehensive-ETG_02 | 10581 | 2020-04-04 | To verify if the option of ETG gets auto filled as "N", As soon as dealer selects "Y" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "Y" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin : WDD2120036L054215 Vin :WDD2050026L005803 | On viewing the added certificate request , "ETG(Engine Transmission Gear Box)" field shows empty data. | Vin Validation No MBCAR98 | N should get selected and saved in ETG field on selecting Y in Comprehensive field. | High | High | Fail | 10601 | 2020-04-08 | Pass
TC_Comprehensive-ETG_03 | 10581 | 2020-04-04 | To verify if the option of ETG gets auto filled as "Y", As soon as dealer selects "N" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "N" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin :WDD2050026L011379 Vin :WDC1569082J118502 | On viewing the added certificate request , "ETG(Engine Transmission Gear Box)" field shows empty data. | Vin Validation No MBCAR99 | Y should get selected and saved in ETG field on selecting N in Comprehensive field. | High | High | Fail | 10601 | 2020-04-08 | Pass
TC_Comprehensive-ETG_04 | 10581 | 2020-04-04 | To verify if the previously filled/selected details are appearing on the Editing Certification Request page. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check ETG(Engine Transmission Gear Box) field. | MBCAR99 | ETG(Engine Transmission Gear Box) field shows "Select an option" on Editing Certification Request page instead of showing N or Y based on the selected Comprehensive field. |  | Edit Certificate page should display all the details entered during the time of creating Certificate request. | High | High | Fail | 10601 | 2020-04-08 | Pass
TC_Comprehensive-ETG_05 | 10581 | 2020-04-04 | To verify if the Editing Certification Request page has a Certificate Number attached with the title or not. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check Title of the page. | MBCAR99 | Certificate Request Number is missing from the title of the page. |  | Title of the page should also have Certificate Number at Editing Certification Request page. | High | High | Fail | 10601 | 2020-04-08 | Not Implemented

## Comprehensive-ETG_ClientUAT
Project Name:-> Mercedes_Benz
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :- | Login credential
Creation Date:- | 2020-04-09 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Apurwa
Version: - |  |  |  |  | Module:- | Certificate Request -Comprehensive-ETG_Client UAT
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Comprehensive-ETG_CLUAT01 | 10610 | 2020-04-09 | To verify that Dealer is able to login to Mercedes-Benz | User has system with an active internet connection. | 1) Enter URL of the portal in your browser and press enter key. 2)Enter login credentials and click on Login button. | ID :- demo-dealer P.W. :- Welcome@123 |  |  | User should be able to login to the portal |  |  | Pass
TC_Comprehensive-ETG_CLUAT02 | 10610 | 2020-04-09 | To verify if the option of ETG gets auto filled as "N", As soon as dealer selects "Y" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "Y" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin : WDD2120036L054215 Vin :WDD2050026L005803 |  |  | N should get selected and saved in ETG field on selecting Y in Comprehensive field. | High | High | Pass
TC_Comprehensive-ETG_CLUAT03 | 10610 | 2020-04-09 | To verify if the option of ETG gets auto filled as "Y", As soon as dealer selects "N" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "N" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. | Vin :WDD2050026L011379 Vin :WDC1569082J118502 |  |  | Y should get selected and saved in ETG field on selecting N in Comprehensive field. | High | High | Pass
TC_Comprehensive-ETG_CLUAT04 | 10610 | 2020-04-09 | To verify if the previously filled/selected details are appearing on the Editing Certification Request page. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check ETG(Engine Transmission Gear Box) field. |  |  |  | Edit Certificate page should display all the details entered during the time of creating Certificate request. | High | High | Pass
TC_Comprehensive-ETG_CLUAT05 | 10610 | 2020-04-09 | To verify if the Editing Certification Request page has a Certificate Number attached with the title or not. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check Title of the page. |  |  |  | Title of the page should also have Certificate Number at Editing Certification Request page. | High | High | Not Implemented

## Claim
Project Name:-> Mercedes_Benz
Created By:- | Atyab Alam |  |  |  | Re-Tested By:- | Jitendra |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-17 |  |  |  | Re-Testing Date:- | 2020-02-27 |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Claim | [6 empty] | Retesting-27-02-2020 |  |  | Retesting- 06-03-2020 |  |  | Retesting- 16/17-03-2020
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power_ID : | Date | Status | Power_ID : | Date | Status | Power_ID : | Date | Status
TC_01/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to login to Mercedes-Benz | Login cridential provided | ID :- demo-dealer P.W. :- Welcome@123 |  |  |  | Will be able to login. |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_02/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to go to Claim page | Login cridential provided | Click on Claim present on top left of the screen |  |  |  | Claim page will open |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_03/Claim | 10058 | 2020-02-17 | To verify that all Static Buttons are allinged properly | Login cridential provided |  |  | There is allingment Issue |  | Static Buttons should be allinged properly |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_04/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Click on Add Claim |  | Certificate No should be marked (*) in order to show it as a mandatory fields. |  | Creating New Claim form will open with the all the mandatory ffields marked (*). |  |  |  | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_05/Claim | 10058 | 2020-02-17 | To Verify that Add New Claim form is Allinged properly | Login cridential provided | Click on Add Claim |  | There is allingment Issue |  | New Claim form should be Allinged properly |  | Low | Fail | 10180 | 2020-02-27 | Not Fixed | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass
TC_06/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Leave all field blank and click on submit |  | Two validation Msg. Appear and work order validation appears first which is not serial wise |  | This field is required msg will display on mandatory field |  | Low | Fail | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Pass- As Discussed | 10350 | 2020-03-17 | Pass
TC_07/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW Work Order :- Service Request Date :- Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Work Order Length length is less than 16 char. |  | Service Request length is less than 16 char. |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_08/Claim | 10058 | 2020-02-17 | To verify that after submitting Wrong Information Creating New Claim page data will be reset | Login cridential provided | Fill data and check validation |  | Unable to reset Data |  | Data of All Fields Should be reset |  | Low | Fail | 10180 | 2020-02-27 |  | 10274 | 2020-03-06 | No need to reset the pre-filled data | 10350 | 2020-03-17 | No need to reset the pre-filled data
TC_09/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Validation msg. is not serial wise |  | Please select Certificate No. |  | High | Fail | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Pass- As Discussed | 10350 | 2020-03-17 | Pass
TC_10/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :-28/02/2020 Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Validation msg. should be Please select Sales Order First. |  | Please select Certificate No. |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_11/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Odometer reading should be less than or equal to warrnaty end kms |  | Odometer reading should be in between warranty reading |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
0 | 10058 | 2020-02-17 |  | Login cridential provided |  | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- 13-02-2020 Service Request Time :- 01:30 Work Order Open Time :- 05:30 Current Odometer Reading :- 40000 Warranty Manager Name :- HOHOHO Dealer Email :- hoho@gogo.xyz Warranty Manager Contact No :- 9876543210 Diagnosis done by Dealer :- yes Repair Cost :- 50000 Repair Estimation :- 1.pdf | [6 empty] | 10180 | 2020-02-27 |  | 10274 | 2020-03-06 | Cannot be executed. | 10350 | 2020-03-17 | Cannot be executed.
TC_13/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided | Click on Add Part Information Claim |  |  |  | Will be redirected to Creating New Part Information Claim page |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_14/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.2 MRP :- Part Location :- | NAN is showing in Total Field. Field should be blank Also Quantity is accepting decimal value |  | Quantity Should not accept decimal value |  | High | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_15/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.1 MRP :- 100 Total :- 110.00000000000001 Part Location :- | There is calculation mistake (Sugg. :- There should be GST on Total price of Part) |  | Total should be 110 |  | High | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_16/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 2 MRP :- 100 Total :- 200 Part Location :- Front Left |  |  | Part Information will be Added |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_17/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Labour Information Claim | Login cridential provided | Click on Add Labour Information Claim |  | There is an alignment issue as the menu headers are getting mis- aligned from its place. |  | Will be redirected to Creating New Labour Information Claim page |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass
TC_18/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Labour Information Claim | Login cridential provided | Fill details total will be calculated automatically | Labour Code :- 1 Rate per Hour :- 200 Operation Time in Hours :- 10 Amount :- 2000 GST% :- 10 GST Amount :- 200 Total Price :- 2200 |  |  | New Labour Information will be added |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_19/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Miscellaneous Expenses | Login cridential provided | Click on Add Miscellaneous Expenses |  |  |  | Will be redirected to Creating New Miscellaneous Expenses |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_20/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Miscellaneous Expenses | Login cridential provided | Fill details total will be calculated automatically | Amount :- 1000 GST % :- 100 |  |  | New Miscellaneous Expenses will be Added |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_21/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Document | Login cridential provided | Click on Add Document |  |  |  | Will be redirected to Creating New Document |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_22/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Document | Login cridential provided | Click on Add Document |  | Unable to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component of 5MB |  | Will be able to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_23/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Edit Claim whose status is not Approved/Rejected | Login cridential provided | 1) Click on Claim 2) Click on Edit option present on top |  |  |  | Dealer should be able to Edit claim details |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_24/Claim | 10058 | 2020-02-17 | To verify that dealer is able to create Claim | Login cridential provided | Click on Add Claim |  | Warranty Manager Name is accepting special character and numeric data |  | Warranty Manager Name should not accept special character and numeric data |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_25/Claim | 10058 | 2020-02-17 | To verify that manager can login to portal or not | Login cridential provided | ID :- demo-TVS P.W. :- Welcome@123 |  |  |  | Manager should be able to login to the portal |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_26/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | 1) Click on Claim 2) Search claim by claim No. :- MBCAC115 |  |  |  | Claim of claim No. :- MBCAC115 Will appear on the screen |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_27/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | 1) Click on Claim 2) Search claim by Customer Name :- GANGADHARA PAYYADE |  |  |  | Claim with customer name GANGADHARA PAYYADE will appear on the screen |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_28/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | Search Claim by Vehicle VIN :- WDD2120346L047456 |  |  |  | Claim with Vehicle VIN :- WDD2120346L047456 will appear on the screen |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_29/Claim | 10058 | 2020-02-17 | To verify that manager can search claim by model of vehicles | Login cridential provided | Model of vehicles :- 2 |  |  |  | No vehicle found |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_30/Claim | 10058 | 2020-02-19 | To verify that manager can search claim by model of vehicles | Login cridential provided | Model of vehicles :- E |  |  |  | All claim on mercedes car with model contains E in it will filtered |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_31/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Status :- Submitted |  |  |  | All claim with status submitted will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_32/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Assigned To :- Demo Dealer |  |  |  | All claim assinged to Demo Dealer will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_33/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Created Time |  | Instead of created time it is searching with created date |  | Should be able search with created time |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_34/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Answered by Dealer | Login cridential provided | 1) Click on Filter 2) Click on Answered by Dealer |  |  |  | All claim that is answered by dealer will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_35/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Approved Claim | Login cridential provided | 1) Click on Filter 2) Click on Approved Claim |  |  |  | All claim whose status is approved will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_36/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Open Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Open Purchase Orders |  |  |  | All claim whose status is open purchase orders will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_37/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Payment Made | Login cridential provided | 1) Click on Filter 2) Click on Payment Made |  |  |  | All claim whose payment is made will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_38/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Pending with Surveyor | Login cridential provided | 1) Click on Filter 2) Click on Pending with Surveyor |  |  |  | All claim whose status is pending with surveyor will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_39/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Post Approval Documents Pending Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Pending Claim |  |  |  | All claim whose post Approval document is pending will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_40/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Post Approval Documents Received Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Recived Claim |  |  |  | All claim whose post Approval document is recived will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_41/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Query by Assurant | Login cridential provided | 1) Click on Filter 2) Click on Query by Assurant |  | Query by TVS Claim is appearing in the dropdowns to filter the claims. |  | All claim on which query is generated by assurant will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass
TC_42/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Received Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Received Purchase Orders |  |  |  | All claim whose purchased order is recived will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_43/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Rejected Claim | Login cridential provided | 1) Click on Filter 2) Click on Rejected Claim |  |  |  | All claim which is rejected will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_44/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Submitted Claim | Login cridential provided | 1) Click on Filter 2) Click on Submitted Claim |  |  |  | All claim whose status is submitted will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_45/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Total Claim | Login cridential provided | 1) Click on Filter 2) Click on Total Claim |  |  |  | total claim registered from day 1 will appear |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_46/Claim | 10058 | 2020-02-19 | To verify that dealer is able to create new Filter | Login cridential provided | 1) Click on Filter 2) Click on Create New Filter | View Name :- qwerty Choose columns and order :- Certificate No. |  |  | Please Select at-least one mandatory Field |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_47/Claim | 10058 | 2020-02-19 | To verify that dealer is able to create new Filter | Login cridential provided | 1) Click on Filter 2) Click on Create New Filter | View Name :- qwerty Choose columns and order :- Certificate No., Current Odometer Reading |  |  | New Filter will be created |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_48/Claim | 10058 | 2020-02-19 | To verify that dealer is able to edit Filter | Login cridential provided | 1) Click on Filter 2) Click on Edit New Filter | View Name :- qwerty Choose columns and order :- Certificate No., Current Odometer Reading, Modified Time |  |  | Modified Time filter option will be added |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_49/Claim | 10058 | 2020-02-19 | To verify that dealer is able to Delete Filter | Login cridential provided | 1) Click on Filter 2) Click on Delete Filter |  | Unable To Delete Filter |  | Newly created filter will be deleted |  | High | Fail | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Deferred
TC_50/Claim | 10058 | 2020-02-19 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor |  |  | Status will change to Pending with Surveyor |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_51/Claim | 10058 | 2020-02-19 | To verify that on changing status ​S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor |  |  | S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will be automatically captured |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_52/Claim | 10058 | 2020-02-19 | To verify that manager can insert Surveyor Contact No. | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Contact No. :- 222 | accepting Surveyor Contact No. less than 10 digit |  | Surveyor Contact No. should be of Atleast 10 digit |  | High | Fail | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass
TC_53/Claim | 10058 | 2020-02-19 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- qwerty | [6 empty] | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_54/Claim | 10058 | 2020-02-19 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim |  |  |  | Surveyor Appointment Date and Surveyor Appointment Time will be automatically Added |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_55/Claim | 10058 | 2020-02-19 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty | There is No option of Entering Claim Manager Name |  | Claim Manager Name will be added |  | High | Fail | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Pass- As Discussed | 10350 | 2020-03-17 | Pass
TC_56/Claim | 10058 | 2020-02-19 | To verify that First Action Date and First Action Time automatically gets captured on adding manager name | Login cridential provided |  |  | First Action Date and First Action Time automatically gets captured on adding Claim manager Details instead of Name |  | First Action Date and First Action Time will automatically get captured |  | High | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass- As Discussed | 10350 | 2020-03-17 | Pass
TC_57/Claim | 10058 | 2020-02-19 | To verify that dealer is able to add comment on claim whose status :- Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Comment | Comment :- Hi |  |  | Comment will be added and status will be changed to Answered by dealer |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_58/Claim | 10058 | 2020-02-19 | To verify that dealer is able to change status to Approved | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Status :- Approved |  |  | Status of Claim will Change to Approved |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_59/Claim | 10058 | 2020-02-19 | To verify that dealer is able to change status to Rejected | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Status :- Rejected |  |  | Status of Claim will Change to Rejected |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_60/Claim | 10058 | 2020-02-19 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  |  |  |  | Approved / Rejected Time and Approved / Rejected Date will automatically gets updated |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_61/Claim | 10058 | 2020-02-19 | To verify that Claim Matured Date andClaim Matured Time will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  |  |  |  | Claim Matured Date and Claim Matured Time will be automatically updated |  |  |  | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_62/Claim | 10058 | 2020-02-19 | To verify that manager is able to download report | Login cridential provided | 1) Login with manager ID 2) Open Report 3) Click on Claim Report | Start Date :- 2020-02-15 End Date :- 2020-02-19 | Total record found in the report will be displayed on screen |  | Should be able to download report and total record found in the report will be displayed on screen |  | High | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_63/Claim | 10058 | 2020-02-19 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- @##$123 | Accepting special character and numeric data in surveyor name |  | Invalid Dealer Name |  | Low | Fail | 10180 | 2020-02-27 | Pass | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_64/Claim | 10180 | 2020-02-27 | To verify if the validation message appears for leaving Certificate Number blank. | User is logged in and is already on creating new claim page. | 1) Leave the Certificate number field blank. 2) Enter data in odometer reading and enter valid data in all the remaining fields.. 3)Click on Save button. |  | Wrong validation message appears for leaving Certificate number blank as "Please Select Agreement First" |  | Spacific and proper validation message for leaving certificate number should get appear. | High | Low |  | 10180 | 2020-02-27 | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_65/Claim | 10180 | 2020-02-27 | To verify if the user is able to submit the claim form by deleting the certificate number after once adding it. | User is logged in and is already on creating new claim page. | 1 Select any certificate number you wish to raise claim forr. 2) Enter valid details in other mandatory fields. 3) Now click on X button appearing before Certificate number. 4) Click on Save button. |  | The validation message coming should be changed to "Please Select Certificate Number." and also the rest of dependent data should get reset to blank. |  | There should be a proper and spacific validation for leaving the certificate number blank and aslo the rest of the dependent fields should get reset to blank on deleting the certificate number. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_66/Claim | 10180 | 2020-02-19 | To verify if the user is able to submit the claim form by entering invalid data in Service Request Number. | User is logged in and is already on creating new claim page. | 1) Enter any Alphanumeric number in combination with blank spases in Service request.. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | Blank spaces in the service request number are not disabled. |  | Blank spaces should be disbaled to be enter. | Low | Low |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_67/Claim | 10180 | 2020-02-27 | To verify if the user is able to submit the claim form by entering invalid data in Work Order Number. | User is logged in and is already on creating new claim page. | 1) Enter any Alphanumeric number in combination with blank spases in Work Order. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | Blank spaces in the Work Order number are not disabled. |  | Blank spaces should be disbaled to be enter. | Low | Low |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_68/Claim | 10180 | 2020-02-27 | To verify if the user is able to submit the claim by entering invalid data in Service Request Date. | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Service Request Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. | Service Request Date: 06-02-2013 | User is able to save the claim form by entering invalid data in Service Request Date and also there is no validation message appears for the same. |  | User should not be able to save the claim form and also there should be a proper and spacific validation message for the same. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass- as discussed It is open
TC_69/Claim | 10180 | 2020-02-27 | To verify if the user is able to submit the claim by entering invalid data in Work Order Date. | User is logged in and is already on creating new claim page. | 1)Enter invalid data in Work Order Date. 2)Enter valid data in rest of the mandatory fields. 3) Click on Save buttton. | Work Order Date: 17-06-2009 | User is able to save the claim form by entering invalid data in Work Order Date and also there is no validation message appears for the same. |  | User should not be able to save the claim form and also there should be a proper and spacific validation message for the same. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass- as discussed It is open
TC_70/Claim | 10180 | 2020-02-27 | To verify if the user is able to update the claim by updating the certificate number having the Certified Assurance End Date which is less than the Work Order Date ( Which is already added while creating the claim) | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update other certificate number. | Work Order Date 19-02-2020 with previous certificate number. Certified Assurance End Date 21-10-2019 | user is able to update the claim by updating the certificate number having the Certified Assurance End Date which is less than the Work Order Date ( Which is already added while creating the claim) and also there is no validation message for the same. |  | User should not be able to update and also there should be a proper validation message for the same. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_71/Claim | 10180 | 2020-02-27 | To verify if the user is able to update the claim by entering invalid data in Warranty Manager Contact No field. | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update with invalid Warranty Manager Contact No. | enter 0 ten times | User is able to update the claim form by entering invalid Warranty Manager Contact No. |  | User should not be able to update the claim form by entering invalid Warranty Manager Contact No. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_72/Claim | 10180 | 2020-02-27 | To verify if the user is able to update the claim by entering invalid data in Repair Cost field. | User is logged in and is already on creating new claim page. | 1)Open the claim to be edit. 2) Click on edit button. 3) Update with invalid Repair Cost. | 0 | User is able to update the claim form by entering invalid Repair Cost. |  | User should not be able to update the claim form by entering invalid Repair Cost | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass- As Discussed | 10350 | 2020-03-17 | Pass
TC_73/Claim | 10180 | 2020-02-28 | To verrify if the calculation in labour information claim is right or not. | User is logged in and is already on creating new claim page. | 1)After submitting the claim click on the add Labour Information Claim. 2)Enter valid data in all the mandatory fields. 3) Observe the Amount and the total amount. | Rate per Hour -150 Operation Time in Hour-0.25 | Total amount is getting calculate as 41.80 and Amount as 38 |  | Amount and the total amount should be equal to Amount=37.5, Total Price= 41.25 | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_74/Claim | 10180 | 2020-02-28 | GST %: % Value cannot exceed more than 100% in Part Information Claim,Labour Information Claim and Miscellaneous Expenses fields. | User is logged in and is already on creating new claim page. | 1)After submitting the claim click on the add Labour Information Claim. 2)Enter 200 in GST %. 3) Observe the Amount and the total amount. | 200 in GST %. | GST %: % Value is exceeding more than 100% in Part Information Claim,Labour Information Claim and Miscellaneous Expenses fields. |  | GST% cannot exceed more than 100% | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Fail-Miscellaneous Expenses
TC_75/Claim | 10180 | 2020-02-28 | To verify if the Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection is clickable or not. | User is logged in and is already on creating new claim page. | 1)After submitting the part information, Labour Information and Miscellaneous click on Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection resp. |  | Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection fields are not clickable. |  | Update Part Rejection, Update Labour Rejection and Update Miscellaneous Rejection fields should be clickable. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_76/Claim | 10180 | 2020-02-28 | To verify if the approval/rejection date & time is getting update when claim manager first approves the claim and then later on due to some reasons he again rejects the claim. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) Change status to Approved. 3) Note down the Approved / Rejected Time and Approved / Rejected Date. 4) After some time or after one day change the status to rejects on the same claim. 5) Note down the Approved / Rejected Time and Approved / Rejected Date. |  | Previous date and time is appearing. |  | Updated date and time should get appear. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass-As discussed. (It will consider only first date)
TC_77/Claim | 10180 | 2020-02-28 | To verify if the user is able to upload the document by uploading invalid fiel in Vehicle History.` | User is logged in and is already on creating new claim page. | 1) Upload invalid file in Vehicle History field. | Upload an .exe fiel. | User isbe able to submit document by uploading invalid file in vehicle history. |  | User should not be able to submit document by uploading invalid fiel. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_78/Claim | 10180 | 2020-02-28 | To verify if the Claim matured date & time field gets updated when dealer updates the comment prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and again go to comment section andd add a comment. |  | Claim matured date & time field does not get update when dealer updates the comment prior to change the status “approved/rejected” in portal |  | New Claim matured date & time should get update as per the newly added comment. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | No need to test in case of updation.
TC_79/Claim | 10180 | 2020-02-28 | To verify if the Claim matured date & time field gets updated when dealer uploads the new document prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. |  | Claim matured date & time field does not get update when dealer upload any new document prior to change the status “approved/rejected” in portal |  | New Claim matured date & time should get update as per the newly added comment. | High | High |  |  |  | Fail | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | No need to test in case of updation.
TC_80/Claim | 10180 | 2020-02-28 | To verify if Claim Manager can update the details of Approve / Rejection Information and Surveyor Information already approved claim to blank, or with any valid and invalid data. | [11 empty] | Fail | 10274 | 2020-03-06 | Deferred | 10350 | 2020-03-17 | Deferred
TC_81/Claim | 10180 | 2020-02-28 | To verify if the user is able to view the dropdown options of Rejection Remark or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value. |  | There is allingment Issue in Rejection Remark drop down menu. |  | User should see the rejection Remark dropdown values. | High | Low |  |  |  | Fail | 10274 | 2020-03-06 | Pass | 10350 | 2020-03-17 | Pass
TC_82/Claim |  |  | To verify if the claim manager is able to view the claims |  | 1) Open any claim. 2)View both ​​Request for ​S​urveyor ​A​ppointment​ ​Date & Request for ​S​urveyor ​A​ppointment​ Time fields. |  | ​​Request for ​S​urveyor ​A​ppointment​ ​Date & Request for ​S​urveyor ​A​ppointment​ Time are not aligned. |  | All the fields should be properly aligned. | [6 empty] | 10274 | 2020-03-06 | Fail | 10350 | 2020-03-17 | Pass
62.5
2.5

## Time_Auto_ClientUAT
Project Name:-> Mercedes_Benz
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 25-03-2020 TO 26-03-2020 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Time Automation in Claim and Dropdpwn in Part Information.
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Time_Automation_01 | 10500 | 2020-03-25 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor | [5 empty] | Pass
TC_Time_Automation_02 | 10500 | 2020-03-25 | To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor | [5 empty] | Pass
TC_Time_Automation_03 | 10500 | 2020-03-25 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- qwerty | [5 empty] | Pass
TC_Time_Automation_04 | 10500 | 2020-03-25 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim | [6 empty] | Pass
TC_Time_Automation_05 | 10500 | 2020-03-25 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty | [5 empty] | Pass
TC_Time_Automation_06 | 10500 | 2020-03-25 | To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_07 | 10500 | 2020-03-25 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_08 | 10500 | 2020-03-25 | To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. | [6 empty] | Pass
TC_Time_Automation_09 | 10500 | 2020-03-25 | To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal. | [8 empty] | Pass
TC_Dropdown_PartInfo_01 | 10502 | 2020-03-25 | To verify if the user is able to view and select the dropdown options of Rejection Remark or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value. | [6 empty] | Pass
TC_Dropdown_LabourInfo_02 | 10502 | 2020-03-25 | To verify if the user is able to view and select the dropdown options of Part Location or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value. | [6 empty] | Pass
aecd

## CertificateRequestReport
Project Name: Renault-EW
Created By:- | Jitendra |  |  | Reviewed By:- |  |  | Developed By:
Creation Date:- | 2020-03-21 |  |  | Review Date:-
Version: - |  |  |  | Module:- | Certification Request MIS Report |  | Power ID: | 10457 |  |  |  | Retesting-10476
Test Case ID | Power ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Power ID | Status
TC_CertificationRequest _01 | 10457 | To verify if the user is able to get navigate to the reports section. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant | 1) Click on Reports menu item. 2)Click on the certificate request report link, | NA |  |  | User should get navigate to the reports page. |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _02 | 10457 | To verify if the user is able to download the report by leaving start date , end date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the fields blank. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _03 | 10457 | To verify if the user is able to download the report by leaving start date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the start date fields blank and enter valid data in the end date. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _04 | 10457 | To verify if the user is able to download the report by leaving start date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the start date fields blank and enter valid data in the end date. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _05 | 10457 | To verify if the user is able to download the report by entering invali data in start date. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the start date field and enter valid data in the end date. 2)Click on Generate Now button. | Start Date: ijugkjghgh End Date: kjbhkhb | User is able to download the report by entering invalid data in start and also there is no validation message for the same. |  | User should not be able to download the report. |  |  | Fail | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _06 | 10457 | To verify if the user is able to download the report by entering invali data in enddate. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the end date field and enter valid data in the start date. 2)Click on Generate Now button. | Start Date: kjhjkhk End Date: kjbhghghghghkg | User is able to download the report by entering invalid data in end date and also there is no validation message for the same. |  | User should not be able to download the report. |  |  | Fail | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _07 | 10457 | To verify if the user is able to download the report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _08 | 10457 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | fail | 2020-03-23 | 10476 | Pass- As per the format given by the client.
TC_CertificationRequest _09 | 10457 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | Pass | 2020-03-23 | 10476 | pass
TC_CertificationRequest _10 | 10457 | To verify if the option to view and download the report is available in Dealer login or not. | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link, | demo-dealer Welcome@1234 | There is no option available to view/download the report in dealer login. |  | User should get navigate to the reports page. |  |  | Fixed Now | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _11 | 10457 | To verify if the option to view and download the report is available in Dealer login or not. | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link, | demo-dealer Welcome@1234 | There is no option available to view/download the report in dealer login. |  |  |  |  | Pass | 2020-03-23 | 10476 | Pass
TC_CertificationRequest _12 | 10457 | To verify if the user is able to view the certificate on portal or not. | User is logged in as Dealer. | 1)Click on Certificate Request menu item. 2)Click on the certificate request to be open, |  | There is a spelling mistake in the Certificate Request field -Odometer Reading During Certification(Final Xentry |  | Certificate Request should get open with all the fields. |  |  | Fail |  | 10476 | Deffered
TC_CertificationRequest _13 | 10513 | To verify if the Certificate Request Mis Report has Certification Request date or not, | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | Pass
TC_CertificationRequest _14 | 10513 | To verify if the Certificate Request Mis Report has Certification Approval Date or not. | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | Pass
TC_CertificationRequest _15 | 10513 | To verify if the Certificate Request Mis Report has Certification Request date or not, | User is logged in as Claim Manager, | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | Pass
TC_CertificationRequest _16 | 10513 | To verify if the Certificate Request Mis Report has Certification Approval Date or not. | User is logged in as Claim Manager, | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | Pass
TC_CertificationRequest _17 | 10513 | To verify if the Certificate Request Mis Report has Certification Request date or not, | User is logged in as Admin. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | Pass
TC_CertificationRequest _18 | 10513 | To verify if the Certificate Request Mis Report has Certification Approval Date or not. | User is logged in as Admin. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | Pass

## Sheet1
http://13.127.10.134/mercedes_dev_bkp/index.php
http://13.127.10.134/mercedes_dev/index.php | 2020-03-21
2020-03-25

## Sheet2
Number of Extended warranty sold comparison MTD last month Vs current month and YTD
SI.No. | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lacs | In Number | In INR Lacs | In Number | In INR Lacs
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18 | model wise
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18 | Region wise
Model wise same data as point MTD & Last MTD & YTD
Brand/Period | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lakhs | In Number | In INR Lakhs | In Number | In INR Lakhs
Dost | 0 | 0 | 0 | 0 | 2796 | 139.66
STiLE | 0 | 0 | 0 | 0 | 0 | 0
Dost Strong | 0 | 0 | 0 | 0 | 2140 | 96.53
DOST- IFS | 0 | 0 | 0 | 0 | 93 | 6.84
DOST- RFS | 0 | 0 | 0 | 0 | 457 | 21.31
DOST REFRESH CNG BSIV LS FSD WHITE | 0 | 0 | 0 | 0 | 0 | 0
DOST REFRESH CNG BSIV LE FSD WHITE | 0 | 0 | 0 | 0 | 0 | 0
DOST-STRONG | 0 | 0 | 0 | 0 | 8 | 0.46
DOST- XPRESS | 0 | 0 | 0 | 0 | 18 | 0.7
DOST SMART | 0 | 0 | 0 | 0 | 1 | 0.1
DOST + | 29 | 1.19 | 34 | 1.38 | 1928 | 90.86
Dost Lite | 0 | 0 | 0 | 0 | 164 | 9.66
DOST(IFS RFS Smart Strong Xpress) | 198 | 8.9 | 160 | 7.01 | 1400 | 66.07
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18
Region Wise Extended Warranty Sold Comparison
Region | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lacs | In Number | In INR Lacs | In Number | In INR Lacs
--Select-- | 0 | 0 | 0 | 0 | 0 | 0
CENTRAL | 4 | 0.13 | 8 | 0.3 | 604 | 28.82
EAST-1 | 0 | 0 | 1 | 0.03 | 103 | 5.03
EAST-2 | 0 | 0 | 0 | 0 | 0 | 0
North 1 | 1 | 0.07 | 0 | 0 | 3 | 0.18
NORTH-1 | 8 | 0.44 | 17 | 1.04 | 344 | 21.35
NORTH-2 | 3 | 0.18 | 2 | 0.08 | 83 | 4.58
SOUTH-1 | 47 | 2.16 | 72 | 2.88 | 2737 | 132.97
SOUTH-2 | 148 | 6.01 | 84 | 3.57 | 3903 | 162.86
WEST | 16 | 1.1 | 10 | 0.5 | 1228 | 76.39
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18

## Sheet3
Number of Extended warranty sold comparison MTD last month Vs current month and YTD
SI.No. | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lacs | In Number | In INR Lacs | In Number | In INR Lacs
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18 | Model Wise
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18 | Region Wise
Model wise same data as point MTD & Last MTD & YTD
Brand/Period | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lakhs | In Number | In INR Lakhs | In Number | In INR Lakhs
Dost | 0 | 0 | 0 | 0 | 2796 | 139.66
STiLE | 0 | 0 | 0 | 0 | 0 | 0
Dost Strong | 0 | 0 | 0 | 0 | 2140 | 96.53
DOST- IFS | 0 | 0 | 0 | 0 | 93 | 6.84
DOST- RFS | 0 | 0 | 0 | 0 | 457 | 21.31
DOST REFRESH CNG BSIV LS FSD WHITE | 0 | 0 | 0 | 0 | 0 | 0
DOST REFRESH CNG BSIV LE FSD WHITE | 0 | 0 | 0 | 0 | 0 | 0
DOST-STRONG | 0 | 0 | 0 | 0 | 8 | 0.46
DOST- XPRESS | 0 | 0 | 0 | 0 | 18 | 0.7
DOST SMART | 0 | 0 | 0 | 0 | 1 | 0.1
DOST + | 29 | 1.19 | 34 | 1.38 | 1928 | 90.86
Dost Lite | 0 | 0 | 0 | 0 | 164 | 9.66
DOST(IFS RFS Smart Strong Xpress) | 198 | 8.9 | 160 | 7.01 | 1400 | 66.07
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18
Region Wise Extended Warranty Sold Comparison
Region | MTD |  | SPLM(Same Period Last Month) |  | YTD
| In Number | In INR Lacs | In Number | In INR Lacs | In Number | In INR Lacs
--Select-- | 0 | 0 | 0 | 0 | 0 | 0
CENTRAL | 4 | 0.13 | 8 | 0.3 | 604 | 28.82
EAST-1 | 0 | 0 | 1 | 0.03 | 103 | 5.03
EAST-2 | 0 | 0 | 0 | 0 | 0 | 0
North 1 | 1 | 0.07 | 0 | 0 | 3 | 0.18
NORTH-1 | 8 | 0.44 | 17 | 1.04 | 344 | 21.35
NORTH-2 | 3 | 0.18 | 2 | 0.08 | 83 | 4.58
SOUTH-1 | 47 | 2.16 | 72 | 2.88 | 2737 | 132.97
SOUTH-2 | 148 | 6.01 | 84 | 3.57 | 3903 | 162.86
WEST | 16 | 1.1 | 10 | 0.5 | 1228 | 76.39
Total | 227 | 10.09 | 194 | 8.39 | 9005 | 432.18