## Bug Report
Project :- | Servinsur-UAT |  |  |  | Lead_Devp. :- | Ajay/Pawan/Deepak
Created_By :- | Jitendra |  |  |  | Power_Task_I.D. :- | 14271
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
14271 |  | 1 | When repairer submits the estimation by selecting “Rejected with Service Fee” then the same case is not appearing in the CA-My Task. |  |  |  |  | High | High | New | Deepak
14271 |  | 2 | When repairer submits the estimation by selecting “Rejected without Service Fee” then the same case is not appearing in the CA-My Task. |  |  |  |  | High | High | New | Deepak
14271 |  | 3 | Estimate section: Case status field under estimate section is showing incomplete value. |  |  |  | https://prnt.sc/10csgl1 | High | High | New | Deepak
14272 |  | 4 | “Repair_Action": "Part Cleaned and Serviced¦Re-fitting" in estimation submission api repair action cannot take multiple values. Very first selcted value of resolution of issue should appear in repair action field. |  |  |  | https://prnt.sc/10ctsad | High | High | New | Deepak

## 14271
Created By:- | Jitendra |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  | Re-Testing Date:- |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Auto_Approval
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Add_Estimation_01 | 14271 | 2021-03-04 | To verify if the Repairers have an option to Reject the estimate by selecting the “Rejection Picklist” | Repairer is already logged in. | 1) select Rejected with service fee. 2) Click on submit button. |  |  |  | Estimate should not get rejected by the repairer |  |  | Pass
TC_Add_Estimation_02 | 14271 | 2021-03-04 | To verify if the Repairers have an option to Reject the estimate by selecting the “Rejection Picklist” | Repairer is already logged in. | 1) select Rejected with service fee. 2) Select any valid reason. 3) Click on submit button. |  |  |  | Estimate should get rejected by the repairer with service fee. |  |  | Pass
TC_Add_Estimation_03 | 14271 | 2021-03-04 | To verify if the Repairers have an option to Reject the estimate by selecting the “Rejection Picklist” | Repairer is already logged in. | 1) select Rejected without service fee. 2) Click on submit button. |  |  |  | Estimate should not get rejected by the repairer |  |  | Pass
TC_Add_Estimation_04 | 14271 | 2021-03-04 | To verify if the Repairers have an option to Reject the estimate by selecting the “Rejection Picklist” | Repairer is already logged in. | 1) select Rejected without service fee. 2) Select any valid reason. 3) Click on submit button. |  |  |  | Estimate should get rejected by the repairer without service fee. |  |  | Pass
TC_Add_Estimation_05 | 14271 | 2021-03-04 | To verify if the CA is able to view the action taken by the repairer on estimate as separate field. | CA is already logged in. | 1) Click on approve estimate quick link. 2) observe the UI. | CPP-603860 ACK-973860 ACK-983860 CPP-993860 |  |  | CA should be able to view the last action taken by repairer as separate field. |  |  | Pass
TC_Add_Estimation_06 | 14271 | 2021-03-04 | To verify if he In case of Auto Approval, a Request sending to CA user for further approval, after that only, repairer can move to the next step. | Repairer is already logged in. | 1) submit an estimation of auto approval case. | CPP-603860 ACK-973860 ACK-983860 CPP-993860 |  |  | In case of Auto Approval, a Request should get sent to CA user for further approval, after that only, repairer can move to the next step. |  |  | Pass
TC_Add_Estimation_07 | 14271 | 2021-03-04 | To verify if the timeline is getting updated only after the CA action on estimate. | CA is already logged in. | 1) Approve an estimation of auto approval case. | CPP-603860 ACK-973860 ACK-983860 CPP-993860 |  |  | Timeline should only get update after CA approves the estimation. |  |  | Pass
When repairer submits the estimation by selecting “Rejected with Service Fee” then the same case is not appearing in the CA-My Task.
When repairer submits the estimation by selecting “Rejected without Service Fee” then the same case is not appearing in the CA-My Task.
[7 empty] | Estimate section: Case status field under estimate section is showing incomplete value. | https://prnt.sc/10csgl1

## 14272
Defect_type": "Manufacturing Defect", "Fault_Category": "Digital Camera - Flash/Display Issue", "aiz_claim_number": "9632", "Repeat_Repair_Age": 0, "Inspection_Completion_Date": "2021-03-04 08:53:19", "Problem_Category_identified": "No Auto Focus", "Problem_SubCategory_identified": "Defocus Mode Selected
{ "Defect_type": "Non Manufacturing Defect", "Fault_Category": "Mobile - Cosmetic Problem", "aiz_claim_number": "9631", "Repeat_Repair_Age": 0, "Inspection_Completion_Date": "2021-03-04 09:21:40", "Problem_Category_identified": "Dis Colouration", "Problem_SubCategory_identified": "Front Cover Faulty" }
{"Defect_type": "Manufacturing Defect", "Fault_Category": "Digital Camera - Flash/Display Issue", "aiz_claim_number": "9632", "Repeat_Repair_Age": 0, "Inspection_Completion_Date": "2021-03-04 08:53:19", "Problem_Category_identified": "No Auto Focus", "Problem_SubCategory_identified": "Defocus Mode Selected"}
{"Defect_type": "Non Manufacturing Defect", "Fault_Category": "Air Conditioner - Cooling Issue", "aiz_claim_number": "603860", "Repeat_Repair_Age": 0, "Inspection_Completion_Date": "2021-03-04 08:33:51", "Problem_Category_identified": "Low Cooling", "Problem_SubCategory_identified": "Communication Wire Faulty"}