## Summary
Lead Dev:Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestions | Deferred
DC PMS Service Request | 51 | 51 | 45 | 0 | 2 | 4
NC PMS Service Request | 53 | 53 | 45 | 0 | 2 | 4
Total | 104 | 104 | 90 | 0 | 4 | 8

## BugReport
Bug Report
Project :- |  | NISSAN EW | [5 empty] | Lead_Developer. :-Alok Srivastava
Created_By :- |  | Sakshi
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To
2021-01-28 | DC PMS ServiceRequest_TC21 | Bug ID_1 |  | User is already logged in and is on New Service Request page. | User is already logged in and is on New Service Request page. | 1) Select agreement number for Agreement Number field. | Plan Type-123cxgsgsd |  | High | High | New | Apurwa
2021-01-29 | DC PMS ServiceRequest_TC22 | Bug ID_2 |  | User is already logged in and is on New Service Request page. | User is already logged in and is on New Service Request page. | 1)Enter invalid data in PLAN TYPE filed 2)Enter valid details in all the remaining fields 3)Click on Save button |  |  | High | High | New | Apurwa
2021-01-30 | DC PMS ServiceRequest_TC24 | Bug ID_3 |  | User is able to Create new Service Request by Selecting the previous date of Service Package Start Date for the Job Card field | User is already logged in and is on New Service Request page. | 1)Select Privious Date of Service Package Start Date in the Date of Job Card Filed 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 |  | High | High | Fixed | Apurwa
2021-01-31 | DC PMS ServiceRequest_TC26 | Bug ID_4 |  | There is minor word spacing mistake of Job Card while selecting the date more than than 15 days from the current date | User is already logged in and is on New Service Request page. | 1)Select 15 days back date from the Current date 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -13/01/2021 |  | High | High | Deferred | Apurwa
2021-02-02 | DC PMS ServiceRequest_TC28 | Bug ID_6 |  | User is able to Create new Service Request by Selecting the previous date of Vehicle Delivery Date for the Job Card field | User is already logged in and is on New Service Request page. | 1)Enter Odometer less than Service Package Start Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -10 |  | High | High | Fixed | Apurwa
2021-02-03 | DC PMS ServiceRequest_TC29 | Bug ID_7 |  | "Assigned To Not valid" validation messages is showing | User is already logged in and is on New Service Request page. | 1)Enter Odometer Greater than Service Package End Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -60000 |  | High | High | New | Apurwa
2021-02-04 | DC PMS ServiceRequest_TC30 | Bug ID_8 |  | "Assigned To Not valid" validation messages is showing | User is already logged in and is on New Service Request page. | 1)Enter Current Visit Odometer Reading greater than Service Package End Kms 2)Select the Current PMS Visit | 1.Current Visit Odometer Reading-60000 2.Current PMS Visit -50000 or 60 months |  | High | High | Fixed | Apurwa
2021-02-05 | DC PMS ServiceRequest_TC31 | Bug ID_9 |  | Service request is created when user is selecting Current PMS Visit Less than Current odometer | User is already logged in and is on New Service Request page. | 1)Enter Current Visit Odometer Reading greater than Service Package End Kms 2)Select the Current PMS Visit | 1.Current Visit Odometer Reading-40000 2.Current PMS Visit -40000 or 48 months |  | High | High | Fixed | Apurwa
2021-02-10 | DC PMS ServiceRequest_TC37 | Bug ID_14 |  | There is missing the Occurrence Column in the Grid, | User is already logged in and is on New Service Request page. | Matching the Grid section with master shared |  |  | High | High | Deferred | Apurwa
2021-02-11 | DC PMS ServiceRequest_TC39 | Bug ID_15 |  | there is no need of placing the Separate column of Labour Unit Rate and Labour MRP Rate | User is already logged in and is on New Service Request page. | Check the Grid section |  |  | High | High | Fixed | Apurwa
2021-02-12 | DC PMS ServiceRequest_TC41 | Bug ID_16 |  | User is able to Sace the service request by entering the invalid data for the Part No. | User is already logged in and is on New Service Request page. | 1.Select the Part name 2.Clear all the data and Enter the invalid data for HSN/SAC Code 3)Click on save Button |  |  | High | High |  | Apurwa
2021-02-13 | DC PMS ServiceRequest_TC42 | Bug ID_17 |  | User is able to Sace the service request by entering the invalid data for the Part No. | User is already logged in and is on New Service Request page. | Check the Grid Section |  |  | High | High | Fixed | Apurwa
2021-02-14 | DC PMS ServiceRequest_TC43 | Bug ID_18 |  | Two times of part name is coming in the grid | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  |  | High | High | Fixed | Apurwa
2021-02-15 | DC PMS ServiceRequest_TC44 | Bug ID_19 |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  |  | High | High | New | Apurwa
2021-02-16 | DC PMS ServiceRequest_TC45 | Bug ID_20 |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero | User is already logged in and is on New Service Request page. | 1)Selecting the Part No one by one and check the grand Total at the same |  |  | High | High | New | Apurwa
2021-02-17 | DC PMS ServiceRequest_TC46 | Bug ID_21 |  | Calculating only the MRP not Labour while creating the Service Request | User is already logged in and is on New Service Request page. | Upload the VIN # photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | High | High | New | Apurwa
2021-02-18 | DC PMS ServiceRequest_TC51 | Bug ID_22 |  | Sequencing of the document after saving the claim gets change. | User is already logged in and is on New Service Request page. | Upload the VIN # photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | High | High | New | Apurwa
2021-02-20 | NC PMS ServiceRequest_TC22 | Bug ID_24 |  | Claim is getting punched when user is entering invalid data in Plan Type field |  | 1)Enter invalid data in PLAN TYPE filed 2)Enter valid details in all the remaining fields 3)Click on Save button | Plan Type-123cxgsgsd |  | High | High | New | Apurwa
2021-02-21 | NC PMS ServiceRequest_TC24 | Bug ID_25 |  | User is able to Create new Service Request by Selecting the previous date of Service Package Start Date for the Job Card field |  | 1)Select Privious Date of Service Package Start Date in the Date of Job Card Field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 |  | High | High | Fixed | Apurwa
2021-02-22 | NC PMS ServiceRequest_TC26 | Bug ID_26 |  | There is minor word spacing mistake of Job Card while selecting the date more than than 15 days from the current date |  | 1).Check the spelling and space |  |  | High | High | Suggestions | Apurwa
2021-02-23 | NC PMS ServiceRequest_TC27 | Bug ID_27 |  | User is able to Create new Service Request by Selecting the previous date of Vehicle Delivery Date for the Job Card field |  | 1)Select Privious Date of Vehicle Delivery Date in the Date of Job Card Filed 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 |  | High | High | Fixed | Apurwa
2021-02-24 | DC PMS ServiceRequest_TC28 | Bug ID_28 |  | Accepting Privious Date of Previous PMS Visit Date in the Date of Job Card Field and user is able to save the claim |  | 1)Select Privious Date of Previous PMS Visit Date in the Date of Job Card Field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | (Previous PMS Visit Date-15-01-2021) Date of Job Card-14-01-2021 |  | High | High | Fixed | Apurwa
2021-02-25 | DC PMS ServiceRequest_TC29 | Bug ID_29 |  | User is able to punch by entering Odometer reading in the Current odometer reading Field Less than Service Package Start Kms |  | 1)Enter Odometer less than Service Package Start Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Current Visit Odometer Reading -1000 |  | High | High | Fixed | Apurwa
2021-02-26 | DC PMS ServiceRequest_TC30 | Bug ID_30 |  | User is able to create new service request by entering odometer in Current Odometer Redaing greater than Service Package End KMS |  | 1)Enter Odometer Greater than Service Package End Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -5020 |  | High | High | Fixed | Apurwa
2021-02-27 | DC PMS ServiceRequest_TC31 | Bug ID_31 |  | User is able to create new agreement by selecting by selecting the incorrect Current PMS Vist in terms of Current odometer Reading |  | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-30000 Current PMS Visit -10000 or 12 months |  | High | High | Deferred | Apurwa
2021-03-01 | DC PMS ServiceRequest_TC33 | Bug ID_33 |  | "Your are not in valid plan" validation messages is showing "Your are not in valid plan" and system is asking the select the agreement number again |  | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-30000 Current PMS Visit -40000 or 12 months |  | High | High |  | Apurwa
2021-03-02 | DC PMS ServiceRequest_TC34 | Bug ID_34 |  | validation messages is showing "Your are not in valid plan" and system is asking the select the agreement number again |  | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-40000 Current PMS Visit -50000 or 60 months |  | High | High | New | Apurwa
2021-03-03 | DC PMS ServiceRequest_TC38 | Bug ID_35 |  | Claim is getting punched when user is already availed the odometer |  | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-49000 Current PMS Visit -40000 or 48 months |  | High | High | Fixed | Apurwa
2021-03-05 | DC PMS ServiceRequest_TC41 | Bug ID_37 |  | there is no need of placing the Separate column of Labour Unit Rate and Labour MRP Rate |  | Check the Grid section |  |  | High | High | Fixed | Apurwa
2021-03-06 | DC PMS ServiceRequest_TC43 | Bug ID_38 |  | User is able to Save the service request by entering the invalid data for the Part No. |  | 1.Select the Part name 2.Clear all the data and Enter the invalid data for Part No 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd |  | High | High | New | Apurwa
2021-03-07 | DC PMS ServiceRequest_TC44 | Bug ID_39 |  | User is able to Save the service request by entering the invalid data for the Part No. |  | 1.Select the Part name 2.Clear all the data and Enter the invalid data for HSN/SAC Code 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd |  | High | High | Deferred | Apurwa
2021-03-08 | DC PMS ServiceRequest_TC45 | Bug ID_40 |  | Two times of part name is coming in the grid |  | Check the Grid Section |  |  | High | High | Fixed | Apurwa
2021-03-09 | DC PMS ServiceRequest_TC46 | Bug ID_41 |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero |  | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  |  | High | High |  | Apurwa
2021-03-11 | DC PMS ServiceRequest_TC48 | Bug ID_43 |  | Calculating only the MRP not Labour while creating the Service Request |  | 1)Selecting the Part No one by one and check the grand Total at the same |  |  | High | High | Fixed | Apurwa
2021-03-12 | DC PMS ServiceRequest_TC53 | Bug ID_44 |  | Sequencing of the document after saving the claim gets change. |  |  |  |  | High | High | Suggestions | Apurwa

## DC PMS SP
Project Name: NISSAN
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2021-01-20 |  | Review Date:-
Version: - |  |  | Module:- | SP-Claims |  | Power ID: | 13762
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
DC PMS ServiceRequest_TC1 | To verify if the user is able to click and view PMS - Service Request dropdowns by clicking on PMS - Service Request option available at the menu section. | User is already logged in | 1)Click on the PMS - Service Request option available at the menu section. | https://nissanphp7.innov.co.in/index.php?module=Campaigns&view=Detail&record=431994 |  |  | User should be able to click and view the PMS - Service Request options as : 1)DC PMS - Service Request 2)NC PMS - Service Request |  |  | pass
DC PMS ServiceRequest_TC2 | To verify if the User is able to get navigate to the DC PMS - Service Request page. | User is already logged in | 1)Click on the PMS - Service Request option available at the menu section. 2)Click on the DC PMS - Service Request option. | NA |  |  | Nissan Care-Sales page should get open having following fields and buttons : 1)Actions (Dropdown) 2)Courier details update(Button) 3)Add Service Request 4)Total DC PMS - Service Request (Filter/Dropdown) 5)Refresh (Icon) 6)Next Page (Icon) 7)Page Jump (Icon) 8)Next Page (Icon) 9)Settings (Button) 10)Quick Create(+) (Button) |  |  | pass
DC PMS ServiceRequest_TC3 | To verify if the User is able to get navigate to the Add Service Request page. | User is already logged in | 1)Click on the PMS - Service Request button from the menu section. 2)Click on the DC PMS - Service Request button option. 3)Click on Add Service Request button. | NA |  |  | Create New Datsun Care - Service Request should get open having Service Request related fields and Save and Cancel button. |  |  | pass
DC PMS ServiceRequest_TC4 | To verify if the User is able to create new Service Request by leaving all the mandatory fields blank. | User is already logged in and is on Create New Datsun Care - Service Request page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. | NA |  |  | User should not be able to create a new Service Request and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
DC PMS ServiceRequest_TC5 | To verify if the User is able to create new Service Request by leaving Agreement Number field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Agreement Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Agreement Number field "Agreement Number is required." |  |  | pass
DC PMS ServiceRequest_TC6 | To verify if the User is able to create new Service Request by leaving Job Card No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Job Card No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Job Card No field " Job Card No is required." |  |  | pass
DC PMS ServiceRequest_TC7 | To verify if the User is able to create new Service Request by leaving Date of Job Card field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Date of Job Card field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Date of Job Card field as " Date of Job Card is required." |  |  | pass
DC PMS ServiceRequest_TC8 | To verify if the User is able to create new Service Request by leaving Current Visit Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Current Visit Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Current Visit Odometer Reading field as Current Visit Odometer Reading is required." |  |  | pass
DC PMS ServiceRequest_TC9 | To verify if the User is able to create new Service Request by leaving the Current PMS Visit field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Current PMS Visit field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Current PMS Visit field as "Current PMS Visitis required." |  |  | pass
DC PMS ServiceRequest_TC10 | To verify if the User is able to create new Service Request by leaving the Warranty Admin Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Warranty Admin Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Warranty Admin Name field as " Warranty Admin Namefield is required." |  |  | pass
DC PMS ServiceRequest_TC11 | To verify if the User is able to create new Service Request by leaving the Dealer Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Email field as " Dealer Email is required." |  |  | pass
DC PMS ServiceRequest_TC12 | To verify if the User is able to create new Service Request by leaving the Dealer Contact No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Contact No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Contact No field as " Dealer Contact No is required." |  |  | pass
DC PMS ServiceRequest_TC13 | To verify if the User is able to create new Service Request by leaving the Dealer Comment field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Comment field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Comment field as " Dealer Comment is required." |  |  | pass
DC PMS ServiceRequest_TC14 | To verify if the User is able to create new Service Request by entering invalid data in Agreement Number and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Agreement Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Invalid data: Blank spaces as characters, Special characters and numbers. |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Agreement Number field as "Invalid Agreement Number." |  |  | pass
DC PMS ServiceRequest_TC15 | To verify if the User is able to create new Service Request by entering invalid data in Job Card No and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Job Card No field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Invalid data: Blank spaces as characters, Special characters and numbers. |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Job Card No field as "Invalid Job Card No." |  |  | pass
DC PMS ServiceRequest_TC16 | To verify if the User is able to create new Service Request by entering invalid data in Date of Job Card and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Date of Job Card. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Date of Job Card field as "Invalid Date of Job Card." |  |  | pass
DC PMS ServiceRequest_TC17 | To verify if the User is able to create new Service Request by entering invalid data in Current Visit Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Current Visit Odometer Reading. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Current Visit Odometer Reading as "Invalid Current Visit Odometer Reading." |  |  | pass
DC PMS ServiceRequest_TC18 | To verify if the User is able to create new Service Request by entering invalid data in Warranty Admin Name and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Warranty Admin Name . 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Warranty Admin Name as "Invalid Warranty Admin Name." |  |  | pass
DC PMS ServiceRequest_TC19 | To verify if the User is able to create new Service Request by entering invalid data in Dealer Email and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Dealer Email. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Dealer Email as "Invalid Dealer Email." |  |  | pass
DC PMS ServiceRequest_TC20 | To verify if the User is able to create new Service Request by entering invalid data in Dealer Contact No and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Dealer Contact No. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Dealer Contact No. as "Invalid Dealer Contact No." |  |  | pass
DC PMS ServiceRequest_TC21 | To verify if the User is able to create new Service Request by entering selecting the Agreement Number | User is already logged in and is on New Service Request page. | 1) Select agreement number for Agreement Number field. | Agreement number-SO245441 | Plan Type Filed is Editable and also Parent Agreement number is blank while Creating the New Service Request |  | All the agreement details should get auto populated in the respective fields and should not Editable |  |  | pass
DC PMS ServiceRequest_TC22 | To verify if the User is able to Create new Service Request by Eneting Invalid data in PLAN TYPE field and enter valid details in all the remaining fields | User is already logged in and is on New Service Request page. | 1)Enter invalid data in PLAN TYPE filed 2)Enter valid details in all the remaining fields 3)Click on Save button | Plan Type-123cxgsgsd | Claim is getting punched when user is entering invalid data in Plan Type field |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data. |  |  | pass
DC PMS ServiceRequest_TC23 | Service Package History-To verify if Usesr is able to create new Service Request by entering Valid in Job Card No and Enter valid data in the remaining fields | User is already logged in and is on New Service Request page. | 1)Enter valid data in Job Card No 2)Enter valid data in the remaining fields 3)Click on SAVE button | Job Card No -RO123456789000 |  |  | User should be able to create new Service Request |  |  | pass
DC PMS ServiceRequest_TC24 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select Privious Date of Service Package Start Date in the Date of Job Card Filed 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 | User is able to Create new Service Request by Selecting the previous date of Service Package Start Date for the Job Card field |  | User should not able select the Create the New Service Request and aslo should not accept the Previous date Service Package Start Date in the Date of Job Card Filed and should have a proper validation message "Your Date of Job Card less than Service Package Start Date." |  |  | pass
DC PMS ServiceRequest_TC25 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select 15 days back date from the Current date 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -13/01/2021 | Validation Message"Jobcard date should be in between last 15 days." |  | Date of job card should not accept the 15 days back date from the Current and have a proper validation Message "Jobcard date should be in between last 15 days." |  |  | pass
DC PMS ServiceRequest_TC26 | To veify the Pop up for validation message | User is already logged in and is on New Service Request page. | 1).Check the spelling and space |  | There is minor word spacing mistake of Job Card while selecting the date more than than 15 days from the current date |  | Validation messaage should be "Job card date should be in between last 15 days" |  |  | pass
DC PMS ServiceRequest_TC27 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select Privious Date of Vehicle Delivery Date in the Date of Job Card Filed 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 | User is able to Create new Service Request by Selecting the previous date of Vehicle Delivery Date for the Job Card field |  | User should not able select the Create the New Service Request and aslo should not accept the Previous date of Vehicle Delivery Date in the Date of Job Card Filed |  |  | pass
DC PMS ServiceRequest_TC28 | Service Package History-To verify if User is able to create new Service Request by entering Current Visit Odometer Reading Field less than Service package Start Kms | User is already logged in and is on New Service Request page. | 1)Enter Odometer less than Service Package Start Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -10 | "Assigned To Not valid" validation messages is showing |  | User should not be able to Create New Service Request and should have a proper validation message "Please Enter greater than Service Package Start KM " |  |  | pass
DC PMS ServiceRequest_TC29 | Service Package History-To verify if User is able to create new Service Request by entering Current Visit Odometer Reading Field Greater than Service package End Kms | User is already logged in and is on New Service Request page. | 1)Enter Odometer Greater than Service Package End Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -60000 | "Assigned To Not valid" validation messages is showing |  | User should not be able to Create New Service Request and should have a proper validation message "Please Enter Less than Service Package End KM " |  |  | pass
DC PMS ServiceRequest_TC30 | Service Package History(Agreement Number SO245399)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field | User is already logged in and is on New Service Request page. | 1)Enter Current Visit Odometer Reading greater than Service Package End Kms 2)Select the Current PMS Visit | 1.Current Visit Odometer Reading-60000 2.Current PMS Visit -50000 or 60 months | Service request is created when user is selecting Current PMS Visit Less than Current odometer |  | User should not be able to create new Service Request and should have a proper valdation message |  |  | pass
DC PMS ServiceRequest_TC31 | Service Package History(Agreement Number SO245449)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field | User is already logged in and is on New Service Request page. | 1)Enter Current Visit Odometer Reading greater than Service Package End Kms 2)Select the Current PMS Visit | 1.Current Visit Odometer Reading-40000 2.Current PMS Visit -40000 or 48 months | "you have select the 40000 so that 10000 20000 30000 has been lapse. please confirm for proceed and cancel for select other one" Validation message is appearing |  | User should not be able to create new Service Request and should have a proper valdation message |  |  | pass
DC PMS ServiceRequest_TC32 | Service Package History(Agreement Number SO245449)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field again(Second time) | User is already logged in and is on New Service Request page. | 1)Enter Current Visit Odometer Reading same as Previous PMS Visit Odometer Reading 2)Select the Current PMS Visit same as Previous PMS Visit Odometer Reading | 1.Current Visit Odometer Reading-40000 2.Current PMS Visit -40000 or 48 months | User is able to create new service request by entering same reading in second time |  | User should not be able to create new service request and should have a proper validation message |  |  | pass
DC PMS ServiceRequest_TC33 | Service Package History(Agreement Number SO245449)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field again(Third time) | User is already logged in and is on New Service Request page. | 1)select same agreement number |  |  |  | User should redirect to the Creating New Datsun Care - Service Request with the details of Service Package History |  |  | pass
DC PMS ServiceRequest_TC34 | To verify the Service Package History section | User is already logged in and is on New Service Request page. | 1)check the Service Package History section |  | Service Package History showing the details and Already Service Labour is already selected |  | Service Package History section should have the following columns: Service Package Plan Service Request Status Service Request Date Service Request# Odometer Reading Total amount |  |  | pass
DC PMS ServiceRequest_TC35 | Service Package History section-To verify the Service Package Plan | User is already logged in and is on New Service Request page. | Matching the details which was entered previously |  | If user is entering the Current odometer reading 40000 then in SP History section showing 10000, 20000, and 30000 is lapsed |  | Service package plan should reflect the data which is previously enterd by the users |  |  | pass
DC PMS ServiceRequest_TC36 | Service Package History section-To verify the Service Package Plan by entering the Current Visit Odometer Reading Field again for the same agreement number | User is already logged in and is on New Service Request page. | Enter same details which was previsouly enterd and click on save | 1.Current Visit Odometer Reading-40000 2.Current PMS Visit -40000 or 48 months | Claim punched, Job Card Information , dealer Information updated with last entered data but Service Package History section is not updated amd also user is bale to create Service request multiple times against same agreement number |  | user should not able to claim once all the Services(Odometer) availed |  |  | pass
DC PMS ServiceRequest_TC37 | To verify the Periodic Maintenance by selecting the Agreement number -SO245457 | User is already logged in and is on New Service Request page. | Matching the Grid section with master shared |  | There is missing the Occurrence Column in the Grid, |  | Periodic Maintenance should be same as the master shared by the Client |  |  | pass
DC PMS ServiceRequest_TC38 | To verify the Periodic Maintenance by selecting the Agreement number -SO245457 | User is already logged in and is on New Service Request page. | Check the column which has to be Non edtitable and freezed |  | Part name, Type,Sgst%,SGST Amount ,CGST% ,CGST Amount ,IGST%,IGST Amount ,MRP,Labour MRP Rate is non editable |  | User should not be able Edit the non Editable column in the Grid as per the Client |  |  | pass
DC PMS ServiceRequest_TC39 | To verify the Periodic Maintenance by selecting the Agreement number -SO245457 | User is already logged in and is on New Service Request page. | Check the Grid section |  | there is no need of placing the Separate column of Labour Unit Rate and Labour MRP Rate |  | the data can be Autopopulate in the Unit Price/Labour for Labour Unit Rate and the data Autopopulate in the MRP for the Labour MRP Rate as per the City Classification |  |  | pass
DC PMS ServiceRequest_TC40 | To verify the Periodic Maintenance by selecting the Agreement number -SO245457 | User is already logged in and is on New Service Request page. | Check the MRP Column by calculating manually | Unit/Price*Qty=GST%=MRP | Calculation is correct |  | Calculation should be correct |  |  | pass
DC PMS ServiceRequest_TC41 | Periodic Maintenance - To verify if user is able to select the Part name , | User is already logged in and is on New Service Request page. | 1.Select the Part name 2.Clear all the data and Enter the invalid data for Part No 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd | User is able to Sace the service request by entering the invalid data for the Part No. |  | System should not allow to Enter the invalid data in the Part No, it should accept only the Alphanumeric value |  |  | pass
DC PMS ServiceRequest_TC42 | Periodic Maintenance - To verify if user is able to select the Part name , | User is already logged in and is on New Service Request page. | 1.Select the Part name 2.Clear all the data and Enter the invalid data for HSN/SAC Code 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd | User is able to Sace the service request by entering the invalid data for the Part No. |  | System should not allow to Enter the invalid data in the Part No, it should accept only the Alphanumeric value |  |  | pass
DC PMS ServiceRequest_TC43 | To verify the Periodic Maintenance by selecting the Agreement number -SO245449 | User is already logged in and is on New Service Request page. | Check the Grid Section |  | Two times of part name is coming in the grid |  | Grid should be same as Master and auto populate according to the Service Done (0k & 10k), Plan should be different as per the Service Done |  |  | pass
DC PMS ServiceRequest_TC44 | Periodic Maintenance- to verify by if the user is able to save the service request without entering data in the Unit Price/Labour | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero |  | User ishould not be able to create the service request and should have a proper validation message to fill Qty column |  |  | pass
DC PMS ServiceRequest_TC45 | Periodic Maintenance- to verify by if the user is able to save the service request without entering data in the Unit Price/Labour | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero and also saving the Claim without entering any Data in the Part No. Field for Labour |  | User ishould not be able to create the service request and should have a proper validation message to fill Qty column |  |  | pass
DC PMS ServiceRequest_TC46 | To verify the Grand total by selecting the Part No one by one | User is already logged in and is on New Service Request page. | 1)Selecting the Part No one by one and check the grand Total at the same |  | Calculating only the MRP not Labour while creating the Service Request |  | Grand total value should get calculated when user is selecting the Part No and also add Labour Price at the same time |  |  | pass
DC PMS ServiceRequest_TC47 | Documents-To verify by the Uploading Job card copy | User is already logged in and is on New Service Request page. | Upload the Job card copy and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Job card copy and able to create new Service Request |  |  | pass
DC PMS ServiceRequest_TC48 | Documents-To verify by the Uploading Vehicle History | User is already logged in and is on New Service Request page. | Upload the Vehicle History and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Job card copy and able to create new Service Request |  |  | pass
DC PMS ServiceRequest_TC49 | Documents-To verify by the Uploading Upload Final Tax Invoice | User is already logged in and is on New Service Request page. | Upload the Upload Final Tax Invoice and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Upload Final Tax Invoice and able to create new Service Request |  |  | pass
DC PMS ServiceRequest_TC50 | Documents-To verify by the Uploading Odometer reading photo | User is already logged in and is on New Service Request page. | Upload the Odometer reading photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Odometer reading photo and able to create new Service Request |  |  | pass
DC PMS ServiceRequest_TC51 | Documents-To verify by the Uploading VIN # photo | User is already logged in and is on New Service Request page. | Upload the VIN # photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Sequencing of the document after saving the claim gets change. |  | User should be able upload the VIN # photo and able to create new Service Request |  |  | pass

## NC PMS SP
Project Name: NISSAN
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2021-01-20 |  | Review Date:-
Version: - |  |  | Module:- | NC-PMS Service Request |  | Power ID: | 13762
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
NC PMS ServiceRequest_TC1 | To verify if the user is able to click and view PMS - Service Request dropdowns by clicking on PMS - Service Request option available at the menu section. | User is already logged in | 1)Click on the PMS - Service Request option available at the menu section. | https://nissanphp7.innov.co.in/index.php?module=Campaigns&view=Detail&record=431994 |  |  | User should be able to click and view the PMS - Service Request options as : 1)DC PMS - Service Request 2)NC PMS - Service Request | High | High | pass
NC PMS ServiceRequest_TC2 | To verify if the User is able to get navigate to the NC PMS - Service Request page. | User is already logged in | 1)Click on the PMS - Service Request option available at the menu section. 2)Click on the NC PMS - Service Request option. | NA |  |  | Nissan Care-Sales page should get open having following fields and buttons : 1)Actions (Dropdown) 2)Courier details update(Button) 3)Add Service Request 4)Total DC PMS - Service Request (Filter/Dropdown) 5)Refresh (Icon) 6)Next Page (Icon) 7)Page Jump (Icon) 8)Next Page (Icon) 9)Settings (Button) 10)Quick Create(+) (Button) | High | High | pass
NC PMS ServiceRequest_TC3 | To verify if the User is able to get navigate to the Add Service Request page. | User is already logged in | 1)Click on the PMS - Service Request button from the menu section. 2)Click on the NC PMS - Service Request button option. 3)Click on Add Service Request button. | NA |  |  | Create New Datsun Care - Service Request should get open having Service Request related fields and Save and Cancel button. | High | High | pass
NC PMS ServiceRequest_TC4 | To verify if the User is able to create new Service Request by leaving all the mandatory fields blank. | User is already logged in and is on Create New Datsun Care - Service Request page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. | NA |  |  | User should not be able to create a new Service Request and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. | High | High | pass
NC PMS ServiceRequest_TC5 | To verify if the User is able to create new Service Request by leaving Agreement Number field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Agreement Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Agreement Number field "Agreement Number is required." | High | High | pass
NC PMS ServiceRequest_TC6 | To verify if the User is able to create new Service Request by leaving Job Card No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Job Card No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Job Card No field " Job Card No is required." | High | High | pass
NC PMS ServiceRequest_TC7 | To verify if the User is able to create new Service Request by leaving Date of Job Card field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Date of Job Card field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Date of Job Card field as " Date of Job Card is required." | High | High | pass
NC PMS ServiceRequest_TC8 | To verify if the User is able to create new Service Request by leaving Current Visit Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Current Visit Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Current Visit Odometer Reading field as Current Visit Odometer Reading is required." | High | High | pass
NC PMS ServiceRequest_TC9 | To verify if the User is able to create new Service Request by leaving the Current PMS Visit field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Current PMS Visit field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Current PMS Visit field as "Current PMS Visitis required." | High | High | pass
NC PMS ServiceRequest_TC10 | To verify if the User is able to create new Service Request by leaving the Warranty Admin Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Warranty Admin Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Warranty Admin Name field as " Warranty Admin Namefield is required." | High | High | pass
NC PMS ServiceRequest_TC11 | To verify if the User is able to create new Service Request by leaving the Dealer Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Email field as " Dealer Email is required." | High | High | pass
NC PMS ServiceRequest_TC12 | To verify if the User is able to create new Service Request by leaving the Dealer Contact No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Contact No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Contact No field as " Dealer Contact No is required." | High | High | pass
NC PMS ServiceRequest_TC13 | To verify if the User is able to create new Service Request by leaving the Dealer Comment field blank and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Leave Dealer Comment field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | NA |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for Dealer Comment field as " Dealer Comment is required." | High | High | pass
NC PMS ServiceRequest_TC14 | To verify if the User is able to create new Service Request by entering invalid data in Agreement Number and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Agreement Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Invalid data: Blank spaces as characters, Special characters and numbers. |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Agreement Number field as "Invalid Agreement Number." | High | High | pass
NC PMS ServiceRequest_TC15 | To verify if the User is able to create new Service Request by entering invalid data in Job Card No and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Job Card No field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Invalid data: Blank spaces as characters, Special characters and numbers. |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Job Card No field as "Invalid Job Card No." | High | High | pass
NC PMS ServiceRequest_TC16 | To verify if the User is able to create new Service Request by entering invalid data in Date of Job Card and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Date of Job Card. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Date of Job Card field as "Invalid Date of Job Card." | High | High | pass
NC PMS ServiceRequest_TC17 | To verify if the User is able to create new Service Request by entering invalid data in Current Visit Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Current Visit Odometer Reading. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Current Visit Odometer Reading as "Invalid Current Visit Odometer Reading." | High | High | pass
NC PMS ServiceRequest_TC18 | To verify if the User is able to create new Service Request by entering invalid data in Warranty Admin Name and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Warranty Admin Name . 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Warranty Admin Name as "Invalid Warranty Admin Name." | High | High | pass
NC PMS ServiceRequest_TC19 | To verify if the User is able to create new Service Request by entering invalid data in Dealer Email and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Dealer Email. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Dealer Email as "Invalid Dealer Email." | High | High | pass
NC PMS ServiceRequest_TC20 | To verify if the User is able to create new Service Request by entering invalid data in Dealer Contact No and enter valid details in the remaining fields. | User is already logged in and is on New Service Request page. | 1) Enter invalid data in Dealer Contact No. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data in Dealer Contact No. as "Invalid Dealer Contact No." | High | High | pass
NC PMS ServiceRequest_TC21 | To verify if the User is able to create new Service Request by entering selecting the Agreement Number and verify Creating New Nissan Care - Service Request | User is already logged in and is on New Service Request page. | 1) Select agreement number for Agreement Number field. | Agreement number-SO245448 | Plan Type Filed is Editable Parent Agreement Number is same as Agreement number |  | All the agreement details should get auto populated in the respective fields and should not Editable | High | High | pass
NC PMS ServiceRequest_TC22 | To verify if the User is able to Create new Service Request by Entering Invalid data in PLAN TYPE field and enter valid details in all the remaining fields | User is already logged in and is on New Service Request page. | 1)Enter invalid data in PLAN TYPE filed 2)Enter valid details in all the remaining fields 3)Click on Save button | Plan Type-123cxgsgsd | Claim is getting punched when user is entering invalid data in Plan Type field |  | User should not be able to create new Service Request and the system must display a proper and specific validation message for entering invalid data. | High | High | pass
NC PMS ServiceRequest_TC23 | Service Package History-To verify if Usesr is able to create new Service Request by entering Valid in Job Card No and Enter valid data in the remaining fields | User is already logged in and is on New Service Request page. | 1)Enter valid data in Job Card No 2)Enter valid data in the remaining fields 3)Click on SAVE button | Job Card No -RO123456789000 |  |  | User should be able to create new Service Request | High | High | pass
NC PMS ServiceRequest_TC24 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select Privious Date of Service Package Start Date in the Date of Job Card Field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 | User is able to Create new Service Request by Selecting the previous date of Service Package Start Date for the Job Card field |  | User should not able select the Create the New Service Request and aslo should not accept the Previous date Service Package Start Date in the Date of Job Card Filed and should have a proper validation message "Your Date of Job Card less than Service Package Start Date." | High | High | pass
NC PMS ServiceRequest_TC25 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select 15 days back date from the Current date 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -13/01/2021 | Validation Message"Jobcard date should be in between last 15 days." |  | Date of job card should not accept the 15 days back date from the Current and have a proper validation Message "Jobcard date should be in between last 15 days." | High | High | pass
NC PMS ServiceRequest_TC26 | To verify the Pop up for validation message | User is already logged in and is on New Service Request page. | 1).Check the spelling and space |  | There is minor word spacing mistake of Job Car |  | Validation messaage should be "Job card date should be in between last 15 days" | High | High | pass
NC PMS ServiceRequest_TC27 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card | User is already logged in and is on New Service Request page. | 1)Select Privious Date of Vehicle Delivery Date in the Date of Job Card Filed 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job card -16/01/2021 | User is able to Create new Service Request by Selecting the previous date of Vehicle Delivery Date for the Job Card field |  | User should not able select the Create the New Service Request and aslo should not accept the Previous dateVehicle Delivery Date in the Date of Job Card Filed | High | High | pass
NC PMS ServiceRequest_TC28 | Service Package History- To verify if User is able to create new Service Request by selecting the date for Date of Job Card |  | 1)Select Privious Date of Previous PMS Visit Date in the Date of Job Card Field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | (Previous PMS Visit Date-15-01-2021) Date of Job Card-14-01-2021 | Accepting Privious Date of Previous PMS Visit Date in the Date of Job Card Field and user is able to save the claim |  | User should not able to Create the New Service Request and aslo should not accept the Privious Date of Previous PMS Visit Date in the Date of Job Card Field and should have a proper validation message "Your Date of Job Card less than Service Package Start Date." | High | High | pass
NC PMS ServiceRequest_TC29 | Service Package History-To verify if User is able to create new Service Request by entering Current Visit Odometer Reading Field less than Service package Start Kms | User is already logged in and is on New Service Request page. | 1)Enter Odometer less than Service Package Start Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Current Visit Odometer Reading -1000 | User is able to punch by entering Odometer reading in the Current odometer reading Field Less than Service Package Start Kms |  | User should not be able to Create New Service Request and should have a proper validation message "Please Enter greater than Service Package Start KM " | High | High | pass
NC PMS ServiceRequest_TC30 | Service Package History(Agreement number SO245439)-To verify if User is able to create new Service Request by entering Current Visit Odometer Reading Field Greater than Service package End Kms | User is already logged in and is on New Service Request page. | 1)Enter Odometer Greater than Service Package End Kms 2)Enter valid details in the remianing fields. 3)Click On Save Button. | * Current Visit Odometer Reading -5020 | User is able to create new service request by entering odometer in Current Odometer Redaing greater than Service Package End KMS |  | User should not be able to Create New Service Request and should have a proper validation message "Please Enter Less than Service Package End KM " | High | High | pass
NC PMS ServiceRequest_TC31 | Service Package History(For Agreement number-SO245443)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-30000 Current PMS Visit -10000 or 12 months | User is able to create new agreement by selecting by selecting the incorrect Current PMS Vist in terms of Current odometer Reading |  | User should not be able to create new Service request and Current odometer reading should be equal to the Current PMS Visit | High | High | pass
NC PMS ServiceRequest_TC32 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-30000 Current PMS Visit -10000 or 12 months | User is able to create new agreement by selecting by selecting the incorrect Current PMS Vist in terms of Current odometer Reading |  | User should not be able to create new Service request and Current odometer reading should be equal to the Current PMS Visit | High | High | pass
NC PMS ServiceRequest_TC33 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-30000 Current PMS Visit -40000 or 12 months | "Your are not in valid plan" validation messages is showing "Your are not in valid plan" and system is asking the select the agreement number again |  | User should not be able to Create new Service request and should have a proper validation for the same | High | High | pass
NC PMS ServiceRequest_TC34 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-40000 Current PMS Visit -50000 or 60 months | validation messages is showing "Your are not in valid plan" and system is asking the select the agreement number again |  | User should not be able to Create new Service request and should have a proper validation for the same | High | High | pass
NC PMS ServiceRequest_TC35 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-40000 Current PMS Visit -50000 or 60 months | validation messages is showing "you have select the 50000 so that 10000 20000 30000 40000 10000 20000 30000 40000 has been lapse. please confirm for proceed and cancel for select other one" while selecting the Current PMS Visit |  | User should not be able to Create new Service request and should have a proper validation for the same | High | High | pass
NC PMS ServiceRequest_TC36 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-40000 Current PMS Visit -50000 or 60 months | validation messages is showing "Your plan out of range" and system is asking the select the agreement number again |  | User should not be able to Create new Service request and should have a proper validation for the same | High | High | pass
NC PMS ServiceRequest_TC37 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-45780 Current PMS Visit -40000 or 48 months |  |  | User should be able to Create new Service request | High | High | pass
NC PMS ServiceRequest_TC38 | Service Package History(For Agreement number-SO245433)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-49000 Current PMS Visit -40000 or 48 months | Claim is getting punched when user is already availed the odometer |  | When user is Availed the Odometer reading, User should not be able to create new service request | High | High | pass
NC PMS ServiceRequest_TC39 | Service Package History(For Agreement number-SO245420)-To verfiy if the user is able to create new Service Request by entering Current Visit Odometer Reading Field and selecting Current PMS Visit again | User is already logged in and is on New Service Request page. | 1)Enter Odometer Odometer 2)Select Current PMS Visit 3)Enter valid details in the remianing fields. 4)Click On Save Button. | Current Visit Odometer-49000 Current PMS Visit -40000 or 48 months | Claim is getting punched when user is already availed the odometer |  | When user is Availed the Odometer reading, User should not be able to create new service request | High | High | pass
NC PMS ServiceRequest_TC40 | To verify the Periodic Maintenance by selecting the Agreement number -SO245458 | User is already logged in and is on New Service Request page. | Check the column which has to be Non edtitable and freezed |  | Part name, Type,Sgst%,SGST Amount ,CGST% ,CGST Amount ,IGST%,IGST Amount ,MRP,Labour MRP Rate is non editable |  | User should not be able Edit the non Editable column in the Grid as per the Client | High | High | pass
NC PMS ServiceRequest_TC41 | To verify the Periodic Maintenance by selecting the Agreement number -SO245458 | User is already logged in and is on New Service Request page. | Check the Grid section |  | there is no need of placing the Separate column of Labour Unit Rate and Labour MRP Rate |  | the data can be Autopopulate in the Unit Price/Labour for Labour Unit Rate and the data Autopopulate in the MRP for the Labour MRP Rate as per the City Classification | High | High | pass
NC PMS ServiceRequest_TC42 | To verify the Periodic Maintenance by selecting the Agreement number -SO245458 | User is already logged in and is on New Service Request page. | Check the MRP Column by calculating manually | Unit/Price*Qty=GST%=MRP | Calculation is correct |  | Calculation should be correct | High | High | pass
NC PMS ServiceRequest_TC43 | Periodic Maintenance - To verify if user is able to select the Part name , | User is already logged in and is on New Service Request page. | 1.Select the Part name 2.Clear all the data and Enter the invalid data for Part No 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd | User is able to Save the service request by entering the invalid data for the Part No. |  | System should not allow to Enter the invalid data in the Part No, it should accept only the Alphanumeric value | High | High | pass
NC PMS ServiceRequest_TC44 | Periodic Maintenance - To verify if user is able to select the Part name , | User is already logged in and is on New Service Request page. | 1.Select the Part name 2.Clear all the data and Enter the invalid data for HSN/SAC Code 3)Click on save Button | Wheel Alignment &amp; Bal. -hdhfdhhffg Wiper Washer fluid -hdhfdhfd Engine Drain Washer -jdhjdfhjfd | User is able to Sace the service request by entering the invalid data for the Part No. |  | System should not allow to Enter the invalid data in the Part No, it should accept only the Alphanumeric value | High | High | pass
NC PMS ServiceRequest_TC45 | To verify the Periodic Maintenance by selecting the Agreement number SO245458 | User is already logged in and is on New Service Request page. | Check the Grid Section |  | Two times of part name is coming in the grid |  | Grid should be same as Master and auto populate according to the Service Done (0k & 10k), Plan should be different as per the Service Done | High | High | pass
NC PMS ServiceRequest_TC46 | Periodic Maintenance- to verify by if the user is able to save the service request without entering data in the Unit Price/Labour | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero |  | User ishould not be able to create the service request and should have a proper validation message to fill Qty column | High | High | pass
NC PMS ServiceRequest_TC47 | Periodic Maintenance- to verify by if the user is able to save the service request without entering data in the Unit Price/Labour | User is already logged in and is on New Service Request page. | 1)Tick all the Part No 2)Edit Qty Column 2)Clear the Data which is coming from the master 3)Click on Save |  | Incorrect pop up message is coming for entering the Qty and Unit Price/Labour Cloumn is auto filled with Zero and also User is bale to save the Cliam without Entering any data in Part no Field for Labour |  | User ishould not be able to create the service request and should have a proper validation message to fill Qty column | High | High | pass
NC PMS ServiceRequest_TC48 | To verify the Grand total by selecting the Part No one by one | User is already logged in and is on New Service Request page. | 1)Selecting the Part No one by one and check the grand Total at the same |  | Calculating only the MRP not Labour while creating the Service Request |  | Grand total value should get calculated when user is selecting the Part No and also add Labour Price at the same time | High | High | pass
NC PMS ServiceRequest_TC49 | Documents-To verify by the Uploading Job card copy | User is already logged in and is on New Service Request page. | Upload the Job card copy and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Job card copy and able to create new Service Request | High | High | pass
NC PMS ServiceRequest_TC50 | Documents-To verify by the Uploading Vehicle History | User is already logged in and is on New Service Request page. | Upload the Vehicle History and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Job card copy and able to create new Service Request | High | High | pass
NC PMS ServiceRequest_TC51 | Documents-To verify by the Uploading Upload Final Tax Invoice | User is already logged in and is on New Service Request page. | Upload the Upload Final Tax Invoice and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Upload Final Tax Invoice and able to create new Service Request | High | High | pass
NC PMS ServiceRequest_TC52 | Documents-To verify by the Uploading Odometer reading photo | User is already logged in and is on New Service Request page. | Upload the Odometer reading photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should be able upload the Odometer reading photo and able to create new Service Request | High | High | pass
NC PMS ServiceRequest_TC53 | Documents-To verify by the Uploading VIN # photo | User is already logged in and is on New Service Request page. | Upload the VIN # photo and 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Sequencing of the document after saving the claim gets change. |  | User should be able upload the VIN # photo and able to create new Service Request | p2 | High | pass

## Sheet1
url-http://13.127.206.20/nissan/index.php?module=Campaigns&view=Edit&userChoise=dc