## Summary
Mercedes Benz
Lead Dev: Ranjeet/Vikash Jha
Module | No. of test Written | No. of test executed | Pass | Fail
Restrict URL access - correction | 13 | 13 | 13 | 0
Approved_Claim_Amt-Dev | 14 | 14 | 8 | 6
Total | 13 | 13 | 13 | 6

## Bug Report
Bug Report
Project :- |  | Mercedes Benz
Created_By :- |  | Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Status on 21-02-2020 | Task ID- Retesting | Open | Close
2020-02-07 | NA | 1 | 11386 | Certificate Request: On uploading a PFD file of more than 5 mb in Final quick test loader keeps on loading and file does not get upload. |  |  |  |  | High | High | New | Apurwa
2020-02-07 | NA | 2 | 11386 | Agreement: User is able to validate the vin against a Vin number : WDC1569086L0009 which is having a certificate request status as Submitted. |  |  |  |  | High | High | New | Apurwa
2020-02-07 | NA | 3 | 11386 | Agreement: On selecting the * Certified Assurance Plan, its dependent fields like Certified Assurance Start Date Certified Assurance End Date Certified Assurance Start Kms Certified Assurance End Kms and Pricing Information should get auto populate. |  |  |  | https://prnt.sc/tadl32 | High | High | New | Apurwa
2020-03-07 | NA | 4 | 11417 | Claim: Dealer is able to create claim by selecting Service Request Date and Work Order Date less than the standard warranty start date and also less than the Certified Assurance Start Date. |  |  |  | https://prnt.sc/tb5q7q | High | High | New | Ranjeet
2020-03-07 | NA | 5 | 11417 | Claim:Dealer is able to create a claim by entering Service Requestnumber and Work Order # of an existing claim. |  |  |  | https://prnt.sc/tb6dsh Existing claim:https://prnt.sc/tb6epr | High | High | New | Ranjeet
2020-03-07 | NA | 6 | 11417 | Claim: Dealer is able to create a claim by entering a Repair Cost as "0" it should be greater than 0 |  |  |  | https://prnt.sc/tb6him | Low | Low | New | Ranjeet
2020-03-07 | NA | 7 | 11417 | Part Information :Dealer is able to add Part Information by entering "0" in MRP and Quantity field. |  |  |  |  | High | High | New | Ranjeet
2020-03-07 | NA | 8 | 11417 | Labour Information :Dealer is able to add Part Information by entering "0" in Operation Time in Minutes and Rate per Hour field. |  |  |  |  | High | High | New | Ranjeet
2020-03-07 | NA | 9 | 11417 | Miscellaneous Information :Dealer is able to add Part Information by entering "0" in Amount field. |  |  |  |  | High | High | New | Ranjeet

## Restrict URL access - correctio
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11384 | 2020-01-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=249643 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Edit&record=249643 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Detail&record=249659 http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249659 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11384 | 2020-01-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249454 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Re-purchase Functionality
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Re-purchase Functionality
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Re-purchase_Functionality_01 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Submitted. | Dealer is already logged-in |  | WDC1569086L0009 | Syatem shows validation message as "VIN Number already exists in the database.' |  | User should not be able to create a new certificate request with a vin number for which there is already a certificate request with status Submitted. |  |  | Fail
TC_Re-purchase_Functionality_02 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Answer By Dealer. | Dealer is already logged-in |  | WDC1569086L002075 | Syatem shows validation message as "VIN Number already exists in the database.' |  | User should not be able to create a new certificate request with a vin number for which there is already a certificate request with status Answer By Dealer.. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Query By Assurant. | Dealer is already logged-in |  | WDC1569086L002075 | Syatem shows validation message as "VIN Number already exists in the database.' |  | User should not be able to create a new certificate request with a vin number for which there is already a certificate request with status Query By Assurant. |  |  | Pass
TC_Re-purchase_Functionality_04 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Rejected. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Rejected.
TC_Re-purchase_Functionality_05 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approved. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Approved.
TC_Re-purchase_Functionality_06 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_07 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_08 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_09 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_10 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_11 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_12 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_13 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_14 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_15 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_16 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_17 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_18 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_19 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_20 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_21 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_22 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_23 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_24 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_25 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_26 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_27 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_28 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_29 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_30 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_31 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_32 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_33 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_34 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_35 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_36 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_37 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_38 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_39 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_40 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_41 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_01/Vin-Validation | 11386 | 2020-02-07 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Easy Care Sales link under menu item. 2)Click on Add easy care button. |  |  |  | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button)
TC_02/Vin-Validation | 11386 | 2020-02-07 | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. |  |  |  | System should display a validation message as "Vehicle Chassis No. is required."
TC_03/Vin-Validation | 11386 | 2020-02-07 | To verify if the user is able to validate Vehicle Chassis No. by entering invalid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. |  |  |  | Chassis no. not avaliable msg. should be displayed
TC_04/Vin-Validation | 11386 | 2020-02-07 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. |  |  |  | It should get validate successfully and a pop-up of Easy Care Agreement details should get appear with OK & Cancel button.
TC_05/Vin-Validation | 11386 | 2020-02-07 | To verify if the Cancel button on Easy Care Agreement details pop-up is working or not. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on Cancel button. |  |  |  | Process should get aborted.
TC_06/Vin-Validation | 11386 | 2020-02-07 | To verify if the User is able to get navigate to the Add Easy Care Agreement page by clicking on OK button on Easy Care Agreement details pop-up. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on OK button. |  |  |  | Creating New Easy Care page should get open having Easy Care Agreement related fields and Save and Cancel button.
TC_Agreement_01 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving all the mandatory fields blank. | User is already logged in and is on New Easy Care Agreement page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to create a new Easy Care Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required.
TC_Agreement_02 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for First Name field "First Name is required."
TC_Agreement_03 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required."
TC_Agreement_04 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required."
TC_Agreement_05 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required."
TC_Agreement_06 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required."
TC_Agreement_07 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required."
TC_Agreement_08 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for city field as "City is required."
TC_Agreement_09 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Vehicle Chasis No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Vehicle Chasis No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Vehicle Chasis No field as "Vehicle Chasis No is required."
TC_Agreement_10 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required."
TC_Agreement_11 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving State field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave State field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for State field as "State is required."
TC_Agreement_12 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required."
TC_Agreement_13 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required."
TC_Agreement_14 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Executive Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Executive Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Executive Name field as "Executive Name is required."
TC_Agreement_15 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Sales Manager Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales Manager Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales Manager Name field as "Sales Manager Name is required."
TC_Agreement_16 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Registration No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration No field as " Registration No is required."
TC_Agreement_17 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required."
TC_Agreement_18 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving Last Service Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Service Odometer Reading field as " Last Service Odometer Reading is required."
TC_Agreement_19 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving the REC Plan field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave REC Plan field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for REC Plan field as "REC Plan is required."
TC_Agreement_20 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by leaving REC Retail field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave REC Retail field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for REC Retail field as "REC Retail is required."
TC_Agreement_21 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in First Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in First Name field as "Invalid First Name."
TC_Agreement_22 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Last Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Name field as "Invalid Last Name."
TC_Agreement_23 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in GSTIN and enter valid details in the remaining fields. (if YES selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in GSTIN field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in GSTIN No. field as "Invalid GSTIN No."
TC_Agreement_24 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Mobile Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Mobile Phone No. field as "Invalid Mobile Phone No."
TC_Agreement_25 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "Invalid Primary Email No."
TC_Agreement_26 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in City and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in City field as "Invalid City "
TC_Agreement_27 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Vehicle Chasis No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Vehicle Chasis No. field as "Invalid Vehicle Chasis No. "
TC_Agreement_28 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Postal Code and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Postal Code. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in VPostal Code as "Invalid Postal Code"
TC_Agreement_29 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in State and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in State. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in State as "Invalid State."
TC_Agreement_30 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Registration No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Registration No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Registration No. field as "Invalid Registration No."
TC_Agreement_31 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Executive Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Executive field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Executive Name field as "Invalid Executive Name."
TC_Agreement_32 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Sales Manager Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Sales Manager field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Sales Manager Name field as "Invalid Sales Manager Name."
TC_Agreement_33 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Odometer Reading field as "Invalid Odometer Reading."
TC_Agreement_34 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Last Service Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Service Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Service Odometer Reading field as "Invalid Last Service Odometer Reading."
TC_Agreement_35 | 11386 | 2020-02-07 | To verify if the User is able to create new Easy Care Agreement by entering valid data iin all the mandatory fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | New Easy Care Agreement should get created followwing a confirmation message as "Easy Care Agreement Successfully Added."
TC_Agreement_36 | 11386 | 2020-02-07 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on New Easy Care Agreement page. | 1)Click on Cancel Button. 2)Click on the Leave button appearing on the confirmation message. |  |  |  | User should move back to the previous screen.
TC_Agreement_37 | 11386 | 2020-02-07 | To verify if the mandatory fields are * marked | User is already logged in and is on New Easy Care Agreement page. | 1) Check the * marked against each mandatory field. |  |  |  | All the mandatory fields should be * marked.
TC_Agreement_38 | 11386 | 2020-02-07 | To verify if the data coming from middleware is non editable or not. | User is already logged in and is on New Easy Care Agreement page. | Observe the data coming from the middleware. |  |  |  | The data coming from middleware should be non editable.
TC_Agreement_39 | 11386 | 2020-02-07 | REC Plan Details: To verify if the details under REC Plan are getting computed correctly or not. |  | Open the newly added agreement.

## Approved_Claim_Amt-Dev
Project Name:-> MB
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- | 2020-03-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Ranjeet
Version: - |  |  | Version: - |  | Module:- | Rejected amount is showing in approved amount
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Date | Status | Power ID | Date | Status
TC_ApprovedClaimAMT_01 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Part Information. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 | 134852.23 |  | The rejected part amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_02 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Labour Information. | User is already logged in | 1)mark the checkbox against the Labour to be reject, 2)Click on Update Labour Rejection | MBCAC198 |  |  | The rejected Labour amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_03 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Miscellaneous Information. | User is already logged in | 1)mark the checkbox against the Miscellaneous to be reject, 2)Click on Update Miscellaneous Rejection | MBCAC198 |  |  | The rejected Miscellaneous amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_04 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Part Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_05 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for Labour information by selecting check box against Rejection check in Labour information. | User is already logged in | 1)mark the checkbox against the Rejection check for Labour Information. | MBCAC198 |  |  | All Labour should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_06 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Miscellaneous Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_07 | 11417 | 2020-03-07 | To verify if the Net Approval amount is showing the amount equal to Total Amt-Rejected Amount | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 |  |  | Net approval amount should be equal to total amt-rejected amount. |  |  | Pass
TC_ApprovedClaimAMT_08 | 11417 | 2020-03-07 | To verify if the Grand Total Calculation is correct or not. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection 3)Check the summary of all the parts and calculate manually | MBCAC198 |  |  | Grand total of all the fields should be correct. |  |  | Pass
30-06-2020