## Summery
Greenlam WMS
Lead Dev: Rahul Verma
Module | No. of test Written | No. of test executed | Pass | Fail
Dealer- Request for Warranty Card |  | NA | 35 | 0
Builder- Request for Warranty Card | NA | NA | 31 | 0
Customer-Request for Warranty Card | NA | NA | 29 | 0
Total | NA | NA | 95 | 0

## Open Bugs
Bug Report
Project :- |  | Greenlam WMS | [5 empty] | Lead_Developer. :-Rahul Verma
Created_By :- |  | Jitendra |  |  | Module: | Request for Warranty Card | [7 empty] | Re-Testing |  |  | Re-Testing (14-04-2020)
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Power ID | Status | Developers Comments | Power ID | Status | Developers Comments | Open | Close
2020-04-01 | NA | 1 | 10527 | Dealer- Request for Warranty Card : Dealer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Dealer is already logged in. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 2 | 10527 | Dealer- Request for Warranty Card :Dealer is able to submit Warranty Card form by leaving "Type of site" field blank. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 3 | 10527 | Dealer-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 4 | 10527 | Dealer-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Dealer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | All the fields are mandatory | 10580 | Fixed
2020-04-01 | NA | 5 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit warrant card by entering invalid data in Customer Name | Dealer is already logged in and is on Add request warranty page. |  | 6515 |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Not Fixed: P9:P62User can copy invalid data and paste in Name field. | DONE | 10626 | Fixed
2020-04-01 | NA | 6 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a form by entering invalid data (More than 10 digits and less than 10 digits) in Customer Phone field. | Dealer is already logged in and is on Add request warranty page. |  | 888955545522115 |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 7 | 10527 | Dealer-Request for Warranty Card : Customer City and Customer State both the fields are disbled (Freezed)to add/edit data. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 8 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the form by entering invalid data in Dealer Invoice No. and also Dealer invoice numberhas maximum length of 10 digits . | Dealer is already logged in and is on Add request warranty page. |  | #VALUE! |  | Mid | High | New | Rahul Verma | Done | 10580 | Not Fixed: User can copy invalid data and paste in invoice number field. | DONE | 10626 | Fixed
2020-04-01 | NA | 9 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the form by entering invalid data in Dealer Invoice Date. | Dealer is already logged in and is on Add request warranty page. |  | 2006-02-22 and 2027-11-24 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed: Dealer is able to submit the form by entering invalid data in Dealer Invoice Date.(2009-02-10) | DONE | 10626 | Fixed-As discussed
2020-04-01 | NA | 10 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving GIL Invoice field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 11 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Product Name field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 12 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Available Quantity field blank. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 13 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit a warranty form by leaving Issue Quantity field blank by default system takes 0 as issue qty. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-01 | NA | 14 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Total Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -8988 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 15 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Issue Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -214748364 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-01 | NA | 16 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submit the warranty form by entering invalid data in Available Quantity field . | Dealer is already logged in and is on Add request warranty page. |  | -2147483648 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 17 | 10527 | Dealer-Request for Warranty Card : Available qty cannot be more than the Total qty. | Dealer is already logged in and is on Add request warranty page. |  | Total Quantity: -8988 Available Quantity: 21474836 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-01 | NA | 18 | 10527 | Dealer-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-01 | NA | 19 | 10527 | Dealer-Request for Warranty Card : GIL Invoice and Product Name both dropdowns does not have any data to be select to submit the form. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | invoice and products will related to user business vertical and territory | 10580 | Fixed
2020-04-01 | NA | 20 | 10527 | Dealer-Request for Warranty Card : Dealer is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 21 | 10527 | Dealer-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 22 | 10527 | Dealer-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 23 | 10527 | Dealer-Request for Warranty Card : Installed By field should not be available to select if dealer have selected "Not yet Installed" as Installation Status. | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Not Fixed | "Not yet Installed" option is also given in Installed By Field | 10626 | Fixed
2020-04-01 | NA | 24 | 10527 | Dealer-Request for Warranty Card : Even after entering valid Pin Code number, system shows a validation message for invalid pin code. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-01 | NA | 25 | 10527 | Dealer-Request for Warranty Card : Dealer is not able to edit the form as the form is not editable once it gets submitted. | Dealer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Dealer only creates the form and then only bcm level user can edit the form | 10580 | Fixed
2020-04-01 | NA | 26 | 10527 | Dealer-Request for Warranty Card : Option for to select Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Dealer is already logged in and is on Add request warranty page. |  |  |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 27 | 10527 | Builder-Request for Warranty Card : Builder Dealer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Builder is already logged in and is on Add request warranty page. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 28 | 10527 | Builder- Request for Warranty Card : Builder is able to submit Warranty Card form by leaving "Type of site" field blank. | Builder is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 29 | 10527 | Builder-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Builder is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 30 | 10527 | Builder-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Builder is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Fields under Customer/Project information is mandatory | 10580 | Fixed
2020-04-02 | NA | 31 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving GIL Invoice field blank. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 32 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Product Name field blank. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 33 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Total Quantity field blank and system takes 0 by dafualt. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 34 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Available Quantity field blank and system takes 0 by dafualt. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 35 | 10527 | Builder-Request for Warranty Card : Builder is able to submit a warranty form by leaving Issue Quantity field blank and system takes 0 by dafualt | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 36 | 10527 | Builder-Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Total Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -15 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 37 | 10527 | Builder-Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Issue Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -5 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 38 | 10527 | Builder -Request for Warranty Card : Builder is able to submit the warranty form by entering invalid data in Available Quantity field . | Builder is already logged in and is on Add request warranty page. |  | -5 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 39 | 10527 | Builder -Request for Builder Card : Available qty cannot be more than the Total qty. | Builder is already logged in and is on Add request warranty page. |  | total qty:10 avail. qty: 20 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 40 | 10527 | Builder-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Builder is already logged in and is on Add request warranty page. |  | total qty:100 avail. qty: -100 issue qty: 250 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 41 | 10527 | Builder-Request for Warranty Card : GIL Invoice and Product Name both dropdowns does not have any data to be select to submit the form. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | invoice and products will related to user business vertical and territory | 10580 | Fixed
2020-04-02 | NA | 42 | 10527 | Builder-Request for Warranty Card : Builder is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Builder is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 43 | 10527 | Builder-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 44 | 10527 | Builder-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 45 | 10527 | Builder-Request for Warranty Card : Installed By field should not be available to select if builder have selected "Not yet Installed" as Installation Status. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 46 | 10527 | Builder-Request for Warranty Card : Builder is not able to edit the form as the form is not editable once it gets submitted. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Form creates on SE level and then only bcm level user can edit the form | 10580 | Fixed
2020-04-02 | NA | 47 | 10527 | Builder-Request for Warranty Card : Option for to select Floor and Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Builder is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 48 | 10527 | Builder-Request for Warranty Card : Option for Type of Surface Treatment and Project Address is not available in warranty form as per the shared document there should be Option for Type of Surface Treatment and Project Address. | Builder is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 49 | 10527 | Customer- Request for Warranty Card : Customer is able to submit Warranty Card form by leaving all the mandatory fields blank. | Customer is already logged in. | 1)Click on the Micasa doors clickable image available on Request for Warranty Card page. 2) leave all the mandatory fields blank and Click on the Save button | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 50 | 10527 | Customer- Request for Warranty Card :Customer is able to submit Warranty Card form by leaving "Type of site" field blank. | Customer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 51 | 10527 | Customer-Request for Warranty Card : Type of Site field should be (*) marked in order to show it as a mandatory field. | Customer is already logged in and is on Add request warranty page. |  | NA |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 52 | 10527 | Customer-Request for Warranty Card : All the fields under Customer/Project Information section are non mandatory. Please confirm and resolve accordingly. | Customer is already logged in and is on Add request warranty page. |  | NA |  | High | High | New | Rahul Verma | All the fields are mandatory | 10580 | Fixed
2020-04-02 | NA | 53 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving GIL Invoice field blank. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 54 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Product Name field blank. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 55 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Total Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 56 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Available Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 57 | 10527 | Customer-Request for Warranty Card : Customer is able to submit a warranty form by leaving Issue Quantity field blank and system takes 0 as deafult value. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | "Not yet Installed" option is also given in Installed By Field | 10626 | Fixed
2020-04-02 | NA | 58 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Total Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -100 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 59 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Issue Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -150 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 60 | 10527 | Customer-Request for Warranty Card : Customer is able to submit the warranty form by entering invalid data in Available Quantity field . | Customer is already logged in and is on Add request warranty page. |  | -250 |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 61 | 10527 | Customer-Request for Warranty Card : Available qty cannot be more than the Total qty. | Customer is already logged in and is on Add request warranty page. |  | Toatl qty : 20 Available qty: 40 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 62 | 10527 | Customer-Request for Warranty Card : Issue Quantity cannot be more than the Available Quantity and Total qty. | Customer is already logged in and is on Add request warranty page. |  | Available Quantity: -40 Issue Quantity:80 |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | DONE | 10626 | Fixed
2020-04-02 | NA | 63 | 10527 | Customer-Request for Warranty Card : Customer is able to submi the form by leaving the Installation Status,Installed By and Approval Status field blank. Please confirm if they are mandatory or not. | Customer is already logged in and is on Add request warranty page. |  |  |  | Mid | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 64 | 10527 | Customer-Request for Warranty Card : There is no option available to download the warranty certificate after the approval from BCM. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 65 | 10527 | Customer-Request for Warranty Card : There should not be an option of Approval Status while filling up the form but it is there and is editable too. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 66 | 10527 | Customer-Request for Warranty Card : Installed By field should not be available to select if Customer have selected "Not yet Installed" as Installation Status. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Not Fixed | "Not yet Installed" option is also given in Installed By Field | 10626 | Fixed
2020-04-02 | NA | 67 | 10527 | Customer-Request for Warranty Card : Customer is not able to edit the form as the form is not editable once it gets submitted. | Customer is already logged in and is on Add request warranty page. |  |  |  | High | High | New | Rahul Verma | Done | 10580 | Fixed
2020-04-02 | NA | 68 | 10527 | Customer-Request for Warranty Card : Option for to select Floor, Door, Cubicle from the main menu and dropdown under the request form is not available to select. However Laminate is there | Customer is already logged in and is on Add request warranty page. |  |  |  | Mid | Mid | New | Rahul Verma | Done | 10580 | Fixed
2020-04-08 | NA | 69 | 10580 | Customer-Request for Warranty Card : If customer selects Floor or Doors from the dropdown of Request for Warranty Card then "Customer/Project Information" fields gets disabled to be edit. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | It is form requirement not a bug | 10626 | Fixed
2020-04-08 | NA | 70 | 10580 | Customer-Request for Warranty Card : Customer can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Customer is already logged in and is on Add request warranty page. |  | Issue Quantity:2.5 Issue Quantity:2.9 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 71 | 10580 | Customer-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 72 | 10580 | Customer-Request for Warranty Card : Customer should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 73 | 10580 | Customer-Request for Warranty Card :Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Customer BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10065 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 74 | 10580 | Customer-Request for Warranty Card :Same Product ID/Code is appearing twice in the Product dropdown list. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE. Data in SAP contain duplicate data except product quantity | 10626 | Fixed
2020-04-08 | NA | 75 | 10580 | Customer-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 76 | 10580 | Customer-Request for Warranty Card : Customer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Customer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 77 | 10580 | Dealer-Request for Warranty Card : If Dealer selects Floor or Doors from the dropdown of Request for Warranty Card then Project Name and Project Address fields gets disabled to be edit. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 78 | 10580 | Dealer-Request for Warranty Card : Dealer can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Dealer is already logged in and is on Add request warranty page. |  | Issue Quantity:1.5 Issue Quantity:1.9 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 79 | 10580 | Dealer-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 80 | 10580 | Dealer-Request for Warranty Card : Dealer should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 81 | 10580 | Dealer-Request for Warranty Card : Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Dealer BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10066 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 82 | 10580 | Dealer-Request for Warranty Card : Dealer Same Product ID/Code is appearing twice in the Product dropdown list. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE. Data in SAP contain duplicate data except product quantity | 10626 | Fixed
2020-04-08 | NA | 83 | 10580 | Dealer-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 84 | 10580 | Dealer-Request for Warranty Card : Dealer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 85 | 10580 | Dealer-Request for Warranty Card : There is a spelling errorin the validation message for entering issue qty more than the available qty. "then" should be "than". | Dealer is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 86 | 10580 | Builder-Request for Warranty Card : If Builder selects Floor or Doors from the dropdown of Request for Warranty Card then Project Name and Project Address fields gets disabled to be edit. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 87 | 10580 | Builder-Request for Warranty Card : Builder can add the Issue Quantity in decimals due to which the "Issue Quantity" can be entered more than the available quantity. | Builder is already logged in and is on Add request warranty page. |  | Issue Quantity:1.6 Issue Quantity:1.9 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 88 | 10580 | Builder-Request for Warranty Card : After entering the Line Items for any product then he is able to add the blank data in next line items. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 89 | 10580 | Builder-Request for Warranty Card : Builder should not be allow to enter "Not yet Installed" in the Installed By field if the Installation Status is Installed. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 90 | 10580 | Builder-Request for Warranty Card : Customer Name and Project Name is blank in the downloaded report and also the Customer/Project Details are also missing fromm the downloaded report. | Builder BCM is already logged in and is on Add request warranty page. |  | Warranty Number: WARRANTY/10069 | [6 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 91 | 10580 | Builder-Request for Warranty Card : Builder Same Product ID/Code is appearing twice in the Product dropdown list. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE. Data in SAP contain duplicate data except product quantity | 10626 | Fixed
2020-04-08 | NA | 92 | 10580 | Builder-Request for Warranty Card : Assigned To field should be auto selected and customer should not be able to select other users/roles for submitting the warranty card. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 93 |  | Builder-Request for Warranty Card : Dealer is not able to select different product under the same invoice. Everytime customer selects different product to be entered system show a validation message. | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 94 |  | Builder-Request for Warranty Card : There is a spelling in the validation message for entering issue qty more than the available qty. "then" should be "than". | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed
2020-04-08 | NA | 95 |  | Customer-Request for Warranty Card : There is a spelling in the validation message for entering issue qty more than the available qty. "then" should be "than". | Builder is already logged in and is on Add request warranty page. | [8 empty] | 10580 | New | DONE | 10626 | Fixed

## TC
Project Name: Greenlam WMS
Updated By:- | Jitendra |  | ReTestedBy:- |  |  | Developed By: | Rahul Verma
Creation Date:- |  |  | Retesting Date:-
Version: - |  |  | Module:- |  |  | Power ID:
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status

## credentials
URL = http://13.232.233.123/wms_greenlam/
cse01 = Welcome@123
cbcm01 =Welcome@123
dse01 = Welcome@123
dbcm01 = Welcome@123
bse01 = Welcome@123
bbcm01 = Welcome@123
1010001148 = Welcome@123
1010000345 = Welcome@123

## Dump
API Name | Bug Description | Pay Load | Error/Success Message | Screenshot
Estimation Approval API | 1. Please change “Entity” to “Claim Approval” in the confirmation message of successful claim approval. | { "aiz_claim_number": "07786738985", "approval_status": "On Hold" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Estimation Approval API | 2.Claim status should not get update in case of CPP but this is happening. | { "aiz_claim_number": "07786738985", "approval_status": "On Hold" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Escalated Cases API | 1. Please change “Entity” to “Escalation Status” in the confirmation message of successful escalation. | { "aiz_claim_number": "07786738985", "escalation": "yes" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
Claim Cancellation API | 1. User is able to cancel the claim without entering “Cancellation Reason” which is a mandatory field. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
| 2. Please change “Entity” to “Escalation Status” in the confirmation message of successful escalation. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }
| 3. Claim status should not get update in case of CPP but this is happening. | { "aiz_claim_number": "07786738985", "claim_status": "cancelled", "cancellation_reason": "Hi this is dummy text" } | { "status": "Success", "message": "Entity has been updated successfully.", "data": null }