## Cover
Functional Test Cases
Project: Mpartner Revamp
Synopsis | Created the initial functional test case document for Iconnect
Author(s) | Jitendra
Current Version
Date | 2020-12-16
Reference : | 1) https://techfour506085.invisionapp.com/console/share/YN1VD85CF3/496473501 2) https://docs.google.com/presentation/d/1-3dG7Xhub_xlTq5k3ikCNLIkq8IPel-BOvAYFTZKDZ0/edit#slide=id.p1

## Summary
Iconnect
Lead Dev: Rahul Pandey
Module | No. of test Written | No. of test executed | Pass | Fail
Digital Scheme | 60 | 55 | 20 | 35
Total | 60 | 55 | 20 | 35

## Bug Report
Project :- |  | Iconnect |  |  |  |  | Lead_Devp. :- |  | Rahul Pandey
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :-
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
13290 | TC_DigitalScheme_01 | Bug1 | Distributor should get navigate to the screen where he will have to select the Ditsributor or Retailer for proceeding further to the digital scheme section. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. |  | https://lh3.googleusercontent.com/-52p7I_ngBk4/X9nlqHSmzDI/AAAAAAAAEHk/FW3NvjjNzDscuyigvlBCUcAKCjPrJN5ugCK8BGAsYHg/s0/2020-12-16.png | High | HIgh | New
13290 | TC_DigitalScheme_04 | Bug2 | Color of the thumbnail title is not as per the theme. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. |  | https://prnt.sc/w3xwm4 | High | Low | New
13290 | TC_DigitalScheme_06 | Bug3 | Scheme title color should be as per the color of the theme. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer . 2) Click on Distributor switch button. 3) Click on Scheme Flyer button. |  | https://prnt.sc/w3xeuh | High | Low | New
13290 | TC_DigitalScheme_08 | Bug4 | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | https://prnt.sc/w3xg43 | High | High | New
13290 | TC_DigitalScheme_12 | Bug5 | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on dustributor switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | https://prnt.sc/w3xg43 | High | Low | New
13290 | TC_DigitalScheme_15 | Bug6 | 1)The retailer info bucket and the input fields for submitting the secondary scheme form should appear after selecting the retailer. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. |  |  | High | High | New
13290 | TC_DigitalScheme_16 | Bug7 | Colons are missing from the Retailer information bucket. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. |  | https://prnt.sc/w3xnal | High | Low | New
13290 | TC_DigitalScheme_17 | Bug8 | 1) In the search bar hint message should come as " Search Retailer" instead of showing All Dealers in the search bar. 2) What will happen when user selects " All Dealers"? there is no such requirement where we can assign coupons to all the retailers at once so All dealers dropdwon value should not be there. 3) After selecting the retailer coupons against him/her should get appear but this is not happening currently. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. 4) enter the name of the retailer. |  | https://prnt.sc/w3xnzz | High | High | New
13290 | TC_DigitalScheme_18 | Bug9 | All the mandatory fields should be highlighted with the * mark. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | https://prnt.sc/w3xog7 | High | Low | New
13290 | TC_DigitalScheme_23 | Bug10 | Before submitting the page showed blank data in number of coupons field but when clicking on the submit button app shows 5 number od coupons and also shows the success message. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave No. of coupons field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  | video shared | High | High | New
13290 | TC_DigitalScheme_24 | Bug11 | User is able to assign the coupon to the selected retailer by entering invalid data in invoice number. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid data invoice number field. 2) Enter valid data in remaining fields. 3)Click on submit button. | *(&& blank spaces | https://prnt.sc/w3xpi0 | High | High | New
13290 | TC_DigitalScheme_25 | Bug12 | User is able to assign the coupon to the selected retailer by entering invalid data in invoice value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value invoice number field. 2) Enter valid data in remaining fields. 3)Click on submit button. | hvdg@$# blank spaces | https://prnt.sc/w3xpi00 | High | High | New
13290 | TC_DigitalScheme_26 | Bug13 | User is able to assign the coupon to the selected retailer by entering invalid data in invoice Date. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value invoice date field. 2) Enter valid data in remaining fields. 3)Click on submit button. | 16/11/1913 | https://prnt.sc/w3xpi0 | High | High | New
13290 | TC_DigitalScheme_27 | Bug14 | User is able to assign the coupon to the selected retailer by entering invalid data in fan value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value fan value field. 2) Enter valid data in remaining fields. 3)Click on submit button. | any amount greater than invoice value | https://prnt.sc/w3xpi0 | High | High | New
13290 | TC_DigitalScheme_28 | Bug15 | User is able to assign the coupon to the selected retailer by entering invalid data in lighting value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value lighting value field. 2) Enter valid data in remaining fields. 3)Click on submit button. | any amount greater than invoice value | https://prnt.sc/w3xpi0 | High | High | New
13290 | TC_DigitalScheme_30 | Bug16 | After the successful submission of the secondary scheme form previously filled data should get reset | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid data in the mandatory fields. 2) Click on submit button. |  |  | High | High | New
13290 | TC_DigitalScheme_32 | Bug17 | User is able to assign coupons greater than the total received coupons. In the performed case user had 10 received coupons but he can assign the coupons to the retailer N number of times. I have submitted 4 times each with 5 coupons. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid data in the mandatory fields having 0 number of coupons. 2) Click on submit button. |  |  | High | High | New
13290 | TC_DigitalScheme_33 | Bug18 | User is able to submit the secondary scheme form with sum of fan value and lighting value greater than the invoice value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid Invoice value 2) enter Fan value and lighting value such that the sum of both the fields should be greater than the invoice value. 3) Enter valid data in remaining fields. 4)Click on submit button. |  | https://prnt.sc/w3xpi0 | High | High | New
13290 | TC_DigitalScheme_34 | Bug19 | No data found toast message is coming when viewing the transferred coupons in the assigned retailers coupon section. | User is already logged-in and is on coupons section. | 1) navigate to the coupons section. |  | https://lh3.googleusercontent.com/-ZMl5w2i-nSA/X9oE2PdRcsI/AAAAAAAAELs/EUu0N3_Y5akLdnb2uHyHiAT-dyY8wl25ACK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalScheme_35 | Bug20 | Total count of the assignd cupons is coming more than the available under the list of coupons issues history. Total count :35 total history items : 10 | User is already logged-in and is on coupons section. | 1) navigate to the coupons issues tab. |  | https://lh3.googleusercontent.com/-AiriNLVk-YQ/X9oB4THN5_I/AAAAAAAAEJA/Jkl7FBsmxDk41Z92sHX_67VKp62duvSdgCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalScheme_37 | Bug21 | Coupons Recieved , Coupon Issues History and Coupons Available tabs should bescrollable as per the mock up screen. and also Total count bucket data should be aligned in the middle ( in all three tabs). | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. |  | https://prnt.sc/w3xtst https://lh3.googleusercontent.com/-ZMl5w2i-nSA/X9oE2PdRcsI/AAAAAAAAELs/EUu0N3_Y5akLdnb2uHyHiAT-dyY8wl25ACK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalScheme_39 | Bug22 | 1) Toastmessage is coming as "Error" when navigating to the history tab. 2)Coupons Recieved , Coupon Issues History and Coupons Available tabs should be scrollable as per the mock up screen. and also Total count bucket data should be aligned in the middle. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. 4) Click on Coupons Issued History |  | https://lh3.googleusercontent.com/-q6Ciizyixuo/X9oCIJRMaYI/AAAAAAAAEJY/UOTz5tH9ZNAyDcKKL8LYU1tLet_rpgnQACK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalScheme_40 | Bug23 | 1) Toastmessage is coming as "Error" when navigating to the tab. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. 4) Click on Coupons Available tab |  |  | High | High | New
13290 | TC_DigitalSchemeRetailer_04 | Bug24 | Scheme title color should be as per the color of the theme. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer . 2) Click on Scheme Flyer button. |  | https://prnt.sc/w3xeuh | High | Low | New
13290 | TC_DigitalSchemeRetailer_05 | Bug25 | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | https://prnt.sc/w3xg43 | High | High | New
13290 | TC_DigitalSchemeRetailer_08 | Bug26 | 1) Toastmessage is coming as "Error" when navigating to the rewards tab. 2) Tabs for redeem gifts , coupon history and unscratched coupons should be scrollable as per the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Click on the Rewards button. |  | https://lh3.googleusercontent.com/-xSYDCVWiBmM/X9oHbdJI5iI/AAAAAAAAENE/GaBg6TmfCEE6eRBLotgNPubYyckvvfVcwCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalSchemeRetailer_09 | Bug27 | there is too much space outside the gift cards please refer to the mock up screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Click on the Rewards button. 3) Click on Redeem Gift tab/ by default it will get open on clicking upon rewards. |  | https://prnt.sc/w3y4kh | Low | Low | New
13290 | TC_DigitalSchemeRetailer_10 | Bug28 | User is able to redeem the gifts with 0 total value amount. | User is already logged-in and is on Redeem gift page. | 1) Click on submit button with the case having 0 amount. |  | https://lh3.googleusercontent.com/-IthHR4WMUG4/X9oHZkV79ZI/AAAAAAAAEMw/lOLflsoJyYgm_OjUw3t50b-bawvEZ3mggCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalSchemeRetailer_13 | Bug29 | User is able to redeem the multiple gifts at once. | User is already logged-in and is on Redeem gift page. | 1) select multiple gift cards. 2)Click on submit button. | Select all 4 cards. | https://lh3.googleusercontent.com/-2ANdRczpouE/X9oHcJV1VWI/AAAAAAAAENM/XHHt-_nYFQU-9eNlMagrnRIImSHZd8yZgCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalSchemeRetailer_14 | Bug30 | 1) No data found toast message is coming when navigating to the Coupons history section. 2) Need to remove "Rs." text. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab |  | https://lh3.googleusercontent.com/-3rdaam2vFLY/X9oHbJUEJbI/AAAAAAAAENA/M9R5CAnoau0cH5i3vk0csOI-XRJOr65PgCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 | TC_DigitalSchemeRetailer_15 | Bug31 | 1) App is getting crash when selecting Completed as the status at coupons history screen. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab. 2) Select Completed from the dropdown. |  |  | High | High | New
13290 | TC_DigitalSchemeRetailer_16 | Bug32 | 1) App is getting crash when selecting Pending as the status at coupons history screen. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab. 2) Select Pending from the dropdown. |  |  | High | High | New
13290 | TC_DigitalSchemeRetailer_17 | Bug33 | 1) No data found toast message is coming when navigating to the Unscratched Coupons section. | User is already logged-in and is on Redeem gift page. | 1) Click on unscratched coupons tab |  | https://lh3.googleusercontent.com/-nSJ3wSahrbc/X9oHah16kLI/AAAAAAAAEM8/RKPJ3G9IRDQ2rqJODBNmFHSSYsrv7gWGwCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New
13290 |  | Bug34 | Footer grid has no text and also when clicking on them they all are redirecting the home page |  |  |  | https://prnt.sc/w3yeja | High | High | New
13290 |  | Bug35 | Fan program under side menu is in hindi |  |  |  | https://lh3.googleusercontent.com/-ml5clOg12NI/X9oKA83ItPI/AAAAAAAAEOI/AIQjMHmQU6kyGX2EAFuTznbuRITfWi5vQCK8BGAsYHg/s0/2020-12-16.jpg | High | High | New

## Digital scheme-Distributor
Project Name:->Iconnect
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul Pandey
Version: - |  |  |  |  | Module:- | Digital Scheme-Disty
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Re-Testing Power ID | Re-Testing Date | Re-Testing Status | Re-Testing Power ID | Re-Testing Date | Re-Testing Status
TC_DigitalScheme_01 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Digital Scheme section by clicking on Digital Scheme link under side drawer. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. |  | Distributor should get navigate to the screen where he will have to select the Ditsributor or Retailer for proceeding further to the digital scheme section. | https://lh3.googleusercontent.com/-52p7I_ngBk4/X9nlqHSmzDI/AAAAAAAAEHk/FW3NvjjNzDscuyigvlBCUcAKCjPrJN5ugCK8BGAsYHg/s0/2020-12-16.png | User should get navigate to the screen where Distributor and Retailer buttons should be there for selecting distributor and Retailer .(if you've loggedin as a distributor.) | High | HIgh | Fail
TC_DigitalScheme_02 | 13290 | 2020-12-16 | To verify the UI of the screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. |  |  |  | UI of the screen should be as per the approved design. |  |  | Could not execute
TC_DigitalScheme_03 | 13290 | 2020-12-16 | To verify if the distributor is able to view the Digital Scheme for Distributor by clicking on Distributor button. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. 2) Click on Distributor button. |  |  |  | User should get navigate to the screen where he can will have three options to select: 1) Scheme Flyer 2)Secondary Scheme Reporting 3) Coupon Status |  |  | Pass
TC_DigitalScheme_04 | 13290 | 2020-12-16 | To verify if the UI of the screen is as per the Mock Up screen or not. (for distributor) | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. |  | Color of the thumbnail title is not as per the theme. | https://prnt.sc/w3xwm4 | UI of the page should be as per the mock up screen. | High | Low | Fail
TC_DigitalScheme_05 | 13290 | 2020-12-16 | To verify if the distributor is able to view the Scheme Flyer screen by clicking on scheme flyer button. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer . 2) Click on Distributor switch button. 3) Click on Scheme Flyer button. |  |  |  | User should be able to see the Scheme Flyer screen where the scheme validity, image of the scheme, download button and Retailer/Distributor switch button will appear. By Default: 1)When we click on the Retailer tab, we can see the bottom tabs with menus like lighting, fans, cl etc. 2)By default the first tabs will be selected in bottom as well as top too. |  |  | Pass
TC_DigitalScheme_06 | 13290 | 2020-12-16 | To verify if the UI of the screen is as per the Mock Up screen or not. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer . 2) Click on Distributor switch button. 3) Click on Scheme Flyer button. |  | Scheme title color should be as per the color of the theme. | https://prnt.sc/w3xeuh | UI of the page should be as per the mock up screen. | High | Low | Fail
TC_DigitalScheme_07 | 13290 | 2020-12-16 | To verify if the distributor is able to view the Digital Scheme for retailer by clicking on retailer switch button. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. |  |  |  | User should get navigate to the screen where schemes available for retailershould appear. |  |  | Pass
TC_DigitalScheme_08 | 13290 | 2020-12-16 | To verify if the user is able to view the Digital Scheme by clicking on the image. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | https://prnt.sc/w3xg43 | User should be able to see the scheme flyer image as pop up. | High | High | Fail
TC_DigitalScheme_09 | 13290 | 2020-12-16 | To verify if the user is able to get switch to the bottom tabs lighting, fans, cl | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. |  |  |  | User should be able to switch to fans tab for scheme flyer. |  |  | Pass
TC_DigitalScheme_10 | 13290 | 2020-12-16 | To verify if the user is able to download the scheme pdf by clicking on the download button in the bottom.. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. 5) Click on download button. |  |  |  | User should be able to download the scheme pdf by clicking on the download button in the bottom.. |  |  | Pass
TC_DigitalScheme_11 | 13290 | 2020-12-16 | To verify if the distributor is able to view the Scheme Flyer for dustributor by clicking on dustributor button. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Scheme Flyer button. 4) Click on dustributor tab. |  |  |  | User should be able to see the Scheme Flyer screen for dustributor where the scheme validity, image of the scheme, download button and Retailer/Distributor switch button will appear. By Default: 1)When we click on the Retailer tab, we can see the bottom tabs with menus like lighting, fans, cl etc. 2)By default the first tabs will be selected in bottom as well as top too. |  |  | Pass
TC_DigitalScheme_12 | 13290 | 2020-12-16 | To verify if the user is able to view the Digital Scheme by clicking on of the image. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on dustributor switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | https://prnt.sc/w3xg43 | User should be able to see the scheme flyer image as pop up. | High | Low | Fail
TC_DigitalScheme_13 | 13290 | 2020-12-16 | To verify if the user is able to get switch to the bottom tabs lighting, fans, cl | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on dustributor switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. |  |  |  | User should be able to switch to fans tab for scheme flyer. |  |  | Pass
TC_DigitalScheme_14 | 13290 | 2020-12-16 | To verify if the user is able to download the scheme pdf by clicking on the download button in the bottom.. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on dustributor switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. 5) Click on download button. |  |  |  | User should be able to download the scheme pdf by clicking on the download button in the bottom.. |  |  | Pass
TC_DigitalScheme_15 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Secondary Scheme Reporting section by clicking on Secondary Scheme Reporting button. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. |  | 1)The retailer info bucket and the input fields for submitting the secondary scheme form should appear after selecting the retailer. |  | User should bet navigate to the Secondary Scheme Reporting screen where following fields n buttons should appear when selecting a retailer: 1) retailer search field 2) bucket where retailer id , name and phone number will appear. 3) Invoice number text field. 4) Invice Value text field. 5) Invoice date field 6) Fan Value text field 7) Lighting value text field 8) No. of coupons 9) Submit button. Note: we can assign coupons for dealers through this section. | High | High | Fail
TC_DigitalScheme_16 | 13290 | 2020-12-16 | To verify the UI of the screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. |  | Colons are missing from the Retailer information bucket. | https://prnt.sc/w3xnal | UI of the screen should be as per the approved design. | High | Low | Fail
TC_DigitalScheme_17 | 13290 | 2020-12-16 | To verify if the user is able to search the retailer by entering the name of the retailer. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Select Distributor. 3) Click on Secondary Scheme Reporting button. 4) enter the name of the retailer. |  | 1) In the search bar hint message should come as " Search Retailer" instead of showing All Dealers in the search bar. 2) What will happen when user selects " All Dealers"? there is no such requirement where we can assign coupons to all the retailers at once so All dealers dropdwon value should not be there. 3) After selecting the retailer coupons against him/her should get appear but this is not happening currently. | https://prnt.sc/w3xnzz | Entered search retailer should get appear and when selecting it the bottom bucket should display its details. | High | High | Fail
TC_DigitalScheme_18 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving all the mandatory fields blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | All the mandatory fields should be highlighted with the * mark. | https://prnt.sc/w3xog7 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | Low | Fail
TC_DigitalScheme_19 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving invoice number field blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave invoice number field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  |  |  | User should not be able to submit the form and also there should be a proper validation message for the same. |  |  | Pass
TC_DigitalScheme_20 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving invoice value field blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave invoice value field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  |  |  | User should not be able to submit the form and also there should be a proper validation message for the same. |  |  | Pass
TC_DigitalScheme_21 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving invoice date field blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave invoice date field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  |  |  | User should not be able to submit the form and also there should be a proper validation message for the same. |  |  | Pass
TC_DigitalScheme_22 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving lighting value field blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave lighting value field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  |  |  | User should not be able to submit the form and also there should be a proper validation message for the same. |  |  | Pass
TC_DigitalScheme_23 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by leaving No. of coupons field blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Leave No. of coupons field blank. 2) Enter valid data in remaining fields. 3)Click on submit button. |  | Before submitting the page showed blank data in number of coupons field but when clicking on the submit button app shows 5 number od coupons and also shows the success message. | video shared | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_24 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in invoice number. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid data invoice number field. 2) Enter valid data in remaining fields. 3)Click on submit button. | *(&& blank spaces | User is able to assign the coupon to the selected retailer by entering invalid data in invoice number. | https://prnt.sc/w3xpi0 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_25 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in invoice value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value invoice number field. 2) Enter valid data in remaining fields. 3)Click on submit button. | hvdg@$# blank spaces | User is able to assign the coupon to the selected retailer by entering invalid data in invoice value. | https://prnt.sc/w3xpi00 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_26 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in invoice date. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value invoice date field. 2) Enter valid data in remaining fields. 3)Click on submit button. | 16/11/1913 | User is able to assign the coupon to the selected retailer by entering invalid data in invoice Date. | https://prnt.sc/w3xpi0 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_27 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in fan value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value fan value field. 2) Enter valid data in remaining fields. 3)Click on submit button. | any amount greater than invoice value | User is able to assign the coupon to the selected retailer by entering invalid data in fan value. | https://prnt.sc/w3xpi0 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_28 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in lighting value. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value lighting value field. 2) Enter valid data in remaining fields. 3)Click on submit button. | any amount greater than invoice value | User is able to assign the coupon to the selected retailer by entering invalid data in lighting value. | https://prnt.sc/w3xpi0 | User should not be able to submit the form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_29 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering invalid data in Number of coupons. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter invalid value Number of coupons field. 2) Enter valid data in remaining fields. 3)Click on submit button. |  |  |  | User should not be able to submit the form and also there should be a proper validation message for the same. |  |  | Pass
TC_DigitalScheme_30 | 13290 | 2020-12-16 | To verify if the user is able to submit the secondary scheme by entering valid data in all the mandatory fields blank. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid data in the mandatory fields. 2) Click on submit button. |  | After the successful submission of the secondary scheme form previously filled data should get reset |  | User should be able to submit the form and the number of coupons should get transferred to the selected retailer and appear in his/her coupons section and also A pop up message should be shown to the distributor with confirmation of the coupons been transferred successfully | High | High | Fail
TC_DigitalScheme_31 | 13290 | 2020-12-16 | To verify if the user is able to submit the secndary scheme form with having number of coupond as 0. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid data in the mandatory fields having 0 number of coupons. 2) Click on submit button. |  |  |  | User should not be able to submit the secondary scheme form and also there should be a proper validation message for the same. |  |  | Could not execute
TC_DigitalScheme_32 | 13290 | 2020-12-16 | To verify if the user is able to submit the secndary scheme with number of coupons greater than the eligible coupons. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid data in the mandatory fields having 0 number of coupons. 2) Click on submit button. |  | User is able to assign coupons greater than the total received coupons. In the performed case user had 10 received coupons but he can assign the coupons to the retailer N number of times. I have submitted 4 times each with 5 coupons. |  | User should not be able to submit the secondary scheme form and also there should be a proper validation message for the same. | High | High | Fail
TC_DigitalScheme_33 | 13290 | 2020-12-16 | To verify if the "Invoice value = fan value+lighting value " or not. | User is already logged-in and is on Secondary Scheme Reporting page. | 1) Enter valid Invoice value 2) enter Fan value and lighting value such that the sum of both the fields should be greater than the invoice value. 3) Enter valid data in remaining fields. 4)Click on submit button. |  | User is able to submit the secondary scheme form with sum of fan value and lighting value greater than the invoice value. | https://prnt.sc/w3xpi0 | Sum of fan value and lighting value cannot exceed the invoice value. | High | High | Fail
TC_DigitalScheme_34 | 13290 | 2020-12-16 | To verify if the assigned/submitted coupons by the distributor to the selected retailer are appearing in the retailers coupns or not | User is already logged-in and is on coupons section. | 1) navigate to the coupons section. |  | No data found toast message is coming when viewing the transferred coupons in the assigned retailers coupon section. | https://lh3.googleusercontent.com/-ZMl5w2i-nSA/X9oE2PdRcsI/AAAAAAAAELs/EUu0N3_Y5akLdnb2uHyHiAT-dyY8wl25ACK8BGAsYHg/s0/2020-12-16.jpg | Submitted coupons should get appear to the Retailers app account | High | High | Fail
TC_DigitalScheme_35 | 13290 | 2020-12-16 | To verify if the transferred coupons by the distributor to the retailer is apparing in the coupons issued tab or not. | User is already logged-in and is on coupons section. | 1) navigate to the coupons issues tab. |  | Total count of the assignd cupons is coming more than the available under the list of coupons issues history. Total count :35 total history items : 10 | https://lh3.googleusercontent.com/-AiriNLVk-YQ/X9oB4THN5_I/AAAAAAAAEJA/Jkl7FBsmxDk41Z92sHX_67VKp62duvSdgCK8BGAsYHg/s0/2020-12-16.jpg | Submitted coupons should get appear to the coupons issues tab. | High | High | Fail
TC_DigitalScheme_36 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Coupons Status section or not by clicking on Coupon Status button. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. |  |  |  | User should get navigate to the Coupon Status screen where user can see the coupon history. There should be 3 top tabs Coupons Received Coupons Issued History Coupons Available this page will show the received coupons count and the list of coupon serial number that is received. |  |  | Pass
TC_DigitalScheme_37 | 13290 | 2020-12-16 | To verify the UI of the screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. |  | Coupons Recieved , Coupon Issues History and Coupons Available tabs should bescrollable as per the mock up screen. and also Total count bucket data should be aligned in the middle ( in all three tabs). | https://prnt.sc/w3xtst https://lh3.googleusercontent.com/-ZMl5w2i-nSA/X9oE2PdRcsI/AAAAAAAAELs/EUu0N3_Y5akLdnb2uHyHiAT-dyY8wl25ACK8BGAsYHg/s0/2020-12-16.jpg | UI of the screen should be as per the approved design. | High | High | Fail
TC_DigitalScheme_38 | 13290 | 2020-12-16 | To verify if the user is able to view the total received coupons in the Coupons Received Tab. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. |  |  |  | By default coupons received page should get appear and also the total number of coupons and the count of the serial numbers should match |  |  | Pass
TC_DigitalScheme_39 | 13290 | 2020-12-16 | To verify if the user is able to view the history of coupons in the Coupons Issued HistoryTab. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. 4) Click on Coupons Issued History |  | 1) Toastmessage is coming as "Error" when navigating to the history tab. 2)Coupons Recieved , Coupon Issues History and Coupons Available tabs should be scrollable as per the mock up screen. and also Total count bucket data should be aligned in the middle. | https://lh3.googleusercontent.com/-q6Ciizyixuo/X9oCIJRMaYI/AAAAAAAAEJY/UOTz5tH9ZNAyDcKKL8LYU1tLet_rpgnQACK8BGAsYHg/s0/2020-12-16.jpg | when clicking on Coupon Issued History tab, it should show the history of coupons. I should also show the coupon received count and the list of coupon serial number that is received with the dealer name and the date. | High | High | Fail
TC_DigitalScheme_40 | 13290 | 2020-12-16 | To verify if the user is able to view the total available coupons in the Coupons Available tab. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on Distributor switch button. 3) Click on Coupon Status button. 4) Click on Coupons Available tab |  | 1) Toastmessage is coming as "Error" when navigating to the tab. |  | When clicking on Coupon Available tab, it should show the list available of coupons count and the list of coupon serial number which are available. | High | High | Fail

## Digital scheme-Retailer
Project Name:->Iconnect
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Rahul Pandey
Version: - |  |  |  |  | Module:- | Digital Scheme-Retailer
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Re-Testing Power ID | Re-Testing Date | Re-Testing Status | Re-Testing Power ID | Re-Testing Date | Re-Testing Status
TC_DigitalSchemeRetailer_01 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Digital Scheme section by clicking on Digital Scheme link under side drawer or else by clicking Digital Scheme footer icon. | User has an active internet connection and device and is already logged-in as a distributor. | 1) Click on the Digital Scheme link available under side drawer. |  |  |  | User should get navigate to the screen where two buttons should appear: 1) Scheme flyer 2) Rewards |  |  | Pass
TC_DigitalSchemeRetailer_02 | 13290 | 2020-12-16 | To verify the UI of the screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. |  |  |  | UI of the screen should be as per the approved design. |  |  | Pass
TC_DigitalSchemeRetailer_03 | 13290 | 2020-12-16 | To verify if the distributor is able to view the scheme flyer screen. | User has an active internet connection and device and is already logged-in. | 1) Click on the Scheme flyer button |  |  |  | User should get navigate to the screen where schemes available for retailer should appear. Dealer should see only Retailer Scheme. When we click on the Scheme Flyer, we should see the bottom tabs with menus like lighting, fans, cl etc. Clicking on a bottom tab , then the scheme thumbnail and scheme name related to that particular tab should be displayed. Also the validity of that scheme should be displayed on the top By default the first tabs will be selected. |  |  | Pass
TC_DigitalSchemeRetailer_04 | 13290 | 2020-12-16 | To verify if the UI of the screen is as per the Mock Up screen or not. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer . 2) Click on Scheme Flyer button. |  | Scheme title color should be as per the color of the theme. | https://prnt.sc/w3xeuh | UI of the page should be as per the mock up screen. |  |  | Fail
TC_DigitalSchemeRetailer_05 | 13290 | 2020-12-16 | To verify if the user is able to view the Digital Scheme by clicking on of the image. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the image thumbnail. |  | Scheme title color should be as per the color of the theme and also the close icon is different from the mock up screen. | https://prnt.sc/w3xg43 | User should be able to see the scheme flyer image as pop up. |  |  | Fail
TC_DigitalSchemeRetailer_06 | 13290 | 2020-12-16 | To verify if the user is able to get switch to the bottom tabs lighting, fans, cl | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. |  |  |  | User should be able to switch to fans tab for scheme flyer. |  |  | Pass
TC_DigitalSchemeRetailer_07 | 13290 | 2020-12-16 | To verify if the user is able to download the scheme pdf by clicking on the download button in the bottom.. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer or else click on Digital Scheme footer icon. 2) Click on retailer switch button. 3) Click on Scheme Flyer button. 4) Click on the Fans bottom tab. 5) Click on download button. |  |  |  | User should be able to download the scheme pdf by clicking on the download button in the bottom.. |  |  | Pass
TC_DigitalSchemeRetailer_08 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Rewards section. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Click on the Rewards button. |  | 1) Toastmessage is coming as "Error" when navigating to the rewards tab. 2) Tabs for redeem gifts , coupon history and unscratched coupons should be scrollable as per the mock up screen. | https://lh3.googleusercontent.com/-xSYDCVWiBmM/X9oHbdJI5iI/AAAAAAAAENE/GaBg6TmfCEE6eRBLotgNPubYyckvvfVcwCK8BGAsYHg/s0/2020-12-16.jpg | User should get redirect to a page that contain 3 tabs. Redeem Gifts Coupons History Unscratched Coupons |  |  | Fail
TC_DigitalSchemeRetailer_09 | 13290 | 2020-12-16 | To verify if the user is able to get navigate to the Redeem Gift section or not. | User has an active internet connection and device and is already logged-in. | 1) Click on the Digital Scheme link available under side drawer. 2) Click on the Rewards button. 3) Click on Redeem Gift tab/ by default it will get open on clicking upon rewards. |  | there is too much space outside the gift cards please refer to the mock up screen. | https://prnt.sc/w3y4kh | User should get navigate to the redeem gift page. dealer should be able to redeem the reward amount by scratching coupon . It should be shown in the top as total value available. Note: Dealer can purchase a gift voucher using this redeem amount. Voucher will be dynamic and the dealer can select only 1 voucher at a time. Selected voucher will have blue color border. Once selecting the voucher and clicking the submit button, the data will be saved in the backend. Manual report will share to LPT, then LPT will share further details. Daily or alternate day cycle for data sharing. |  |  | Fail
TC_DigitalSchemeRetailer_10 | 13290 | 2020-12-16 | To verify if the user is able to redeem the reward point when the total amount is "0". | User is already logged-in and is on Redeem gift page. | 1) Click on submit button with the case having 0 amount. |  | User is able to redeem the gifts with 0 total value amount. | https://lh3.googleusercontent.com/-IthHR4WMUG4/X9oHZkV79ZI/AAAAAAAAEMw/lOLflsoJyYgm_OjUw3t50b-bawvEZ3mggCK8BGAsYHg/s0/2020-12-16.jpg | There should be a proper validation message for it. |  |  | Fail
TC_DigitalSchemeRetailer_11 | 13290 | 2020-12-16 | To verify if the user is able to redeem the reward point when the total amount is invalid to be redeemed. | User is already logged-in and is on Redeem gift page. | 1) Click on submit button with the case having invalid amount to be redeem. |  |  |  | There should be a proper validation message for it. |  |  | Could not execute
TC_DigitalSchemeRetailer_12 | 13290 | 2020-12-16 | To verify if the user is able to redeem the reward point with the valid amount. | User is already logged-in and is on Redeem gift page. | 1) select the gift card. 2)Click on submit button when there is a valid amount to be redeem. |  |  |  | Dealer should be able to redeem the amount rewarded by scratching coupon through the various Coupons options in the application. -The gifts will also be delivered through the application itself |  |  | Could not execute
TC_DigitalSchemeRetailer_13 | 13290 | 2020-12-16 | To verify if the user is able to redeem multiple cards at once. | User is already logged-in and is on Redeem gift page. | 1) select multiple gift cards. 2)Click on submit button. | Select all 4 cards. | User is able to redeem the multiple gifts at once. | https://lh3.googleusercontent.com/-2ANdRczpouE/X9oHcJV1VWI/AAAAAAAAENM/XHHt-_nYFQU-9eNlMagrnRIImSHZd8yZgCK8BGAsYHg/s0/2020-12-16.jpg | Gift cards should not get redeemed. |  |  | Fail
TC_DigitalSchemeRetailer_14 | 13290 | 2020-12-16 | To verify if the user is able to view the history of coupons in the Coupons HistoryTab. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab |  | 1) No data found toast message is coming when navigating to the Coupons history section. 2) Need to remove "Rs." text. | https://lh3.googleusercontent.com/-3rdaam2vFLY/X9oHbJUEJbI/AAAAAAAAENA/M9R5CAnoau0cH5i3vk0csOI-XRJOr65PgCK8BGAsYHg/s0/2020-12-16.jpg | User should get switch to coupon history section where a drop down option will be there , it contains 2 dynamic option completed and pending. |  |  | Fail
TC_DigitalSchemeRetailer_15 | 13290 | 2020-12-16 | To verify if the user is able to see the history of coupons having Completed as status. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab. 2) Select Completed from the dropdown. |  | 1) App is getting crash when selecting Completed as the status at coupons history screen. |  | App should show the list of coupons details that are completed from the LPT side. |  |  | Fail
TC_DigitalSchemeRetailer_16 | 13290 | 2020-12-16 | To verify if the user is able to see the history of coupons having Pending as status. | User is already logged-in and is on Redeem gift page. | 1) Click on Rewards Hitsory tab. 2) Select Pending from the dropdown. |  | 1) App is getting crash when selecting Pending as the status at coupons history screen. |  | App should show the list of coupons details which are pending. |  |  | Fail
TC_DigitalSchemeRetailer_17 | 13290 | 2020-12-16 | To verify if the user is able to view the list of unscratched coupons. | User is already logged-in and is on Redeem gift page. | 1) Click on unscratched coupons tab |  | 1) No data found toast message is coming when navigating to the Unscratched Coupons section. | https://lh3.googleusercontent.com/-nSJ3wSahrbc/X9oHah16kLI/AAAAAAAAEM8/RKPJ3G9IRDQ2rqJODBNmFHSSYsrv7gWGwCK8BGAsYHg/s0/2020-12-16.jpg | User should get switch to unscratched coupons section where all the unused/unscratched coupons will get appear. |  |  | Fail
TC_DigitalSchemeRetailer_18 | 13290 | 2020-12-16 | to verify if the user is able to scratch a coupon by clicking on it. | User is already logged-in and is on Redeem gift page. | 1) Click on unscratched coupons tab. 2) Click on the coupon you wish to scratch. 3) Scratch the coupon. |  |  |  | When clicking on a particular coupon in the list, a popup will open. There we can scratch it, in order to redeem the giftand the redeemed value should get add in the total rewarded amount. |  |  | Could not execute