## Sheet1
Mercedes-Benz
Lead Dev: Alok Srivastava
Module | No. of test Written | No. of test executed | Pass | Fail
Agreement | 35 | 35 | 35 | 0
Reports | 29 | 29 | 29 | 0
Amendment | 25 | 25 | 25 | 0
certificate Download | 13 | 13 | 13 | 0
Certification Request | 165 | 162 | 162 | 3
Total | 267 | 264 | 264 | 3

## Sheet8
Bug Report
Project :- |  | Mecedes Benz |  |  |  |  | Lead_Devp. :- |  | Alok Srivastava
Created_By :- |  | Sakshi Tiwari |  |  |  |  | Power_Task_I.D. :- |  | 13037
Date | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-11-20 | TC_02/ Cretification_Request | Bug ID_1 | missing of right bracket for Odometer Reading During Certification(Final Xentry | user logged into the system | Click on Certification Request present on top Left of the screen |  |  |  |  | new | Alok Srivastava
2020-11-20 | TC_164/ Cretification_Request | Bug ID_2 | Validation Status : There is a type error in the validation status field if the status is approved. It should be "Approved"instead of Approve. | User is logged in and is already on Certification Request page. | 1)Click on add certification. 2)Enter valid details in all the mandatory fields. 3)Upload valid documents. |  |  |  |  | new | Alok Srivastava
| TC_167/ Cretification_Request | Bug ID_3 | uploaded files are not refelecting | User is logged in and is already on Certification Request page. | 1)Click on created certification number 2)click on Add Document |  |  |  |  | new | Alok Srivastava

## Sheet6
Test Cases
Project Name: Mercedes Benz
Created By:- | Sakshi |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-11-19 |  | Review Date:- |  |  | Power Task ID:
Version: - |  |  | Module:- | Doc Upload Changes
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC1_Doc_Upload | To verify if the user is able to post a comment by entering valid data in the comment section. | User is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Click on Comments link available on the right side menu. 2)Enter a comment on comment section. 3)Click on Post button. |  | Whenever dealer postes a comment by clicking on Post button then the page should also gets refreshed button after getting submitted the comment stays at the same page howver on refresh the page manually the comment appears as posted. |  | User should be able to post a comment after clicking on post button after entering valid data and the same comment should get appear on the comments page and should get sent to the dealer. | High | High | Fail
TC2_Doc_Upload | To verify if the validation status of the selected Certification Request is getting change or not if the status is changed by the assurant person. | User is logged in and is already on Certification Request page. | 1)Click on add certification. 2)Enter valid details in all the mandatory fields. 3)Upload valid documents. |  | Validation Status : There is a typo error in the validation status field if the status is approved. It should be "Approved"instead of Approve. | https://prnt.sc/r05pmq | Validation message should get change to Approved. | Low | Low | Fail
TC3_Doc_Upload | To verify if the validation status of the selected Certification Request is getting change or not if the status is changed by the assurant person. | User is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Click on add certification. 2)Enter valid details in all the mandatory fields. 3)Upload valid documents. |  | Validation Status : There is a typo error in the validation status ffield if the status is approved. It should be "Rejected"instead of Reject. | https://prnt.sc/r05sn1 | Validation message should get change to Rejected. | Low | Low | Fail
TC4_Doc_Upload | To verify if the dealer is able to edit/update the certificate details if the validation status is approved. | User is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Try to edit the certification details. |  | Certification details should get disable to edit and also edit button should get hide. |  |  |  |  | Pass
TC5_Doc_Upload | To verify if the dealer is able to edit/update the certificate details if the validation status is Rejected. | User is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Try to edit the certification details. |  | Certification details should get disable to edit and also edit button should get hide. |  |  |  |  | Pass
TC6_Doc_Upload | To verify if the dealer is able to view the changed validation status made by the asssurant person |  | 1)Login as assurant person. 2)Select the Vin Validation No. whose status is to be change. 3)Change the status from submitted to the query by assurant. |  | Status is changed to query by assurant and the same is appearing to the corresponing dealer. |  | Status should get changed to query by assurant and the same should get appear to the corresponing dealer. |  |  | Pass
TC7_Doc_Upload | To verify if the status is getting changed after the approval/rejection of the certification. | User is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Post a comment or upload any valid document. |  | Status is not gettinh changed. |  | Status should not get change. |  |  | Pass

## Sheet2
Project Name:-> Mercedes_Benz
Created By:- | sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 19.11.2020 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | alok
Version: - |  |  |  |  | Module:- | Time Automation in Claim and Dropdpwn in Part Information.
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Time_Automation_01 | 10500 | 2020-03-25 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor | [5 empty] | Pass
TC_Time_Automation_02 | 10500 | 2020-03-25 | To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor | [5 empty] | Pass
TC_Time_Automation_03 | 10500 | 2020-03-25 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- qwerty | [5 empty] | Pass
TC_Time_Automation_04 | 10500 | 2020-03-25 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim | [6 empty] | Pass
TC_Time_Automation_05 | 10500 | 2020-03-25 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty | [5 empty] | Pass
TC_Time_Automation_06 | 10500 | 2020-03-25 | To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_07 | 10500 | 2020-03-25 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided | [7 empty] | Pass
TC_Time_Automation_08 | 10500 | 2020-03-25 | To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document. | [6 empty] | Pass
TC_Time_Automation_09 | 10500 | 2020-03-25 | To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal. | [8 empty] | Pass
TC_Dropdown_PartInfo_01 | 10502 | 2020-03-25 | To verify if the user is able to view and select the dropdown options of Rejection Remark or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value. | [6 empty] | Pass
TC_Dropdown_LabourInfo_02 | 10502 | 2020-03-25 | To verify if the user is able to view and select the dropdown options of Part Location or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value. | [6 empty] | Pass

## Certificaterequest
Project Name:-> Mercedes_Benz
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-11-19 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:- | Certification_Request
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to login | Login cridential provided | 1)Enter Url 2)Login with valid user name and pwd | url-https://mercedes.innov.co.in/index.php?module=SalesOrder&view=Edit&record=262289 ID :- 5-AD-Hyderabad P.W. :- Welcome@12345 |  |  | should be able to login and redirected to Homepage |  |  | pass
TC_02/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to go to Certification Request page | Dealer is Already Login | Click on Certification Request present on top Left of the screen |  | missing of right bracket for Odometer Reading During Certification(Final Xentry |  | should be Re-directed to Certification Request Page. |  |  | Fail
TC_03/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to open Add Certification form. | Dealer is Already Login | Click on Add Certification present on top left of the screen |  |  |  | Add Certification form shpuld open |  |  | pass
TC_04/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Certification Request Page | Leave all column blank and click on save |  |  |  | This field is required Validation should appear on top of all Mandatory Field |  |  | pass
TC_05/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Certification Request Page | Leave Class blank and fill all the remaining mandatory field. |  |  |  | This field is required Validation will appear on top of Class Field |  |  | pass
TC_06/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop Down will appear on Class | On Creating New Certification Request Page | Click on Class |  |  |  | Dropdown Will appear. |  |  | pass
TC_07/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Leave Vehicle Model blank and fill all the remaining mandatory field |  |  |  | This field is required Validation will appear on top of Vehicle Model Field |  |  | pass
TC_08/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop Down will appear on Vehicle Model | On Creating New Certification Request Page | Click on Vehicle Model |  |  |  | Dropdown Will appear. |  |  | pass
TC_09/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Leave Duration/Tenure blank and fill all the remaining mandatory field |  |  |  | This field is required Validation will appear on top of Duration/Tenure Field |  |  | pass
TC_10/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Leave Vin no. blank and fill all the remaining mandatory field |  |  |  | This field is required Validation will appear on top of Vin no. Field |  |  | pass
TC_11/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 10 digit numeric Vin no. | Vin No. :- 1234567890 |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_12/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 18 digit numeric Vin no. | Vin No. :- 123456789123456789 |  |  | Will not be able to enter 18-Digit Vin No. |  |  | pass
TC_13/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 17 digit numeric Vin no. | Vin No. :- 123456789123456789 |  |  | Invalid Vin No. Validation will appear |  |  | pass
TC_14/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 16 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&* |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_15/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 17 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&*@ |  |  | Invalid Vin No. Validation will appear |  |  | pass
TC_16/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 18 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&*@# |  |  | Will not be able to enter 18-Digit Vin No. |  |  | pass
TC_17/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 16 digit Vin no. | Vin No. :- abcdeabcdeabcdeabc |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_18/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 17 digit Vin no. | Vin No. :- abcdeabcdeabcdeab |  |  | Invalid Vin No. Validation should appear |  |  | pass
TC_19/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 18 digit Vin no. | Vin No. :- abcdeabcdeabcdea |  |  | should not be able to enter 18-Digit Vin No. |  |  | pass
TC_20/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Enter 17 digit Vin no. | Vin No. :- AAAAAAAASDFGHJ123 (alpha-numeric) |  |  | should be able to enter Vin No. |  |  | pass
TC_21/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field and Leave Fuel Type blank. |  |  |  | This field is required validation should appear on Fuel Type. |  |  | pass
TC_22/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop Down will appear on Fuel Type | On Creating New Certification Request Page | Click on Fuel Type |  |  |  | Dropdown should appear. |  |  | pass
TC_23/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field and Leave Standard Warranty Start Date blank. |  |  |  | This field is required validation should appear on Standard Warranty Start Date. |  |  | pass
TC_24/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field | Standard Warranty Start Date :- 03-03-2020 |  |  | validation should appear(Standard Warrany Start Date should be between 2014-11-20 and 2017-11-19). |  |  | pass
TC_25/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field | Standard Warranty Start Date :- 02-03-2015 |  |  | validation should appear(Standard Warrany Start Date should be between 2014-11-20 and 2017-11-19). |  |  | pass
TC_26/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field | Standard Warranty Start Date :-12-07-2016 |  |  | Will accept Standard Warrany Start. |  |  | pass
TC_27/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field | Standard Warranty Start Date :- 04-03-2017 |  |  | Standard Warrany Start Date should be between 2015-03-03 and 2017-03-03 validation will appear. |  |  | pass
TC_28/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Creating New Certification Request | On Creating New Certification Request Page | Fill all the mandatory Field | Standard Warranty Start Date :-12-07-2016 |  |  | Will accept Standard Warrany Start. |  |  | pass
TC_29/ Cretification_Request | 13037 | 2020-11-19 | To verify that Standard Warranty End Date will automatically fetch date on entering Standard Warranty Start Date | On Creating New Certification Request Page | Fill all the mandatory field |  |  |  | Standard Warranty End Date will automatically fetch date on entering Standard Warranty Start Date |  |  | pass
TC_30/ Cretification_Request | 13037 | 2020-11-19 | To verify that Standard Warranty End Date is not editable field | On Creating New Certification Request Page |  |  |  |  | Should not be able to edit Standard Warranty End Date |  |  | pass
TC_31/ Cretification_Request | 13037 | 2020-11-19 | To verify that Vehicle Invoice Date will automatically fetch date on entering Standard Warranty Start Date | On Creating New Certification Request Page | Fill all the mandatory field |  |  |  | Vehicle Invoice Date will automatically fetch date on entering Standard Warranty Start Date |  |  | pass
TC_32/ Cretification_Request | 13037 | 2020-11-19 | To verify that Vehicle Invoice Date is not editable field | On Creating New Certification Request Page |  |  |  |  | Should not be able to edit Vehicle Invoice Date |  |  | pass
TC_33/ Cretification_Request | 13037 | 2020-11-19 | To verify that Transmission Type is a mandatory field | On Creating New Certification Request Page | Leave Transmission Type blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Transmission Type Field |  |  | pass
TC_34/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on Transmission Type | On Creating New Certification Request Page | Click on Transmission Type |  |  |  | Drop down Will appear. |  |  | pass
TC_35/ Cretification_Request | 13037 | 2020-11-19 | To verify that ETG(Engine Transmission Gear Box) is a mandatory field | On Creating New Certification Request Page | Leave ETG(Engine Transmission Gear Box) blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of ETG(Engine Transmission Gear Box) Field |  |  | pass
TC_36/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on ETG(Engine Transmission Gear Box) | On Creating New Certification Request Page | Click on ETG(Engine Transmission Gear Box) |  |  |  | Drop down Will appear. |  |  | pass
TC_37/ Cretification_Request | 13037 | 2020-11-19 | To verify if the option of ETG gets auto filled as "N", As soon as dealer selects "Y" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "Y" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. |  |  |  | N should get selected and saved in ETG field on selecting Y in Comprehensive field. |  |  | pass
TC_38/ Cretification_Request | 13037 | 2020-11-19 | To verify if the option of ETG gets auto filled as "Y", As soon as dealer selects "N" in the Comprehensive field and the same should get saved after submitting the Certification Request form. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Click on Add Certification. 3) Select "N" from the dropdown of Comprehensive field. 4) Enter valid details in remaning mandatory fields. 5) Click on Save button. |  |  | Vin Validation No MBCAR99 | Y should get selected and saved in ETG field on selecting N in Comprehensive field. |  |  | pass
TC_39/ Cretification_Request | 13037 | 2020-11-19 | To verify if the previously filled/selected details are appearing on the Editing Certification Request page. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check ETG(Engine Transmission Gear Box) field. |  |  |  | Edit Certificate page should display all the details entered during the time of creating Certificate request. |  |  | pass
TC_40/ Cretification_Request | 13037 | 2020-11-19 | To verify if the Editing Certification Request page has a Certificate Number attached with the title or not. | Dealer is already logged in. | 1) Click on Certificate Request from menu item. 2) Select the certificate number to be edit. 3) Click on the Edit button. 4) Check Title of the page. |  |  |  | Title of the page should also have Certificate Number at Editing Certification Request page. |  |  | pass
TC_41/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer Location is mandatory Field. | On Creating New Certification Request Page | Leave Dealer Location blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Type of Car Field |  |  | pass
TC_42/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer Location | On Creating New Certification Request Page | Fill all the Mandatory field | Dealer Location :- 212324 |  |  | Invalid Dealer Location validation msg. will appear |  |  | pass
TC_43/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer Location | On Creating New Certification Request Page | Fill all the Mandatory field | Dealer Location :- !@#$% |  |  | Invalid Dealer Location validation msg. will appear |  |  | pass
TC_44/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer Location | On Creating New Certification Request Page | Fill all the Mandatory field | Dealer Location :- qwerty |  |  | Will accept Dealer Location |  |  | pass
TC_45/ Cretification_Request | 13037 | 2020-11-19 | To verify that * Currently under SCP4 is a mandatory field | On Creating New Certification Request Page | Leave Currently under SCP4 blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Currently under Advance assurance Field |  |  | pass
TC_46/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on Currently under Advance assurance | On Creating New Certification Request Page | Click on Currently under Advance assurance |  |  |  | Drop down Will appear. |  |  | pass
TC_47/ Cretification_Request | 13037 | 2020-11-19 | To verify that Odometer Reading during Certification is mandatory field | On Creating New Certification Request Page | Leave Odometer Reading during Certification blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Odometer Reading during Certification Field |  |  | pass
TC_48/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 123456 |  |  | Odometer reading value should be less than 100000 validation will appear |  |  | pass
TC_49/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 0 |  |  | Will accept Odometer Reading during Certification |  |  | pass
TC_50/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 100000 |  |  | Will accept Odometer Reading during Certification |  |  | pass
TC_51/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- -10 |  |  | should not accept negative value in Odometer Reading during Certification |  |  | pass
TC_52/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- qwertyu |  |  | Should not accept alphabet in Odometer Reading during Certification |  |  | pass
TC_53/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Odometer Reading during Certification | On Creating New Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- @#$%^ |  |  | should not accept Special Character in Odometer Reading during Certification |  |  | pass
TC_54/ Cretification_Request | 13037 | 2020-11-19 | To verify that Currently under SCP4 is a mandatory field | On Creating New Certification Request Page | Leave Currently under SCP4 blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Currently under SCP4 Field |  |  | pass
TC_55/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on Currently under SCP4 | On Creating New Certification Request Page | Click on Currently under SCP4 |  |  |  | Drop down Will appear. |  |  | pass
TC_56/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer name is mandatory field | On Creating New Certification Request Page | Leave Dealer name blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Dealer name Field |  |  | pass
TC_57/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer name :- !@#$ |  |  | Will not accept special Character in Dealer name |  |  | pass
TC_58/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer name :- 1234 |  |  | Will not accept numerical value in Dealer name |  |  | pass
TC_59/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer name :- qwerty |  |  | Will accept Alphabet data in Dealer name |  |  | pass
TC_60/ Cretification_Request | 13037 | 2020-11-19 | To verify that Validation Status is a mandatory field | On Creating New Certification Request Page | Leave Validation Status blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Validation Status Field |  |  | pass
TC_61/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on Validation Status | On Creating New Certification Request Page | Click on Validation Status |  |  |  | Drop down Will appear. |  |  | pass
TC_62/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer SPOC Name is mandatory field | On Creating New Certification Request Page | Leave Dealer SPOC Name blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Dealer SPOC Name Field |  |  | pass
TC_63/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Name :- !@#$ |  |  | Will not accept special Character in Dealer SPOC Name |  |  | pass
TC_64/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Name :- 1234 |  |  | Will not accept numerical value in Dealer SPOC Name |  |  | pass
TC_65/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Name | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Name :- qwerty |  |  | Will accept Alphabet data in Dealer SPOC Name |  |  | pass
TC_66/ Cretification_Request | 13037 | 2020-11-19 | To verify that Currently under Certified assurance is a mandatory field | On Creating New Certification Request Page | Leave Currently under Certified assurance blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Currently under Certified assurance Field |  |  | pass
TC_67/ Cretification_Request | 13037 | 2020-11-19 | To verify that Drop down appears on Currently under Certified assurance | On Creating New Certification Request Page | Click on Currently under Certified assurance |  |  |  | Drop down Will appear. |  |  | pass
TC_68/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer SPOC Phone No. is a mandatory field | On Creating New Certification Request Page | Leave Dealer SPOC Phone No. blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Dealer SPOC Phone No. Field |  |  | pass
TC_69/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Phone No. | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- !@#$ |  |  | Please Enter Valid mobile number validation will appear |  |  | pass
TC_70/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Phone No. | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 1234 |  |  | Please Enter 10 digit mobile number validation will appear |  |  | pass
TC_71/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Phone No. | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- qwerty |  |  | Please Enter Valid mobile number validation will appear |  |  | pass
TC_72/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Phone No. | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 1234567890 |  |  | Will accept mobile number |  |  | pass
TC_73/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Phone No. | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 12345678901 |  |  | Will not allow to enter 11-digit mobile number |  |  | pass
TC_74/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer SPOC Email is a mandatory field | On Creating New Certification Request Page | Leave Dealer SPOC Email blank and fill all remaining mandatory field |  |  |  | This field is required Validation will appear on top of Dealer SPOC Email Field |  |  | pass
TC_75/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Email | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Email :- 12345 |  |  | Please enter a valid email address validation msg. will appear |  |  | pass
TC_76/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to enter Dealer SPOC Email | On Creating New Certification Request Page | Fill all the mandatory field | Dealer SPOC Email :- qwerty@asd.zxc |  |  | Will accept Dealer SPOC Email |  |  | pass
TC_77/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Final quick test document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Final quick test file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_78/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach ADD document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Final quick test file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_79/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Technical Evaluation document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Technical Evaluation file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_80/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Technical Evaluation document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Technical Evaluation file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_81/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Vehicles History document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Vehicles History file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_82/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Vehicles History document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Vehicles History file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_83/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Dealer Declaration document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Dealer Declaration file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_84/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to attach Dealer Declaration document | On Creating New Certification Request Page | Fill all the mandatory field | Attach Dealer Declaration file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_85/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Certification | Already Login | 1) Go to certification request page. 2) Open the Certificate that we want to edit | Click on Edit option present on top right of the screen |  |  | Editing Certification Request page will open |  |  | pass
TC_86/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Class | On Editing Certification Request Page | Click on Class | Select different Class |  |  | Will be able to Edit Class. |  |  | pass
TC_87/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Class | On Editing Certification Request Page | Click on Class | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_88/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vehicle Model | On Editing Certification Request Page | Click on Vehicle Model | Select different Vehicle Model |  |  | Will be able to Vehicle Model. |  |  | pass
TC_89/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vehicle Model | On Editing Certification Request Page | Click on Vehicle Model | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_90/ Cretification_Request | 13037 | 2020-11-19 | To verift that dealer is able to Edit Duration/Tenure | On Editing Certification Request Page | Click on Duration/Tenure | Select different Duration/Tenure |  |  | Will be able to Edit Duration/Tenure. |  |  | pass
TC_91/ Cretification_Request | 13037 | 2020-11-19 | To verift that dealer is able to Edit Duration/Tenure | On Editing Certification Request Page | Click on Duration/Tenure | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_92/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Leave Vin no. blank and fill all the remaining mandatory field |  |  |  | This field is required Validation will appear on top of Vin no. Field |  |  | pass
TC_93/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 10 digit numeric Vin no. | Vin No. :- 1234567890 |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_94/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 18 digit numeric Vin no. | Vin No. :- 123456789123456789 |  |  | Will not be able to enter 18-Digit Vin No. |  |  | pass
TC_95/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 17 digit numeric Vin no. | Vin No. :- 123456789123456789 |  |  | Invalid Vin No. Validation will appear |  |  | pass
TC_96/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 16 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&* |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_97/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 17 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&*@ |  |  | Invalid Vin No. Validation will appear |  |  | pass
TC_98/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 18 digit sepcial character Vin no. | Vin No. :- !@#$%^&*!@#$%^&*@# |  |  | Will not be able to enter 18-Digit Vin No. |  |  | pass
TC_99/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 16 digit Vin no. | Vin No. :- abcdeabcdeabcdeabc |  |  | Vehicle Chassis No. can only be of 17 digit validation will appear |  |  | pass
TC_100/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 17 digit Vin no. | Vin No. :- abcdeabcdeabcdeab |  |  | Invalid Vin No. Validation will appear |  |  | pass
TC_101/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 18 digit Vin no. | Vin No. :- abcdeabcdeabcdea |  |  | Will not be able to enter 18-Digit Vin No. |  |  | pass
TC_102/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vin No. | On Editing Certification Request Page | Enter 17 digit Vin no. | Vin No. :- abcde12345abcde12 (alpha-numeric) |  |  | Will be able to enter Vin No. |  |  | pass
TC_103/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Fuel Type | On Editing Certification Request Page | Click on Fuel Type | Select different Fuel Type |  |  | Will be able to Edit Fuel Type |  |  | pass
TC_104/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Fuel Type | On Editing Certification Request Page | Click on Fuel Type | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_105/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Standard Warranty Start Date | On Editing Certification Request Page | Click on Standard Warranty Start Date | Standard Warranty Start Date :- 03-03-2020 |  |  | Standard Warrany Start Date should be between 2015-03-03 and 2017-03-03 validation will appear. |  |  | pass
TC_106/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Standard Warranty Start Date | On Editing Certification Request Page | Click on Standard Warranty Start Date | Standard Warranty Start Date :- 02-03-2015 |  |  | Standard Warrany Start Date should be between 2015-03-03 and 2017-03-03 validation will appear. |  |  | pass
TC_107/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Standard Warranty Start Date | On Editing Certification Request Page | Click on Standard Warranty Start Date | Standard Warranty Start Date :- 03-03-2015 |  |  | Will accept Standard Warrany Start. |  |  | pass
TC_108/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Standard Warranty Start Date | On Editing Certification Request Page | Click on Standard Warranty Start Date | Standard Warranty Start Date :- 04-03-2017 |  |  | Standard Warrany Start Date should be between 2015-03-03 and 2017-03-03 validation will appear. |  |  | pass
TC_109/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Standard Warranty Start Date | On Editing Certification Request Page | Click on Standard Warranty Start Date | Standard Warranty Start Date :- 03-03-2017 |  |  | Will accept Standard Warrany Start. |  |  | pass
TC_110/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Standard Warranty End Date | On Editing Certification Request Page | Click on Standard Warranty End Date |  |  |  | Will not be able to Edit Standard Warranty End Date |  |  | pass
TC_111/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Vehicle Invoice Date | On Editing Certification Request Page | Click on Vehicle Invoice Date |  |  |  | Will not be able to Edit Vehicle Invoice Date |  |  | pass
TC_112/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Transmission Type | On Editing Certification Request Page | Click on Transmission Type | Select different Transmission Type |  |  | Will be able to Edit Transmission Type |  |  | pass
TC_113/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Transmission Type | On Editing Certification Request Page | Click on Transmission Type | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_114/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit ETG(Engine Transmission Gear Box) | On Editing Certification Request Page | Click on ETG(Engine Transmission Gear Box) | Select different ETG(Engine Transmission Gear Box) |  |  | Will be able to Edit ETG(Engine Transmission Gear Box) |  |  | pass
TC_115/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit ETG(Engine Transmission Gear Box) | On Editing Certification Request Page | Click on ETG(Engine Transmission Gear Box) | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_116/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Comprehensive | On Editing Certification Request Page | Click on Comprehensive | Select different Comprehensive |  |  | Will be able to Edit Comprehensive |  |  | pass
TC_117/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Comprehensive | On Editing Certification Request Page | Click on Comprehensive | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_118/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Type of Car | On Editing Certification Request Page | Click on Type of Car | Select different Type of Car |  |  | Will be able to Edit Type of Car |  |  | pass
TC_119/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Type of Car | On Editing Certification Request Page | Click on Type of Car | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_120/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer Location | On Editing Certification Request Page | Leave Dealer Location blank |  |  |  | This field is required Validation will appear on top of Type of Car Field |  |  | pass
TC_121/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer Location | On Editing Certification Request Page | Fill all the Mandatory field | Dealer Location :- 212324 / !@#$% |  |  | Invalid Dealer Location validation msg. will appear |  |  | pass
TC_122/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer Location | On Editing Certification Request Page | Fill all the Mandatory field | Dealer Location :- qwerty |  |  | Will accept Dealer Location |  |  | pass
TC_123/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under Advance assurance | On Editing Certification Request Page | Click on Currently under Advance assurance | Select different Currently under Advance assurance |  |  | Will be able to Edit Currently under Advance assurance |  |  | pass
TC_124/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under Advance assurance | On Editing Certification Request Page | Click on Currently under Advance assurance | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_125/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Leave Odometer Reading during Certification blank |  |  |  | This field is required Validation will appear on top of Odometer Reading during Certification Field |  |  | pass
TC_126/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 123456 |  |  | Odometer reading value should be less than 100000 validation will appear |  |  | pass
TC_127/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 0 |  |  | Will accept Odometer Reading during Certification |  |  | pass
TC_128/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- 100000 |  |  | Will accept Odometer Reading during Certification |  |  | pass
TC_129/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- -10 |  |  | Will not accept negative value in Odometer Reading during Certification |  |  | pass
TC_130/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- qwertyu |  |  | Will not accept alphabet in Odometer Reading during Certification |  |  | pass
TC_131/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Odometer Reading during Certification | On Editing Certification Request Page | Fill all mandatory field | Odometer Reading during Certification :- @#$%^ |  |  | Will not accept Special Character in Odometer Reading during Certification |  |  | pass
TC_132/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under SCP4 | On Editing Certification Request Page | Click on Currently under SCP4 | Select different Currently under SCP4 |  |  | Will be able to Edit Currently under SCP4 |  |  | pass
TC_133/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under SCP5 | On Editing Certification Request Page | Click on Currently under SCP4 | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_134/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer Name | On Editing Certification Request Page | Leave Dealer name blank |  |  |  | This field is required Validation will appear on top of Dealer name Field |  |  | pass
TC_135/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer Name | On Editing Certification Request Page | Fill all the mandatory field | Dealer name :- !@#$ / 1234 |  |  | Will not accept special Character in Dealer name |  |  | pass
TC_136/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer Name | On Editing Certification Request Page | Fill all the mandatory field | Dealer name :- qwerty |  |  | Will accept Alphabet data in Dealer name |  |  | pass
TC_137/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to edit Validation Status | On Editing Certification Request Page | Click on Validation Status | Select different Validation Status |  |  | Will be able to Edit Validation Status |  |  | pass
TC_138/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to edit Validation Status | On Editing Certification Request Page | Click on Validation Status | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_139/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer SPOC Name | On Editing Certification Request Page | Leave Dealer SPOC Name blank |  |  |  | This field is required Validation will appear on top of Dealer SPOC Name Field |  |  | pass
TC_140/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer SPOC Name | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Name :- !@#$ / 1234 |  |  | Will not accept special Character in Dealer SPOC Name |  |  | pass
TC_141/ Cretification_Request | 13037 | 2020-11-19 | To verify that Dealer is able to Edit Dealer SPOC Name | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Name :- qwerty |  |  | Will accept Alphabet data in Dealer SPOC Name |  |  | pass
TC_142/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under Certified assurance | On Editing Certification Request Page | Click on Currently under Certified assurance | Select different Currently under Certified assurance |  |  | Will be able to Edit Currently under Certified assurance |  |  | pass
TC_143/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Currently under Certified assurance | On Editing Certification Request Page | Click on Currently under Certified assurance | Select :- Select an Option |  |  | This field is mandatory validation will appear |  |  | pass
TC_144/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Leave Dealer SPOC Phone No. blank |  |  |  | This field is required Validation will appear on top of Dealer SPOC Phone No. Field |  |  | pass
TC_145/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- !@#$ |  |  | Please Enter Valid mobile number validation will appear |  |  | pass
TC_146/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 1234 |  |  | Please Enter 10 digit mobile number validation will appear |  |  | pass
TC_147/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- qwerty |  |  | Please Enter Valid mobile number validation will appear |  |  | pass
TC_148/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 1234567890 |  |  | Will accept mobile number |  |  | pass
TC_149/ Cretification_Request | 13037 | 2020-11-19 | To Verify that dealer is able to Edit Dealer SPOC Phone No. | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Phone No. :- 12345678901 |  |  | Will not allow to enter 11-digit mobile number |  |  | pass
TC_150/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer SPOC Email | On Editing Certification Request Page | Leave Dealer SPOC Email blank |  |  |  | This field is required Validation will appear on top of Dealer SPOC Email Field |  |  | pass
TC_151/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer SPOC Email | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Email :- asd1234 |  |  | Please enter a valid email address validation msg. will appear |  |  | pass
TC_152/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer SPOC Email | On Editing Certification Request Page | Fill all the mandatory field | Dealer SPOC Email :- qwerty@asd.zxc |  |  | Will accept Dealer SPOC Email |  |  | pass
TC_153/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Final quick test | On Editing Certification Request Page | Fill all the mandatory field | Attach Final quick test file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_154/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Final quick test | On Editing Certification Request Page | Fill all the mandatory field | Attach Final quick test file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_155/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Technical Evaluation | On Editing Certification Request Page | Fill all the mandatory field | Attach Technical Evaluation file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_156/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Technical Evaluation | On Editing Certification Request Page | Fill all the mandatory field | Attach Technical Evaluation file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_157/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vehicles History | On Editing Certification Request Page | Fill all the mandatory field | Attach Vehicles History file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_158/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Vehicles History | On Editing Certification Request Page | Fill all the mandatory field | Attach Vehicles History file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_159/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer Declaration | On Editing Certification Request Page | Fill all the mandatory field | Attach Dealer Declaration file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_160/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Dealer Declaration | On Editing Certification Request Page | Fill all the mandatory field | Attach Dealer Declaration file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_161/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Additional attach doc. | On Editing Certification Request Page | Fill all the mandatory field | Click on Add More Documents attach file upto 5 MB (other than PDF) |  |  | Please Select Pdf file Validation msg. will appear |  |  | pass
TC_162/ Cretification_Request | 13037 | 2020-11-19 | To verify that dealer is able to Edit Additional attach doc. | On Editing Certification Request Page | Fill all the mandatory field | Click on Add More Documents attach file upto 5 MB (In PDF format) |  |  | Will accept PDF file upto 5 MB |  |  | pass
TC_163/ Cretification_Request | 13037 | 2020-11-19 | To verify if the dealer is able to post a comment by entering valid data in the comment section of existing vin number | Dealer is logged in and is already on Certification Request page of added/selected Vin Validation No. | 1)Click on Comments link available on the right side menu. 2)Enter a comment on comment section. 3)Click on Post button. |  |  |  | Dealer should be able to post a comment after clicking on post button after entering valid data and the same comment should get appear on the comments page and should get sent to the dealer. |  |  | pass
TC_164/ Cretification_Request | 13037 | 2020-11-19 | To verify if the validation status of the selected Certification Request is getting change or not if the status is changed by the assurant person. | User is logged in and is already on Certification Request page. | 1)Click on add certification. 2)Enter valid details in all the mandatory fields. 3)Upload valid documents. |  | Validation Status : There is a typo error in the validation status field if the status is approved. It should be "Approved"instead of Approve. |  | Validation message should get change to Approved. |  |  | Fail
TC_165/ Cretification_Request | 13037 | 2020-11-19 | to verify Updates functionality | User is logged in and is already on Certification Request page. | Click on Updates Available on the right side of Certification request page |  |  |  | All the data that dealer and assurant have changed should be visible in order to requirement |  |  | pass
TC_166/ Cretification_Request | 13037 | 2020-11-19 | To verify if data is updated or not | User is logged in and is already on created Certification Request page. | 1)Click on created certification number 2)click Updates |  |  |  | changed data should be with proper time and date |  |  | Pass
TC_167/ Cretification_Request | 13037 | 2020-11-19 | To verify Add Document Functionality (User can be Dealer,Assurant and Admin) | User is logged in and is already on created Certification Request page. | 1)Click on created certification number 2)click on Add Document |  | uploaded files are not refelecting |  | all the file uploaded by users should be refelect on this page |  |  | Fail
| 13037 | 2020-11-19 | To verify that manager is able to change Status from Submitted to Answer by dealer | Login cridential provided of manager | 1) Login with manager ID 2) Open Claim 3) Click on Edit | change Status from Submitted to Answer by dealer |  |  | status should change |  |  | pass
| 13037 | 2020-11-19 | To verify that on changing status ​Submitted to Query By Assurant | Login cridential provided of manager | 1) Login with manager ID 2) Open certification request 3) Click on Edit | changing status ​Submitted to Query By Assurant |  |  | status should change |  |  | pass

## Agreement
Project Name:-> Mercedes_Benz
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-11-20 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:- | Agreement
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Agreement_1 | 13037 | 2020-11-20 | To verify by clicking on agreement | dealer is already logged |  |  |  | as expected | agreement page should displays |  |  | pass
TC_Agreement_2 | 13037 | 2020-11-20 | To verify agreement page | dealer is already logged | click on agreement module |  |  | as expected | should display the users detail with proper |  |  | pass
TC_Agreement_3 | 13037 | 2020-11-20 | To Verify Refresh button for all the sections | Dealer in on home page |  |  |  | as expected | button should be clickable and refresh the section |  |  | pass
TC_Agreement_4 | 13037 | 2020-11-20 | To verify Tab functionality | User is already logged-in |  |  |  |  | Tab functionality should work proper |  |  | pass
TC_Agreement_5 | 13037 | 2020-11-20 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Agreement link under menu item. 2)Click on Add agreement button. |  |  | as expected | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button) |  |  | pass
TC_Agreement_6 | 13037 | 2020-11-20 | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. | NA |  | as expected | System should display a validation message as "Vehicle Chassis No. is required." |  |  | pass
TC_Agreement_7 | 13037 | 2020-11-20 | To verify if the user is able to validate Vehicle Chassis No. by entering invalid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)@@@@######12345 2)01A8A369B45QWERTY 3)ABCD8KGH7JH123456 4)Blank spaces |  | as expected | Validation should appear Chassis no. not avaliable msg. should be displayed |  |  | pass
TC_Agreement_8 | 13037 | 2020-11-20 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3)Click on ok button | Vehicle Chessis No. :- 1)ZXCVBLKJHGF123498 |  | as expected | It should get validate successfully and Check list page open with OK button and redirect to add agreement page |  |  | pass
TC_Agreement_9 | 13037 | 2020-11-20 | To verify if dealer is able to create new agreement | dealer is on new agreement page |  |  |  |  | all the specified fields should present as per the requirement |  |  | pass
TC_Agreement_10 | 13037 | 2020-11-20 | Verify that the required/mandatory fields are marked with * against the field. | dealer is on new agreement page |  |  |  |  | All the mandatory fields should marked with * against the field. |  |  | pass
TC_Agreement_11 | 13037 | 2020-11-20 | Verify the page has both submit and cancel and save buttons | dealer is on new agreement page |  |  |  |  | Agreement page should have both cancel and save buttons. |  |  | pass
TC_Agreement_12 | 13037 | 2020-11-20 | to verify if all the mandatory fields marked with asterisk(*) | Dealer is on Creating New Agreement page |  |  |  | as expected | all the mandatory gields should have with asterisk(*). |  |  | pass
TC_Agreement_13 | 13037 | 2020-11-20 | To verify the computed data is not editable by dealer | Dealer is on Creating New Agreement page |  |  |  |  | Should not allowed to change/ enter any computed data |  |  | pass
TC_Agreement_14 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving all the field blank | Dealer is on Creating New Agreement page | leave all the mandatory fields and Click on Save button |  |  |  | Dealer should not be able to create new agreement |  |  | pass
TC_Agreement_15 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave First Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | pass
TC_Agreement_16 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | pass
TC_Agreement_17 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Mobile phone field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Mobile phone field "this field is required." |  |  | pass
TC_Agreement_18 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Primary Email field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Primary Emailfield blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Primary Email field "this field is required." |  |  | pass
TC_Agreement_19 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Address field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Address field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Address field "this field is required." |  |  | pass
TC_Agreement_20 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Postal Code field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) LeavePostal code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Postal code field "this field is required." |  |  | pass
TC_Agreement_21 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Address field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Address field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Address field "this field is required." |  |  | pass
TC_Agreement_22 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving City field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave City field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for City field "this field is required." |  |  | pass
TC_Agreement_23 | 13037 | 2020-11-20 | To verify that Drop Down will appear on City | User is already logged in and is on New Agreement page. | Click on City |  |  |  | Dropdown Will appear. |  |  | pass
TC_Agreement_24 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving State field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Statefield blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for State field "this field is required." |  |  | pass
TC_Agreement_25 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Assigned To field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Assigned To field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Assigned To field "this field is required." |  |  | pass
TC_Agreement_26 | 13037 | 2020-11-20 | To verify that Drop Down will appear on Assigned To | User is already logged in and is on New Agreement page. | Click on Assigned To |  |  |  | Dropdown Will appear. |  |  | pass
TC_Agreement_27 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Sold By Exec Name field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Sold By Exec Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Sold By Exec Name field "this field is required." |  |  | pass
TC_Agreement_28 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Sold By Exec ID field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Sold By Exec ID field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Sold By Exec ID field "this field is required." |  |  | pass
TC_Agreement_29 | 13037 | 2020-11-20 | To verify if price Type is Not Editable | User is already logged in and is on New Agreement page. |  |  |  |  | Price type should not be able to change |  |  | pass
TC_Agreement_30 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving Registration No field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Registration No field "this field is required." |  |  | pass
TC_Agreement_31 | 13037 | 2020-11-20 | To verify if the User is able to create new Agreement by leaving * Odometer Reading During Certificate Issuance field field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave * Odometer Reading During Certificate Issuance field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for * Odometer Reading During Certificate Issuance field "this field is required." |  |  | pass
TC_Agreement_32 | 13037 | 2020-11-20 | To verify if the user is able to create neew agreement by leaving Certification Technical Report upload * and enter valid details in all the remaining fields | User is already logged in and is on New Agreement page. | 1) Leave Certification Technical Report upload field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Agreement and the system must display a proper and specific validation message for * Certification Technical Report upload field "this field is required." |  |  | pass
TC_Agreement_33 | 13037 | 2020-11-20 | To verify if the user is able to create neew agreement by leaving Certified Assurance Plan and enter valid details in all the remaining fields | User is already logged in and is on New Agreement page. | 1) Leave Certified Assurance Plan upload field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Agreement and the system must display a proper and specific validation message for Certified Assurance Plan field "this field is required." |  |  | pass
TC_Agreement_34 | 13037 | 2020-11-20 | To verify if the user is able to create new agreement by entering valid details in all the remaining fields | User is already logged in and is on New Agreement page. | 1)Enter valid details in the remianing fields. 2)Click On Save Button. |  |  |  | User should be able to create new agreement |  |  | pass
TC_Agreement_35 | 13037 | 2020-11-20 | To verify if user able to generate certifcate | User is on agreement page | 1)Click on Generate Agreement Certificate |  |  |  | User should be able to download his/her certificate |  |  | pass

## CertificateDownload
Project Name:-> Mercedes_Benz
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-11-20 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:- | Agreement
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Agreement_1 | 13037 | 2020-11-20 | Verify the generated certificate | User logged into the system | Select any Existing Agreement number and generate Certificate |  |  |  | User should be able to generate Certificate |  |  | pass
TC_Agreement_2 | 13037 | 2020-11-20 | To verify is user is able to download the certificate | User logged into the system | Select any Existing Agreement number and generate Certificate | Agreement number=MBCA1139 |  |  | User should be able to generate Certificate |  |  | pass
TC_Agreement_3 | 13037 | 2020-11-20 | To verify if the downloaded file size is same as per specification | User logged into the system | Check File size |  |  |  | Dowloaded file size should be same, which was showing before dowload |  |  | pass
TC_Agreement_4 | 13037 | 2020-11-20 | to verify if the downloaded file | User logged into the system |  |  |  |  | Downloaded file should be saved at the predefined location |  |  | pass
TC_Agreement_5 | 13037 | 2020-11-20 | To verify if user is able to open the certifcate | User logged into the system | open file |  |  |  | user should be able to open the downloaded file |  |  | pass
TC_Agreement_6 | 13037 | 2020-11-20 | To verify is user is able to download the certificate | User logged into the system | Select any Existing Agreement number and generate Certificate | Agreement number= |  |  | User should be able to generate Certificate |  |  | pass
TC_Agreement_7 | 13037 | 2020-11-20 | To verify if the downloaded file size is same as per specification | User logged into the system | Check File size |  |  |  | Dowloaded file size should be same, which was showing before dowload |  |  | pass
TC_Agreement_8 | 13037 | 2020-11-20 | to verify if the downloaded file | User logged into the system |  |  |  |  | Downloaded file should be saved at the predefined location |  |  | pass
TC_Agreement_9 | 13037 | 2020-11-20 | To verify if user is able to open the certifcate | User logged into the system | open file |  |  |  | user should be able to open the downloaded file |  |  | pass
TC_Agreement_10 | 13037 | 2020-11-20 | To verify is user is able to download the certificate | User logged into the system | Select any Existing Agreement number and generate Certificate | Agreement number=MBCA1139 |  |  | User should be able to generate Certificate |  |  | pass
TC_Agreement_11 | 13037 | 2020-11-20 | To verify if the downloaded file size is same as per specification | User logged into the system | Check File size |  |  |  | Dowloaded file size should be same, which was showing before dowload |  |  | pass
TC_Agreement_12 | 13037 | 2020-11-20 | to verify if the downloaded file | User logged into the system |  |  |  |  | Downloaded file should be saved at the predefined location |  |  | pass
TC_Agreement_13 | 13037 | 2020-11-20 | To verify if user is able to open the certifcate | User logged into the system | open file |  |  |  | user should be able to open the downloaded file |  |  | pass

## Sheet5
To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor
To verify that on changing status ​Submitted to Pending with surveyor, Request for S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor
To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- qwerty
To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim
To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty
To verify that First Action Date and First Action Time automatically gets captured on adding claim manager name | Login cridential provided
To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided
To verify if the System will capture the time of last submitted document in portal prior to change the status “approved/rejected” in portal. | User is logged in as a claim manager. | 1) Open the claim whose status needs to be changed. 2) go to comment section and add a comment. 3) System should capture the Claim matured date & time. 4) Now clear the Claim matured date & time and upload any new document.
To verify if the System will capture the time of last submitted comment in portal prior to change the status “approved/rejected” in portal.
To verify if the user is able to view and select the dropdown options of Rejection Remark or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value.
To verify if the user is able to view and select the dropdown options of Part Location or not. | User is logged in and is already on creating new claim page. | 1) Click on Add Labour Information. 2) Click on Rejection Remark in order to see the dropdown value.

## Amendment
Project Name:-> Mercedes_Benz
Created By:- | Sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-11-20 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:-Amendment
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
Amendment_TC_1 | 13037 | 2020-11-20 | To verify if dealer is able to create new certificate | Dealer is logged into the system | 1)Enter URL 2)Log in valid Credentials 3) click on Create certificate 4)Click on add create | 1)url-https://mercedes.innov.co.in/index.php?module=SalesOrder&view=Edit&record=262289 2)User name -5-AD-Hyderabad 3)pwd-Welcome@12345 |  |  | Dealer should be able to create certificate and should display Creating New Certification Request page |  |  | pass
Amendment_TC_2 | 13037 | 2020-11-20 | To verify if dealer is can create new certificate by clicking on save button without filling any data in the mandatory fields | Dealer is logged into the system | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | Dealer should not be able to create a new Cerfificate and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Amendment_TC_3 | 13037 | 2020-11-20 | To verify if the dealer is able to create new Certificate without selecting class drop-down and enter valid details in the remaining fields. | Dealer is logged into the system | 1) Class fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Dealer should not be able to create a new Cerfificate and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Amendment_TC_4 | 13037 | 2020-11-20 | To verify if the dealer is able to create new Certificate by leaving Vehicle Model field blank and enter valid details in the remaining fields. | Dealer is logged into the system | 1) don’t select any * Vehicle Model. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Dealer should not be able to create a new Cerfificate and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Amendment_TC_5 | 13037 | 2020-11-20 | To verify if the dealer is able to create new cerificate by entering valid data in all the mandatory fields | Claim Manager is already logged in. |  |  |  |  | Should create new agreement successfully |  |  | pass
Amendment_TC_6 | 13037 | 2020-11-20 | To verify if manager is appoving the certificate | Claim Manager is already logged in. | 1)Enter URL 2)Log in valid Credentials | 1)https://mercedes.innov.co.in/index.php?module=SalesOrder&view=Edit&record=262289 2)User name-Demo-Assurant 3)Pwd-Welcome@123456 |  |  | Claim manager should get navigate to the certificate Request details page of selected Vin Validation No. |  |  | pass
Amendment_TC_7 | 13037 | 2020-11-20 | To verify if the claim manager is getting navigated to the details of Certification Request of the selected Vin Validation No. | Claim Manager is already logged in. | 1) Click on Certificate Request option available in the Menu items. 2) Click on the Vin Validation No to be edited. |  |  |  | Claim manager should get navigate to the certificate Request details page of selected Vin Validation No. |  |  | pass
Amendment_TC_8 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Class field by clicking the field-name. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Class field in order to edit it. 2) Select the valid Values from the dropdown. |  |  |  | Class field should get updated in the selected Certificate Request. |  |  | pass
Amendment_TC_9 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Class field by leaving class name field blank. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Class field in order to edit it. 2) Select the " Select an option" from the dropdown. |  |  |  | Certificate Request form should not get updated and also there should be a proper validation message for the same. |  |  | pass
Amendment_TC_10 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Vehicle Model field by clicking the field-name. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Vehicle Model field in order to edit it. 2) Select the valid Values from the dropdown. |  |  |  | Vehicle Model field should get updated in the selected Certificate Request. |  |  | pass
Amendment_TC_11 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Vehicle Model field by leaving Vehicle Model field blank. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Vehicle Model field in order to edit it. 2) Select the " Select an option" from the dropdown. |  |  |  | Certificate Request form should not get updated and also there should be a proper validation message for the same. |  |  | pass
Amendment_TC_12 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Duration/Tenure field by leaving class name field blank. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Duration/Tenure field in order to edit it. 2) Select the " Select an option" from the dropdown. |  |  |  | Certificate Request form should not get updated and also there should be a proper validation message for the same. |  |  | pass
Amendment_TC_13 | 13037 | 2020-11-20 | To verify if the claim manager is able to directly edit the Duration/Tenure field by clicking the field-name. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the Duration/Tenure field in order to edit it. 2) Select the valid Values from the dropdown. |  |  |  | Duration/Tenure field should get updated in the selected Certificate Request. |  |  | pass
Amendment_TC_14 | 13037 | 2020-11-20 | To verify if the claim manager is VIN (Vehicle identification number) field by leaving VIN field blank. | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | 1)Click on the VIN (Vehicle identification number) field in order to edit it. 2) Clear the previously filled data and click anywhere outside the field. |  |  |  | VIN (Vehicle identification number) should not get updated and also there should be a proper validation message for the same "VIN Number already exists in the database". |  |  | pass
Amendment_TC_15 | 13037 | 2020-11-20 | To verify if manager is appoving the certificate by selecting the price and Validation Status | Claim Manager is already logged in and is on Certificate Request details page of the selected vin number. | select Price Type as standard and select Approve for Validation status |  |  |  | Manager should approve the certificate |  |  | pass
Amendment_TC_16 | 13037 | 2020-11-20 | to verify if dealer is able to punch the agreement | Dealer is logged into the system | 1)Enter URL 2)Log in valid Credentials 3) click on Create certificate 4)Click on add create | 1) 2)User name -5-AD-Hyderabad 3)pwd-Welcome@1234 | New Agreement page open |  | should display new agreement page and Dealer sholud able to create new agreement |  |  | pass
Amendment_TC_17 | 13037 | 2020-11-20 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Agreement link under menu item. 2)Click on Add agreement button. |  |  | as expected | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button) |  |  | pass
Amendment_TC_18 | 13037 | 2020-11-20 | To verify if the dealer is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | Dealer is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- POIUJKHFGTVB45678 |  | as expected | It should get validate successfully and a pop-up of Agreement details should get appear with OK & Cancel button. |  |  | pass
Amendment_TC_19 | 13037 | 2020-11-20 | To verify if the Dealer is able to create new Agreement by leaving all the mandatory fields blank. | User is already logged in and is on Agreement page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  | as expected | User should not be able to create a new Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Amendment_TC_20 | 13037 | 2020-11-20 | to verify by entering valid data in all the fields | Dealer is already logged in and is on New Agreement page. | 1)enter valid data in all the fields 2) click on save button |  |  | as expected | Before Creating should ask for creating agreement with proper validation "Have you checked the complete Certification Technical Report upload thoroughly ?" |  |  | pass
Amendment_TC_21 | 13037 | 2020-11-20 | to verify by entering valid data in all the fields | Dealer is already logged in and is on New Agreement page. | 1)enter valid data in all the fields 2) click on save button |  |  | as expected | dealer should be to create new agreement and redirect to the next page of MBCA1139 |  |  | pass
Amendment_TC_22 | 13037 | 2020-11-20 | To verify if dealer is able to amend the info | Dealer is already logged in and is on New Agreement page. | Click on amendment button and change the City and State | City-from Delhi to Bengaluru State-Karnataka |  |  | should ask from dealer to confirm for the amendment with proper validation "Please confirm the data you have entered is correct by click on OK, Once the OK has been selected you can not do any further changes" |  |  | pass
Amendment_TC_23 | 13037 | 2020-11-20 | Verify if manager is accepting the agreement by changing the status | Manager is logged |  |  |  |  | manager should accept or reject the agreement |  |  | pass
Amendment_TC_24 | 13037 | 2020-11-20 | to verify the status of the agreement | Dealer is logged into the system again |  |  |  |  | Status should be changed from pending to accept |  |  | pass
Amendment_TC_25 | 13037 | 2020-11-20 | Verify if dealer is able to amend by selecting the agreement number which have been created 15 days back from todays date | dealer logged into the system | Selecting the agreement number MBCA862 |  | amendment button is not visible for this agreement number |  | Dealer should not be able to amend his/her agreement |  |  | pass

## Reports
Project Name:-> Mercedes_Benz
Created By:- | sakshi |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-11-19 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:- | Reports
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Report_1 | 13037 | 2020-11-19 | To verify if the user is able to get navigate to the reports section. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant | 1) Click on Reports menu item. 2)Click on the certificate request report link, | NA |  |  | User should get navigate to the reports page. |  |  | pass
TC_Report_2 | 13037 | 2020-11-19 | To verify if the user is able to download the report by leaving start date , end date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the fields blank. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report and should have a proper vaildation. |  |  | pass
TC_Report_3 | 13037 | 2020-11-19 | To verify if the user is able to download the report by leaving start date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the start date fields blank and enter valid data in the end date. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report and ask for to Please enter Start Date. |  |  | pass
TC_Report_4 | 13037 | 2020-11-19 | To verify if the user is able to download the report by leaving start date blank. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Leave all the start date fields blank and enter valid data in the end date. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | pass
TC_Report_5 | 13037 | 2020-11-19 | To verify if the user is able to download the report by entering invalid data in start date. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the start date field and enter valid data in the end date. 2)Click on Generate Now button. | Start Date: ijugkjghgh End Date: kjbhkhb | User is able to download the report by entering invalid data in start and also there is no validation message for the same. |  | User should not be able to download the report. |  |  | pass
TC_Report_6 | 13037 | 2020-11-19 | To verify if the user is able to download the report by entering invalid data in enddate. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter invalid data in the end date field and enter valid data in the start date. 2)Click on Generate Now button. | Start Date: kjhjkhk End Date: kjbhghghghghkg | User is able to download the report by entering invalid data in end date and also there is no validation message for the same. |  | User should not be able to download the report. |  |  | pass
TC_Report_7 | 13037 | 2020-11-19 | To verify if the user is able to download the report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should not be able to download the report. |  |  | pass
TC_Report_8 | 13037 | 2020-11-19 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | pass
TC_Report_9 | 13037 | 2020-11-19 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | pass
TC_Report_10 | 13037 | 2020-11-19 | To verify if the option to view and download the report is available in Dealer login or not. | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link, | demo-dealer Welcome@1234 | There is no option available to view/download the report in dealer login. |  | User should get navigate to the reports page. |  |  | pass
TC_Report_11 | 13037 | 2020-11-19 | To verify if the user is able to view the certificate on portal or not. | User is logged in as Dealer. | 1)Click on Certificate Request menu item. 2)Click on the certificate request to be open |  | There is a spelling mistake in the Certificate Request field -Odometer Reading During Certification(Final Xentry |  | Certificate Request should get open with all the fields. |  |  | pass
TC_Report_12 | 13037 | 2020-11-19 | To verify if the Certificate Request Miscellaneous Report has Certification Request date or not, | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | pass
TC_Report_13 | 13037 | 2020-11-19 | To verify if the Certificate Request Mis Report has Certification Approval Date or not. | User is logged in as Dealer. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | pass
TC_Report_14 | 13037 | 2020-11-19 | To verify if the Certificate Request Mis Report has Certification Request date or not, | User is logged in as Claim Manager | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | pass
TC_Report_15 | 13037 | 2020-11-19 | To verify if the Certificate Request Miscellaneous Report has Certification Approval Date or not. | User is logged in as Claim Manager | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | pass
TC_Report_16 | 13037 | 2020-11-19 | To verify if the Certificate Request Miscellaneous Report has Certification Request date or not, | User is logged in as Admin. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Request Date. |  |  | pass
TC_Report_17 | 13037 | 2020-11-19 | To verify if the Certificate Request Miscellaneous Report has Certification Approval Date or not. | User is logged in as Admin. | 1) Click on Reports menu item. 2)Click on the certificate request report link. 3)Enter valid start and end date. 4)Click on Generate Now button. 5) Check the downloaded report. | NA |  |  | Report should have Certification Approval Date. |  |  | pass
TC_Report_18 | 13037 | 2020-11-19 | To verify if the user is able to download the CA Sales report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should be able to download the report. |  |  | pass
TC_Report_19 | 13037 | 2020-11-19 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | pass
TC_Report_20 | 13037 | 2020-11-19 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | pass
TC_Report_21 | 13037 | 2020-11-19 | To verify if the user is able to download the Claim Report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should be able to download the report. |  |  | pass
TC_Report_22 | 13037 | 2020-11-19 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | pass
TC_Report_23 | 13037 | 2020-11-19 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | pass
TC_Report_24 | 13037 | 2020-11-19 | To verify if the user is able to download the Claim Labour Report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should be able to download the report. |  |  | pass
TC_Report_25 | 13037 | 2020-11-19 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | pass
TC_Report_26 | 13037 | 2020-11-19 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | pass
TC_Report_27 | 13037 | 2020-11-19 | To verify if the user is able to download the Claim Part Information Report by entering valid data in both the fields. (User can be Dealer,Assurant and Admin) | User is logged in as Assurant and is on reports page. | 1) Enter valid data in both the fields. 2)Click on Generate Now button. | NA |  |  | User should be able to download the report. |  |  | pass
TC_Report_28 | 13037 | 2020-11-19 | To verify if the fields name in the downloaded report is same as that of field names in the portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the names of the fields in portal and report is same or not. |  | Dealer Name is "Certifying Dealer" in downloaded report and Dealer Location is "Location" |  | Field names in both portal and report should be identical. |  |  | pass
TC_Report_29 | 13037 | 2020-11-19 | To verify if the data appearing in the downloaded report is same as that of portal. | User is logged in and is on reports page. | 1)Download the report by entering valid data in all the mandatory fields. 2)Open the downloaded report. 3)Closely verify the data of the fields in portal and report is same or not. |  |  |  | Data corresponding to each field in both portal and report should be identical. |  |  | pass