## OnGrid Apk-Bugs
Bug Report
Project :- |  | Mpartner-OnGrid APK |  |  |  |  | Lead_Devp. :- |  | Shalu
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 12619
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Developers Status | Retesting Power ID | Retesting Date | Retesting Power ID | Retesting Date | Testers Comments | Open_Date | Close_Date
12619 | NA | 1 | Solar Load Calculator: No error appears for entering invalid pin number | User is already logged-in as distributor | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invlid data in Pin code and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 000000, 00,1235 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 2 | Solar Load Calculator: No error appears for entering invalid monthly bills. | User is already logged-in as distributor | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invalid data in Pin Monthly bill and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 0 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 3 | Solar Load Calculator: App does not calculate the load even with the valid data. That is nothing happens when clicking on calculate button with valid data. | User is already logged-in as distributor | s | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu | done showing dialog and server response will take time , and after then error message show | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 4 | Solar Load Calculator: No error appears for entering invalid pin number | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invlid data in Pin code and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 000000, 00,1235 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 5 | Solar Load Calculator: No error appears for entering invalid monthly bills. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invalid data in Pin Monthly bill and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 0 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 6 | Solar Load Calculator: App does not calculate the load even with the valid data. That is nothing happens when clicking on calculate button with valid data. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu | done showing dialog and server response will take time , and after then error message show | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 7 | Side Menu: Duplicate Solar Calculator option is there under side menu options. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 8 | Solar Load Calculator: Server issues is coming when clicking on Calculate button. So therefore i am not able to verify the further process. | User is already logged-in as distributor. | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 9 | Solar Load Calculator: Server issues is coming when clicking on Calculate button. So therefore i am not able to verify the further process. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12646 | NA | 10 | Solar Load Calculator: Server issues is coming when clicking on Calculate button by entering monthly bill of large amount (400000Rs or 500000Rs) | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=400000,500000 | Video shared on hangout | High | High | Deferred | Shalu | We can't add any limitation of the bill at our end. already discuss with Jyoti ma'am. |  |  | 12646 | 16-10-2020
12646 | NA | 11 | Solar Load Calculator: Server issues is coming when clicking on Calculate button by entering monthly bill of small amount (200rs or 150rs) | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | Video shared on hangout | High | High | Deferred | Shalu | We can't add any limitation of the bill at our end. already discuss with Jyoti ma'am. |  |  | 12646 | 16-10-2020
12646 | NA | 12 | On Grid System: Generate,Consume, Export and Save links are not working. That is they are not clickable. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | https://prnt.sc/v0c5pv | High | High | Deferred | Shalu | Generate, Consume, Export, and Save links are the static header there is no click, Its a non- linkable heading, UI is as per ios. |  |  | 12646 | 16-10-2020
12646 | NA | 13 | On Grid System: Click here link is not working under your estimate header. That is its not clickable. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | https://prnt.sc/v0c6yy | High | High | Fixed-Link removed | Shalu | done |  |  | 12646 | 16-10-2020
12646 | NA | 14 | Suggestion:On grid solar report:When sharing this file, there should be a some pre-written description about the report. |  |  |  | https://prnt.sc/v0c97q | High | High | Deferred | Shalu | Suggestion: we need to discuss it with the client. |  |  | 12646 | 16-10-2020
12646 | NA | 15 | On Grid System: After saving the results once report gets downloaded and then If user clicks on the share button then app again downloads the report which is wrong. App should only display the sharing option it does not download the report in such cases. |  |  |  |  | High | High | Deferred | Shalu | As per client requirement, we can share and download. |  |  | 12646 | 16-10-2020

## Solar On Grid Calculator Proces
S. No | Feedback | Observation | Screenshot | Status
1 | When selecting state other than 7 listed states, cursor is just loading As discussed, other remaining states should be linked to output of DELHI NCR | 1) I have selected 799155 and 515001 as pincode but on selecting them system shows “Server Issue. Please try again later” toast msg. 2) When entering 510051 as pin code, it gets changed to 110043 and app goes into “Please wait” loop. | Video shared. | Fixed
2 | Added Tree Should be in number value, not percentage value |  |  | Fixed
3 | fields are not kept optional as discussed, form should have SKIP option |  |  | Fixed
4 | SAVE RESULTS button and SHARE icon have same functions, both asks for form filling and then provides sharing options SAVE RESULTS button should save the report directly in mobile once it is pressed | Customer Information pop up is not coming when clicking on Save Results button. |  | Fixed
5 | When sharing report, it is coming in a tabular format Report should be similar to output which comes in app along with Customer’s and Partner’s details along with product features and below disclaimer at the end of the report also- *Actual calculations and results for the site/location/application may vary from case to case depending on the actual ground conditions specific to the user. Users are advised to avail the facility of a site survey done by Luminous Channel Partners before undertaking actual solar installation. Report should also have Luminous logo in it | 1) Complete details are not coming in the PDF as that of the output of the app. Right side portions are cropped. 2) Customers/Partners details are overlapping with the output of the app result. 3) Not disclaimer is appearing in the PDF report. | 1)https://prnt.sc/vd63yq 2)https://prnt.sc/vd66xy | Fixed
6 | customer’s details filled in form are coming under partner’s details in report |  | 1)https://prnt.sc/vd66xy 2)https://prnt.sc/vd6tcf | Fixed
7 | partner’s details filled in form are coming under customer’s details in report |  | 1)https://prnt.sc/vd66xy 2)https://prnt.sc/vd6tcf | Fixed
8 |  | Not Validation comes for entering invalid Mobile number and Invalid email address in customer information form. | https://prnt.sc/vd99st | Fixed
9 |  | App is getting crash when submitting the solar calculator form with pin code 510051 which is a valid pin code of anantpur state | Video shared on group | Fixed
10 |  | share icon needs to be removed from the downloaded PDF file | https://lh3.googleusercontent.com/-INX3MSknOm4/X6T1YFQvR4I/AAAAAAAAC10/IUr0S8HqgwI5fDjv3g-oQ0294q3EabZLgCK8BGAsYHg/s0/2020-11-05.png | Fixed
11 |  | Customer address is missing from the downloaded PDF file | https://lh3.googleusercontent.com/-9HHDg1dWJlk/X6T4__Fad7I/AAAAAAAAC2c/5DzrKC-xZw0KZCkSgiEHFrEoBpU2TLW2gCK8BGAsYHg/s0/2020-11-05.png | Fixed

## Summary
Mpartner-Solar Calculator
Lead Dev: Shalu
Module | No. of test Written | No. of test executed | Fixed | Not Fixed | New | Deffered
Solar Calculator | 23 | 23 | 12 | 5 | 1 | 5
Total | 23 | 23 | 12 | 9 | 1 | 5

## eWarranty- Pine lab Integration
S. No | Feedback | Observation | Screenshot | Status
1 | 1) Cannot unblock dealer once it is blocked, pressing unblock button shows message “Blocked successfully” |  |  | Fixed
2 | 2) Footer icons were again missing at the first time login |  |  | I have not faced this issue
3 | 3) Received OTP from pinelabs page, but after submitting otp and clicking login button, it gets logged out |  |  | Fixed
4 | 4) Could not check the dealer id since I cannot unblock it from app |  |  | Fixed- I am able to block and unbloack through distributor
5 |  | I am.logged in as a distributor and I am getting this toast msg. | https://lh3.googleusercontent.com/-Os9CGZQ0tss/X6PCjG68kLI/AAAAAAAACwY/i4YMMPnAVdEydhzPoz5wdPaMIZYFMKNKACK8BGAsYHg/s0/2020-11-05.jpg | Fixed
6 |  | No data found toast msg is wrong. But There are two records | https://lh3.googleusercontent.com/-8Y2Yxh5llbQ/X6PDysxHN3I/AAAAAAAACws/YopjQo7gHrsXj9xzKoXOdpq0-Z3snPORgCK8BGAsYHg/s0/2020-11-05.jpg | Fixed
7 |  | I have blocked two dealers (9900000001 and 9900000002) from distributor 9999995 but in toast msg on both the dealer login, distributor name is wrong. | https://prnt.sc/vdwz9k https://prnt.sc/vdwzsn | Fixed
8 |  | When i logout from the Pinelab then app should redirect me to the Pinelab home page ( Page where “Enter” button appears.) but currently app is redirecting to the dashboard section of the ewarranty. | Video shared with the developer | Fixed
9 |  | Distributor 2 is able to block/unblock the dealers blocked by distributor 1. |  | Fixed

## Sheet18
Given many time shalu
http://166.62.100.102/UserVerificationPermission/Index
Userid - Admin
PWD - W@admin