## Test cases
Project Name:->HRM
Created By:- | Saurabh Saini |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-07-27 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Swetha/Rahul
Version: - |  |  |  |  | Module:- | HRM
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severity | iOS Status | Android Status
Installation
App Installation | 11642 | 2020-07-27 | Verify whether the application has been installed successfully or not. | 1) Connect the device with internet. 2) User must have an apk file. | 1. Open the google drive on which the apk has shared in Android mobile device. 2. Install it. | NA | 1) App has successfully launched 2) App icon is visible |  | 1) App should get installed 2)App icon should be visible in the device launcher | High | High | Pass
App icon | 11642 | 2020-07-27 | Verify whether the app icon is as per the design or not | User must have installed the app. | 1. Open the google drive on which the apk has shared in Android mobile device. 2. Install it. | NA | After installation App icon is as per the design |  | The app icon should be as per the design provided. | High | Low | Pass
App launch | 11642 | 2020-07-27 | Verify whether the application has been launched successfully or not. | User must have installed the app. | 1. Tap on the app icon | NA | App is successfully launched and the splash screen is appearing |  | When user tap on the App icon the app should get launched and the splash screen should appear. | High | High | Pass
Splash Screen | 11642 | 2020-07-27 | Verify that the application’s display shall adapt to the screen size | User must have installed the app. | 1.Tap on the mobile app icon on the screen | NA | The splash adapt the device size |  | The splash screen should adapt to the device screen size. | High | Major | Pass
Landing Screen | 11642 | 2020-07-27 | Verify Landing screen after splash screen. | User must have installed the app. | 1.Tap on the mobile app icon on the screen. 2. Splash screen will appear. 3. Wait for few seconds. | NA | The landing page is appearing after the splash screen |  | After the splash screen landing page of the app should appear. | High | High | Pass
Login
Login Screen | 11642 | 2020-07-27 | Verifying the functionality of employee code field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login screen will appear 3) Enter the 5-digit valid employee code | Employee code: 10019 | After tapping on 'NEXT' button user redirect to the OTP screen |  | After entering the employee code user should redirect to OTP screen | High | High | Pass
Login Screen | 11642 | 2020-07-27 | Verifying the functionality of employee code field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login screen will appear 3) Enter the 5-digit invalid employee code | Employee code: 10035 | Getting the message please enter the employee code |  | After entering the invalid employee code user should get a message "please enter the valid employee code" | Medium | High | Pass
Login Screen | 11642 | 2020-07-27 | Verifying the functionality of employee code field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login screen will appear 3) Tap on the employee field code | NA | Getting only numeric keyboard |  | After tapping on the employee code only numeric keyboard should open | Low | Minor | Pass
Login Screen | 11642 | 2020-07-27 | Verifying the functionality of employee code field | 1) User must have installed the app 2) Do not Connect the device with internet. | 1) Launch the App 2) Login screen will appear 3) Tap on the employee field code and enter the code 4) Disconnect from internet 5) Tap on Send OTP button | Employee code: 10036 | Got the message "please connect to internet |  | User should get the message "please connect to internet" | Medium | High | Pass
Login Screen | 11642 | 2020-07-27 | Verifying the functionality of employee code field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login screen will appear 3) Do not enter the Employee code and tap on the Send OTP button | NA | Without entering the employee code tapping on send otp gives a message " please enter employee id" |  | After tapping on Send OTP button without entering the employee code user should get the message "Please enter the Employee code first" | Medium | High | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the content on the OTP screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button | Employee code: 10019 | All the details are appearing as per the requirement |  | Below Content should appear on the OTP verification screen: 1) OTP enter field 2) Confirm Button 3) Resend Button 4) Timer 5) Message " we have sent you OTP password to validate your number 'Mobile no'. | Medium | Major | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the OTP field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button | 1) Employee code: 10019 2) OTP send to phone no | Navigating to home page |  | After tapping on confirm OTP field user should navigate to home page | Medium | High | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the OTP field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the invalid 4 digit OTP 4) Tap on the CONFIRM OTP button | 1)Employee code: 10019 2) OTP 1201 | Getting the message please enter the correct OTP |  | After tapping on confirm OTP field user should get the message "please enter correct OTP". | Low | Minor | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the OTP field | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Try to enter more than 4 digit in OTP field Observe that the User is able to enter more than 4 digit | 1) Employee code: 10019 2) OTP:12012442 | Able to enter more than 4 digit |  | User should not be able to enter more than 4 digit | Medium | High | Fail
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the Timer | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) On the OTP verification screen 4) Validate the duration of timer | 1) Employee code: 10019 | Timer runs for 30 second |  | The timer should run for 30 second | Medium | High | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the Timer | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) On the OTP verification screen 4) Put the app in background 5) Now use the app again | 1) Employee code: 10019 | Timer gets stop after putting the App in background |  | The timer should not get stop after putting the app in background | Medium | Major | Fail
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the RESEND OTP button | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the Employee code and tap on the Send OTP button 3) On the OTP verification screen 4) If the timer is running 4) Check the visibility of RESET button | 1) Employee code: 10019 | Reset button is enable even the timer is running |  | The RESET button should get disable if the timer is running | Medium | Minor | Fail
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the RESEND OTP button | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the Employee code and tap on the Send OTP button 3) On the OTP verification screen 4) If the timer is not running 4) Check the visibility of RESET button | 1) Employee code: 10019 | When the timer is running reset button is enable |  | The RESET button should get enable if the timer is not running | Low | Minor | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the OTP send to phone | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the Employee code and tap on the Send OTP button 3) On the OTP verification screen, wait for the timer to exhausted 4) Now tap on the Resend OTP button | 1) Employee code: 10019 | Previous OTP gets expire |  | Previous OTP should get expire if the user has tapped on resend button and only recent OTP should work. | Medium | High | Pass
OTP Verification Screen | 11642 | 2020-07-27 | Verifying the functionality of the login with incorrect OTP and then correct OTP | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the Employee code and tap on the Send OTP button 3) First enter the Incorrect OTP and then use the Correct OTP Observe that after login User gets stuck on the Dashboard screen | 1) Employee code: 10019 | User is getting stuck on dashboard screen |  | User should not get stuck on the Dashboard screen | Medium | High | Fail
Dashboard
Dashboard | 11642 | 2020-07-27 | Verifying the content present on the home screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear | 1) Employee code: 10019 2) OTP send to phone no | All required details are appearing |  | Below content should present on the home screen 1) Dashboard 2) Attendance 3) Holiday list 4) Apply leave 5) Menu button 6) Today option 7) Next 2 Days | Medium | High | Pass
Dashboard | 11642 | 2020-07-27 | Verifying the functionality of today option on the home screen | 1) User must have installed the app 2) Connect the device with internet. 3) Already applied for the WFH | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear 6) Tap on Today option | 1) Employee code: 10019 2) OTP send to phone no | Today applied WFH data is appearing twice |  | After tapping on the today option WFH applied for today will appear | Medium | Major | Fail
Dashboard | 11642 | 2020-07-27 | Verifying the leave details in today and next 2 days section section | 1) User must have installed the app 2) Connect the device with internet. 3) Already applied for the leave and leave is approved | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear 6) Tap on Today option 7) Verify that the appoved leaved details is appearing | 1) Employee code: 10019 2) OTP send to phone no | Leave data is not visible in the today and Next 2 days section |  | Approved leave details should also appear in today and next 2 days section | Medium | Major | Fail
Dashboard | 11642 | 2020-07-27 | Verifying the content in today section | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear 6) Tap on Today option 7) Multiple section will come | 1) Employee code: 10019 2) OTP send to phone no | Inside today all the sections are appearing 1) WFH 2) Coming Late 3) Work with client |  | All the below section should appear 1) WFH 2) Coming Late 3) Work with client | Medium | Major | Pass
Dashboard | 11642 | 2020-07-27 | Verifying the functionality of Next 2 days option on the home screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear 6) Tap on Next 2 days option | 1) Employee code: 10019 2) OTP send to phone no | All the data for the next two days leave are appearing |  | After tapping on the Next 2 days option upcoming leave applied for next 2 days will appear | Medium | High | Pass
Dashboard | 11642 | 2020-07-27 | Verifying the content in Next 2 days section | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Dashboard screen will appear 6) Tap on Next 2 days option 7) Multiple section will come | 1) Employee code: 10019 2) OTP send to phone no | Inside Next 2 days all the sections are appearing 1) WFH 2) Coming Late 3) Work with client |  | All the below section should appear in next 2 days 1) WFH 2) Coming Late 3) Work with client |  |  | Pass
Attendance
Attendance | 11642 | 2020-07-27 | Verifying the attendance option on the home screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Home screen will appear 6) Tap on Attendance option | 1) Employee code: 10019 2) OTP send to phone no | Current month is appearing |  | After tapping on the attendance option current month calendar will appear | Medium | High | Pass
Attendance | 11642 | 2020-07-27 | Verifying the color applied on attendance for leave and present | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Home screen will appear 6) Tap on Attendance option | 1) Employee code: 10019 2) OTP send to phone no | Punch-in details are appearing in green while leave are appearing in red |  | For the punch in date/present that date will appear in green color while for not punched/absent that date will mark as Red. | Low | Minor | Pass
Attendance | 11642 | 2020-07-27 | Verifying the entry and exit time after tapping on particular date | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Home screen will appear 6) Tap on Attendance option 7) Select any working date | 1) Employee code: 10019 2) OTP send to phone no | Entry and exit time is appearing after tapping on the particular date |  | After tapping on the particular date the entry and exit time for that date should appear | Medium | High | Pass
Attendance | 11642 | 2020-07-27 | Verifying the selection of month | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the valid Employee code and tap on the Send OTP button 3) Enter the valid 4 digit OTP (which is send to phone no) 4) Tap on the CONFIRM OTP button 5) Home screen will appear 6) Tap on Attendance option 7) Change the month to previous month by tapping on back arrow | 1) Employee code: 10019 2) OTP send to phone no | Employee is able to select the month and In respective to month data is appearing |  | After tapping on the back button, month should get change and the data should appear as per the month selection | Medium | High | Pass
Holiday List
Holiday list | 11642 | 2020-07-27 | Verifying the functionality of Holiday list option | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Holiday list | 1) Employee code: 10019 2) OTP send to phone no | User is able to see list of holiday |  | After tapping on the holiday list user should be able to see the complete holidays of the respective year | Low | Minor | Pass
Holiday list | 11642 | 2020-07-27 | Verifying the functionality of Holiday list option | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Holiday list 4) Select the year 2021 | 1) Employee code: 10019 2) OTP send to phone no | List of holiday is appearing as per the year selected |  | Holiday list should appear as per the year selected | Medium | High | Pass
Holiday list | 11642 | 2020-07-27 | Verifying the Edit functionality in Holiday list | 1) User must have installed the app 2) Connect the device with internet. 3) Log-in with director credentials | 1) Login with valid id into the App as a Director 2) Tap on Holiday list 3) Select any holiday and tap on edit icon on it 4) Tap on update | 1) Director code: 10019 2) OTP send to phone no | User is able to edit the Holiday name and date of the holiday |  | After tapping on the Edit icon User should be able to edit the Holiday name and date of the holiday | Medium | High | Pass
Holiday list | 11642 | 2020-07-27 | Verifying the Add functionality in Holiday list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App as a Director 2) Dashboard screen will appear 3) Go to the menu bar and tap on Holiday list 4) Tap on Add icon 5) Fill all the details 6) Tap on create | 1) Director code: 10019 2) OTP send to phone no | User is able to add the new holiday by entering the Holiday name and date of the holiday |  | After tapping on add icon user is able to add the new holiday by entering the name and date of the holiday. | Low | Minor | Pass
Holiday list | 11642 | 2020-07-27 | Verifying the cancel button functionality in create Holiday | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App as a Director 2) Dashboard screen will appear 3) Go to the menu bar and tap on Holiday list 4) Tap on Add icon 5) Fill all the details 6) Tap on Cancel | 1) Director code: 10019 2) OTP send to phone no | New holiday is not created after tapping on the cancel button |  | After tapping on cancel new holiday should not get created | Low | Minor | Pass
Holiday list | 11642 | 2020-07-27 | Verifying the new Added holiday detail in Holiday list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App as a Director 2) Dashboard screen will appear 3) Go to the menu bar and tap on Holiday list 4) Tap on Add icon 5) Fill all the details 6) Tap on create 7) Come back to list | 1) Director code: 10019 2) OTP send to phone no | New added holiday is visible in the list |  | After tapping on create, Go to list and check, The newly added holiday should be visible in the list | Low | Minor | Pass
Github
Github | 11642 | 2020-07-27 | Verifying the functionality of Github option | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App as a director 2) Go to the menu bar, and tap on Github option | 1) Employee code: 10019 2) OTP send to phone no | Getting both the option 1) Names 2) Issues |  | After tapping on the Github, Two option should appear 1) Names 2) Issues | Medium | High | Pass
Github | 11642 | 2020-07-27 | Verifying the functionality of names in github | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Github option 3) Tap on Names | 1) Employee code: 10019 2) OTP send to phone no | All the employee list is appearing for the particular mentor |  | Under names section all the mentee name should appear for that particular logged mentor | Medium | High | Pass
Github | 11642 | 2020-07-27 | Verifying the commit details in github | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Github option 3) Tap on Names 4) Tap on any name | 1) Employee code: 10019 2) OTP send to phone no | Getting all the yesterday commit after tapping on the employee name |  | After tapping on any name, all the yesterday commit will appear for that particular user. | Low | Minor | Pass
Github | 11642 | 2020-07-27 | Verifying the commit details in date range in github | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Github option 3) Tap on Names 4) set the date range for the user | 1) Employee code: 10019 2) OTP send to phone no | After selecting the date all the commit for that particular date is appearing |  | As per the date selection all the commit should appear for that particular date | Medium | High | Pass
Github | 11642 | 2020-07-27 | Verifying the date range in github | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Github option 3) Tap on Names 4) set the date range for the user | 1) Employee code: 10019 2) OTP send to phone no | User is able to select only past dates in the date range |  | User should be able to select the only past dates not the future dates | Medium | High | Pass
Github | 11642 | 2020-07-27 | Verifying the issue option in github | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Github option 3) Tap on Issues | 1) Employee code: 10019 2) OTP send to phone no | In issues section Mentees names are appearing who has not committed the code. |  | Inside the issues all the mentee names should appear who has not committed his/her code. | Medium | Major | Pass
User profile
User profile | 11642 | 2020-07-27 | Verifying the details appear in the user profile | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Enter the Employee code and tap on the Send OTP button 3) Enter the sent OTP and tap on Submit button 4) Go to the menu bar and select the user profile | 1) Employee code: 10019 2) OTP send to phone no | Complete user details is appearing on the user profile section |  | Below Content should appear on the user profile screen: 1) Full name 2) emp_code 3) mobile no 4) official_email 5) personal_email 6) department 7) designation 8) Date of joining 9) Profile picture | Medium | High | Pass
User profile | 11642 | 2020-07-27 | Verifying the functionality of uploading profile pic | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login in to App 3) Go to the menu bar and select the user profile 4) Tap on the add profile section | 1) Employee code: 10019 2) OTP send to phone no | User is able to upload the profile photo |  | After tapping on the user profile two option should appear 1) Select from gallery 2) Take picture | Medium | Low | Pass
User profile | 11642 | 2020-07-27 | Verifying the functionality of uploading profile pic | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login in to App 3) Go to the menu bar and select the user profile 4) Tap on the add profile section 5) Select any photo from gallery 6) tap on ok button | 1) Employee code: 10019 2) OTP send to phone no | Image selected from gallery is visible on the user profile |  | Selected image should be visible on user profile | Medium | High | Pass
User profile | 11642 | 2020-07-27 | Verifying the functionality of uploading profile pic | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login in to App 3) Go to the menu bar and select the user profile 4) Tap on the add profile section 5) Tap on camera 6) Click the photo and tap on OK | 1) Employee code: 10019 2) OTP send to phone no | Clicked photo is visible on the user profile |  | Clicked image should be visible to user profile | Low | Minor | Pass
User profile | 11642 | 2020-07-27 | Verifying the Edit functionality of user profile | 1) User must have installed the app 2) Connect the device with internet. | 1) Launch the App 2) Login in to App 3) Go to the menu bar and select the user profile | 1) Employee code: 10019 2) OTP send to phone no | Edit functionality is not there |  | Edit user details functionality should not be there for the user | Low | Minor | Pass
Employee management
Employee | 11642 | 2020-07-27 | Verifying the functionality of employee list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on employee list | 1) Director code: 10019 2) OTP send to phone no | All the employees name is appearing in the list |  | After tapping on the employee all the employee list will appear | Low | Minor | Pass
Employee | 11642 | 2020-07-27 | Verifying the edit the employee data functionality in employee list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on employee list 4) Tap on any employee name 5) Enter the details which we want to update 6) Tap on update button | 1) Director code: 10019 2) OTP send to phone no | After entering the new details and tapping on update the employee details is getting update |  | After tapping on update button all the newly entered data should be updated for the user | Medium | High | Pass
Employee | 11642 | 2020-07-27 | Verifying the add the employee data functionality in employee list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on employee list 4) Tap on add icon 5) Enter the entire details for the employee 6) Tap on create | 1) Director code: 10019 2) OTP send to phone no | New created employee data is created in the list but after tapping on the employee name, App gets crash |  | After tapping on the create button, Employee data should get created and able to view the complete details | Medium | High | Fail
Employee | 11642 | 2020-07-27 | Verifying the add the employee data functionality and upload pic from gallery in employee list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on employee list 4) Tap on add icon 5) Enter the entire details for the employee 6) Upload the pic from gallery 7) Tap on create | 1) Director code: 10019 2) OTP send to phone no | Selected gallery pic is visible on the employee pic |  | After tapping on the create button, Employee should be created the selected gallery pic should be visible on profile | Medium | High | Pass
Employee | 11642 | 2020-07-27 | Verifying the add the employee data functionality and upload pic from camera in employee list | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on employee list 4) Tap on add icon 5) Enter the entire details for the employee 6) Take picture from camera 7) Tap on create | 1) Director code: 10019 2) OTP send to phone no | captured camera pic is visible on the employee pic |  | After tapping on the create button, Employee should be created the captured camera pic should be visible on profile | Medium | High | Pass
Leave Management
Apply leave | 11642 | 2020-07-27 | Verifying the Content present on the Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave | 1) Employee code: 10019 2) OTP send to phone no | All the required data is appearing |  | Below content should present on the Apply Leave screen 1) Total CL and PL left 2) Employee id 3) Dropdown to select leave type 4) Checkbox for half day or full day 5) Select start date of leave (Date picker) 6) Select End date of leave (Date picker) 7) Mail sent to mentor(Mail suggestion) 8) Reason (Input field) | Medium | Major | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the option present in leave type dropdown on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on select leave dropdown | 1) Employee code: 10019 2) OTP send to phone no | All the required data is appearing |  | After tapping to select leave type below option should appear 1) Casual leave 2) Sick leave 3) Privilege leave 4) LWP 5) Work from home | Medium | High | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of leave type dropdown | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on select leave dropdown 5) Close it without selecting the option | 1) Employee code: 10019 2) OTP send to phone no | Error message is missing for the user if the user does not select the option from dropdown |  | Error message should appear if the user does not select the option from dropdown | Medium | High | Fail
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of half day check box on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on half day check box | 1) Employee code: 10019 2) OTP send to phone no | Check box is successfully selected |  | After tapping on the half day check box, The check Box should get select | Medium | High | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of Select from date on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on select from date 5) Date picker calendar will open, select any date | 1) Employee code: 10019 2) OTP send to phone no | User is not able to select the date, firstly user has to tap on another date then only user is able to select the current date |  | User should be able to select the date from calendar | Low | Major | Fail
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of Select to date on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on select from date 5) Date picker calendar will open, select any date | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the From_date date from the calendar |  | User should be able to select the date from date picker from the select to Option | Medium | High | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of Select to date on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on select from date 5) Date picker calendar will open 6) Try to select the date which is less than from date | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the to_date which is less than from_date |  | User should not be able to select date from "to_date" which is less than "From_date" date. | Medium | Major | Fail
Apply leave | 11642 | 2020-07-27 | Verifying the functionality Send to mail on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on "send to mail" option | 1) Employee code: 10019 2) OTP send to phone no | Employee is able to select the email id |  | User should be able to select the email id of techfour solution domain | Medium | High | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the functionality Leave reason field on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Tap on "Leave reason" option | 1) Employee code: 10019 2) OTP send to phone no | User is able to enter the date in the leave reason field but user skip the field by just entering the space in field |  | User should be able to enter the data in the leave reason field and cannot skip this field | Low | Minor | Fail
Apply leave | 11642 | 2020-07-27 | Verifying the functionality "APPLY NOW" button on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Enter the required complete data 5) Tap on the Apply now button | 1) Employee code: 10019 2) OTP send to phone no | User is able to apply the leave successfully |  | After tapping on Apply now button, Leave should successfully applied | Medium | High | Pass
Apply leave | 11642 | 2020-07-27 | Verifying the Details of leave appear on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Enter the required complete data 5) Tap on the Apply now button Observe the leave count in your account | 1) Employee code: 10019 2) OTP send to phone no | Data of leave is not updating after applying the leave |  | After applying the leave the data should get change as per the applied leave | Medium | Major | Fail
Apply leave | 11642 | 2020-07-27 | Verifying the functionality of Apply leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear 3) Tap on Apply leave 4) Enter the required complete data 5) Tap on the Apply now button twice | 1) Employee code: 10019 2) OTP send to phone no | After tapping on the Apply button twice same leave applied for twice |  | Apply button should get disable if the user tap on the Apply button multiple times for the same date or should get error message | Medium | Major | Fail
Approved leave | 11642 | 2020-07-27 | Verifying the Details appear on Approved leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approved leave | 1) Employee code: 10019 2) OTP send to phone no | Appearing both the tab 1) Current 2) Past |  | After tapping on the Approved leave, two section should appear 1) Current 2) Past | Medium | Minor | Pass
Approved leave | 11642 | 2020-07-27 | Verifying the current tab functionality on Approved leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approved leave 4) Go to current tab | 1) Employee code: 10019 2) OTP send to phone no | Not appearing the current approved leave |  | After tapping on current tab all the approved current leave should appear | Medium | High | Fail
Approved leave | 11642 | 2020-07-27 | Verifying the past tab functionality on Approved leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approved leave 4) Go to past tab | 1) Employee code: 10019 2) OTP send to phone no | Data is visible for the past approved leave |  | After tapping on past tab all the approved past leave should appear | Medium | Major | Pass
Approve leave | 11642 | 2020-07-27 | Verifying the Details appear in the Approve leave section | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approve leave | 1) Employee code: 10019 2) OTP send to phone no | List of all leave is appearing who are waiting for the approval |  | After tapping on approve leave entire leave list which is waiting for approval should appear | Medium | High | Pass
Approve leave | 11642 | 2020-07-27 | Verifying the Details appear in the Approve leave section for the applied leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approve leave 4) Go to the details of the leave | 1) Employee code: 10019 2) OTP send to phone no | Applied half day leave is appearing leave count 1 in approve section |  | Leave details should match as per the fiiled by employee | Medium | High | Fail
Approve leave | 11642 | 2020-07-27 | Verifying the Functionality of giving approval to the leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approve leave 4) Enter the remark and tap on approve | 1) Employee code: 10019 2) OTP send to phone no | After filling the reason and tapping on approve button the leave gets approve |  | After tapping on approve button the leave should get approved | Medium | Major | Pass
Approve leave | 11642 | 2020-07-27 | Verifying the Functionality of Rejection to the leave | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Leave management 3) Tap on Approve leave 4) Enter the remark and tap on reject | 1) Employee code: 10019 2) OTP send to phone no | After filling the reason and tapping on reject button the leave gets reject |  | After tapping on reject button the leave should get reject | Medium | High | Pass
OUT OF OFFICE
Out of Office | 11642 | 2020-07-27 | Verifying the Content present on the "out of office" option | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office | 1) Employee code: 10019 2) OTP send to phone no | Getting all the option in the "NOT IN OFFICE" section 1) Coming late 2) Work from home 3) Work with client |  | After tapping on the "Out of office" option user should be able to see the dropdown in which multiple option should be there which are mentioned below: 1) Coming late 2) Work from home 3) Work with client | Medium | High | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality appear after selecting the reason from dropdown | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown | 1) Employee code: 10019 2) OTP send to phone no | All the options are available which are required to apply the "Not in Office" |  | After selecting the option from the dropdown multiple field should appear which are mentioned below: 1) Half day or full day dropdown 2) Select from date 3) Select to date 4) Reason 5) Submit button | Medium | Major | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of selecting option from dropdown | 1) User must have installed the app 2) Connect the device with internet. | 1) Log-in into the App with valid employee id and OTP 2) Go to Menu bar, Select the Out of office and select the late coming 3) On the "Not in office" screen Unselect it from dropdown, Fill all the details and try to submit Observe that the app get crash | 1) Employee code: 10019 2) OTP send to phone no | App gets crash if the user apply for "Not in office" without selecting the option from dropdown |  | Restrict the user should not able to unselect the type of "Not in office" which user selected just before. | Medium | Major | Fail
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of half day check box | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on out of office 3) Select the WFH 4) Tap on half day check box | 1) Employee code: 10019 2) OTP send to phone no | After tapping on checkbox the checkbox get selected |  | After tapping on the half day check box, The check Box should get select | Medium | High | Pass
Out of Office | 11642 | 2020-07-27 | App gets crash if the user select half day in WFH section | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Menu bar, Select the Out of office and select the WFH 3) On the "Not in office" screen select the half day and try to put the date same and month different 4) Submit it | 1) Employee code: 10019 2) OTP send to phone no | App gets crash if the months are different but the date is same |  | User should be restricted to same date in both(From_date, To_date) is the user has selected half day |  |  | Fail
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of Select to date on Not in office screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Try to select the date from the "Select from date" | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the date from From_date section |  | User should be able to select the "select from date" from date picker | Medium | High | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of Select to date on Not in office screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Try to select the date from the "Select to date" | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the date from "to_date section |  | User should be able to select the date from the "Select to date" | Medium | Major | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of Select to date on "Not in office" screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Select the from_date (27/09/2020) 5) Select the to_date(24/09/2020) | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the to_date less than from_date |  | User should not be able to select date from "To_Date" option which is less than "From_date" date | Medium | High | Fail
Out of Office | 11642 | 2020-07-27 | Verifying the functionality Send to mail on "Not in office" screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Try to select the date from the "Select to date" 5) Tap on "send to mail" | 1) Employee code: 10019 2) OTP send to phone no | User is able to select the email id from suggestion |  | User should be able to select the email id of techfour solution domain | Medium | High | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality Reason field on Apply leave screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Try to select the date from the "Select to date" 5) Tap on "send to mail" and select mail 6) Tap on Reasop field and enter the data | 1) Employee code: 10019 2) OTP send to phone no | User is able to enter the data in the reason field |  | User should be able to enter the data in the reason field | Low | Minor | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of Submit button on "Not in office" screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Work from home" option from dropdown 4) Try to select the date from the "Select to date" 5) Tap on "send to mail" and select mail 6) Tap on Reason field and enter the data 7) Tap on submit button | 1) Employee code: 10019 2) OTP send to phone no | User is successfully able to submit the "NOT IN OFFICE" concern |  | After tapping on the submit button user should successfully applied "Not in office" concern | Medium | High | Pass
Out of Office | 11642 | 2020-07-27 | Verifying the functionality of Coming late option on "Not in office" screen | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Go to the menu bar, and tap on Out of Office 3) Select the option "Coming late" option from dropdown | 1) Employee code: 10019 2) OTP send to phone no | User is not getting the option of half day after selecting the coming late option |  | After selecting the "coming late" option user should not get the option of half or full day. | Medium | Major | Pass
LOG-OUT
Logout | 11642 | 2020-07-27 | Verifying the Logout functionality | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on Logout option | 1) Director code: 10019 2) OTP send to phone no | User successfully gets logout after tapping on the logout |  | After tapping on logout option user should logout from the app | Medium | High | Pass
Logout | 11642 | 2020-07-27 | Verifying the functionality after Logout | 1) User must have installed the app 2) Connect the device with internet. | 1) Login with valid id into the App 2) Dashboard screen will appear, go to menu bar 3) Tap on Logout option 4) Try to login again | 1) Director code: 10019 2) OTP send to phone no | User logout user need employee id and OTP to login again |  | After logout user need employee id and OTP again to login in app | Medium | High | Pass

## Module
Testing of HRM iOS App |  | Lead Dev | Swetha
Module | No of test cases written | No of test executed | Pass | Fail
Installation | 5 | 5 | 5 | 0
Login | 15 | 15 | 11 | 4
Dashboard | 6 | 6 | 4 | 2
Attendance | 4 | 4 | 4 | 0 | Testing of HRM Android App |  | Lead Dev | Rahul/Shalu
Holiday list | 6 | 6 | 6 | 0 | Module | No of test cases written | No of test executed | Pass | Fail
Leave management | 19 | 19 | 11 | 8 | Login | 15 | 15 | 12 | 3
Github | 6 | 6 | 6 | 0 | Dashboard | 6 | 6 | 4 | 2
User profile | 5 | 5 | 5 | 0 | Holiday list | 6 | 6 | 2 | 4
Employee management | 5 | 5 | 4 | 1 | Leave management | 19 | 19 | 11 | 8
Logout | 2 | 2 | 2 | 0 | Out of office | 12 | 12 | 5 | 7
Total | 85 | 85 | 67 | 18 | Employee management | 5 | 5 | 1 | 4
[5 empty] | Logout | 2 | 2 | 2 | 0
Testing of HRM iOS App |  | Lead Dev | Swetha |  | Total | 65 | 65 | 37 | 28
Module | No of test cases written | No of test executed | Pass | Fail
Installation | 5 | 5 | 5 | 0
Login | 15 | 15 | 12 | 3
Dashboard | 6 | 6 | 5 | 1
Attendance | 4 | 4 | 4 | 0
Holiday list | 6 | 6 | 6 | 0
Leave management | 19 | 19 | 16 | 3
Github | 6 | 6 | 6 | 0
Out of office | 12 | 12 | 10 | 2
User profile | 5 | 5 | 5 | 0
Employee management | 5 | 5 | 4 | 1
Logout | 2 | 2 | 2 | 0
Total | 85 | 85 | 75 | 10

## iOS issues
Project :- |  | HRM |  |  |  |  | Lead_Dev. :-
Created_By :- |  | Saurabh Saini |  |  |  |  | Power_Task_I.D. :-
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Developers Comments | QA Comment
| Login | 1 | Timer gets stop for the user, When the user put the app in background | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) Put the app into background and use the another app. 5) Now use the HRM app again Observe that the timer gets stop when the user put the app in background Expected result: The timer should not get stop even after putting the app in background | Employee id: 10019 |  |  |  | Reopen |  |  | Still the timer gets stop if the user put the App in background and use another app
| Login | 2 | When the timer is running the "Resend" button is enable | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) When the timer is running "Resend" button is enable. Expected result: The "Resend" button should enable only when the timer shows 0 seconds. | Employee id: 10019 |  |  |  | Closed |  | Done | Still user is able to tap on Resend button when the timer is runnining second time
| Dashboard | 3 | User gets stuck on the home screen | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) Enter the incorrect OTP and tap on "confirm" button 5) Now enter the correct OTP and tap on confirm button Observe that after entering the incorrect OTP and then entering correct OTP causes user stuck on the Dashboard page Expected result: The user should not get stuck. | 1) Employee id: 10019 2) OTP send to phone no |  |  |  | Reopen |  |  | First login as employee and then login as Director User will get stuck on home screen.
| Login | 4 | OTP field is accepting more than 4 digit | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) Tap on OTP field and enter digit Observe that the user is able to enter more than 4 digit Expected result: User should be able to enter only 4 digit in the OTP field | 1) Employee id: 10019 |  |  |  | Closed |  | Done
| Apply leave | 5 | While selecting current date user need to select the other date first and then user is able to select the current date | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP. 2) Go to Apply leave section,go to_from date and try to select the current date 3) Observe that user is unable to select the current date by tapping on it, User first need to tap on another date then user is able to select the current date Expected result: By directly tapping on the current date user should be able to select the current date. | 1) Employee id: 10019 2) OTP send to phone no |  |  |  | Closed |  | Done
| Apply leave | 7 | User is able to apply the leave multiple time for the same day | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details and tap on apply button 3) Tap on Apply button multiple times Observe that after tapping on the Apply button multiple times the same leave applied multiple times Expected: For the same day user should be able to apply the leave once. | 1) Employee id: 10019 2) OTP send to phone no | [5 empty] | need to get a msg from backend Note: Need to implement the same for Out of office scenario
| Apply leave | 8 | By giving space in reason field user is able to apply leave | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Provide space in the reason field observe that user is successfully able to apply leave Expected result: Character must be present in the leave reason section | 1) Employee id: 10019 2) OTP send to phone no |  |  |  | Closed |  | Done
| Apply leave | 9 | Error message "please select leave type" is missing for the user if the user open the leave type dropdown and without selecting the option close the dropdown | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Open the leave type dropdown but don't select any leave type and close it 4) Tap on apply Observe that after tapping on the Apply, No error message will appear Expected result: After tapping on the Apply, user should get the message "Please select the leave type" | 1) Employee id: 10019 2) OTP send to phone no |  |  |  | Closed |  | Done
| Apply leave | 10 | User is able to set the to_date less than from_date | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Select the from_date first and tap on to_date 4) Select the date which comes first from from_date Observe that user is able to select to_date which is less than from_date Expected result: From_date should always be less or equal to to_date | 1) Employee id: 10019 2) OTP send to phone no |  |  |  | Reopen |  | Done | User is able to apply leave when the date are same
| Approve leave | 11 | Applying half day leave appear leave count 1 in approve section | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details and apply the half day leave 3) Login as a director 4) Go to menu bar, Select the leave management and tap on approve leave Observe that in the approve leave section, half day apply leave will have the leave count 1 Expected result: Leave count should appear 1/2 instead of 1. | 1) Employee id: 1002 2) OTP send to phone no | [5 empty] | backend issue
| Employee | 12 | App gets crash after tapping on the newly created employee name | 1) Connect the device with internet. 2) Install the application | 1) Login as a director 2) Go to menu bar, Select the Employee and and create the new employee data 3) Now tap on the name of new created employee name Observe that after tapping on the new created employee the app gets crash Expected result: the App should not get crash after tapping on the new employee name | 1) Employee id: 1002 2) OTP send to phone no |  |  |  | Closed |  | Done
| Dashboard | 13 | In the today tab similar data appear twice | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Menu bar, Select the Out of office and apply half day WFH for the same day 3) Come to dashboard today tab Observe that the data appear twice in the today tab Expected result: the similar data should appear once | 1) Employee id: 1002 2) OTP send to phone no | [5 empty] | backend issue
| Out of office | 14 | App gets crash if the user apply for "Not in office" without selecting the option from dropdown | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Menu bar, Select the Out of office and select the late coming 3) On the "Not in office" screen Unselect it from dropdown, Fill all the details and try to submit Observe that the app get crash Expected result: Restrict the user not able to unselect the type of "Not in office" which user selected just before. | 1) Employee id: 1002 2) OTP send to phone no |  |  |  | Closed |  | Done
| Out of office | 15 | App gets crash if the user select half day in WFH section | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Menu bar, Select the Out of office and select the WFH 3) On the "Not in office" screen select the half day and try to put the date same and month different 4) Submit it Observe that the App gets crash Expected result: The App should not get crash and the user should get the message "please select the same date and month for the half day". | 1) Employee id: 1002 2) OTP send to phone no |  |  |  | Closed |  | Done | The App is not getting crash but when the user apply the half day in that case the date, month and year should be same Or don't allow user to enter the enter the TO_DATE put it same by default the user selected for FROM_DATE in half day case
| Dashboard | 16 | Kindly block the app in landscape mode |  | As the App is not accessible in landscape mode so please block it |  |  |  |  | Closed |  | Done
| Login | 17 | When the timer is exhausted user is unable to tap on "Confirm OTP" button | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) Let the time get finished Observe that the user is unable to tap on the "Confirm OTP" Button Expected result: Even the timer is finished user should be able tap on "Confirm OTP" button | 1) Employee id: 1002 2) OTP send to phone no |  |  |  | Closed |  | Done
| Logout | 18 | On doing log-out getting task list screen in background | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Go to menu bar and tap on the Log-out Observe that the Task list screen appear in background Expected result: Only the menu bar data or dashboard screen should appear |  |  |  |  | Closed |  | done
| User profile | 19 | After updating the user profile, user need to do logout to see the updated profile pic in menu bar | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Go to menu bar and tap on user profile 4) Update the user profile and go to menu bar Observe that the updated profile will not be visible for the user Expected result: Update profile should visible in menu bar also without doing logout |  |  |  |  | Closed |  | done
| Holiday List | 20 | Ater updating or addition of new holiday hit the holiday list Api so that user get the latest holiday list | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Tap on holiday list and update or add the new holiday Observe that the user need to switch the other screen to get the latest holiday list Expected result: After update or Addition of new holiday, Hit the Holiday list API so that the user will get the latest holiday list without switiching to other screen |  |  |  |  | Closed |  | Done
| Employee management | 21 | After selecting any value from calendar, it's automatically get close | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Tap on menu bar and go to employee management 4) Tap on any employee name and try to update the joining date Observe that even after selecting date only calendar automatically gets close. Expected result: User should be able to select the date, Month and year in one time. |  |  |  |  | Closed |  | Done
| Employee management | 22 | Keyboard is not getting close | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Tap on menu bar and go to employee management 4) Tap on Search bar,enter the data and select the employee now tap on back icon Observe that user will get the opened keyboard. Expected result: Without tapping on the search bar, keyboard should not get open. |  |  |  |  | Closed |  | Done
| Employee management | 23 | Updating profile pic for one employee get visible on other employee profile also | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentails 3) Tap on menu bar and go to employee management 4) Update one employee profile pic Observe that updated profie pic visible to another employee profile also Expected result: Update profile for employee should visible on respective only |  |  |  |  | Closed |  | Done | As of now user will select his/her profile photo by himself or herself
| Apply leave | 24 | Need to remove the WFH from select leave type | [6 empty] | Closed |  | Done
| Apply leave | 25 | Approve section for lalit sir is missing | [6 empty] | Closed |  | Done
| Dashboard | 26 | Data is not visible on the dashboard screen | [6 empty] | Closed |  | Done
On attendance App gets crash

## Android issue
|  | HRM |  |  |  |  | Lead_Dev. :-
Created_By :- |  | Saurabh Saini |  |  |  |  | Power_Task_I.D. :-
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Developers Comments | QA Comment
| Login | 1 | When the timer is running the "Resend" button is enable | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on "Send OTP" button 4) When the timer is running "Resend" button is enable. Expected result: The "Resend" button should enable only when the timer shows 0 seconds. | Employee id: 10019 |  |  |  | Open |  |  | Still button gets enable when the timer is running second time
| Login | 2 | Message "Please connect to internet" is missing on login screen | 1) Disconnect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Tap on the Next button Observe that if the user is not connected to internet and tapping on next button user is not getting message Expected result: User should get the message "Please connect to internet" | Employee id: 10019 | [6 empty] | Closed
| Holiday List | 3 | Last holiday icon gets overlap with the new create holiday icon | 1) Connect the device with internet. 2) Install the application | 1) Login into the App with the valid credentials 2) Go to menu bar 3) Select the holiday list 4) observe that the new create holiday icon overlap with the last holiday edit icon Expected result: Icon should not get overlap. | Employee id: 1002 | [6 empty] | Closed
| Holiday List | 4 | Newly added holiday is not visible | 1) Connect the device with internet. 2) Install the application | 1) Login into the App with the valid credentials 2) Go to menu bar 3) Select the holiday list and create new holiday 4) observe that after creating of new holiday, New holidays are not visible in the list Expected result: Newly created holiday should be visible in the list | Employee id: 10019 | [6 empty] | Closed
| Holiday List | 5 | Update functionality is not working for the holiday | 1) Connect the device with internet. 2) Install the application | 1) Login into the App with the valid credentials 2) Go to menu bar 3) Select the holiday list and tap on edit button of any holiday 4) observe that user is unable to update the holiday as the updated changes are not visible Expected result: Updated changes should get visible to the user. | Employee id: 10019 |  |  |  | Open |  |  | Please make both the field(Holiday name, Date) mandatory as of now user is able to submit the holiday without entering name or date
| Holiday List | 6 | Verifying the update functionality for the holiday list | 1) Connect the device with internet. 2) Install the application | 1) Login into the App with the valid credentials 2) Go to menu bar 3) Select the holiday list and tap on edit button of any holiday After tapping on the edit icon already present data for that holiday is not appear. Expected result: After tapping on edit icon data present for that leave should appear in update pop-up | Employee id: 10019 |  |  |  | Open
| Login | 7 | Invalid OTP message is missing | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Enter the incorrect OTP Observe that incorrect OTP message is missing Expected result: Incorrect OTP message should appear | Employee id: 10019 |  |  |  | Open
| Dashboard | 8 | Hard code data is not visible on the dashboard screen | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code 3) Enter the correct OTP Observe that on the dashboard screen data is not visible Expected result: Correct data should be visible on the dashboard screen | Employee id: 10019 |  |  |  | Open
| Login | 9 | Getting incorrect mobile no on OTP verification screen | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the employee code Observe that in the OTP verification screen user is getting the incorrect mobile no Expected result: Correct no of employee should be visible on the screen | Employee id: 10019 |  |  |  | Open
| Holiday List | 10 | User is not able to select the any year | 1) Connect the device with internet. 2) Install the application | 1) Login into the App with the valid credentials 2) Go to Holiday list 3) Tap on the year section Observe that user is unable year Expected result: User should be able to select the any year in calendar | Employee id: 10019 |  |  |  | Open
| Holiday List | 11 | AFter updating or addition of new holiday hit the holiday list Api so that user get the latest holiday list | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentials 3) Tap on holiday list and update or add the new holiday Observe that the user need to switch the other screen to get the latest holiday list Expected result: After update or Addition of new holiday, Hit the Holiday list API so that the user will get the latest holiday list without switching to other screen | Employee id: 10019 |  |  |  | Open
| Employee management | 12 | Remove the footer data when the user select any option from menu bar | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentials 3) Tap on menu bar and go to employee list Observe that the options (Dashboard,Attendance, Holiday list, Apply leave) is appearing in the footer Expected result: Options (Dashboard,Attendance, Holiday list, Apply leave) should not appear in the footer | Employee id: 10019 |  |  |  | Open
| Employee management | 13 | Date picker is missing for the DOJ | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentials 3) Tap on menu bar and go to employee list 4) Tap on add icon Observe that the Date picker is missing for the DOJ option Expected result: Date picker should be available for the user for the DOJ option | Employee id: 10019 |  |  |  | Open
| Employee management | 14 | After employee creation user remains on the same screen | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentials 3) Tap on menu bar and go to employee list 4) Tap on add icon, Fill the details and submit it Observe that after creation of the new employee user remains on the same page Expected result: User should navigate to employee list page | Employee id: 1002 |  |  |  | Open
| Employee management | 15 | While updating the employee detail previous details are not appearing in the update section | 1) Connect the device with internet. 2) Install the application | 1) Launch the App 2) Enter the valid credentials 3) Tap on menu bar and go to employee list 4) Tap on edit icon Observe that the employee details is not appearing in the update pop-up Expected result: he employee details should appear in the update pop-up. | Employee id: 1002 |  |  |  | Open
| Apply leave | 16 | Need to remove the WFH from select leave type | [6 empty] | Open
| Apply leave | 17 | When user select half day User is not restricted to select the same To_date and From_date |  | 1) Launch the App 2) Enter the valid credentials 3) Tap Apply leave and select the half day Observe that when user select half day User is not restricted to select the same To_date and From_date Expected result: Whenever user select the half day user should be restricted to select the same date. |  |  |  |  | Open
| Apply leave | 18 | User is able to set the to_date less than from_date | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Select the from_date first and tap on to_date 4) Select the date which comes first from from_date Observe that user is able to select to_date which is less than from_date Expected result: From_date should always be less or equal to to_date |  |  |  |  | Open
| Apply leave | 19 | User is unable to select the "mail to" option while applying leave | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Tap on mail to option Observe that Hard code data is present in mail_to option Expected result: mail list should open from where user can select the mail |  |  |  |  | Open
| Apply leave | 20 | Error message "please enter leave reason" is missing when the user try to submit leave without entering the reason | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Go to Apply leave section, enter the complete details 3) Don't enter the leave reason Observe that error message missing to enter the leave reason Expected result: User should get the message please enter the leave type |  |  |  |  | Open
| Dashboard | 21 | Message "Please connect to internet" is missing on Dashboard screen | 1) Disconnect the device with internet. 2) Install the application | 1) Login into the App 2) Go to dashboard screen Observe that if the user is not connected to internet on dashboard screen , user is not getting message "please connect to internet" Expected result: User should get the message "Please connect to internet" | Employee id: 10019 |  |  |  | Open
| Apply leave | 22 | Approve section for leave approval for lalit sir is missing | [6 empty] | Open
| Apply leave | 23 | Similar data appearing in the past and current section | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Approved leave Observe that the similar data is appearing in the current and Past section Expected result: Inside past section all the taken leave and in current all the current which are yet to take should appear | Employee id: 10019 |  |  |  | Open
| Apply leave | 24 | Approve section for leave approval is missing while login as Director | [6 empty] | Open
| Out of office | 25 | While selecting coming late "mail_to" is not multiple select | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Out of office 3) Select the coming late and tap on mail_to Observe that mail_to option is not multiple select Expected result: mail_to option should be multi select |  |  |  |  | Open
| Out of office | 26 | Unable to apply coming late option as get the error "no address associated with hostname" | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Out of office 3) Select the coming late, fill all the details and submit it Observe that getting the error "no hostname associated" Expected result: User should successfully able to apply th coming late option |  |  |  |  | Open
| Out of office | 27 | Search bar is missing for the mail_to option | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Out of office 3) Select the coming late and tap on mail_to Observe that search bar option is missing for the mail_to option Expected result: Search bar should be there for the mail_to option |  |  |  |  | Open
| Out of office | 28 | Unable to apply any option "Coming late, WFH and work with client | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Out of office 3) Select any option and fill all the details Observe that after tapping on the submit button nothing is happening Expected result: After tapping on the submit button user should apply for the respective option |  |  |  |  | Open
| Out of office | 29 | Submit button is missing in "Work with client" option | 1) Connect the device with internet. 2) Install the application | 1) Login into the App 2) Go to menu bar and tap on the Out of office 3) Select work with client and fill all the details Observe that submit button is missing Expected result: submit button should be available for the user to apply the "Work with client" |  |  |  |  | Open
| Out of office | 30 | When user select half day User is not restricted to select the same To_date and From_date |  | 1) Launch the App 2) Enter the valid credentials 3) Tap Out of office, Select the WFH and select the half day Observe that when user select half day User is not restricted to select the same To_date and From_date Expected result: Whenever user select the half day user should be restricted to select the same date. |  |  |  |  | Open
| Out of office | 31 | User is able to set the to_date less than from_date | 1) Connect the device with internet. 2) Install the application | 1) Log-in into the App with valid employee id and OTP 2) Enter the valid credentials 3) Tap Out of office, Select the WFH 3) Select the from_date first and tap on to_date 4) Select the date which comes first from from_date Observe that user is able to select to_date which is less than from_date Expected result: From_date should always be less or equal to to_date |  |  |  |  | Open