## Sheet1
Bug Report
|  |  | Project | Greenlam Warranty Management System (Dealer)
|  |  | Created By | Jitendra
Module
Date | Bug ID | Bug Description | Pre-Conditions | Steps to Reproduce | Test Data | Attachments | Severity | Priority | Status | Assigned to | Developers Status | Developers Comments | Developers URL | Testers Comments | Open | Close
2020-02-01 | 1 | Data of existing GIL orders is not appearing on the dealer's home (GIL orders) page. | User is on the website's Sign-in page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Click on the Sign-in button. | username 3911000170 password Welcome@123 | https://prnt.sc/qvy2t9 | High | High | New | Pawan Kumar
2020-02-01 | 2 | Data of existing GIL Invoices is not appearing on the dealer's home (GIL Invoices) page. | User is logged in to the system and is on Home Page. | 1)Click on GIL Invoices menu item. 2)Observe the data in the fields corresponding to the GIL invoices are coming or not. | NA | https://prnt.sc/qvy49z | High | High | New | Pawan Kumar
2020-02-01 | 3 | Data of existing My Invoices is not appearing on the dealer's home (My Invoices) page. | User is logged in to the system and is on Home Page. | 1)Click on My Invoices menu item. 2)Observe the data in the fields corresponding to the My invoices are coming or not. | NA | https://prnt.sc/qvy4k8 | High | High | New | Pawan Kumar
2020-02-01 | 4 | Data of admin's profile is not coming. | User is logged in to the system and is on Home Page. | 1)Click on user icon appearing at the top right corner of the page. 2)Click on the My account dropdown value from the dropdown list. 3)Click on the Basic Details. | NA | https://prnt.sc/qvy5di | High | High | New | Pawan Kumar
2020-02-01 | 5 | Suggestion: There should be an option to Reset Password in case of forgotton Password. | User is on the website's Sign-in page. | [5 empty] | New | Pawan Kumar
2020-02-01 | 6 | Login: There should be a proper and spacific validation message for leaving username field blank as "Username is Required." instead of "Please enter username & password" | User is on the website's Sign-in page. | 1)Leave the Username field blank. 2)Enter valid password in the Password field. 3)Click on the "Sign-in" button. |  |  | Low | Mid | New | Pawan Kumar
2020-02-01 | 7 | Login: There should be a proper and spacific validation message for leaving Password field blank as "Password is Required." instead of "Please enter username & password" | User is on the website's Sign-in page and is registered to the website. | 1)Enter the valid username in the field provided. 2)Leave the password field blank. 3)Click on the Sign-in button. |  |  | Low | Mid | New | Pawan Kumar
2020-02-01 | 8 | Login: There should be spacific validation message for entering invalid Username as "Invalid Username" instead of "Invalid Credentials". | User is on the website's Sign-in page and is registered to the website. | 1)Enter invalid username in the field provided. 2)Enter valid password in the field provided. 3)Click on the Sign-in button. |  |  | Low | Low | New | Pawan Kumar
2020-02-01 | 9 | Login: There should be spacific validation message for entering invalid Password as "Invalid Password" instead of "Invalid Credentials". | User is on the website's Sign-in page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter invalid password in the field provided. 3)Click on the provided Sign-in button. |  |  | Low | Low | New | Pawan Kumar
2020-02-01 | 10 | Home page: After logging into the system with valid credentials Home Page should get open but currently GIL Orders page is getting open which is wrong. | User is on the website's Sign-in page and is registered to the website. | 1)Enter valid username (email address) in the field provided. 2)Enter valid password in the field provided. 3)Click on the Sign-in button. | username 3911000170 password Welcome@123 |  | High | High | New | Pawan Kumar
2020-02-03 | 11 | Change Password: Validation message coming after entering invalid password is wrong its displaying "User not exist check user name and password" change password does not have any dependancy on user. | User is at the change password page. | 1)Enter invalid/wrong Data in the Old password field. 2)Enter valid details in the new and confirm password field. 3)Click on the Submit button. | Blank spaces as characters, less than 8 digits, without an uppar case, lower case ans special characters. | https://prnt.sc/qwnnwk | High | Low | New
2020-02-03 | 12 | Change Password: User is able to change his her password by entering invalid data in New and Cofirm Password field. | User is at the change password page. | 1)Enter invalid/wrong Data in the New Password field. 2)Enter Same password as that of New Password in confirm password field. 3)Enter valid data in old Password field. 4)Click on the Submit button. | Blank spaces as characters, less than 8 digits, without an uppar case, lower case ans special characters. |  | High | High | New
2020-02-03 | 13 | Change Password: There is No Validation message coming for entering invalid data in New Password. There should be a proper and spaciffic validation message for it according to the Password Rules. | User is at the change password page. | 1)Enter invalid/wrong Data in the new password field. 2)Enter valid details in the Old and confirm password field. 3)Click on the Submit button. | Blank spaces as characters, less than 8 digits, without an uppar case, lower case ans special characters. |  | High | Low | New
2020-02-03 | 14 | Gil Orders-Installation: there should be a spacific validation message for entering invalid product name. | User is at Add Installation page of selected order number. | 1)Enter invalid data in Product Name field of Product blank. 2)Click on Add Product button. | 4534534 | https://prnt.sc/qwo3ee | Low | Low | New
2020-02-03 | 15 | Gil Orders-Installation: User is able to add installation by entering installation date prior to one day of invoice date. | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter invalid data in Installation date field. 2)Click on Submit button. | 28-11-2019 Installation date should be between invoice date and currentt date. For order number 1804000239, Invoice date is 29/11/2019. | https://prnt.sc/qwo72u https://prnt.sc/qwo776 | High | High | New
2020-02-03 | 16 | Gil Orders-Installation: Installation date is wrong if user views the added installation available in the list of installation After successfully adding an installation. Its showing current date in installation date but the added date in installation is 28/11/2019. (Installation date should be between invoice date and currentt date. For order number 1804000239, Invoice date is 29/11/2019.) | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter invalid data in Installation date field. 2)Click on Submit button. | Test data:28-11-2019 | https://prnt.sc/qwo8u9 | High | High | New
2020-02-03 | 17 | Gil Orders-Installation: User is able to add insallation by entering only blank spaces as characters in Handed over by field. (User can enter space only in combination with an alphabetical character) | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter invalid data in Handed over by field. 2)Click on Submit button. | Blank spaces. |  | Low | Low | New
2020-02-03 | 18 | Gil Orders-Installation: User is able to add insallation by entering only blank spaces as characters in Description field. (User can enter space only in combination with an alphabetical character) | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter invalid data in Description field. 2)Click on Submit button. | Blank spaces. |  | Low | Low | New
2020-02-03 | 19 | Gil Orders-Installation: User is able to add the installatiob by uploading invalid file type in Site Photos. And also there should a validation message for the same. | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter valid data in all the mandatory fields. 2)Upload invaid file type/over size file. 3)Click on Submit button. | Upoad invalid file type other than photo type. | https://prnt.sc/qwonb3 | High | Mid | New
2020-02-03 | 20 | Gil Orders-Installation: There is no validation message appears for uploading invalid file or oversize file in installation note however the same file does not get added in the installation. | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter valid data in all the mandatory fields. 2)Upload invaid file type/over size file. 3)Click on Submit button. | Upoad invalid file type other than photo type. |  | Low | Low | New
2020-02-03 | 21 | Gil Orders-Installation: If user clicks on Delete icon against the record to be deleted then the page gets navigate to the detail page of the clicked installation. | User is at list of Installation page of selected order number and also have entered product details. | 1)Click on Delete icon appearing against the record to be delete. |  |  | High | high | New
2020-02-03 | 22 | Gil Orders-Installation:Already created Installation is getting delete if user clicks on the "X" icon appearing on the confirmation message to delete the record. | User is at list of Installation page of selected order number and also have entered product details. | 1)Click on Delete icon appearing against the record to be delete. 2)Click on "X" icon appearing at the right top corner of confirmation message to delete. | NA |  | High | high | New
2020-02-03 | 23 | Gil Orders-Installation: There should be a character limit for description and Handed over by field as currently user can add large data in both the fields. And also there should be a proper validation message for the same. | User is at Add Installation page of selected order number and also have entered product details. | 1)Enter large data in description and handeed over by field. 2)Enter valid details in all the remianing mandatory fields. 3)Click on Submit button. |  |  | Mid | Mid | New
2020-02-03 | 24 | Gil Orders-Update Installation: User ism able to update the installation by entering invalid PRODUCT Name. | User is at Update Installation page of selected order number. | 1)Clear and Enter invalid data in Product Name field of Product blank. 2)Click on Update Product button. | 4534534 | https://prnt.sc/qwtbcr |  |  | New
2020-02-03 | 25 | Gil Orders-Update Installation: At update installation page of selected installation there shouldn't be an option to add a product for new installation that is option to add product details however user cannot add any new installation from here. | User is at list of Installation page of selected order number and also have entered product details. | 1)Click on the Update icon appearing against the record you wish to update. 2)Select the Product from the select list. |  | https://prnt.sc/qwowk1 | High | high | New
2020-02-03 | 26 | Gil Orders-Update Installation: User is not able to update the Installation date. | User is at list of Installation page of selected order number and also have entered product details. | 1)Click on the Update icon appearing against the record you wish to update. 2) Select any valid date between the date of invoice tto current date. | 2020-02-02 |  | High | high | New
2020-02-03 | 27 | Gil Orders-Update Installation: User is able to save the Updated installation form with invalid date of installation.. | User is at list of Installation page of selected order number and also have entered product details. | 1)Click on the Update icon appearing against the record you wish to update. 2) Select any invalid date which does not lies between the date of invoice to current date. | 2019-11-28 |  | High | high | New
2020-02-03 | 28 | Gil Orders-Update Installation: User is able to update insallation by entering only blank spaces as characters in Handed over by field. | User is at Update Installation page of selected order number and also have entered product details. | 1) Enter invalid data in Handed over by field. 2)Click on Update button. | Blank spaces. |  | Low | Low | New
2020-02-03 | 29 | Gil Orders-Invoice: Invoice Date on List of invoice page is different( 25-11-2019) and if user views/opens the same invoice then on the invoice details page the invoice date is different (28-01-2020) under the same Order number. Order Details : 1804000146 | User is at list of Invoice page of selected order number and also have entered product details. | 1)Click on the GIL Orders menu button from the menu section. 2)Click on Action button of selected order number. 3)Click on Invoices link note down the invoice date of any invoice. 4)Click on the view bytton of the same invoice and note down the installation date. 5)Now see both the invoice dates. |  | https://prnt.sc/qwrknj https://prnt.sc/qwrkzt | High | high | New
2020-02-03 | 30 | Gil Orders-Updated Installation: There is no validation message appears for uploading invalid file or oversize file in installation note however the same file does not get added in the installation. | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter valid data in all the mandatory fields. 2)Upload invaid file type/over size file. 3)Click on Submit button. | Upoad invalid file type other than photo type. |  | Low | MID | New
2020-02-03 | 31 | Gil Orders-Installation: User is able to update the installation by uploading invalid file type in Site Photos. And also there should a validation message for the same. | User is at Add Installation page of selected order number and also have entered product details. | 1) Enter valid data in all the mandatory fields. 2)Upload invaid file type/over size file. 3)Click on Submit button. | Upoad invalid file type other than photo type. |  | High | High | New
2020-02-03 | 32 | Gil Orders-Warranty - User is able to add warranty by entering invalid warranty years. | User is at Add Warranty page of selected order number. Warranty By Invoice has been selected | 1)Enter invalid data in Available Quantity field of Product blank. 2)Click on Add Product button. | 0,-5 in warranty years | https://prnt.sc/qwu74z | High | High | New
2020-02-03 | 33 | Gil Orders-Warranty- Warranty number is incomplete. | User is at List of Warranty page. | 1)Check the warranty number of added warranties. |  | https://prnt.sc/qwu9ph https://prnt.sc/qwuigh | High | High | New
2020-02-03 | 34 | Gil Orders-Warranty- Calculation of end date is wrong it should be 02/02/2021 from today after one year but the website is calculating one extra day as 03/02/2021 | User is at List of Warranty page. | 1)Enter 1 as warranty year. 2)Now select the warranty start date and check the warranty end date. | Warranty year=1 | https://prnt.sc/qwuetc | High | High | New
2020-02-03 | 35 | Gil Orders-Warranty-there is no validation message for entering invalid Product Name. for both warranty by invoice and installation case) | User is at Add Warranty page of selected order number. Warranty By Invoice has been selected | 1)Enter invalid data in Product Name field of Product blank. 2)Click on Add Product button. |  | https://prnt.sc/qwtxm6 |  |  | New
2020-02-03 | 36 | Gil Orders-Warranty-warranty is getting added by entering invalid warrany start date that is user cannot select a start date prior to the invoice date. | User is at Add Warranty page of selected order number. Warranty By Invoice has been selected | 1)Enter warranty date prior to the invoice start date. 2)Enter valid details in the remaining fields. 3)Click on submit button. |  | https://prnt.sc/qwulzv https://prnt.sc/qwuma5 | High | High | New
2020-02-04 | 37 | Gil Orders-Warranty-User is able to add warranty by adding Quantity more than the invoice quantity as Available qauntity does not get decrease on the basis of existing warranty. Warranty By Invoice | User is at Add Warranty page of selected order number. Warranty By Invoice has been selected | 1)Enter qty to issue any random number. 2)Enter valid details in the remaining fields. 3)Click on submit button. 4)Again add waaranty by slecting same product and observe "qty to issue" field is still showing the total quantity in available qty. |  | https://prnt.sc/qx6mp8 https://prnt.sc/qx6n20 https://prnt.sc/qx6ngk https://prnt.sc/qx6nmj https://prnt.sc/qx6ntx | High | High | New
2020-02-04 | 38 | Gil Orders-Warranty- user is able to enter qty to issue more than the total product qty due to which the previously added qarranty cards displaying negative qty . | User is at Add Warranty page of selected order number. Warranty By Invoice has been selected | 1)Enter qty to issue any random number. 2)Enter valid details in the remaining fields. 3)Click on submit button. 4)Again add waaranty by slecting same product and observe "qty to issue" field is still showing the total quantity in available qty add the total available qauntity in qty to issue field. 5)Submit the form. 6)Now open list of warranty. |  | https://prnt.sc/qx6mp8 https://prnt.sc/qx6n20 https://prnt.sc/qx6ngk https://prnt.sc/qx6nmj https://prnt.sc/qx6ntx | High | High | New
2020-02-04 | 39 | Gil Orders-Warranty-User is able to add warranty by adding Quantity more than the invoice quantity as Available qauntity does not get decrease on the basis of existing warranty. Warranty By installation. | User is at Add Warranty page of selected order number. Warranty By installation has been selected | 1)Enter qty to issue any random number. 2)Enter valid details in the remaining fields. 3)Click on submit button. 4)Again add waaranty by slecting same product and observe "qty to issue" field is still showing the total quantity in available qty. |  | https://prnt.sc/qx6y3u | High | High | New
2020-02-04 | 40 | Gil Orders-Warranty: Warranty is getting delete instead of closing of confirmation messageif user clicks on the close icon appearing on the confirmation message. | User is at List of Warranty page. | 1)Click on delete icon appearing against the selected Warranty. 2)Click on Close icon appearing on the confirmation message. |  |  | High | High | New
2020-02-04 | 41 | Gil Orders-Update Warranty: At update warranty page of any warrnaty available qty is showing on less than the total invoice qty. Provided it’s the only added warranty against the same product and invoice number. | User is at list of warranty page. | 1)click on view button against the warranty you wish to view. 2)Now observe the invoice qty and available qty Provided it’s the only added warrantty against the same product and invoice number. |  | https://prnt.sc/qx782u https://prnt.sc/qx78aq | High | High | New
2020-02-04 | 42 | Gil Orders-Update Warranty:User is not able to update the warranty by selecting more products under the same invoice number. | User is at Update Warranty page of selected order number. Warranty By Insallation has been selected | 1)Leave the Insallation Number field of Product blank. 2)Click on Update Product button. | NA | https://prnt.sc/qywr8f | High | High | New
2020-02-04 | 43 | Gil Orders-Update Warranty: If user deletes an existing warranty on update warranty page then the option to add new warranty should get enable. | User is at list of warranty page. | 1)Click on any warranty you wish to edit. 2)Click on "X" button appearing against the warranty details. |  | https://prnt.sc/qx7lgr | High | High | New
2020-02-04 | 44 | Gil Orders-End User:User is able to add end user by entering invalid data in full name field. | User is at Add End User page | 1)Enter invalid data in Full Name field of End User blank. 2)Click on Add End User button. | @$@#$# | https://prnt.sc/qx7y1p | High | High | New
2020-02-04 | 45 | Gil Orders-End User:User is able to add end user by entering invalid data in email address field. | User is at Add End User page | 1)Enter invalid data in Email Address field of End User blank. 2)Click on Add End User button. | hhgl.h@i | https://prnt.sc/qx7y1p | High | High | New
2020-02-04 | 46 | Gil Orders-End User: For Pin 123456 the mapping of city and state is wrong. There is no areaa of delhi with pin code 123456. | User is at Add End User page | 1)Enter invalid data in Pin field of End User blank. 2)Click on Add End User button. | 2238-01-03 | https://prnt.sc/qx7v0k | High | High | New
2020-02-04 | 47 | Gil Orders-End User: Selected User is getting delete instead of closing the confirmation message if user clicks on the close icon on confirmation message. | User is at List of End User page. | 1)Click on delete icon appearing against the selected End User. 2)Click on Close icon appearing on the confirmation message. |  |  | High | High | New
2020-02-04 | 48 | Gil orders-End User : User is able to submit the form by leaving Warranty field blank. | User is at Add End User page | 1) Select Warranty from the select list. 2)Enter valid data in all the mandatory field except leaving any field blank (Fullname blank) 3)Close warranty details pop-up. 4)Enter valid data in full name. 5)Click on submit button. |  | https://prnt.sc/qx9hnv https://prnt.sc/qx9wb0 | High | High | New
2020-02-04 | 49 | Gil orders-End User : There should be a validation for entering a large data in first Name field. | User is at Add End User page | 1)Enter large data in Full Name field of End User blank. 2)Click on Add End User button. |  | https://prnt.sc/qx9oy8 | low | low | New
2020-02-04 | 50 | Gil orders-End User : There should be a validation for entering a large data in Address field. | User is at Add End User page | 1)Enter large data in Address field of End User blank. 2)Click on Add End User button. |  | https://prnt.sc/qx9oy8 | low | low | New
2020-02-04 | 51 | Gil orders-End User : User should not be able to view warranty details without entering User details as currently user can view the warranty details by selecting warranty number if that’s thw logic then there is no point of including select warranty inside Add user section. | User is at Add End User page | 1)Select warranty number. 2)Leave all the other mandatory fields blank. 3)Click on Submit button. |  | https://prnt.sc/qx9ssx | Mid | Mid | New
2020-02-04 | 52 | Suggestions: Gil orders-End User: If user selects any warranty from the dropdown and by mistake he has selected a wrong warranty and again he has selected the correct warranty then the details corresponding to the correct warranty should appear but currently its not happening and the user have to delete the previous warranty and again has to select it. | [6 empty] | New
2020-02-04 | 53 | Gil Orders_Update Warranty: User is not able to update the warranty by selecting more products under the same invoice number. | User is at Update Warranty page of selected order number. Warranty By Invoice has been selected | 1)Leave the Invoice Number field of Product blank. 2)Click on Update Product button. | NA | https://prnt.sc/qxa898 | High | High | New
2020-02-04 | 54 | Gil Orders_Update Warranty: There should be an Update button instead of Submit button although the functional behaviour is same but its not spacific. | User is already logged in | 1)Click on the GIL Orders menu button from the menu section. 2)Click on Action button of selected order number. 3)Click on End User link. 4)Click on UpdateEnd User button. | NA | https://prnt.sc/qxak8t | Low | Low | New
2020-02-04 | 55 | Gil Orders-update End User:User is able to update end user by entering invalid data in full name field. | User is at Update End User page | 1)Clear and Enter invalid data in Full Name field of End User blank. 2)Click on Update End User button. | feaga@$@$@# | https://prnt.sc/qxaqz5 | Mid | Mid | New
2020-02-04 | 56 | Gil Orders-update End User:User is able to update end user by entering invalid data in email address field. | User is at Update End User page | 1)Clear and Enter invalid data in Email Address field of End User blank. 2)Click on Update End User button. | h253235h@i | https://prnt.sc/qxaqz5 | Mid | Mid | New
2020-02-04 | 57 | Gil Orders-update End User: User should is be able to Update End User and also there should be a proper and spacific validation message for Pin Number field. | User is at Update End User page | 1)Clear and Enter invalid data in Pin Number field of End User blank. 2)Click on Update End User button. | 123456 | https://prnt.sc/qxav8e | Mid | Mid | New
2020-02-04 | 58 | Gil Orders-update End User: Blank validation message appears for entering blank spaces as digits in Pin code field. | User is at Update End User page | 1)Clear and Enter invalid data in Pin Number field of End User blank. 2)Click on Update End User button. | Blank Spaces as digits | https://prnt.sc/qxawkj | Mid | Mid | New
2020-02-04 | 59 | My Invoice: There is no validation appears for Customer Type while creating an invoice. | user is already logged in and is on Create Invoice Page. | 1)Leave the Customer Type field blank. 2)Enter valid data in remaining mandatory fields. 3)Click on Add Product button. |  | https://prnt.sc/qxd49b | High | High | New
2020-02-04 | 60 | My Invoice: Customer Type field should be marked (*) in order to show it as a mandatory field. | user is already logged in and is on Create Invoice Page. |  |  | https://prnt.sc/qxd49b | High | High | New
2020-02-04 | 61 | My Invoice: User is able to add an invoice by entering invalid data in invooice number field. | user is already logged in and is on Create Invoice Page. | 1)Enter invalid data in Invoice number field. 2)Enter valid data in the remaining mandatory fields. 3)Click on Add Product button. | Blank spaces as characters, special characters , alphabets. |  | High | High | New
2020-02-04 | 62 | My Invoice: User is able to add an invoice by entering invalid date in invoice date field. That is user should not be able to add future date in the invoice date field. | user is already logged in and is on Create Invoice Page. | 1)Enter invalid date in invoice date field. 2)Enter valid data in the remaining mandatory fields. 3)Click on Add Product button. | 2033-02-09 | https://prnt.sc/qxd94a | High | High | New
2020-02-04 | 63 | My Invoice: User is able to create ivoice by entering invalid emai address. | user is already logged in and is on Create Invoice Page. | 1)Enter invalid data in Customer email field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | test@gm |  | Low | Low | New
2020-02-04 | 64 | My Invoice: There should be a character limit for address field. | user is already logged in and is on Create Invoice Page. | 1)Enter invalid data in Customer address field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | NA |  | Low | Low | New
2020-02-04 | 65 | My Invoice: User is able to create invoice by entering wrong customer pin. | user is already logged in and is on Create Invoice Page. | 1)Enter invalid data in Customer pin field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 123456 |  | High | High | New
2020-02-04 | 66 | My Invoice: User is not able to create invoice even after submitting the form with valid data in all the mandatory fields. | user is already logged in and is on Create Invoice Page. | 1)Enter valid dataa in all the mandatrory fields. 2)Click on Submit button. |  | https://prnt.sc/qxdt6p | High | High | New
2020-02-07 | 67 | Create Tickets: User is able to create Ticket Rquest by entering invalid data in Customer Name field and also there should be a proper and spacific validation message for Customer Name field. | user is already logged in and is on Create Ticket Request Page. | 1)Enter invalid data in Customer Name field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | Lo@#@fdfd5345 large data |  | low | low | New
2020-02-07 | 68 | Create Tickets: User is able to create Ticket Rquest by entering invalid data(Large data ) in Address field and also there should be a proper and spacific validation message for Address field. | user is already logged in and is on Create Ticket Request Page. | 1)Enter invalid data in Address field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | Large data |  | Low | Mid | New
2020-02-07 | 69 | Create Tickets: Tickets: There is no validation message appears for entering invalid/wrong pin. | user is already logged in and is on Create Ticket Request Page. | 1)Enter invalid data in Pin Code field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 123456 445557 | https://prnt.sc/qysr4p | low | Low | New
2020-02-07 | 70 | Create Tickets: User is able to create request by entering wrong order date. | user is already logged in and is on Create Ticket Request Page. | 1)Enter invalid data in Order Date field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 07-02-2020 but actual order date corresponding to the order number is 30-09-2019 |  | High | High | New
2020-02-07 | 71 | Create Tickets: User is able to create request by entering wrong invoice date. | user is already logged in and is on Create Ticket Request Page. | 1)Enter invalid data in Invoice Date field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 06-02-2020 but actual invoice date corresponding to the invoice number is 25-11-2019 |  | High | High | New
2020-02-07 | 72 | Update Tickets: No validation appears for leaving order number field blank | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Leave the Order Number field blank. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | NA |  | Mid | Mid | New
2020-02-07 | 73 | Update Tickets No validation appears for leaving invoice number field blank | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Leave the Invoice Number field blank. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | NA |  | Mid | Mid | New
2020-02-07 | 74 | Update Tickets: User is able to update with invalid data in name field. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Customer Name field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | gsgsg@$7568 |  | Low | Low | New
2020-02-07 | 75 | Update Tickets: User is able to update with invalid email address. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Email Address field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | wfa@shdshcom |  | mid | mid | New
2020-02-07 | 76 | Update Tickets: There should be a validation foe entering large data in address field. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Address field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | Large data |  | mid | mid | New
2020-02-07 | 77 | Update Tickets: There is no validation appears for entering invalid pin code. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Pin Code field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | NA |  | mid | mid | New
2020-02-07 | 78 | Update Tickets: User should not be able to update with invalid order date. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Order Date field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 07-02-2020 but actual order date corresponding to the order number is 30-09-2019 |  | High | HIGH | New
2020-02-07 | 79 | Update Tickets: User should not be able to update with invalid invoice date. | user is already logged in and is on Update Ticket Request Page. | 1)Clear and Enter invalid data in Invoice Date field. 2)Enter valid data in remining mandatory fields. 3)Click on Submit button. | 06-02-2020 but actual invoice date corresponding to the invoice number is 25-11-2019 |  | High | High | New
Note : MY INVOICE section is yet to be tested because im not able to create an invoice even after submitting the form with valid details due to which further sub modules are getting block.

## Sheet2
Project: | Greenlam Warranty Management System (Dealer)
Module : | GIL Orders
Total No. of Test Case Run | 72
Total Number of Found Bugs | 17
Total Test Case written | 82