## Rakesh
S No. | Main Header | Sub-Header | Observation | Tested On | Current Status | Category | Remarks by Assurant | Remarks by Techfour (MOM-14/7/20) | Time efforts-Ajay | Time efforts-AjayK1 | Time efforts-QA | Time efforts-pawan
6 | Web Portal | Repairer Profile | Engineer assigned with new appointment date, on dashboard the claim status is "Reschuduled" it should be Engineer assigned | 2020-06-14 | discussed | Critical | Same issue on 12/7/2020 UAT | pending | Done |  | 3 Hrs
30 | Web Portal | claims progress timeline | Post Estimate approval no status to change to “Repair in progress or Part pending” | 2020-06-20 | discussed | Critical | Same issue on 12/7/2020 UAT | TBD-internal
13 | CA login | CA Dashboard | Selected Acko as fillter but still CPP claim is apearing on screen | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | QA
8 | Dashborad | Program filter | Unable to open the cases from Ageing bucket | 2020-06-14 |  | Critical | Same issue on 12/7/2020 UAT | pending
10 | Web Portal | Case request | Not able to Edit engineer profile | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | pending
12 | Web Portal | Estimate page | Not able to edit repairer profile | 2020-06-20 | discussed | Show Stopper | Same issue on 12/7/2020 UAT | pending
14 | CA login | CA case requests | Case no should be external claim no & not saleforce ticke tno | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | Done
16 | Web Portal | Visit assign (post estimate approval) | CA should see the pending approval cases with ageing, In CA's dashboard it does not have clarity | 2020-06-20 | discussed | Critical | Same issue on 12/7/2020 UAT | pending
17 | Web Portal | Visit assign (post estimate approval) | Not able to understand which case needs to be approved first | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | pending
23 | Web Portal | Visit assign (new case) | At the time of repair visit – it is again asking for reason for rescheduling – system calculate diff from 1st visit schedule date. | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | Duplicate
29 | Web Portal | Post Estimate approval | Enter Repair TAT – Field not required to show while repair completion, we can place Repair TAT and visit TAT at start | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | Done
31 | Web Portal | Visit assign (post estimate approval) | Program name not visible on Claim notification | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | reject
39 | App | Dashboard | No difference between visit intimation and repair intimation to engineer | 2020-07-12 |  | Critical | New issues | Duplicate
41 | SFDC | Case page | Timeline should be more clear – Its Est approved but feels like repair complete. | 2020-07-12 |  | Critical | New issues | Duplicate
56 | Web Portal | Visit assign (post estimate approval) | No information about program name and claim status | 2020-07-12 |  | Show Stopper | New issues | will resolve in new UI
53 | Web Portal | CA login for est approval | For new claim also SFDC is showing "repeat repair" | 2020-07-12 |  | Critical | New issues | -We are showing same doc twice, should be at one place with lables -show doc label same like when we click on Attachment icon in inspection section
55 | Web Portal | CA login for est approval | Not Able to assign repair visit post estimate approval/ time slot error (1st selected 10.30 then changed to new slot | 2020-07-12 |  | Critical | New issues | New-pending UI overlapping
57 | SFDC | Post Estimate approval | Documents without lable, CA cant understand which document to check for what | 2020-07-12 |  | Show Stopper | New issues | SFDC clarity required
58 | Web Portal | Visit assign (post estimate approval) | Not able to see requested and approved value with lable | 2020-07-12 |  | Show Stopper | New issues -Cant move ahead to do further UAT on this case thorugh APP | New-pending case id-608
59 | SMS | Customer SMS for repair visit | Post est approval amount started reflecting in SF but requested amount is still blank | 2020-07-12 |  | Critical | New issues | check SMS-inspection SMS shouldn't sent twice, 2nd sms should be repair visit -required seprate discussion on SMS concept with rakesh/shailena | QA
60 | Web Portal | Visit assign | Post 2nd visit (for repair)if found new issue and part need to change then engineer submit the observation on App, but no flow thereon on Web portal, not able to update from co-ordinator login also | 2020-07-12 |  | Show Stopper | New issues | will resolve in new UI
63 | Web Portal | Estimation | Post visit completion also the slot is full, it should be clear for next visit | 2020-07-12 |  | Show Stopper | New issues | New- pending change tigger point- should go on case rejection status seprate discussion with rakesh/shailena, TBD internally
64 | SFDC | Estimation | Estimate rejection is internal, SMS received by customer about estimate rejection and repudiation is not as per process | 2020-07-12 |  | Critical | New issues | SFDC clarity required
66 | Web Portal | Repair completion | Estimate rejection is not reflecting in SFDC | 2020-07-12 |  | Show Stopper | New issues | New-pending repairer & CSR both can enter OTP-new point
67 | Web Portal | Repair completion | Generate invoice is not visible if co-ordinator update the case as RC, no provision to enter customer OTP (APP shows OTP pending) | 2020-07-12 |  | Show Stopper | New issues | Duplicate-pt 66
68 | Web Portal | Invoice generation | Need to enter OTP though App only for RC-CC and to enable "Generate Invoice" | 2020-07-12 |  | Show Stopper | New issues | new-pending case id-609 | QA
1 | Web Portal | Schedule Visit | SNP name is diff, Selected Demo account 2, but it display as Ashoka entp | 2020-06-14 | discussed | Show Stopper | Resolved | Closed(Resolved)
7 | Mobile Portal | Login to App | New case assigned for 12/7/2020 is reflecting in >22 days ageing | 2020-06-14 |  | Show Stopper | Resolved | Closed(Resolved)
9 | Web Portal | SMS to customer | While assigning 2nd visit for repair completion, it shows time slot is booked but icon is green not RED | 2020-06-14 |  | Show Stopper | Resolved | Closed(Resolved)
11 | Web Portal | Saleforce | Repair visit (post approval) also shows Inspection reschedule – it should be repair visit | 2020-06-20 | discussed | Show Stopper | Resolved | duplicate
18 | SMS | SMS to customer | RC done by Co-ordinator,then tried genearting inovice it gives error "something went wrong try again later" tried 3 times but no success | 2020-06-20 |  | Show Stopper | Resolved | Closed(Resolved)
20 | SFDC | RC - CC stage | Not able to assign engineer and select appointment date & reschedule reason. | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | SFDC point
21 | Web Portal | Visit assign (new case) | Not able to get OTP for login as engineer user name - 7738381172 | 2020-06-20 |  | Show Stopper | Resolved | Closed(Resolved)
25 | Engineer App | Visit completion | SMS not received after visit assignent | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | Duplicate- check on new build
26 | Engineer App | Documents | Visit completed but SFDC shows Visit assigned - No sync between Re-Assure and SFDC | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | Duplicate- check on new build
27 | SFDC | WOLI | No SMS at any point during claims process | 2020-06-20 |  | Show Stopper | Same issue on 12/7/2020 UAT | SFDC point
28 | SFDC | Estimate approved | RC – CC done by CSR but Generate invoice not activated | 2020-06-20 |  | Show Stopper | Resolved but new issue arised | SFDC point
32 | Engineer App | Repair completion visit | Tried to assign new case to new engineer – time slot error (Engineer name -Sri) | 2020-06-20 | discussed | Show Stopper | Resolved | Duplicate
33 | Engineer App | Repair completion visit | Visit completed and all fields and photos submitted - But still it gives error "Please fill all fields" | 2020-06-20 | discussed | Show Stopper | Same issue on 12/7/2020 UAT | Duplicate- check on new build
34 | Web Portal | Repair completion | Even if the visit not completed due to error "Please fill all fields", all documents get uploaded automatically | 2020-06-20 |  | Show Stopper | Resolved | Closed(Resolved)
35 | SMS | claim creation | In Re-Assure its service charge But in Salesforce its reflecting as Part | 2020-07-12 |  | Show Stopper | New issues | Email part is pending
36 | Web Portal | Dashboard | Case Number: 16665910 - Approved value is less than requested value i.e, 2242 but saleforce shows the same Requested value as Approved value i.e., 2360 | 2020-07-12 |  | Critical | New issues | New-pending
37 | SFDC | Repair schedule date/appointment date | For 2nd visit of repair completion (post approval) on engineer APP it ask for visit photos again, ideally it should directly go to “Is repair completed check box”. Engineer cant fill inspection details again at the time of repair visit. | 2020-07-12 |  | Show Stopper | New issues | Duplicate
40 | App | Fault diagnosed | Even afte selecting all fields and photos again , it gives error “Please fill all fields” | 2020-07-12 |  | Critical | New issues | QA
43 | Web Portal | Estimation | Case no - 16665910 - three times clicked on “Repair completed” checkbox with Resolution of issue & repair complete date but Case status remain “Visit scheduled” – no change | 2020-07-12 |  | Show Stopper | New issues | You can delete the row using delete icon (as estimation UI is under development, delete icon is mission. Once it resolved you can perform this action)
44 | Web Portal | Estimation | When we change the appointment date, it is not reflecting in SFDC | 2020-07-12 |  | Show Stopper | New issues | confusion between sub total and part total, need to sort this will remove in new UI, fields name will be same as SFDC
45 | Web Portal | Estimation | Problem diagnosed by engineer for camera - not correct | 2020-07-12 |  | Critical | New issues | new
46 | Web Portal | Estimation | Not allowing to select "0" transportation | 2020-07-12 |  | Show Stopper | New issues - clarity taken from Uttam | new
47 | Web Portal | Estimation | Wrong sub total | 2020-07-12 |  | Critical | New issues | will remove in new UI
48 | Web Portal | Estimation | Remark should not be mandatory during estimation | 2020-07-12 |  | Show Stopper | New issues | new-pending - need to remove validation - in case net amount is greater then reserve amount, then net amount will become new reserve amount(that will be updated on SFDC side only)
49 | Web Portal | Estimation | At times GST should be zero if work is getting done through Authorized ASC, repairer can put "0" GST % | 2020-07-12 |  | Show Stopper | New issues | new- delete icon missing from new UI
50 | Web Portal | Estimation | Service charges and transportation repeated on screen | 2020-07-12 |  | Show Stopper | New issues | click on Estimation-all details are visible- clarity required QA with cross browser
51 | SFDC | Estimation | Authorized amount cannot be more than reserve - Need to remove this validation | 2020-07-12 |  | Show Stopper | New issues | duplicate- SFDC clarity required
52 | Web Portal | CA login for est approval | No option to remove the part from estimate list | 2020-07-12 |  | Show Stopper | New issues | new-pending
54 | Web Portal | CA login for est approval | Not able to see complete estimate details as it was filled like part, service charge etc. | 2020-07-12 |  | Critical | New issues | New-pending Cross broswer issue
61 | App | Repair in 1st visit | Requested value is not reflecting in SFDC, estimated value shows “0” | 2020-07-12 |  | Show Stopper | New issues -Cant move ahead to do further UAT on this case thorugh APP | Duplicate- check on new build
62 | SFDC | Estimation | CA not able to see which case to approve, the ageing bracket is not correct, recently added case is not reflecting in 0 or 0-3 days bucket | 2020-07-12 |  | Show Stopper | New issues | Duplicate- check on new build
65 | App | Repair completion | Estimation screen fields overlapped, not able to view properly | 2020-07-12 |  | Show Stopper | New issues | Duplicate- check on new build
42 | SFDC | Spring CM - docs | Not able to submit if repair is completed on site in 1st visit – it gives error – Pls fill all fields even though all fields are correctly selected/filled | 2020-07-12 |  | Show Stopper | New issues | duplicate- SFDC clarity required
4 | Web Portal | Case request | for 2nd case also the requested value is 0 in SFDC | 2020-06-14 | discussed | Critical | Same issue on 12/7/2020 UAT | pending
3 | Web Portal | Dashboard | If RC at in 2nd visit - App does not allow to "submit", it shows error "pls fill all fields" even though all fields are properly filled | 2020-06-14 | discussed | Critical | Same issue on 12/7/2020 UAT | pending
5 | Web Portal | Engineer profile | Document nomenclature is not correct, uploaded Jobsheet but its not reflecting in spring CM | 2020-06-14 | discussed | Critical | Same issue on 12/7/2020 UAT | pending
2 | Web Portal | Create User | C299920000248 –Claim number created with phone 9699558678 & email ID teckno.in@gmail.com, SMS received but email not received | 2020-06-14 | discussed | Critical | Same issue on 12/7/2020 UAT | Pending
15 | CA login | Estimate approval | Should not allow both IGST & CGST+SGST in single claim/for same repairer | 2020-06-20 |  | Show Stopper | Resolved but new issue arised | Duplicate
19 | Web Portal | Repair completion | Case no - 16665914 - Selected higher value than requested value – system accepted the higher value, but approved value doesn’t change | 2020-06-20 | discussed | Critical | Same issue on 12/7/2020 UAT | pending
22 | Engineer App | Dashboard | Post estimate approval when repairer assign engineer 2nd time – supervisor can see old visit scheduled date, this will create confusion | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | pending
24 | Engineer App | Dashboard | Claim number not visible on notification of claim (Engineer name - Engineer06) | 2020-06-20 |  | Critical | Same issue on 12/7/2020 UAT | pending
38 | App | Visit pending | Only one visit can be assigned per time slot | 2020-07-12 |  | Critical | New issues | TBD-internally need identifier to define the visit/repair status

## Sanish
S. No | Main Header | Sub-Header | Observation | Tested On | Tested By | Category | Assigned to | Current Status | Remarks by Techfour (MOM-14/7/20) | Remarks by Assurant | Time efforts-Ajay | Time efforts-AjayK1 | Time efforts-pawan | Time efforts-QA | Sanjeev
1 | Web Portal | case View | No History view of the case | 2020-07-12 | Sanish | Critical |  |  | Add new section- Case Status History |  | 5hr | 2hr | NA | 4 hours | 14hr
2 | Web Portal | Case Request | View By Claim no & Policy no option is not available | 2020-07-12 | Sanish | Critical |  |  | New Pending- will add Claim no & Policy No search |  | 30mins | NA | NA |  | 2hr
18 | User Creation | Engineer profile | Duplicate email not allowed | 2020-07-12 | Sanish | Critical |  |  | Make email no mandatory or allow duplicate email to enter(for engg only) |  | NA | 30min | NA |  | 1hr
15 | Web Portal | OTP | No option to add OTP other than App and On App OTP is not accepted | 2020-07-12 | Sanish | Show Stopper |  |  | CSR unable to insert the OTP |  | TBD-mohit sir | TBD-mohit sir | TBD-mohit sir
3 | Web Portal | Page View | No Remark option to update Remarks of update | 2020-07-12 | Sanish | Critical |  |  | Phase-2 | -show Timestamp on remark - maintain global wise remark-2nd phase
4 | Web Portal | Estimate | Transportation is mandatory field | 2020-07-12 | Sanish | Critical |  |  | Duplicate
5 | Web Portal | Estimate | Estimate amount Vs reverse amount conflict | 2020-07-12 | Sanish | Show Stopper |  |  | Duplicate
6 | Web Portal | Estimate | Expected closure date can only be selected <7 days | 2020-07-12 | Sanish | Critical |  |  | new pending- will remove validation
7 | CA login | Estimate | can only be viewed then Approve estimate is selected | 2020-07-12 | Sanish | Critical |  |  | QA-cross browser issue
8 | CA login | Estimate | Estimate view is over lapped | 2020-07-12 | Sanish | Critical |  |  | QA-cross browser issue
9 | CA login | Inspection details | can only be viewed then Approve estimate is selected | 2020-07-12 | Sanish | Critical |  |  | duplicate- pt 7 |  | Duplicate
10 | CA login | Documents View | Incomplete documents available on CA login | 2020-07-12 | Sanish | Critical |  |  | Closed- may doc taking time to upload |  | Not an issue
11 | Web Portal | Visit assignment | Only 1 cases per engineer per slot can be assigned. Total of 3 cases per day can be assigned | 2020-07-12 | Sanish | Show Stopper |  |  | Duplicate |  | Duplicate
12 | App | Repair visit | Repair visit details are to be filled up again | 2020-07-12 | Sanish | Critical |  |  | Duplicate | share new build
13 | App | Case View | Engineer is unable to view a case once updated | 2020-07-12 | Sanish | Critical |  |  | Will share you new app build | share new build
14 | App | OTP | RC OTP is not accepted by APP | 2020-07-12 | Sanish | Show Stopper |  |  | QA | share new build
16 | Web Portal/CA Login | Page View | Details not visible unless clicked on Clock Sign | 2020-07-12 | Sanish | Critical |  |  | closed-have to click on history icon in order to view the history details
17 | Web Portal | Invoice generation | Invoice generation not possible since Case could be completed without OTP | 2020-07-12 | Sanish | Show Stopper |  |  | closed- as per logic, without OTP invoice will not genrate
19 | App | Engineer profile | user details are not matching with portal details |  | Sanish | Critical |  |  | QA

## Estimation
| header | sub header | Observation |  | QA Status | Remark by techfour | Time efforts-Ajay | Time efforts-AjayK1 | Time efforts-pawan | QA Efforts | Sanjeev
43 | Web Portal | Estimation | Not allowing to select "0" transportation | Rakesh | Not Fixed | Cross icon Missing from new UI | NA | 1hr | NA | 5-6 hours | BY end of week
44 | Web Portal | Estimation | Wrong sub total | Rakesh | Fixed | Remove duplicate subtotal, transpotataion, service from the below table - rename total to Net Payable | Done | Done | Done
45 | Web Portal | Estimation | Remark should not be mandatory during estimation | Rakesh | Not Fixed |  | Done by Ajay
47 | Web Portal | Estimation | Service charges and transportation repeated on screen | Rakesh | Fixed | remove in new UI | Done | Done | Done
48 | Web Portal | Estimation | Authorized amount cannot be more than reserve - Need to remove this validation | Rakesh | Fixed-Validation is removed | if estimated amount is greater than reserve, system should allow - remove validation later stage- resrve amount will update at SFDC | done
49 | Web Portal | Estimation | No option to remove the part from estimate list | Rakesh | Not Fixed | Cross icon Missing from new UI | Duplicate | Duplicate | Duplicate
50 | Web Portal | Estimation | Not able to see complete estimate details as it was filled like part, service charge etc. | Rakesh | Fixed | remove in new UI-Overlapping issue | NA | NA | NA
52 | Web Portal | CA login for est approval | CA not able to see which case to approve, the ageing bracket is not correct, -recently added case is not reflecting in 0 or 0-3 days bucket | Rakesh | qa |  | Duplicate/QA
54 | Web Portal | CA login for est approval | Estimation screen fields overlapped, not able to view properly | Rakesh |  | Firefox, edge/explorer | NA | NA | QA
53 | Web Portal | CA login for est approval | Documents without lable, CA cant understand which document to check for what | Rakesh |  | Claer from ajay | NA | Done | NA
55 | Web Portal | CA login for est approval | Not able to see requested and approved value with lable | Rakesh | my approval sub menu | Assigned to pawan | Duplicate
63 | Web Portal | Estimation | Estimate rejection is internal, SMS received by customer about estimate rejection and repudiation is not as per process | Rakesh |  |  | TBD with Reject with & without payment point
4 | Web Portal | Estimate | Transportation is mandatory field | Sanish |  | Duplicate- pt 43
5 | Web Portal | Estimate | Estimate amount Vs reverse amount conflict | Sanish |  | Duplicate -pt 48
6 | Web Portal | Estimate | Expected closure date can only be selected <7 days | Sanish |  | remove days validation | Done | NA | NA
7 | CA login | Estimate | can only be viewed then Approve estimate is selected | Sanish | discussion | Accordion not working edge/firefox |  |  | QA- Lower priority
8 | CA login | Estimate | Estimate view is over lapped | Sanish |  | Duplicate- Browser issue
57 | SFDC | Post Estimate approval | Post est approval amount started reflecting in SF but requested amount is still blank | Rakesh |  | On Hold
64 | SFDC | Estimation | Estimate rejection is not reflecting in SFDC | Rakesh |  | On Hold
62 | SFDC | Estimation | for 2nd case also the requested value is 0 in SFDC | Rakesh |  | On Hold
51 | SFDC | Estimation | Requested value is not reflecting in SFDC, estimated value shows “0” | Rakesh |  | On Hold
46 | Web Portal | Estimation | At times GST should be zero if work is getting done through Authorized ASC, repairer can put "0" GST % | Rakesh |  | On Hold
|  |  | Repair type field is mandatory , So there should be asterix mark against it. | Jitendra

## Sign Off
Main Header | Sub-Header | Observation | Go Live Critical | Tested On | Tested By | Current Status | Category | Remarks by Techfour | Remark by Assurant (14-15 july -MOM) | Sign off confirmation | Time efforts-Ajay | Time efforts-AjayK1 | Time efforts-pawan | QA Efforts | Sanjeev
Web Portal | Case Manager | Automatic estimation approval |  |  | Shailena |  | Show Stopper | introduce new status- Estimate rejection. if invoice is rejected By CM/network head/COO, then loop will continue to estimate section | -share extra effort time -add in BRD | Approved | 16hrs | NA | NA | 8 Hours | 4days
Web Portal | Visit schedule | visit schedule, appoinmnet date, reschdule reason fields confusion ( Pending clarification on CSR ) | 1 |  | Rakesh/shailena | Not Fixed | Critical | New-pending | -Remove visit schedule date-not required to display - first visit- clear valdation from business - second visit- if date assigned by CSR, then appointmnet date will be reschedule date with same engg - Inspection section- we should show latest/remark information - need to take final confirmation with bsiness | Approved | 2hr | 1.5hr | NA |  | 7hr
Web Portal | Visit schedule | Time slot UI/concept | 1 |  | Rakesh/shailena | Fixed | Critical | New-pending | - will not restrict user on time slot but will bound within selected hourly timeslot - divide slot hourly(Divide first and second half basis) - show 8-9 slot icon -hover on icon- show time for ex- 10-11,11-12 -no priority concept | Approved | NA | 3hr | Done |  | 6hr
Web Portal | Create User> | Repairer can create a new user as "3rd party service provider" - | [5 empty] | New-pending | -will add this value under picklist and process will be same -Once the claim assigned to 3rd party service providers, then there is no role of the web portal standard process. -CSR will handle such case at their end -In MIS report, these 3rd party case will identify separately | Approved | TBD-Sanjeev | TBD | TBD
Web Portal | Estimate page | Should not allow both IGST & CGST+SGST in single claim/for same repairer | [5 empty] | Clarity required | Logic need to be taken from Uttam
Web Portal | Estimate page | At times GST should be zero if work is getting done through Authorized ASC, repairer can put "0" GST % | [5 empty] | Clarity required | (Concept clarity taken from Uttam )
Web Portal | Dashboard | The dashboard needs to be reworked, the status wise total is not user friendly, refer ss. |  | 2020-06-21 | Shailena |  | Show Stopper | -2nd phase point- bucket and ageing wise data display - for graphic view- show counter along with % for better readability | Share Time efforts, will take this poiny after UAT and as per the time efforts
Web Portal | Role Permissions | Provide same Repairer permission rights to CSR role except CSR will have no cap restriction on previous Visited Date (Assurant team will decide later about back date restriction) |  |  | Shailena |  | Show Stopper | TBD- internal | Share time effort according to work flow will do after UAT point
Web Portal | Add inspection | Inspection result field needs to be added for ACKO in the inspection section | 2 |  | Radha/arpit |  | Critical | Clarity required | schedule meeting with arpit- send reminder |  | TBD | TBD | TBD
Web Portal | Menu | My Approval option new screen for CA/NH/COO | [8 empty] | 4hr | NA | 8hr |  | 3days
Web Portal | Estimation Approval | New Status - Rejected with Payment / Rejected without Payment | [8 empty] | TBD | TBD | TBD
Web Portal |  | Bulk approval for Invoice
Web Portal ( 58) | Visit assign (post estimate approval) | Post 2nd visit (for repair)if found new issue and part need to change then engineer submit the observation on App, but no flow thereon on Web portal, not able to update from co-ordinator login also | 2 |  | Rakesh | Not Fixed |  |  |  |  | QA-ajay
Web portal | Case request | From- To date filter on creation date |  |  |  | Not Fixed |  |  |  |  | 2hr | na | 2hr |  | 6hr

## App Changes
| Screen | Changes | Remarks | QA-Status | Assigned To | Attachment | Remarks by techfour | test by | Time efforts-Ajay | Time efforts-shalu | QA Efforts | Sanjeev
Mobile App | Dashboard screen-Pending Visits | Show External Claim No: | QA | Fixed | Shalu | https://prnt.sc/tjghxw |  |  | Done | done
|  | Show actual status for pending visits- Inspection Visit & Repair visit |  | Fixed | Shalu/Ajay | https://prnt.sc/tjghxw | Shalu needs parameter Visit_Type API Name: http://dev-reassureapi.innov.co.in/mobile/api/v1/schedulevisit/list?actual_visit_date=&status= |  |  |  | BY end of week | BY end of this week
|  | Show product name |  | Fixed | Shalu | https://prnt.sc/tjghxw
|  | Remove Contract no (CPP), Program Name: | Its external claim number not contract number. | NA | Shalu | https://prnt.sc/tjghxw
|  | Remove 3 digit case id | QA | Fixed | Shalu | https://prnt.sc/tjghxw
|  | Show inofromation symbole (i), on hover complete customer address will get displayed |  | On Hold | Later
|  | Sequencing should be ascending order (show first Previous date visits, then current then future visits) |  | Fixed | Ajay | https://prnt.sc/tjgggi |  |  | Done | NA
|  | Add Search By Claim No- Engg can search cases whether its a close/completed or pending |  | On Hold | Later
| Calender | Calender should show all visit date wise counter whether its completed or pending | Later | On Hold | Later
| Pending visits > detail page | On top, show Claim No, Product type along with customer details | Inspection Screen -Claim No and Product type will always show visit wise throughout screens - Rename screen title to "Inspection details" | Fixed | Shalu | https://prnt.sc/tjgeqa |  |  | done | done(showing claim no and product type above on the visit status according to the discussion
|  | Contract details accordion moves to last | done | Fixed | Shalu | https://prnt.sc/tjgflz |  |  |  | done
|  | Against each accordion, show text "Please Click Here" |  | Fixed | Shalu | https://prnt.sc/tjgflzz
|  | Doc submission:Claim Form to be made non mandatory for ACKO as there is no physical CF | done | Fixed | Shalu |  |  |  |  | Done- remove astrix(according to the condition)
|  | Doc submission: Purchase Inv. to be made non mandatory for ACKO/CPP | done | Fixed | Ajay |  | Its fixed from my side whatever error is coming from backend side i am showing according to the responce message |  |  | done- remove astrix(done)
| Side Menu | Add new menu- Completed Visit - All the completed or closed visits will move to this menu from pending section |  | On Hold | Later
40 | App | Fault diagnosed | Problem diagnosed by engineer for camera - not correct | Fixed | QA |  |  | Rakesh |  | Done-QA
61 | App | Repair in 1st visit | Not able to submit if repair is completed on site in 1st visit – it gives error – Pls fill all fields even though all fields are correctly selected/filled | Fixed | QA |  |  | Rakesh |  | Done-QA
65 | App | Repair completion | If RC at in 2nd visit - App does not allow to "submit", it shows error "pls fill all fields" even though all fields are properly filled | Fixed | QA |  |  | Rakesh |  | Done-QA
38 | App | Visit pending | No difference between visit intimation and repair intimation to engineer | Fixed | Shalu/Ajay |  | Shalu needs parameter Visit_Type API Name: http://dev-reassureapi.innov.co.in/mobile/api/v1/schedulevisit/list?actual_visit_date=&status= | Rakesh |  | Duplicate
39 | App | Dashboard | No information about program name and visit status | Fixed | QA |  |  | Rakesh |  | Duplicate
12 | App | Repair visit | Repair visit details are to be filled up again | Fixed | QA |  |  | Sanish |  | Done-QA
13 | App | Case View | Engineer is unable to view a case once updated | Not Fixed | QA |  |  | Sanish |  | Done-QA
14 | App | OTP | RC OTP is not accepted by APP | Fixed | Shalu |  |  | Sanish
10 | App | Engineer profile | user details are not matching with portal details | Fixed | QA |  |  | Sanish |  | Done-QA
11 | App | Repair Summary: For inspection visit Repair summary should display, Status, Reschedule Reason , Vist Schedule date , actual date. |  | New | Ajay sir | https://prnt.sc/tjgj0r https://prnt.sc/tjgjma
12 | App | Mobile App -Repair Visit-Repair Summary is showing duplicate history. |  | New | Ajay sir
13 | App | App is getting crash on uploading oversized file. |  | New | Shalu
14 | App | After submitting valid OTP to customer confirm. there should be a confirmation message that customer have confirmed successfully and if user clicks on OK button on validation message user should get navigate to dashboard. But currently success msg is coming as a toast and OK button is appearing along with the OTP submission field and button. |  | New | Shalu | https://prnt.sc/tk2ta5
15 | App | Dev Instance case id 605 Received three sms for repair complete and three for OTP |  | New | Ajay sir
16 | App | Case ID 609 Dev instance Repair is not getting submitted. |  | Fixed | Shalu/Ajay

## SFDC
S. No | Main Header | Sub-Header | Observation | Case No. | Slide no | Tested By | MOM -17/7/20
8 | SFDC | Status not changed | Case status on portal is changed but same not update on SFDC - 16665898, 16665899 |  |  | Sagar Mali | SFDC side issue
17 | Acko - SFDC | Case | 1.No product category available on case page layout, not even hovering window | 406-5267091-7028367 |  | Shailena | TBD-SFDC & Shailena
18 | Acko - SFDC | Create Claim | Why doesn’t product category get auto populated? Allowing wrong product category for WO & SA | 406-5267091-7028370 |  | Shailena | TBD-SFDC & Shailena
19 | Acko - SFDC | WO- Service A/C - Servicer A/C | Takes too long for the drop down to open |  |  | Shailena | TBD-SFDC & Shailena
30 | SFDC | Repairer Email | Time Slot selection on SFDC ? Repairer email say 10am-8pm , this should be actual time slot selected by CSR | 406-5267091-7028370 |  | Shailena | TBD-SFDC & Shailena
36 | SFDC/Reassure | Create Claim | SFDC allows to select wrong product category and relevant fault diagnosis, due to which probably the correct product picklists not getting populated, when the fault category is changed in SFDC, the same info is not getting populated in Reassure, so the case is stuck now, cant proceed further. | 406-5267091-7028370 |  | Shailena | TBD-SFDC & Shailena
37 | Web Portal | Repairer Profile Case Status Update Cancelled | If case cancelled by repairer, SFDC Case status is getting changed to Closed - Rejected, here SA should get cancelled NOT the case. SA still appears as Scheduled. According to this flow , we are giving our system control to the repairer for rejection | 406-5267091-7028370 |  | Shailena | TBD-SFDC & Shailena
86 | Web Portal | Saleforce | Visit completed but SFDC shows Visit assigned - No sync between Re-Assure and SFDC |  | 2 | Rakesh Padate | Spring CM issue
95 | web portal | RC - CC stage | RC – CC done by CSR but Generate invoice not activated |  | 3 | Rakesh Padate | Reassure issue
102 | SFDC | WOLI | In Re-Assure its service charge But in Salesforce its reflecting as Part |  | 4 | Rakesh Padate | TBD-SFDC & rakesh
103 | SFDC | Estimate approved | Case Number: 16665910 - Approved value is less than requested value i.e, 2242 but saleforce shows the same Requested value as Approved value i.e., 2360 |  | 5 | Rakesh Padate | Reassure issue
44 | Web Portal | Estimation | When we change the appointment date, it is not reflecting in SFDC |  | 6 | Rakesh | Before inspection step, reassure will call API
42 | SFDC | Spring CM - docs | Not able to submit if repair is completed on site in 1st visit – it gives error – Pls fill all fields even though all fields are correctly selected/filled |  | 7 | Rakesh | Reassure issue
61 | SFDC | Repair in 1st visit | Requested value is not reflecting in SFDC, estimated value shows “0” |  | 8 | Rakesh | SFDC will test on this case
59 | SMS | Customer SMS for repair visit | Post est approval amount started reflecting in SF but requested amount is still blank |  | 9 | rakesh | SFDC will test on this case
64 | SFDC | Customer SMS for repair visit | Estimate rejection is internal, SMS received by customer about estimate rejection and repudiation is not as per process |  | 10 | rakesh | Reassure side
27 | SFDC | WOLI | No SMS at any point during claims process |  |  | rakesh
| Web Portal | Add inspection | Inspection result field needs to be added for ACKO in the inspection section |  |  | Radha | discussed- same point as adding defect type feild in inspection & estimation submission
| Web Portal |  | SMS communication for inhome product |  |  |  | TBD- shailena
SFDC => Reassure
|  | Client | SFDC <= Reassure
|  | Client | SFDC
|  |  | 1 | yes
|  |  | 2 | yes
3

## clarity required
Shailena/Rakesh
|  |  |  | Status | Sub status | Observation | Customer status | customer status text | SMS text-ACKO | SMS text-CPP
Header | Sub Header | Observation | MOM -17/7/20 | Estimate Approval | Rejected with Service fee | Repair will not done, It will go next level for Invoice process. | Repudiation | you will recieve detailed repudiation letter shortly | Estimate Rejection:We sincerely regret to inform you, that your estimate is not approved for repairs. You can expect a detailed repudition email from us soon.Check <bitly link> for real-time repair status. | Estimate Rejection:We sincerely regret to inform you, that your estimate is not approved for repairs. You can expect a detailed repudition email from us soon.Check <bitly link> for real-time repair status.
Web Portal | Estimation Approval | New Status - Rejected with Payment / Rejected without Payment | Status updated in "Complete requirement doc" | Estimate Approval | Rejected without Service fee | - It will close in this stage - Repudiation wil select and auto mail will trigger(This is just a thought process, will discuss on later stage) | Repudiation | you will recieve detailed repudiation letter shortly | Estimate Rejection:We sincerely regret to inform you, that your estimate is not approved for repairs. You can expect a detailed repudition email from us soon.Check <bitly link> for real-time repair status. | Estimate Rejection:We sincerely regret to inform you, that your estimate is not approved for repairs. You can expect a detailed repudition email from us soon.Check <bitly link> for real-time repair status.
Web Portal | Create User | Repairer can create a new user as "3rd party service provider" - | Add this value in picklist for identification will also help in MIS report
Uttam
Header | Sub Header | Observation | MOM -17/7/20
Web Portal | Estimate page | Should not allow both IGST & CGST+SGST in single claim/for same repairer | Other than maharashtra we will use IGST -rename SGST to SGST/UTGST
Web Portal | Estimate page | At times GST should be zero if work is getting done through Authorized ASC, repairer can put "0" GST % | assurant team will discuss this on later