## HomePage
Project Name:-Renault EW
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 04.11.2020 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok
Version: - |  |  |  | Module:- |  | Home Page
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
HomePage_TC1 | 12889 | 2020-11-04 | Verify if a Dealer will be able to login with a valid username and valid password. | dealer logged into the system | 1)Enert URL 2)Type user name and pwd 3)hit on Sign in button | URL-https://renaultew.innov.co.in/index.php 2)User name-AGJA-Agra 3)Pwd-Welcome@123 |  | as expected | Dealer should be able to login and home page displays |  |  | pass
HomePage_TC2 | 12889 | 2020-11-04 | Verify "Home" Functionality | dealer logged into the system |  |  |  | as expected | home page should be clickable and displays with all the links as per the requirement |  |  | pass
HomePage_TC3 | 12889 | 2020-11-04 | Verify all the Modules on the Home page are Clickable and redirect to the next page | Dealer in on home page |  |  |  | as expected | all the modules refelect on home page |  |  | pass
HomePage_TC4 | 12889 | 2020-11-04 | To Verify Refresh button for all the sections | Dealer in on home page |  |  |  | as expected | button should be clickable and refresh the section |  |  | pass
HomePage_TC5 | 12889 | 2020-11-04 | Verify "All Easy Care SALES Lists" |  |  |  |  | as expected | should move to the next page of "Add Easy Care" |  |  | pass
HomePage_TC6 | 12889 | 2020-11-04 | verify +Add Easy Care Functionality | Dealer is on agreement page |  |  |  | as expected | should be clickable and move to the next page and ask to validate Vehicle Chasis No for creating new agreement |  |  | pass
HomePage_TC7 | 12889 | 2020-11-04 | to verify if browser back button | Dealer is on Validation page |  |  |  | as expected | should be clickable and back to agreement page |  |  | pass
HomePage_TC8 | 12889 | 2020-11-04 | verify Filter functionality | Dealer is on agreement page |  |  |  | as expected | The dealer should be able to filter results using all parameters on the page. |  |  | pass
HomePage_TC9 | 12889 | 2020-11-04 | to verify by clicking on Create new filter | Dealer is on agreement page |  |  |  | as expected | should open creating new view page |  |  | pass
HomePage_TC10 | 12889 | 2020-11-04 | to verify Creating new View page | Dealer is on Creating new view page |  |  |  | as expected | dealer should not be able to create new filter |  |  | pass
HomePage_TC11 | 12889 | 2020-11-04 | Verify that the Drop down is Clickable or Not | Dealer is on agreement page |  |  |  | as expected | dropdown should be clickable and when Click on drop down then the Dropdown list should be Showing . |  |  | pass
HomePage_TC12 | 12889 | 2020-11-04 | to verify without selecting any category on drop down |  |  |  |  | as expected | Check that the default item(ALL Easy Care SALES List[Test]) is getting displayed on drop down when the user first visits the page. |  |  | pass
HomePage_TC13 | 12889 | 2020-11-04 | verify that the selected category on drop down list. | Dealer is on agreement page |  |  |  | as expected | verify that the selected category on drop down list is getting highlighted on selecting the item. |  |  | pass

## Agreement
Project Name:-Renault EW
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 04.11.2020 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok sriwashtava
Version: - |  |  |  | Module:- |  | Agreement
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
Agreement_TC_1 | 12889 | 2020-11-04 | To verify by clicking on agreement | dealer is already logged |  |  |  | as expected | agreement page should displays |  |  | pass
Agreement_TC_2 | 12889 | 2020-11-04 | To verify agreement page | dealer is already logged | click on agreement module |  |  | as expected | should display the users detail with proper |  |  | pass
Agreement_TC_3 | 12889 | 2020-11-04 | To Verify Refresh button for all the sections | Dealer in on home page |  |  |  | as expected | button should be clickable and refresh the section |  |  | pass
Agreement_TC_4 | 12889 | 2020-11-04 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Agreement link under menu item. 2)Click on Add agreement button. |  |  | as expected | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button) |  |  | pass
Agreement_TC_5 | 12889 | 2020-11-04 | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. | NA |  | as expected | System should display a validation message as "Vehicle Chassis No. is required." |  |  | pass
Agreement_TC_6 | 12889 | 2020-11-04 | To verify if the user is able to validate Vehicle Chassis No. by entering invalid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)@@@@######12345 2)01A8A369B45QWERTY 3)ABCD8KGH7JH123456 4)Blank spaces |  | as expected | Chassis no. not avaliable msg. should be displayed |  |  | pass
Agreement_TC_7 | 12889 | 2020-11-04 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)MEEBBA001H8520050 |  | as expected | It should get validate successfully and Check list page open with Submit button and and Cancel button. |  |  | pass
Agreement_TC_8 | 12889 | 2020-11-04 | Check List page To Verify Check list Page | User is on Check list page | 1)Enter valid data in Chassis No. 2)Click on Validate button. |  |  | as expected | Page should contain with all the fields with cancel nad submit button as per the requirement |  |  | pass
Agreement_TC_9 | 12889 | 2020-11-04 | Check List page-To verify if the details coming from the server is freezed/non editable or not. | User is on Check list page |  |  |  | as expected | Details coming from the server should be non editable. |  |  | pass
Agreement_TC_10 | 12889 | 2020-11-04 | To Verify Check List Page- clicking on submit button by leaving all the mandatory fields | User is on Check list page | 1)click on Submit |  |  | as expected | Dealer should not be able move to the next page for creating new agreement and valiadation massage should appear with "Please enter current odometer reading" with ok button. |  |  | pass
Agreement_TC_11 | 12889 | 2020-11-04 | To verify Check List page- click on submit button with Entering Current Odometer Reading and leave remaining fields | User is on Check list page |  | Current odometer reading=1000 |  | as expected | ahould accept the current odometer reading but should not allow to create new agreement and validation message should apear with "Please select your first free service option" |  |  | pass
Agreement_TC_12 | 12889 | 2020-11-04 | To verify Check List page- Select on radio button yes for 1st free service and click on submit. | User is on Check list page |  | KMS= 500 Date=2/12/2017 |  | as expected | Should not allow to move to the next page to create new agreement, validation message should apear with "Please select your Second free service option" with ok button |  |  | pass
Agreement_TC_13 | 12889 | 2020-11-04 | To verify Check List page- Select on radio button yes for 2nd free service and click on submit. | User is on Check list page |  | KMS= 400 Date=2/11/2017 |  | as expected | Should not allow to move to the next page to create new agreement, validation message should apear with "Please select your third free service option" with ok button |  |  | pass
Agreement_TC_14 | 12889 | 2020-11-04 | To verify Check List page- Select on radio button yes for 3rd free service date less than second date and click on submit. | User is on Check list page |  | KMS= 600 Date=2/10/2017 |  | as expected | Validation message appear with "Third service date can not be less than Second Service Date" |  |  | pass
Agreement_TC_15 | 12889 | 2020-11-04 | To verify Check List page- Select on radio button yes for 3rd free service and click on submit. | User is on Check list page |  | kms=400 Date=29/12/2017 |  | as expected | should not allow to go to next page for creating new agreement and validation msg will appear with "Please select your pms_30k option" |  |  | pass
Agreement_TC_16 | 12889 | 2020-11-04 | To verify Check List page-Select no for 30K PMS and click on Submit button by leaving remaing fields | User is on Check list page |  |  |  | as expected | should not allow to go to next page for creating new agreement and validation msg will appear with "Accidental Impact Minor " |  |  | pass
Agreement_TC_17 | 12889 | 2020-11-04 | To verify Check List page-Select no for Accidental impact minor and click on Submit button by leaving remaing fields | User is on Check list page |  |  |  | as expected | should not allow to go to next page for creating new agreement and validation msg will appear with "Accidental Impact Major " |  |  | pass
Agreement_TC_18 | 12889 | 2020-11-04 | To verify Check List page-Select no for Accidental impact major and click on Submit button by leaving remaing fields | User is on Check list page |  |  |  | as expected | should not allow to go to next page for creating new agreement and validation msg will appear with "Pre-Existing Concern " |  |  | pass
Agreement_TC_19 | 12889 | 2020-11-04 | To verify Check List page-Select no for Pre-Existing Concern and click on Submit button by leaving remaing fields | User is on Check list page |  |  |  | as expected | should not allow to go to next page for creating new agreement and validation msg will appear with "Please upload Vehicle History " |  |  | pass
Agreement_TC_20 | 12889 | 2020-11-04 | To verify Check List page-Select file for Vehicle and click on Submit button by leaving remaing fields | User is on Check list page |  |  |  | as expected | should not allow to go to next page for creating new agreement. |  |  | pass
Agreement_TC_21 | 12889 | 2020-11-04 | To Verify Check List page- enter valid details in all the field and click on submit button. | Dealer is on Creating New Agreement page |  |  |  | as expected | sholud allow to create new agreement, and validation msg will appear in pop-up "Based on your inputs, It is found that all the regular PMS is carried out as RIPL recommendation, Hence the vehicle is eligible for R-secure ATW Plan.Please Note: In case during service request adjudication, if the vehicle is not maintained as per RIPL – PMS schedule & any major accidental impact/repair found, then no service request will be admitted under R-Secure ATW period." |  |  | pass
Agreement_TC_22 | 12889 | 2020-11-04 | to verify if all the mandatory fields marked with asterisk(*) | Dealer is on Creating New Agreement page |  |  |  | as expected | all the mandatory gields should have with asterisk(*). |  |  | pass
Agreement_TC_23 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | pass
Agreement_TC_24 | 12889 | 2020-11-04 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)MEEBBA001H8520050 |  | as expected | It should get validate successfully and a pop-up of Easy Care Agreement details should get appear with OK & Cancel button. |  |  | pass
Agreement_TC_25 | 12889 | 2020-11-04 | To verify if the Cancel button on Agreement details pop-up is working or not. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on Cancel button. |  |  | as expected | Process should get aborted. |  |  | pass
Agreement_TC_26 | 12889 | 2020-11-04 | To verify if the User is able to get navigate to the Add Agreement page. | User is already logged in | 1)Click on the Agreement button from the menu section. 2)Click on Add Agreement button. |  |  | as expected | Creating New agreement page should get open having Agreement related fields and Save and Cancel button. |  |  | pass
Agreement_TC_27 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving all the mandatory fields blank. | User is already logged in and is on Agreement page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  | as expected | User should not be able to create a new Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Agreement_TC_28 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | pass
Agreement_TC_29 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | pass
Agreement_TC_30 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required." |  |  | pass
Agreement_TC_31 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." |  |  | pass
Agreement_TC_32 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | pass
Agreement_TC_33 | 12889 | 2020-11-04 | To verify if the User is able to create new Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required." |  |  | pass
Agreement_TC_34 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for city field as "City is required." |  |  | pass
Agreement_TC_35 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | pass
Agreement_TC_36 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving State field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave State field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for State field as "State is required." |  |  | pass
Agreement_TC_37 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required." |  |  | pass
Agreement_TC_38 | 12889 | 2020-11-04 | To verify if the User is able to create new Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | pass
Agreement_TC_39 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Executive Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Executive Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Executive Name field as "Executive Name is required." |  |  | pass
Agreement_TC_40 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Sales Manager Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Sales Manager Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Sales Manager Name field as "Sales Manager Name is required." |  |  | pass
Agreement_TC_41 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Registration No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Registration No field as " Registration No is required." |  |  | pass
Agreement_TC_42 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required." |  |  | pass
Agreement_TC_43 | 12889 | 2020-11-04 | To very by not selecting ok for All PMS Done? And enter valid details in the remaining fields | User is already logged in and is on New Agreement page. | 1)Leave ALL PMS Done? 2) Enter valid detalis in the remianing fields. 3)Click On Save Button |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Odometer Reading field as "All PMS Done is required." |  |  | pass
Agreement_TC_44 | 12889 | 2020-11-04 | to verify if the Dealer is able to create new agreement by not selecting Select Extended Warranty and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1)Leave Select Extended Warranty filed 2) Enter valid detalis in the remianing fields. 3)Click On Save Button |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Odometer Reading field as " Select Extended Warranty is required." |  |  | pass
Agreement_TC_45 | 12889 | 2020-11-04 | to verify by entering valid data in all the fields | User is already logged in and is on New Agreement page. | 1)enter valid data in all the fields 2) click on save button |  |  | as expected | dealer should be to create new agreement and redirect to the next page of RIP264244 |  |  | pass
Agreement_TC_46 | 12889 | 2020-11-04 | to verify Generate Agreement Certificate Functionality-to verify if the link is available | RIP264244 page | click on Generate Agreement Certificate link |  |  | as expected | link should be available |  |  | pass
Agreement_TC_47 | 12889 | 2020-11-04 | To verify Generate Agreement Certificate Functionality-to verify if the link is Clickable |  |  |  |  | as expected | link should be clickable |  |  | pass
Agreement_TC_48 | 12889 | 2020-11-04 | To verify Generate Agreement Certificate Functionality-to verify if dealer is able to download the certificate |  |  |  |  | as expected | dealer should be able to download the certificate |  |  | pass
Agreement_TC_49 | 12889 | 2020-11-04 | To verify if Dealer is able to change his/her plan |  |  |  |  | as expected | Amendment page display with Amendment and Cancel radio button, Reason field, and submit button. |  |  | pass
Agreement_TC_50 | 12889 | 2020-11-04 | Verify Amendment page - click on submit button without entering any data. |  |  |  |  | as expected | page should nt allow to amend and proper valaidation message should appear with "Please Enter the reason of Amendment update." |  |  | pass
Agreement_TC_51 | 12889 | 2020-11-04 | to verify by Selecting reason of Amendment Incorrect vehicle registration number Correction in customer name |  | 1)select Incorrect Vehicle Registration number and Correction in Customer name 2) click on submit button |  |  | as expected | Editing Agreement - RIP264244 page display |  |  | pass
Agreement_TC_52 | 12889 | 2020-11-04 | To verify if dealer is able to update the details | dealer is on Editing Agreement - RIP264244 page | 1)Change customer name and Reg number 2) click on save button | Customer name- sakshi reg number-A12345FVDFV |  | as expected | A12345FVDFV page display with Amendment Details |  |  | pass
Agreement_TC_53 | 12889 | 2020-11-04 | Verify Amendment Details |  |  |  |  | as expected | Amendment Details should show bottom of the the agreement page with |  |  | pass
Agreement_TC_54 | 12889 | 2020-11-04 | To verify if agreement is punched |  |  |  |  | Agreement punched and showing with agreement number(RIP264244 ) | Agreement should punched and visible on agreement page with agreement number. |  |  | pass
|  |  | To verify the status of the new agreement for (agreement number-RIP264244 ) | User is already logged in and is on New Agreement page. |  |  |  | status -Pending for amendment | Status field should show proper validation "Pending for amendment"
|  |  | to verify if manager is approving the Amendment | Manger is login | 1)Enter URL 2)Enter User name name amd Pwd 3) hit on login 4)Click on Agreement Module and select the same agreement number -RIP264244 |  |  | Agreement number-RIP264244 page display | Manger should accept or reject the amendment and all the data should be same as what data user has filled in all the fields.
|  |  | to verify agreement page on manger side | manager is already logged | 1)click on agreement 2) select agreement number -RIP264244 |  |  |  | manger should accept or reject the user's amendment and should display with poper all the mandatory fields with amendment details section.
|  |  | to verify Amendment Details section | manager is already logged |  |  |  | Amendment Details showing the first name, Registration no and Update Reason fields | Amendment Details section should have with proper all the update Reasons what user has changed on his/her side.
|  |  | To verify by selecting accept from dropdown | manager is already logged | select Accept from status dropdown and hit on Save button |  |  | changes has been done for FirstName, Last name and Reg No | Manager should be able to accept the changes
|  |  | To Verify the data is coming from the middleware is same as master. | manager is already logged |  |  |  |  | All the data should mached with master data
|  |  | To verfy if the Prices for customer and Basic are same as Dealer EW Report for agreement number -RIP264244 | Dealer is on agreement page | 1)go with Admin Credentials 2)Click on Report and Download Dealer EW report by selecting the parameter of date 3)and again login with user and open agreement number |  |  | prices are same as Dealer EW Report | Prices should be same as Dealer EW Report
|  |  | To verfy if the Prices for customer and Basic are same as Dealer EW Report for agreement number -RIP264101 | Dealer is on agreement page | 1)go with Admin Credentials 2)Click on Report and Download Dealer EW report by selecting the parameter of date 3)and again login with user and open agreement number |  |  | prices are same as Dealer EW Report | Prices should be same as Dealer EW Report
Agreement_TC_55 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving Last Service Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for Last Service Odometer Reading field as " Last Service Odometer Reading is required." |  |  | pass
Agreement_TC_56 | 12889 | 2020-11-04 | To verify if the User is able to create new Easy Care Agreement by leaving the REC Plan field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave REC Plan field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for REC Plan field as "REC Plan is required." |  |  | pass
Agreement_TC_57 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by leaving REC Retail field blank and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Leave REC Retail field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for REC Retail field as "REC Retail is required." |  |  | pass
Agreement_TC_58 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in First Name and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in First Name field as "Invalid First Name." |  |  | pass
Agreement_TC_59 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in Last Name and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in Last Name field as "Invalid Last Name." |  |  | pass
Agreement_TC_60 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in GSTIN and enter valid details in the remaining fields. (if YES selected for GSTIN Applicable) | User is already logged in and is on New Agreement page. | 1) Enter invalid data in GSTIN field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in GSTIN No. field as "Invalid GSTIN No." |  |  | pass
Agreement_TC_61 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in Mobile Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in Mobile Phone No. field as "Invalid Mobile Phone No." |  |  | pass
Agreement_TC_62 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "Invalid Primary Email No." |  |  | pass
Agreement_TC_63 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in City and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in City field as "Invalid City " |  |  | pass
Agreement_TC_64 | 12889 | 2020-11-04 | To verify if the User is able to create new Agreement by entering invalid data in Vehicle Chasis No. and enter valid details in the remaining fields. | User is already logged in and is on New Agreement page. | 1) Enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | as expected | User should not be able to create new Agreement and the system must display a proper and specific validation message for entering invalid data in Vehicle Chasis No. field as "Invalid Vehicle Chasis No. " |  |  | pass

## easy_Care_Sales
Project Name: Renault-EW
Created By:- | Sakshi Tiwari |  |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-11-06 |  |  | Review Date:-
Version: - |  |  |  | Module:- | Easy Care Sales |  | Power ID: | 12889
Test Case ID | Power_ID :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severity | Status
Easy_care_sales_TC_1 | 12889 | to Verify if all the manadatory fields are having * and auto fetch data are not editable | User is already logged in and is on Add New Easy Care Agreement page. | 1)Enter Url 2)Enter Admin and pwd 3)click on Easy Care Sales click on Add Easy care Sales Enter VIN number | Vin Number:MEEBBA006G8403694 | non Editable |  | all the mandatory Fields should have * and Autofetch data should not be editable |  |  | pass
Easy_care_sales_TC_2 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving all the mandatory fields blank. | User is already logged in and is on Add New Easy Care Agreement page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  | As expected |  | User should not be able to create a new Easy Care Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass
Easy_care_sales_TC_3 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | pass
Easy_care_sales_TC_4 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | pass
Easy_care_sales_TC_5 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required." |  |  | pass
Easy_care_sales_TC_6 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." |  |  | pass
Easy_care_sales_TC_7 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | pass
Easy_care_sales_TC_8 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required." |  |  | pass
Easy_care_sales_TC_9 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | As expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for city field as "City is required." |  |  | pass
Easy_care_sales_TC_10 | 12889 | To verify if the Vehicle Chasis No not be editable | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Vehicle Chasis No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Vehicle Chasis No is autofetched and not editable |  | Vehicle Chasis No should not be editable |  |  | pass
Easy_care_sales_TC_11 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | pass
Easy_care_sales_TC_12 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required." |  |  | pass
Easy_care_sales_TC_13 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | pass
Easy_care_sales_TC_14 | 12889 | to verify by not selecting Does Vehicle belongs to Fleet field | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  |  |  |  | pass
Easy_care_sales_TC_15 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message Please select Fleet status for Odometer Reading. |  |  | pass
Easy_care_sales_TC_16 | 12889 | To verify if the User is able to create new Easy Care Agreement by selecting YES from Does Vehicle belongs to Fleet dropDown | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | as expected |  | pop up with valiadtion message reset amc plan with ok button |  |  | pass
Easy_care_sales_TC_17 | 12889 | To verify if the User is able to create new Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | enter valid details in the remaining fields. | 1) Select Yes from Does Vehicle belongs to fleet dropdown and enter valid data in odometer reading 2)Enter valid details in the remianing fields. 3)Click On Save Button. | odometer Reading=6500 | as expected |  |  |  |  | pass
Easy_care_sales_TC_18 | 12889 | to verify by not selecting REC Plan and enter valid details in the remaining fields. | enter valid details in the remaining fields. |  |  | as expected |  | User should not be able to create new Easy care Agreement. |  |  | pass
Easy_care_sales_TC_19 | 12889 | Verify by selecting any REC plan | User is already logged in and is on Add New Easy Care Agreement page. |  |  | plan selected |  | user should be able select REC plan and User should be able to create new Easy Care Agreement |  |  | pass
Easy_care_sales_TC_20 | 12889 | Verify by selecting any REC plan for 357/REC-KWID AMT-P357-2Y-20K | User is already logged in and is on Add New Easy Care Agreement page. | Filled all the mandattory fields and Select REC plan 357/REC-KWID AMT-P357-2Y-20K | vin number=MEEBBA006G8403694 | As expected |  | user should be able select REC plan and User should be able to create new Easy Care Agreement |  |  | pass
Easy_care_sales_TC_21 | 12889 | To verify if REC Start Period | User is already logged in and is on Add New Easy Care Agreement page. | check the REC Start Period |  | date is correct date same as on punching date |  | REC Start Period date should be shown on the punching date |  |  | pass
Easy_care_sales_TC_22 | 12889 | To verify REC Plan Details if data is comimg from the middleware is not editable | User is already logged in and is on Add New Easy Care Agreement page. | observe the data coming from the middleware. |  | data is non-editable |  | data should not be editable for REC Plan Details section |  |  | pass
Easy_care_sales_TC_23 | 12889 | To verify Rec plan Details Section if All the details is same as middleWare | User is already logged in and is on Add New Easy Care Agreement page. | observe the data coming from the middleware. |  | As expected |  | should be same as middileware |  |  | pass
Easy_care_sales_TC_24 | 12889 | To verify if Agreement is punched with Agreement number | User is already logged in and is on New Easy Care Agreement page. | Click on Easy Care Sales |  | As expected |  | should be refelect with agreement number |  |  | pass
Easy_care_sales_TC_25 | 12889 | To verify if user is able to generate His/or her certificate | user is on Agreement Page | Click on Generate Agreement Certificate |  | Amc sales Report downloaded |  | AMC Sales report should be generated in pdf file |  |  | pass
Easy_care_sales_TC_26 | 12889 | AMENDMENT:To verify if the User is able to Amend his/her | user is on Agreement Page | Click on Amendment Button |  | As expected |  | Should be able change his/her plan |  |  | pass
Easy_care_sales_TC_27 | 12889 | AMENDMENT:To verify if the User is able to Amend his/her plan after 15 days of punching | user is on Agreement Page | Click on Amendment Button |  | As expected |  | Agreement Page should open with Validation message "the Agreement can not amended as 15 days have elapsed .No amendment can be done after 15 day of Agreement Creation" |  |  | pass
Easy_care_sales_TC_28 | 12889 |  |  |  |  | As expected |  |  |  |  | pass
Easy_care_sales_TC_29 | 12889 | Vin Validation:To Verify if user is able to punch new agreement | User is logged into the System | 1)Enter Url 2)Enter Admin and pwd 3)click on Easy Care Sales click on Add Easy care Sales Enter VIN number to validate | 1)http://13.127.10.134/renaultnew_dev/index.php?module=ProjectTask&view=Edit 2)UserName=BHJA-Bhopal an pwd=Welcome@003 vin number=MEEBBA003K7679412 | As expected |  | Nin number should validate and all the mandatory Fields should have * and Autofetched data should not be editable |  |  | pass
Easy_care_sales_TC_30 | 12889 | To verify by entering less than Last Service Odometer Reading in current Odometer Reading field | on agreement page | Enter invalid odometer reading | current Odometer Reading = 2000 | As expected |  | User should not be able to create a new Easy Care Agreement and the system must display a proper and specific validation message "Current Odometer can not less than Last Service Odometer Reading" |  |  | pass
Easy_care_sales_TC_31 | 12889 | To verify by entering more than Last Service Odometer Reading in current Odometer Reading field | on agreement page |  | current Odometer Reading = 4000 | As expected |  | System must display a proper and specific validation message "Ensure Odometer reading entered by you is correct" and user should |  |  | pass
Easy_care_sales_TC_32 | 12889 | Last PMS Done DropDown: To Verify if Dorop-Down is clickable or Not and scrolled down by clicking down arrow then the drop down list showing or not. | on agreement page |  |  | As expected |  | user should be clickable and drop-down scrolled down on clicking the down arrow |  |  | pass
Easy_care_sales_TC_33 | 12889 | To verify by selecting NO PMS from Dropdown List for Last PMS Done | on agreement page |  |  | As expected |  | NO PMS should be select from last PMS done Down |  |  | pass
Easy_care_sales_TC_34 | 12889 | Prices:TO Verify if parices are same as Master by selecting REC plan for 328/REC-KWID-P328-3Y-30K | User is already logged in and is on Add New Easy Care Agreement page. | Filled all the mandattory fields and Select REC plan 324/REC-KWID-P324-2Y-20K | vin number=MEEBBA006G3347401 | As expected |  | customer price and basic price for the selected plan should be same as REC master. |  |  | pass
Easy_care_sales_TC_35 | 12889 | Verify by selecting any REC plan for 329/REC-KWID-P329-4Y-40K |  |  |  | As expected |  | customer price and basic price for the selected plan should be same as REC master. |  |  | pass
Easy_care_sales_TC_36 | 12889 | Prices:TO Verify parices should be same as Master by selecting REC plan for 329/REC-KWID-P329-4Y-40K | User is already logged in and is on Add New Easy Care Agreement page. | Filled all the mandattory fields and Select REC plan 329/REC-KWID-P329-4Y-40K |  | As expected |  | customer price and basic price for the selected plan should be same as REC master. |  |  | pass
Easy_care_sales_TC_37 | 12889 | To verify if Dealer is able to change his/her plan |  |  |  | As expected | as expected | Amendment page display with Amendment and Cancel radio button, Reason field, and submit button. |  |  | pass
Easy_care_sales_TC_38 | 12889 | Verify Amendment page - click on submit button without entering any data. |  |  |  | As expected | as expected | page should nt allow to amend and proper valaidation message should appear with "Please Enter the reason of Amendment update." |  |  | pass
Easy_care_sales_TC_39 | 12889 | to verify by Selecting reason of Amendment Incorrect vehicle registration number Correction in customer name |  | 1)select Incorrect Vehicle Registration number and Correction in Customer name 2) click on submit button |  | As expected | as expected | Editing Agreement - REC12461 page display |  |  | pass
Easy_care_sales_TC_40 | 12889 | To verify if dealer is able to update the details | dealer is on Editing Easy Care- REC12461page | 1)Change customer name and Reg number 2) click on save button | Customer name- rimmy to sak reg number-1234567 to abc1234567 | As expected | as expected | REC12461page display with Amendment Details and details should be changed |  |  | pass
Easy_care_sales_TC_41 | 12889 | Verify Amendment Details | dealer is on Editing Easy Care- REC12461page |  |  | As expected | as expected | Amendment Details should show bottom of the the new easy care sales agreement page with |  |  | pass
Easy_care_sales_TC_42 | 12889 | To verify if agreement is punched | dealer is on Editing Easy Care- REC12461page |  |  | As expected | easy care punched and showing with agreement number(REC12461page ) | Easy care sales should punched and visible on agreement page with Easy care number. |  |  | pass
Easy_care_sales_TC_43 | 12889 | To verify the AMC status of the new agreement for (Easy care-REC12461 ) | User is already logged in and is on Editing Easy care Sales page . |  |  | As expected | status -Pending for amendment | AMC Status field should show proper validation "Pending for amendment" |  |  | pass
Easy_care_sales_TC_44 | 12889 | to verify if manager is approving the Amendment | Manger is login | 1)Enter URL 2)Enter User name name amd Pwd 3) hit on login 4)Click on Easy Care Sales Module and select -agreement number-REC12461 | 1)https://renaultew.innov.co.in/index.php?module=ProjectTask&view=Detail&record=3031964 2)usre name=S00074-Anshu 3)Pwd-Welcome@123 | As expected | Agreement number--REC12461 page display | Manger should accept or reject the amendment and all the data should be same as what data user has filled in all the fields. |  |  | pass
Easy_care_sales_TC_45 | 12889 | to verify AMC agreement page on manger side | manager is already logged | 1)click on Easy Care sales 2) select agreement number --REC12461 |  | As expected | Agreement number--REC12461 page display | manger should accept or reject the user's amendment and should display with poper all the mandatory fields with amendment details section. |  |  | pass
Easy_care_sales_TC_46 | 12889 | to verify AMC Amendment Details section | manager is already logged |  |  | As expected | Amendment Details showing the first name, Registration no and Update Reason fields | Amendment Details section should have with proper all the update Reasons what user has changed on his/her side. |  |  | pass
Easy_care_sales_TC_47 | 12889 | To verify by selecting accept from dropdown | manager is already logged | select Accept from status dropdown and hit on Save button |  | As expected | changes has been done for FirstName, Last name and Reg No | Manager should be able to accept the changes |  |  | pass
Easy_care_sales_TC_48 | 12889 | To verify if the AMC status has been changed or not | manager is already logged |  |  | As expected | AMC Status-Active | AMC Status should be changed from "Pending for amendment" to "Active" |  |  | pass
Easy_care_sales_TC_49 | 12889 | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Easy Care Sales link under menu item. 2)Click on Add easy care button. |  |  |  | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button)
Easy_care_sales_TC_50 | 12889 | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. | NA |  |  | System should display a validation message as "Vehicle Chassis No. is required."
Easy_care_sales_TC_51 | 12889 | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)MEEBBA007L2716167 |  |  | It should get validate successfully and a pop-up of Easy Care Agreement details should get appear with OK & Cancel button.
Easy_care_sales_TC_52 | 12889 | To verify if the User is able to create new Easy Care Agreement by entering valid data in all the mandatory fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Last PMS Done field has two times of 10K PMS |  | New Easy Care Agreement should get created followwing a confirmation message as "Easy Care Agreement Successfully Added." |  |  | Fail

## Courier_Details_update(Claim)
Project Name:-Renault EW
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 05.11.2020 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok
Version: - |  |  |  | Module:- |  | Courier Details Update(Claim)
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Courier Details_01 | 12889 | 2020-11-05 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button without selecting any claim number. | NA | User was not get redirect to the Courier Details Update page and also there was a proper validation message for the same. |  | User should not get redirect to the Courier Details Update page and also there should be a proper validation message for the same. |  |  | Pass
TC_Courier Details_02 | 12889 | 2020-11-05 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number having status other than approved. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button by selecting any claim which is not approved. | NA | There was a proper validation message as "Claim is not approved." |  | there should be a proper validation message as "Claim is not approved." |  |  | Pass
TC_Courier Details_03 | 12889 | 2020-11-05 | To verify if the user is able to get navigate to the "courier details update" by selecting Claim Number. for which the courier details to be update. | User is already logged in and is on Add Claim page. | 1)Select the Claim Number no. for which thee courier details to be update. 2)Click on the Courier Details Update button. |  | User redirected to the concerned page with all the fields and buttons. |  | User should get redirect to the Courier Details Update page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) |  | Pass | Pass
TC_Courier Details_04 | 12889 | 2020-11-05 | To verify if the user is able to update courier details by leaving all the mandatory fields blank. | User is on the "courier details update" page. | 1)Click on the Save buton without entering any data in mandatory fields. | NA | System shows a validation message as "Please Enter Document Courier Date." but the message can revised to " All the mandatory fields marked with * are required so as to make it more appropriate and complete. |  | Courier details should not get update and system should display a proper validation message for leaving all the fields blank. |  |  | Pass
TC_Courier Details_05 | 12889 | 2020-11-05 | To verify if the user is able to update courier details by leaving "Document Send" field unchecked. | User is on the "courier details update" page. | 1)Leave the Document Send checkbox unchecked and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message(Please Select Dealer Document Sent ..) for leaving the Document Send field blank. |  |  | Pass
TC_Courier Details_06 | 12889 | 2020-11-05 | To verify if the user is able to update courier details by leaving the Document Courier Date field blank. | User is on the "courier details update" page. | 1)Leave the Document Courier Date field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message (Please Enter Document Courier Date.)for leaving the Document Courier Date field blank. |  |  | Pass
TC_Courier Details_07 | 12889 | 2020-11-05 | To verify if the user is able to update courier details by leaving the POD Number field blank. | User is on the "courier details update" page. | 1)Leave the POD Number field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the POD Number field blank. |  |  | Pass
TC_Courier Details_08 | 12889 | 2020-11-05 | To verify if the user is able to update courier details by leaving the Courier Company Name field blank. | User is on the "courier details update" page. | 1)Leave the Courier Company Name field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for (Please Enter Courier Company Name.)leaving the Courier Company Name field blank. |  |  | Pass
TC_Courier Details_09 | 12889 | 2020-11-05 | to verify if user is able to Update Courier details by entering valid data in all the fields | User is on the "courier details update" page. | 1)select Document Send 2)select Document Courier Date 3)Enter POD Number 4)Enter Courier Company Name 5) click on save button | 1) date-2020/11/11 2)pod number-123455 3)Courier Company Name-DTDC |  |  | Courier deatails should get update and system should display a proper validation message "Record has been Successfully Submitted....." |  |  | Pass
TC_Courier Details_10 | 12889 | 2020-11-05 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is on the "courier details update" page. | 1)Click on Cancel Button. | NA |  |  | The page should get close. |  |  | Pass
TC_Courier Details_11 | 12889 | 2020-11-05 | To verify claim Details page | user is on the Claim Details page | 1)Click on the claim no |  |  |  | Status sholud change from approved to Post Approval Documents Sent |  |  | Pass
TC_Courier Details_12 | 12889 | 2020-11-05 | to verify Physical Document Tracking | user is on the Claim Details page | 1)Click on the claim no |  |  |  | updatde data should be visible on Physical Document Tracking
TC_Courier Details_13 | 12889 | 2020-11-05 | To verify Document Received by Assurant | user logged with manager credentials | 1)Enter url 2)Enter valid user name and pwd 2)click on Claim 3)click on courier details update | 1)URL-https://renaultew.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=2900403 2)userName-S00074-Anshu 3)pwd-Welcome@123 |  |  | should display Document Tracking Panel page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) 7) Document Received*(Checkbox) 8)Document Received Date.*(yyyy-mm-dd).(field)
TC_Courier Details_14 | 12889 | 2020-11-05 | to verify Document Tracking Pannel page without selecting Document Received checkbox | user logged on Document Tracking Panel Page with manager credentials | 1)leave the Document Received box and enter the valid data in all the remaining fields 2)click on save |  |  |  | should ask for selecting for Document Received checkbox with proper validation msg "Please Select Document Received"
TC_Courier Details_15 | 12889 | 2020-11-05 | to verify if record has been uploaded successfully for claim number with entering with valid data in all the fields | user logged on Document Tracking Panel Page with manager credentials | select date for Document Received Date. And click on save button | Document Received Date-2020-11-19 |  |  | Record should be Successfully Submit and proper validation message should appear " Record has been Successfully Submitted....."
TC_Courier Details_16 | 12889 | 2020-11-05 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on Add Claim page. | 1)Click on Cancel Button. | NA |  |  | The page should get close.

## Courier_Deatils_Update(AMC)
Project Name:-Renault EW
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 06.11.2020 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok
Version: - |  |  |  | Module:- |  | Courier Details Update(AMC)
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Courier Details_01 | 12889 | 06.11.2020 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button without selecting any claim number. | NA | User was not get redirect to the Courier Details Update page and also there was a proper validation message for the same. |  | User should not get redirect to the Courier Details Update page and also there should be a proper validation message for the same. |  |  | pass
TC_Courier Details_02 | 12889 | 06.11.2021 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number having status other than approved. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button by selecting any claim which is not approved. | NA | There was a proper validation message as "Claim is not approved." |  | there should be a proper validation message as "Claim is not approved." |  |  | pass
TC_Courier Details_03 | 12889 | 06.11.2022 | To verify if the user is able to get navigate to the "courier details update" by selecting Claim Number. for which the courier details to be update. | User is already logged in and is on Add Claim page. | 1)Select the Claim Number no. for which thee courier details to be update. 2)Click on the Courier Details Update button. |  | User redirected to the concerned page with all the fields and buttons. |  | User should get redirect to the Courier Details Update page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) |  |  | pass
TC_Courier Details_04 | 12889 | 06.11.2023 | To verify if the user is able to update courier details by leaving all the mandatory fields blank. | User is on the "courier details update" page. | 1)Click on the Save buton without entering any data in mandatory fields. | NA | System shows a validation message as "Please Enter Document Courier Date." but the message can revised to " All the mandatory fields marked with * are required so as to make it more appropriate and complete. |  | Courier details should not get update and system should display a proper validation message for leaving all the fields blank. |  |  | pass
TC_Courier Details_05 | 12889 | 06.11.2024 | To verify if the user is able to update courier details by leaving "Document Send" field unchecked. | User is on the "courier details update" page. | 1)Leave the Document Send checkbox unchecked and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message(Please Select Dealer Document Sent ..) for leaving the Document Send field blank. |  |  | pass
TC_Courier Details_06 | 12889 | 06.11.2025 | To verify if the user is able to update courier details by leaving the Document Courier Date field blank. | User is on the "courier details update" page. | 1)Leave the Document Courier Date field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message (Please Enter Document Courier Date.)for leaving the Document Courier Date field blank. |  |  | pass
TC_Courier Details_07 | 12889 | 06.11.2026 | To verify if the user is able to update courier details by leaving the POD Number field blank. | User is on the "courier details update" page. | 1)Leave the POD Number field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the POD Number field blank. |  |  | pass
TC_Courier Details_08 | 12889 | 06.11.2027 | To verify if the user is able to update courier details by leaving the Courier Company Name field blank. | User is on the "courier details update" page. | 1)Leave the Courier Company Name field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for (Please Enter Courier Company Name.)leaving the Courier Company Name field blank. |  |  | pass
TC_Courier Details_09 | 12889 | 06.11.2028 | to verify if user is able to Update Courier details by entering valid data in all the fields | User is on the "courier details update" page. | 1)select Document Send 2)select Document Courier Date 3)Enter POD Number 4)Enter Courier Company Name 5) click on save button | 1) date-2020/11/11 2)pod number-123455 3)Courier Company Name-DTDC |  |  | Courier deatails should get update and system should display a proper validation message "Record has been Successfully Submitted....." |  |  | pass
TC_Courier Details_10 | 12889 | 06.11.2029 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is on the "courier details update" page. | 1)Click on Cancel Button. | NA |  |  | The page should get close. |  |  | pass
TC_Courier Details_11 | 12889 | 06.11.2030 | To verify claim Details page | user is on the Claim Details page | 1)Click on the claim no |  |  |  | EMC Care Claim Status sholud change from approved to Post Approval Documents Sent |  |  | pass
TC_Courier Details_12 | 12889 | 06.11.2031 | to verify Physical Document Tracking | user is on the Claim Details page | 1)Click on the claim no |  |  |  | updatde data should be visible on Physical Document Tracking |  |  | pass
TC_Courier Details_13 | 12889 | 06.11.2032 | To verify Document Received by Assurant | user logged with manager credentials | 1)Enter url 2)Enter valid user name and pwd 2)click on Easy Care Claim 3)click on courier details update | 1)URL-https://renaultew.innov.co.in/index.php?module=PurchaseOrder&view=Detail&record=2900403 2)userName-S00074-Anshu 3)pwd-Welcome@123 |  |  | should display Document Tracking Panel page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) 7) Document Received*(Checkbox) 8)Document Received Date.*(yyyy-mm-dd).(field) |  |  | pass
TC_Courier Details_14 | 12889 | 06.11.2033 | to verify Document Tracking Pannel page without selecting Document Received checkbox | logged on Document Tracking Panel Page with manager credentials | 1)leave the Document Received box and enter the valid data in all the remaining fields 2)click on save |  |  |  | should ask for selecting for Document Received checkbox with proper validation msg "Please Select Document Received" |  |  | pass
TC_Courier Details_15 | 12889 | 06.11.2034 | To verify by selecting back date for Document Received Date | logged on Document Tracking Panel Page with manager credentials |  |  |  | Record has been successfully Submitted | should not accept the |  |  | pass
TC_Courier Details_16 | 12889 | 06.11.2035 | to verify if record has been uploaded successfully for claim number with entering with valid data in all the fields | user logged on Document Tracking Panel Page with manager credentials | select date for Document Received Date. And click on save button | Document Received Date-2020-11-19 |  |  | Record should be Successfully Submit and proper validation message should appear " Record has been Successfully Submitted....." |  |  | pass
TC_Courier Details_17 | 12889 | 06.11.2036 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on Add Claim page. | 1)Click on Cancel Button. | NA |  |  | The page should get close. |  |  | pass

## BugReport
Bug Report
Project :- |  | Renault EW(Easy Care Sales) | [5 empty] | Lead_Developer. :-Alok Srivastava
Created_By :- |  | Sakshi
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To
2020-11-07 | Easy_care_sales_TC_52 | Bug_1 | 12889 | Last PMS Done field has two times of 10K PMS | Dealer is on easy care agreement page | 1)Enter URL 2)Enter User name amd Pwd 3) hit on login 4)Click on Easy Care Sales Module and Click on Add Easy care 5)Enter valid vin and validate | 1)https://renaultew.innov.co.in/index.php?module=ProjectTask&view=Detail&record=3031964 2)usre name=S00074-Anshu 3)Pwd-Welcome@123 4)MEEBBA007L2716167 |  |  |  | New | alok srivastava

## Sheet3
Renault EW
Lead Dev: Alok Srivastava
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestions
Home Page | 13 | 13 | 13 | 0 | 0
Agreement | 64 | 64 | 64 | 0 | 0
Easy Care Sales | 52 | 52 | 51 | 1 | 0
Courier Details Update(Claim) | 16 | 10 | 10 | 0 | 0
Easy Care Claims | 9 | 9 | 9 | 0 | 0
Courier Details Update(AMC) | 17 | 17 | 17 | 0 | 0
Total | 77 | 71 | 70 | 1 | 0