## Summary
Testing of Volvo Eicher |  |  | Lead Dev. | Vikash Jha
Module | Login Account | No. of test Written | No. of test executed | Pass | Fail
Vin-Validation | Dealer | 12 | 12 | 10 | 2
Total |  | 12 | 12 | 10 | 2

## Bug_Report
Bug Report
Project :- |  | Volvo Eicher |  |  |  |  | Lead_Devp. :- |  | Vikash Jha
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10008
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-13 |  | Bug_ID_01 | Part Information Claim Details :- Page data reset on leaving MRP blank and Entering Quantity | User is on the Creating New Claim page. |  | Part Code :- asf Quantity :- 2 | https://drive.google.com/open?id=1McNDMvavbVYGuQ1SK3Yth9Z6ZHlFzwUS |  | Low | New | Vikash Jha
2020-02-13 |  | Bug_ID_02 | Creating New Labour Information Claim :- Page data reset on leaving Operation Time[In Minutes] blank and entering Rate. | User is on the Creating New Claim page. |  | Labour Code :- asd Rate :- 300 | https://drive.google.com/open?id=1df6Xi4taz4fhbDudEVqk9kcOjU9TPxpl |  | Low | New | Vikash Jha
2020-02-13 |  | Bug_ID_03 | Part Information Claim :- Rejection is showing (0 or 1) | User is on the Creating New Claim page. |  |  | https://drive.google.com/open?id=13ZyRfd8pFie7x1RdCwm31Y9mXUYjB-Iv |  | High | New | Vikash Jha
2020-02-13 |  | Bug_ID_04 | Unable to upload file name in PDF format of more than 2MB where max. upload size is 5MB (Uploaded Document is not Valid) msg. display | Creating New Document page |  |  | https://drive.google.com/open?id=1e94Y-vvHTBao5bDzoQPa1sAGX52qMqBY |  | High | New | Vikash Jha
2020-02-13 |  | Bug_ID_05 | Unable to upload ODO Meter Reading Photo of more than 2MB where max. upload size is 5MB (Uploaded Document is not Valid) msg. display | Creating New Document page |  |  | https://drive.google.com/open?id=1eY-opjtTu6toq8yoO8WHIFDcfxrNlekP |  | High | New | Vikash Jha
2020-02-13 |  | Bug_ID_06 | If unable to Upload document Title automatically disappear | Creating New Document page |  |  | https://drive.google.com/open?id=16yn6kYpGKY6RjqZG6iQv4MMIvmuj8402 |  | Low | New | Vikash Jha
2020-02-13 |  | Bug_ID_07 | search claim by Claim Time but it is searching Claim by Claim Date | Search Claim |  |  | https://drive.google.com/open?id=1KY96HuPX9iFKXKCmnkb6r-Jgi9v9IBvJ |  | Low | New | Vikash Jha
2020-02-13 |  | Bug_ID_08 | There is UI issue on claim view page | view claim |  |  | https://drive.google.com/open?id=1WSFxLqkat13G3EuLkTZSLx8iFEHjyXE_ |  | Low | New | Vikash Jha
2020-02-13 |  | Bug_ID_09 | There is UI issue on Status and Reason of Rejection | Edit claim on assurant account |  |  | https://drive.google.com/open?id=1so4ywIm2SKblEKfx4yvrX5UQTRaL74pP |  | Low | New | Vikash Jha
2020-02-05 |  | Bug_ID_10 | When dealer submits a Request for ​S​urveyor ​A​ppointment​ by updating the claim form when its already under Pending with Surveyor status then the status gets changed to "Answered by Dealer" instead it should remain the same. [Status should be update in Answered by Dealer-Surveyor] [DONE] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_11 | Claim Manager: There is no validation for Surveyor contact number. User can enter invalid data in Surveyor contact number. (1234 as contact no.) |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_12 | Claim Manager: User is able to change the status to Payment made without entering payment details. |  |  |  |  | High | High | Fixed | Vikash Jha | No Need to Change
2020-02-06 |  | Bug_ID_13 | New Part Information Claim: Description,Discount, Vat fields should be enable to edit/add data. |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-06 |  | Bug_ID_14 | New Part Information Claim: VAT should get change to GST (%). [Update From DB - DONE] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_15 | Claim should come in header with other main menu [add claim in menu from setting - DONE] | - | - |  | https://prnt.sc/qytajb | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_16 | highlighted fields should not be visible to dealers and this should come under Surveyor Information section [ setting from profile - DONE] |  |  |  | https://prnt.sc/qytt3r | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_17 | highlighted fields not required [DONE] [Field Inactive from setting] |  |  |  | https://prnt.sc/qytutz | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_18 | Use any of the one field from the highlighted |  |  |  | https://prnt.sc/qytvix | High | High | Fixed | Vikash Jha | No Need to Change
2020-02-07 |  | Bug_ID_19 | Length of the field - Dealer Contact No should be equal to 10 and only numeric. Space and or any other character not allowed [Update Contact From Database] |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_20 | Field "Description" should be editable |  |  |  | https://prnt.sc/qyutmb | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_21 | Field "Discount %" should be editable |  |  |  | https://prnt.sc/qyv3dm | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_22 | Vat to be removed |  |  |  | https://prnt.sc/qyv3ob | High | High | Fixed | Vikash Jha | Fixed
2020-02-07 |  | Bug_ID_23 | filed to be added in part information 1> CGST% 2> SCGS% 3> IGST% 4> CGST Amount 5> SGCT Amount 6< IGST Amount |  |  |  |  | High | High | Fixed | Vikash Jha | No Need to Change
2020-02-07 |  | Bug_ID_24 | Tota will be equal to {(price - discounted amonut) +GST} |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_25 | Creating New Claim: Agreement Number field should be "*" marked in order to represent it as a mandatory field. [CHNAGES-DONE] | User has a working system with an active internet connection. | 1) Login the portal with the correct login credentials. 2)Click on "All" dropdown. 3)Click on "Claim" option. 4)Click on "Add Claim" button. 5) Observe the Agreement Number (It is a mandatory field in order to add claim user needs to enter this) |  | https://prnt.sc/quxugo | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_26 | Creating New Claim: The priority for showing validation message should be from top to bottom. E.g: If user clicks on the Save button without entering any data in the mandatory fields then system first needs to show the validation message for Agreement Number. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave all the mandatory fields blank. 2)Click on the save button. |  |  | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_27 | Creating New Claim: User is able to submit the claim form by entering less than 7 digits Job Card Number. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1) Enter invalid data in Job Card Number (Less than 7 digits) 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  |  | Mid | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_28 | Creating New Claim: Validation message appearing for leaving the Agreement number field blank is wrong. It should be "Please Select Agreement Number First" instead of Please Select SalesOrder First [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave the Agreement number field blank. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quy5su | Low | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_29 | Creating New Claim: User is able to submit the claim form by entering Date of job card (29-01-2020) which does not lies between the Ext . Warranty Start Date(Ext . Warranty Start Date) and Ext. Warranty End Date(29-11-2023) [NEED TO DISCUSS] | User is on the Creating New Claim page. | 1) Enter invalid data in Date of Job Card. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quygby | High | High | Fixed | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_30 | Creating New Claim: The validation message coming after Re-selecting the Aggregate Part List dropdown List is non informative it can be modified to : "Please select Aggregate Part List" instead of "Agreement in OEM warranty" [NO-NEED-TO-CHANGE DISCUSS] | User is on the Creating New Claim page. | 1)Re-Select Aggregate Part List dropdown to "Select Aggregate Part" |  | https://prnt.sc/quymbw | Low | Low | Fixed | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_31 | Creating New Claim: The validation message appearing for leaving the Aggregate Part List blank is wrong. It should be "Please select Aggregate Part List" instead of JobCard Date Should be less than or equal to warranty end date. [CHNAGES-DONE] | User is on the Creating New Claim page. | 1)Leave theAggregate Part List field blank. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quyqft | Low | Low | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_32 | Claims Page: Date and time of creating a new claim is not correct. That is Its showing a lag of one day and 16 hours from the actual day and time of creation. [Update User Time-Zone in User Details] |  |  |  | https://prnt.sc/quyu4s | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_33 | Creating New Claim: The details appearing after selecting an Aggregate Part should be non-editable/freezed but few of the fields are still editable like Warranty Admin Name,Dealer Email and Dealer Contact No. [NEED TO DISCUSS] | User is on the Creating New Claim page. |  |  | https://prnt.sc/quyzbe | High | High | Fixed | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_34 | Creating New Claim: Validation message appearing for entering wrong EHS HRS-less than EW Start EHS (Engine hours) is wrong it should display "Engine hours should be between 6001 and 10000" instead of \ Agreement is in oem warranty [NEED TO DISCUSS] |  |  |  | https://prnt.sc/quz8eu | High | High | Fixed | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_35 | Creating New Claim: There should be a validation message for entering a Date of Job Card less than the Ext . Warranty Start Date as "Date of Job Card should not be less than Ext . Warranty Start Date" [NEED TO DISCUSS] | User is on the Creating New Claim page. | 1)Enter Date of Job Card less than Ext . Warranty Start Date. 2) Enter valid data in the remaining mandatory fields. 3) Click on Save button. |  | https://prnt.sc/quzbf4 | High | High | Fixed | Vikash Jha | No Need to Change
2020-01-30 |  | Bug_ID_36 | Claim details page: In the agreement/policy warranty is spacified in EW Start EHS and EW End EHS but after raising the claim its showing in Ext. Warranty Start kms and Ext. Warranty End kms. Please refer to the screenshot for more details. [CHANGES DONE] |  |  |  | https://prnt.sc/quzsjj https://prnt.sc/quztlv | High | High | Fixed | Vikash Jha | Fixed
2020-01-30 |  | Bug_ID_37 | Creating New Document: User is not able to save a new document page as the Title of the Jobcard is freezed/non editable which is a mandatory field. [NO NEED TO CHANGE] |  |  |  | https://prnt.sc/qv13o9 | High | High | Fixed | Vikash Jha | No Need to Change
2020-02-05 |  | Bug_ID_38 | Creating Part Information Claim:If user adds qauntity first and then he enters the MRP then system does not counts MRP and shows NAN in price,Discount Amount and Total |  |  |  | https://prnt.sc/qxsevh https://prnt.sc/qxsgg4 | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_39 | Creating New Labour Information Claim: There shouls be a unit for Operation Time as hours or day. |  |  |  | https://prnt.sc/qxsi9v | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_40 | Creating New Labour Information Claim: If user adds Rate first and then he enters the Operation Time then system does not counts Price and shows NAN in price and Total |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_41 | Document Tracking Panel: User is able to submit the document tracking panel by entering future date in Document Courier Date. |  |  |  |  | Mid | Mid | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_42 | Document Tracking Panel: User is able to submit the document tracking panel by entering blank spaces in Document Courier Date. |  |  |  |  | Low | Low | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_43 | TVS Manager: Claim Update- if the claim status is approved then user should not be able to select/enter "Reason of Rejection" but currently this is happening. |  |  |  | https://prnt.sc/qxu2yq | High | High | Fixed | Vikash Jha | No Need to Change
2020-02-05 |  | Bug_ID_44 | Creating New Part Information Claim: Quantity cannot be in decimal value. |  |  |  |  | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_45 | Creating New Part Information Claim: Calculation of Part information is getting wrongly computed that is if user enters a decimal value in MRP as 200 and quantity in decimal as 1.00 then it does not take decimal into consideration while caluclating and gives the total price as 20000 instead of 200 |  |  |  | https://prnt.sc/qxuz2l | High | High | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_46 | Creating New Labour Information Claim: Operation time should be a mandatory field as the Price is getting calculatd on the basis of it and also there should be a proper validation for the same. [DONE mandatory from setting] |  |  |  |  | Mid | Mid | Fixed | Vikash Jha | Fixed
2020-02-05 |  | Bug_ID_47 | Editing New Labour Information Claim:If user does not changes the rate and only changes the Operation Time then the price does not get updated. |  |  |  |  | High | High | New | Vikash Jha | Fixed | Whole field resets.
2020-02-05 |  | Bug_ID_48 | Creating New Miscellaneous Expenses: user is able to enter negative integers in the amount field and also if user enters any positive vaue in service tax then the total price compute sit wrongly by taking service tax value as negative even when the enteres value was positive. |  |  |  | https://prnt.sc/qxvcvg | High | High | Fixed | Vikash Jha | Fixed
2020-02-15 | TC_03/Issue_New_Eicher_Xtend | Bug_ID_49 | Two validation msg. appears | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@@@######12345 |  |  | High | New
2020-02-15 | TC_04/Issue_New_Eicher_Xtend | Bug_ID_50 | Once Chassis no. not avaliable msg. displayed fiesld data should be reset | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@@@######12345 |  |  | Low | New

## Vin-Validation
Project Name: Volvo_Eicher
Created By:- | Atyab Alam |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-14 |  | Review Date:- |  |  | Developed By :- | Vikash Jha
Version: - |  |  | Module:- | Issue_New_Eicher_Xtend |  | Power_ID :- | 10026
Test Case ID/Module | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/Issue_New_Eicher_Xtend | To verify that Dealer is able to Login to Claim management Portal | Login Credential Provided | ID :- kiran-bikaner Password :- Welcome@123 |  |  |  | Dealer should be able to login and will be redirected to homepage
TC_02/Issue_New_Eicher_Xtend | To verify that Dealer is able to open Issue New Eicher Xtend | Login Credential Provided | Click on Issue New Eicher Xtend |  |  |  | Issue New Eicher Xtend page will open
TC_03/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Enter Space in Vehicle Chessis No. | Two validation msg. appears |  | Vehicle Chassis No. can only be of 17 digit. Msg. will be displayed |  | High | Fail
TC_04/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- @@@@@@######12345 | Once Chassis no. not avaliable msg. displayed fiesld data should be reset |  | Chassis no. not avaliable msg. should be displayed |  | Low | Fail
TC_05/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- 01A8A369B45QWERTY |  |  | Chassis no. not avaliable msg. should be displayed
TC_06/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- ABCD8KGH7JH123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_07/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- CC090QWE5GH456258 |  |  | Chassis no. not avaliable msg. should be displayed
TC_08/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- VV6DF1AC0GH789852 |  |  | Chassis no. not avaliable msg. should be displayed
TC_09/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- BH1J5ABCDEF123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_10/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- GF0D5FFF544123456 |  |  | Chassis no. not avaliable msg. should be displayed
TC_11/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- BB0QWERT9YUABC123 |  |  | Chassis no. not avaliable msg. should be displayed
TC_12/Issue_New_Eicher_Xtend | To verify that Dealer is able to Enter Vehicle Chassis No. | Login Credential Provided | Click on Issue New Eicher Xtend | Vehicle Chessis No. :- GH0A0SDE8GH458965 |  |  | Chassis no. not avaliable msg. should be displayed