## Summery
Renault EW
Lead Dev: Alok Srivastava
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestions/Enhancements | Deferred
Courier Details | 13 | 13 | 11 | 0 | 0 | 2
Easy Care Sales | 45 | 45 | 28 | 17 | 0 | 0
Easy Care Claims | 26 | 26 | 19 | 7 | 0 | 0
Update Easy Care Sales | 42 | 42 | 32 | 10 | 0 | 0
Update Easy Care Claims | 24 | NA | NA | NA | NA | NA
Price_Logic_Change | 8 | 8 | 3 | 3 | 2 | 0
ATW_Plan | 7 | 7 | 7 | 0 | 0 | 0
Activate _UpgradedPlan | 13 | 13 | 4 | 9 | 1 | 0
Total | 178 | 154 | 104 | 46 | 3 | 2

## Open_Bugs
Bug Report
Project :- |  | Renault EW | [5 empty] | Lead_Developer. :-Alok Srivastava
Created_By :- |  | Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Status on 21-02-2020 | Task ID- Retesting | Open | Close
2020-02-19 | TC_Courier Details_09 | Bug_ID_01 | 10086 | Courier details are getting update with invalid Document Courier Date. | User is on the "courier details update" page. | 1)Enter invalid data in Document Courier Date field and enter valid data in the remaining fields. 2)Click on the Save buton. | 2033-02-24,or any future date. Text field. |  | High | High | Fixed | Alok Srivastava | ##As Discussed with Greeshma Maa’m Not in Priority for now |  | Fixed | 10123 |  | 2020-02-21
2020-02-19 | TC_Courier Details_10 | Bug_ID_02 | 10086 | Courier details are getting update with invalid POD number. | User is on the "courier details update" page. | 1)Enter invalid data in POD Number field and enter valid data in the remaining fields. 2)Click on the Save buton. | Blank spaces, special characters. @#@ |  | High | High | Deferred | Alok Srivastava | ##As Discussed with Greeshma Maa’m Not in Priority for now |  | Deferred | 10123 |  | 2020-02-21
2020-02-19 | TC_Courier Details_04 | Bug_ID_03 | 10086 | System shows a validation message as "Please Enter Document Courier Date." but the message can revised to " All the mandatory fields marked with * are required so as to make it more appropriate and complete. | User is on the "courier details update" page. | 1)Click on the Save buton without entering any data in mandatory fields. | NA |  | Low | Low | Fixed | Alok Srivastava | DONE |  | Fixed | 10123 |  | 2020-02-21
2020-02-19 | TC_Courier Details_11 | Bug_ID_04 | 10086 | Courier details are getting update with invalid Courier Company Name | User is on the "courier details update" page. | 1)Enter invalid data in Courier Company Name field and enter valid data in the remaining fields. 2)Click on the Save buton. | Blank spaces, special characters. @#@ |  | High | Mid | Deferred | Alok Srivastava | ##As Discussed with Greeshma Maa’m Not in Priority for now |  | Deferred | 10123 |  | 2020-02-21
2020-02-19 | TC_Courier Details_08 | Bug_ID_05 | 10086 | Courier Company Name is mandatory so it should be * marked in order to show it as mandatory. | User is on the "courier details update" page. | 1)Leave the Courier Company Name field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  | High | Low | Fixed | Alok Srivastava | DONE |  | Fixed | 10123 |  | 2020-02-21
2020-02-19 |  |  |  | Suggestion: After submitting the courier details with valid data there should be a success pop-up, on clicking upon OK button on Pop-up the page should get auto close. | [6 empty] | Deferred | Alok Srivastava | ##As Discussed with Greeshma Maa’m Not in Priority for now |  | Deferred | 10123 |  | 2020-02-21
2020-02-24 | TC_03/Vin-Validation | Bug_ID_06 | 10121 | 1)There is no validation message appears for entering blank spaces in Vehicle Chasis No. field. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | blank spaces |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_03/Vin-Validation | Bug_ID_07 | 10121 | There is no validation message appears for entering any invalid number(any random number which is not present in the existing records) of 17 digits. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | V123456789 |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_03/Vin-Validation | Bug_ID_08 | 10121 | The validation number appearing for entering less than 17 digits chasis number is not correct. As it should be either Vehicle Chasis No. is not valid or Vehicle Chasis Number is not valid. in current msg abbreviation of number is not correct due to which its making it "No" instead of "No.". | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. |  |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_05 | Bug_ID_09 | 10121 | Priority of validation message coming for leaving GSTIN field blank for selecting yes on GSTIN applicable field is wrong its showing the validation after entering valid data in every mandatory field. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | Low | low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_21 | Bug_ID_10 | 10121 | User is able to submit the agreement form by enterng invalid data in First Name field. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | @#@$221 |  | low | low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_22 | Bug_ID_11 | 10121 | User is able to submit the agreement form by enterng invalid data in Last Name field. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1223@# |  | low | low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_24 | Bug_ID_12 | 10121 | User is able to submit the agreement form by enterng invalid data in Mobile Phone No. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1434 |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_26 | Bug_ID_13 | 10121 | User is able to submit the agreement form by enterng invalid data in city. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@# |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_27 | Bug_ID_14 | 10121 | User is able to submit the agreement form by enterng invalid data in state. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_28 | Bug_ID_15 | 10121 | User is able to submit the agreement form by enterng invalid data in Postal Code. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Postal Code. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123 |  | High | high | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_29 | Bug_ID_16 | 10121 | User is able to submit the agreement form by enterng invalid data in STATE. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in State. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ |  | Low | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_30 | Bug_ID_17 | 10121 | User is able to submit the agreement form by enterng invalid data in Registration No. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Registration No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@#!!rgsdds |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_31 | Bug_ID_18 | 10121 | User is able to submit the agreement form by enterng invalid data in Executive Name. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Executive field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !@!@121 |  | Mid | Mid | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_32 | Bug_ID_19 | 10121 | User is able to submit the agreement form by enterng invalid data in Sales Manager Name. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Sales Manager field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123@!# |  | Mid | Mid | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_33 | Bug_ID_20 | 10121 | User is able to create an agreement by entering odometer reading less than the Last Service Odometer Reading. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Service Odometer Reading:6000 Odometer Reading 5000 |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_34 | Bug_ID_21 | 10121 | User is able to create an agreement by entering invalid data in Last Service Odometer Reading. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Service Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 600test |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_08 | Bug_ID_22 | 10121 | System shows a validation message but it does not get closed on clicking on OK button. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Date of Job Card field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_13 | Bug_ID_23 | 10121 | User is able to submit claim by entering invalid data in Warranty Admin Name. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Warranty Admin Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123456 |  | Low | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_15 | Bug_ID_24 | 10121 | User is able to submit claim by entering invalid data in Dealer Contact. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Dealer Contact Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 12 |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_17 | Bug_ID_25 | 10121 | User is able to submit claim by entering invalid data in Date of Job Card. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Date of Job Card. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 2036-02-05 |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_18 | Bug_ID_26 | 10121 | User is able to submit claim by entering invalid data in Odometer Reading. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Odometer Reading. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | -9 |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareClaims_25 | Bug_ID_27 | 10121 | REC Start Date, REC End Date and Vehicle Delivery Date are editable. | User is already logged in and is on New Easy Care Claim page. | 1) Select REC SALES NUMBER 2) try to edit the fields of Easy Care Claims Details section. |  |  | High | High | New | Alok Srivastava
2020-02-24 | TC_Query_1 | Bug_ID_28 | 10121 | Easy Care Claims Status is showing approved status on dealer module. | User is already logged in and is on New Easy Care Claim page. | 1) see the Easy Care Claims Status |  |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_37 | Bug_ID_29 | 10121 | fleet status (Does Vehicle belongs to Fleet?) should be * marked. | User is already logged in and is on New Easy Care Agreement page. | 1) Check the * marked against each mandatory field. |  |  | High | Low | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_38 | Bug_ID_30 | 10121 | First Name, Last Name and Phone Number are editbale they should be freezed. | User is already logged in and is on New Easy Care Agreement page. | Observe the data coming from the middleware. |  |  | High | High | New | Alok Srivastava
2020-02-24 | TC_EasyCareSales_39 | Bug_ID_31 | 10121 | Customer Price is showing 14961 but if user calculate the customer price manually then total comes out as 14960. |  | Open the newly added agreement. |  |  | High | High | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_27 | Bug_ID_32 | 10121 | User is able to update the agreement form by enterng invalid data in First Name field. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | @#@$221 |  | Low | Low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales__28 | Bug_ID_33 | 10121 | User is able to update the agreement form by enterng invalid data in Last Name field. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1223@# |  | High | High | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales__30 | Bug_ID_34 | 10121 | User is able to update the agreement form by enterng invalid data in Mobile Phone No. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 143412 |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_32 | Bug_ID_35 | 10121 | User is able to update the agreement form by enterng invalid data in city. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@# |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_34 | Bug_ID_36 | 10121 | User is able to update the agreement form by enterng invalid data in Postal Code. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Postal Code. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1234 |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_35 | Bug_ID_37 | 10121 | User is able to update the agreement form by enterng invalid data in STATE. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in State. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_36 | Bug_ID_38 | 10121 | User is able to update the agreement form by enterng invalid data in Registration No. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Registration No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@#!!rgsdds3235yu |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_37 | Bug_ID_39 | 10121 | User is able to update the agreement form by enterng invalid data in Executive Name. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Executive field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !@!@121 |  | low | low | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareSales_38 | Bug_ID_40 | 10121 | User is able to update the agreement form by enterng invalid data in Sales Manager Name. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Sales Manager field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123@!# |  | High | High | New | Alok Srivastava
2020-02-24 | TC_UpdateEasyCareClaims_40 | Bug_ID_41 | 10121 | User is able to update an agreement by entering odometer reading less than the Last Service Odometer Reading. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Last Service Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Service Odometer Reading:2001 Odometer Reading 2000 |  |  |  |  | Alok Srivastava
2020-02-24 | Price_Logic_01 | Bug_ID_42 | 10175 | Price Flag field is editable. | User is already on create agreement page. | 1) Validate the vin number for creatting new agreement. 2)Enter the valid data in all the mandatory fields. |  |  | High | High | New | Alok Srivastava
2020-02-26 | Price_Logic_02 | Bug_ID_43 | 10175 | In the agreement details the price is "Customer Price 6240" and in EWS Retail Details of the same plan its "Final Price 6239" | User is already on create agreement page. | 1)Create an agreement and select the best suitable plan. 2) now open the EWS Retail Details of the same selected plan. 3)Compare the details of both. | EWS Retal No EWS3025 |  | High | High | New | Alok Srivastava
2020-02-26 | Suggestion_Price_Logic_01 | Bug_ID_44 | 10175 | There should be a history of flag changes on the admin portal. |  |  |  |  | High | High | New | Alok Srivastava
2020-02-26 | Suggestion_Price_Logic_02 | Bug_ID_45 | 10175 | There should be an option tomanage flags on the front-end. |  |  |  |  | High | High | New | Alok Srivastava
2020-02-26 | Price_Logic_03 | Bug_ID_46 | 10175 | If user update any EWS plan price and after that he creates a new agreement then the updated price should get appear for the new agreement. |  | 1) Edit the price of the ews plan. 2)Create a new agreement against which the same updated ews plan can be selected. 3) Compare the price both in create agreement page and ews details page. |  |  | High | High | New | Alok Srivastava
2020-03-11 | TC_ATW_01 | Bug_ID_47 | 10307 | User is able to raise the claim against the agerement number which is under Cooling-Off Period and also there is a validation message but still user can raise the claim. | User is raising the claim under Cooling Off period. | 1) Raise the claim by taking an agreement number under ATW Plan and is under Cooling offf period. 2) Fill the claim form with the valid data. |  |  | High | High | Pass | Alok Srivastava
2020-03-11 | TC_ATW_02 | Bug_ID_48 | 10307 | the validation message saying " There are no Plans for this Vin no. should get appear after the vin number validation instead of showing on the create agreement page. | User is loggged in | 1) Enter vin number having the vehicle aging more than or equal to 7 years. |  |  | High | High | Pass | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC1 | Bug_ID_49 | 10334 | The confirmation message appearing is grammatically wrong and also there is a spelling mistake as pilicy. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC2 | Bug_ID_50 | 10334 | After clicking on OK button appearing on confirmation message to select upgraded plan is wrong that is system shows a vehicle chasiss number as validation message for no reasons. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC2 | Bug_ID_51 | 10334 | After clicking on OK button appearing on validation message for vehicle chasis number system gets redirect and gets reload. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC3 | Bug_ID_52 | 10334 | Dealer is able to raise the claim against the parent agreement (expired) after activating the upgraded plan. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC4 | Bug_ID_53 | 10334 | Dealer is able to update the claim against the parent agreement (expired) after activating the upgraded plan. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on any Claim to be updated. 3)clear the agreement number and enter the agreement number which is already expired. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC5 | Bug_ID_54 | 10334 | If there is no upgrade plan available for a perticular model and dealer tries to raise the claim by entering odometer eading more than the valid end odometer reading then system shows series of validation message. There should be only one validation message as "Odometer reading should be less than or equal to Ext. warranty end kms.". | User is loggged in. There is no upgraded plan availble for the selected vin. | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. | agreement number : RIP244809 |  | High | High | New | Alok Srivastava
2020-03-13 | ActiveRenaultEW_TC6 | Bug_ID_55 | 10334 | Wrong validation message appears when dealer enters odometer reading more than the valid range in case of using upgraded plan. |  |  |  |  | High | High | New | Alok Srivastava
2020-03-14 | ActiveRenaultEW_TC7 | Bug_ID_56 | 10334 | User is able to raise the claim against the upgraded plan without activating it. System does not ask to active the plan. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Enter the upgraded agreement number directly by copy-paste. 4) Enter odometer reading and enter valid data in the remaining fields. 5)clickon save button. |  |  | High | High | New | Alok Srivastava
2020-03-14 | ActiveRenaultEW_TC8 | Bug_ID_57 | 10334 | User is able to raise the claim by entering invalid data in Dealer Contact No. | 9.2234e+18 | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on sAVE button and click on ok button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. |  |  | High | Mid | New | Alok Srivastava
2020-03-14 | ActiveRenaultEW_TC9 | Bug_ID_58 | 10334 | User is not able to update the claim having status as Pre Approval Document Pending. Everytime user updates any detail system shows a validation message as "The Selected Status does not exist in dropdown ." |  | 1) Select any agreement having status Pre Approval Document Pending. 2) Update any detail with valid data. 3)Click on Save button. |  |  | High | High | New | Alok Srivastava
2020-03-14 | ActiveRenaultEW_TC9 | Bug_ID_59 | 10334 | Enhancement: At the edit claim page the SAVE button should get change to Update. |  |  |  |  | High | Mid | New | Alok Srivastava
2020-03-14 | ActiveRenaultEW_TC10 | Bug_ID_60 | 10334 | User is able to raise the claim by entering invalid data in Warranty Admin Name. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on sAVE button and click on ok button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | #@@$!!# |  | High | Mid | New | Alok Srivastava
2020-01-04 | TC_ATWClientUAT_06 | Bug_ID_61 | 10522 | User should not be able to apply for an ATW plan if there is an existing active plan and there should be a proper validation message for the same. | User is loggged in | 1) Enter a vin number having active plan in the vin validation page. | MEERBC007K8004506 |  | High | High | New | Alok Srivastava
2020-01-04 | TC_ATWClientUAT_03 | Bug_ID_62 | 10522 | The confirmation message appearing for improper service for ATW plan having html tag <br> in it please remove it. |  |  |  |  | High | Low | New | Alok Srivastava

## ATW_Plan
Project Name: Renault-EW
Updated By:- | Jitendra |  | ReTestedBy:- | Jitendra |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-03-11 |  | Retesting Date:- | 2020-03-16
Version: - |  |  | Module:- | ATW_Plan |  | Power ID: | 10307 |  |  |  | Retesting-16-03-2020
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power Task ID | Status -16-03-2020
TC_ATW_01 | To verify if the user is able to raise the claim under ATW plan within the Cooling-off Period | User is raising the claim under Cooling Off period. | 1) Raise the claim by taking an agreement number under ATW Plan and is under Cooling offf period. 2) Fill the claim form with the valid data. |  | User is able to raise the claim against the agrrement number which is under Cooling-Off Period and also there is a validation message but still user can raise the claim. | MEEJSRGW4F5001912 | User should not be able to raise the claim against the agrrement number which is under Cooling-Off Period and also there should be a proper validation message for the same. | High | High | Fail | 10342 | Pass
TC_ATW_02 | To verify if the user is able select the Plan on any Vehicle chasis no. having vehicle aging more than 7 years | User is loggged in | 1) Enter vin number having the vehicle aging more than or equal to 7 years. |  | User is not able to proceed with the ATW plan but the validation message saying " There are no Plans for this Vin no. should get appear after the vin number validation. | MEEJSRGW4F5001912 | User should not be able to proceed with the ATW plan as the vehicle aging is 7 years and is no more eligible for this plan. | High | High | Fail | 10342 | Pass
TC_ATW_03 | To verify if the user is able select the Plan on any Vehicle chasis no. having odometer reading equal to or more than 99999Kms | User is loggged in | 1) Enter vin number having odometer reading equal to or more than 99999Kms |  |  |  | User should not be able to proceed with the ATW plan as the odometer reading 99999 and is no more eligible for this plan. |  |  | Pass | 10342 | Pass
TC_ATW_04 | To verify if the duration of the plan is 6 months or not. when vehicle againg equal to 6 years and 6 months and he opts for ATW plan then the | User is loggged in | 1) Enter vin number having the vehicle aging equal to 6 years and 6 months years. |  | The total duration of the plan should be equal to 6 months but system raises the claim for one year. |  | User should be able to raise the claim for only 6 months after the activation of the policy. | High | High | Pass | 10342 | Pass
TC_ATW_05 | To verify if the total Kms of service is 10000Kms or not when vehicle odometer reading is 90000kms | User is loggged in | 1) Enter vin number having the vehicle vehicle odometer reading is 90000kms |  |  |  | User should be able to raise the claim for 10000kms. |  |  | Pass | 10342 | Pass
TC_ATW_06 | To verify if the user is able to Apply for an ATW Plan with having an active existing plan. | User is loggged in |  |  |  |  | User should not be able to apply for an ATW plan and there should be a propr validation message for the same. |  |  | Pass | 10342 | Pass
TC_ATW_07 | To verify if the user is able to Apply for an aTW Plan with having all the valid data and valid pre-requisites for itt. | User is loggged in |  |  |  |  | User should be able to apply for an ATW plan. |  |  | Pass | 10342 | Pass

## ATW_Plan_clientUAT
Project Name: Renault-EW
Updated By:- | Jitendra |  | ReTestedBy:- | Jitendra |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-03-26 |  | Retesting Date:-
Version: - |  |  | Module:- | ATW_Plan_clientUAT |  | Power ID: | 10522
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_ATWClientUAT_01 | To verify if the user is able to raise the claim under ATW plan within the Cooling-off Period | User is raising the claim under Cooling Off period. | 1) Raise the claim by taking an agreement number under ATW Plan and is under Cooling offf period. 2) Fill the claim form with the valid data. | MEEJSRGW4F5001912 and MEEHSRC85E6002859 RIP232041 | Validation message is appearing and cagreement details does not get appear when selecting the agreement number under coolin goff period. |  | User should not be able to raise the claim against the agrrement number which is under Cooling-Off Period and also there should be a proper validation message for the same. |  |  | Pass
TC_ATWClientUAT_02 | To verify if the user is able select the Plan on any Vehicle chasis no. having vehicle aging more than 7 years | User is loggged in | 1) Enter vin number having the vehicle aging more than or equal to 7 years. | MEEJSRGW4F5001912 and MEERBC004K8002812 | User is not able to proceed with the ATW plan but the validation message saying " There are no Plans for this Vin no. should get appear after the vin number validation. |  | User should not be able to proceed with the ATW plan as the vehicle aging is 7 years and is no more eligible for this plan. |  |  | Pass
TC_ATWClientUAT_03 | To verify if the user is able select the Plan on any Vehicle chasis no. having odometer reading equal to or more than 99999Kms | User is loggged in | 1) Enter vin number having odometer reading equal to or more than 99999Kms |  |  |  | User should not be able to proceed with the ATW plan as the odometer reading 99999 and is no more eligible for this plan.
TC_ATWClientUAT_04 | To verify if the duration of the plan is 1 year or not. when vehicle againg equal to 6 years and he opts for ATW plan then the | User is loggged in | 1) Enter vin number having the vehicle aging equal to 6 years and 6 months years. | MEEHSRC85E6002859 | The total duration of the plan should is equal to 11 months as the total againg of 7 years is ended before the completion of the policy duration of 1 year. |  | User should be able to raise the claim for only 1 year after the activation of the policy. if the total aging is under 6 years if its more than 6 years and less than 7 years then the remaining months should be available for service duration. |  |  | Pass
TC_ATWClientUAT_05 | To verify if the total Kms of service is 10000Kms or not when vehicle odometer reading is 95000kms | User is loggged in | 1) Enter vin number having the vehicle vehicle odometer reading is 90000kms | MEEHSRAW5F2083660 |  |  | User should be able to raise the claim for 10000kms. |  |  | Pass
TC_ATWClientUAT_06 | To verify if the user is able to Apply for an ATW Plan with having an active existing plan. | User is loggged in | 1) Enter a vin number having active plan in the vin validation page. | MEERBC007K8004506 |  |  | User should not be able to apply for an ATW plan if there is an existing active plan and there should be a proper validation message for the same. |  |  | Fail
TC_ATWClientUAT_07 | To verify if the user is able to Apply for an aTW Plan with having all the valid data and valid pre-requisites for itt. | User is loggged in |  |  |  |  | User should be able to apply for an ATW plan. |  |  | Pass
TC_ATWClientUAT_08

## Activate _UpgradedPlan
Project Name: Renault-EW
Updated By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-03-13 |  | Review Date:-
Version: - |  |  | Module:- | Active Renault EW-Activate _UpgradedPlan |  | Power ID: | 10334
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
ActiveRenaultEW_TC1 | To verify if the user is able to select the Upgraded plan if the user enters odometer reading lying under upgraded plan. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 | The confirmation message appearing is grammatically wrong and also there is a spelling mistake as pilicy. |  | There should be a proper and spacific confirmation message before selecting the upgraded plan. | High | High | Fail
ActiveRenaultEW_TC2 | To verify if the user is able to select the upgraded plan by clicking on confirmation message appearing after clicking on Save button. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 | After clicking on OK button appearing on confirmation message to select upgraded plan is wrong that is system shows a vehicle chasiss number as validation message for no reasons. |  | User should be able to click on the confirmation message and proceed with the upgraded plan. | High | High | Fail
ActiveRenaultEW_TC3 | To verify if the user is able to raise the claim against the parent agrrement after activating the upgraded agreement. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 | Dealer is able to raise the claim against the parent agreement (expired) after activating the upgraded plan. |  | Dealer should not be able to raise the claim against the parent agreement (expired) after activating the upgraded plan. | High | High | Fail
ActiveRenaultEW_TC4 | To verify if the user is able to update the claim against the parent agreement after activating the upgraded agreement. | User is already logged in as a dealer. (There is an upgraded plan against a vin) | 1)Click on the claim menu item. 2) Click on any Claim to be updated. 3)clear the agreement number and enter the agreement number which is already expired. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | EW Plan agrmt :RIP244819 upgraded plan agrmt:RIP244820 Odometer reading: 70000 | Dealer is able to update the claim against the parent agreement (expired) after activating the upgraded plan. |  | Dealer should not be able to update the claim against the parent agreement (expired) after activating the upgraded plan. | High | High | Fail
ActiveRenaultEW_TC5 | To verify if the user is able to raise the claim against the upgraded agreement when its not having any upgraded agreement. | User is loggged in. There is no upgraded plan availble for the selected vin. | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on OK button on validation message. | agreement number : RIP244809 | If there is no upgrade plan available for a perticular model and dealer tries to raise the claim by entering odometer eading more than the valid end odometer reading then system shows series of validation message. There should be only one validation message as "Odometer reading should be less than or equal to Ext. warranty end kms.". |  | User should not be able to raise the claim. And aalso there should be a proper validation messagee for the same. | High | High | Fail
ActiveRenaultEW_TC6 | To verify if the user is able to raise the claim by entering odometer reading more than/less than the valid range in case of using upgraded plan. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter invalid data in the remaining fields. 5) Click on OK button on validation message. |  | Wrong validation message appears when dealer enters odometer reading more than/less than the valid range in case of using upgraded plan. |  |  | High | mid
ActiveRenaultEW_TC7 | To verify if the user is able to raise the claim against the upgraded plan without even activating it. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Enter the upgraded agreement number directly by copy-paste. 4) Enter odometer reading and enter valid data in the remaining fields. 5)clickon save button. |  | User is able to raise the claim against the upgraded plan without activating it. System does not ask to active the plan. |  |  | High | High | Fail
ActiveRenaultEW_TC8 | To verify if the user is able to raise the claim by entering the invalid Dealer Contact No. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on sAVE button and click on ok button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | 9.2234e+18 | User is able to raise the claim by entering invalid data in Dealer Contact No. |  | User should not be able to raise the claim by entering invalid data in Dealer Contact No. | High | Mid | Fail
ActiveRenaultEW_TC9 | To verify if the user is able to update the claim or not. |  | 1) Select any agreement having status Pre Approval Document Pending. 2) Update any detail with valid data. 3)Click on Save button. |  | User is not able to update the claim having status as Pre Approval Document Pending. Everytime user updates any detail system shows a validation message as "The Selected Status does not exist in dropdown ." |  | User should be able to update the claim having status as Pre Approval Document Pending. Everytime user updates any detail system shows a validation message as "The Selected Status does not exist in dropdown ." | High | High | Fail
ActiveRenaultEW_TC10 | To verify if the user is able to raise the claim by entering the invalid Warranty Admin Name. |  | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading and enter valid data in the remaining fields. 5) Click on sAVE button and click on ok button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | #@@$!!# | User is able to raise the claim by entering invalid data in Warranty Admin Name. |  | User should not be able to raise the claim by entering invalid data in Warranty Admin Name. | High | Mid | Fail
ActiveRenaultEW_TC11 | To verify if the user is able to select and raise the upgraded plan on the basis of odometer reading. | User is loggedin as a dealer | 1)Click on the claim menu item. 2) Click on Add Claim. 3)Select the agreement against which the claim is to be raise. 4) Enter odometer reading lying in the upgraded plan range and enter valid data in the remaining fields. 5) Click on sAVE button and click on ok button on validation message. 6) Click on OK button n confirmation message for moving to the upgraded plan. | 65000 |  |  | User should be able to raise the claim. | High | High | Pass
ActiveRenaultEW_TC12 | To verify if the user is able to select the upgraded plan while creating the upgraded plan. | User is loggedin as a dealer | 1) Enter the vin no having the ext. warranty already created and validate it. 2) Click on OK button on pop-up on vin validation screen. 3) Enter all the mandatory fields. 4) Select the upgraded plan. |  |  |  | User should be able to select the claim. | High | High | Pass
ActiveRenaultEW_TC13 | To verify if the status of the parent agreement is getting changed to "expired" after activating the upgraded plan. | User is loggedin as a dealer | 1) Activate the upgraded plan. |  |  |  | Status of the Parent plan should get change to "Expire" | High | High | Pass

## Test_Cases_Courier Details
Project Name: Renault-EW
Created By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-19 |  | Review Date:-
Version: - |  |  | Module:- | Courier Details |  | Power ID: | 10086
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Courier Details_01 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button without selecting any claim number. | NA | User was not get redirect to the Courier Details Update page and also there was a proper validation message for the same. |  | User should not get redirect to the Courier Details Update page and also there should be a proper validation message for the same. |  |  | Pass
TC_Courier Details_02 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number having status other than approved. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button by selecting any claim which is not approved. | NA | There was a proper validation message as "Claim is not approved." |  | there should be a proper validation message as "Claim is not approved." |  |  | Pass
TC_Courier Details_03 | To verify if the user is able to get navigate to the "courier details update" by selecting Claim Number. for which the courier details to be update. | User is already logged in and is on Add Claim page. | 1)Select the Claim Number no. for which thee courier details to be update. 2)Click on the Courier Details Update button. | NA | User redirected to the concerned page with all the fields and buttons. |  | User should get redirect to the Courier Details Update page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) |  |  | Pass
TC_Courier Details_04 | To verify if the user is able to update courier details by leaving all the mandatory fields blank. | User is on the "courier details update" page. | 1)Click on the Save buton without entering any data in mandatory fields. | NA | System shows a validation message as "Please Enter Document Courier Date." but the message can revised to " All the mandatory fields marked with * are required so as to make it more appropriate and complete. |  | Courier details should not get update and system should display a proper validation message for leaving all the fields blank. | Low | Low | Fail
TC_Courier Details_05 | To verify if the user is able to update courier details by leaving "Document Send" field unchecked. | User is on the "courier details update" page. | 1)Leave the Document Send checkbox unchecked and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the Document Send field blank. |  |  | Pass
TC_Courier Details_06 | To verify if the user is able to update courier details by leaving the Document Courier Date field blank. | User is on the "courier details update" page. | 1)Leave the Document Courier Date field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the Document Courier Date field blank. |  |  | Pass
TC_Courier Details_07 | To verify if the user is able to update courier details by leaving the POD Number field blank. | User is on the "courier details update" page. | 1)Leave the POD Number field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the POD Number field blank. |  |  | Pass
TC_Courier Details_08 | To verify if the user is able to update courier details by leaving the Courier Company Name field blank. | User is on the "courier details update" page. | 1)Leave the Courier Company Name field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the Courier Company Name field blank. |  |  | Pass
TC_Courier Details_09 | To verify if the user is able to update courier details by entering invalid data in Document Courier Date field. | User is on the "courier details update" page. | 1)Enter invalid data in Document Courier Date field and enter valid data in the remaining fields. 2)Click on the Save buton. | 2033-02-24,or any future date. Text field. | Courier details are getting update with invalid Document Courier Date. |  | Courier details should not get update and system should display a proper validation message for entering invalid data in Document Courier Date field. | High | High | Fail
TC_Courier Details_10 | To verify if the user is able to update courier details by entering invalid data in POD Number field. | User is on the "courier details update" page. | 1)Enter invalid data in POD Number field and enter valid data in the remaining fields. 2)Click on the Save buton. | Blank spaces, special characters. @#@ | Courier details are getting update with invalid POD number. |  | Courier details should not get update and system should display a proper validation message for entering invalid data in POD Number field. | High | High | Fail
TC_Courier Details_11 | To verify if the user is able to update courier details by entering invalid data in Courier Company Name field. | User is on the "courier details update" page. | 1)Enter invalid data in Courier Company Name field and enter valid data in the remaining fields. 2)Click on the Save buton. | Blank spaces, special characters. @#@ | Courier details are getting update with invalid Courier Company Name |  | Courier details should not get update and system should display a proper validation message for entering invalid data in Courier Company Name field. | High | Low | Fail
TC_Courier Details_12 | To verify if the user is able to update courier details by entering valid data in all the mandatory fields. | User is on the "courier details update" page. | 1)Enter valid data in all the mandatory fields. 2)Click on Save button. | NA |  |  | Courier details should get updated. |  |  | Pass
TC_Courier Details_13 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is on the "courier details update" page. | 1)Click on Cancel Button. | NA |  |  | The page should get close.

## Test_Cases_Easy Care Sales
Project Name: Renault-EW
Created By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-21 |  | Review Date:-
Version: - |  |  | Module:- | Easy Care Sales |  | Power ID: | 10121
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/Vin-Validation | To verify if the Dealer is able to get navigate to the the vehicle chasis validation page or not. | User is already logged-in | 1)Click on Easy Care Sales link under menu item. 2)Click on Add easy care button. |  |  |  | Dealer should be able to get navigate to the vehicle chasis validation page having following fields andd button: 1) Vehicle Chasis No (Field) 2) Validate (Button) |  |  | Pass
TC_02/Vin-Validation | To verify if the user is able to validate Vehicle Chassis No by leaving it blank. | User is already on vehicle vadiation screen. | 1)Click on Validate button without entering any data in Vehicle Chassis No. | NA |  |  | System should display a validation message as "Vehicle Chassis No. is required." |  |  | Pass
TC_03/Vin-Validation | To verify if the user is able to validate Vehicle Chassis No. by entering invalid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter invalid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)@@@@######12345 2)01A8A369B45QWERTY 3)ABCD8KGH7JH123456 4)Blank spaces | 1)There is no validation message appears for entering blank spaces in Vehicle Chasis No. field. 2) There is no validation message appears for entering any invalid number(any random number which is not present in the existing records) of 17 digits. 3) The validation number appearing for entering less than 17 digits chasis number is not correct. As it should be either Vehicle Chasis No. is not valid or Vehicle Chasis Number is not valid. in current msg abbreviation of number is not correct due to which its making it "No" instead of "No.". |  | Chassis no. not avaliable msg. should be displayed | High | Low | Fail
TC_04/Vin-Validation | To verify if the user is able to validate Vehicle Chassis No. by entering valid data in Chassis No. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. | Vehicle Chessis No. :- 1)MEERBC004KB015983 |  |  | It should get validate successfully and a pop-up of Easy Care Agreement details should get appear with OK & Cancel button. |  |  | Pass
TC_05/Vin-Validation | To verify if the Cancel button on Easy Care Agreement details pop-up is working or not. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on Cancel button. |  |  |  | Process should get aborted. |  |  | Pass
TC_06/Vin-Validation | To verify if the User is able to get navigate to the Add Easy Care Agreement page by clicking on OK button on Easy Care Agreement details pop-up. | User is already on vehicle vadiation screen. | 1)Enter valid data in Chassis No. 2)Click on Validate button. 3) Click on OK button. |  |  |  | Creating New Easy Care page should get open having Easy Care Agreement related fields and Save and Cancel button. |  |  | Pass
TC_EasyCareSales_01 | To verify if the User is able to create new Easy Care Agreement by leaving all the mandatory fields blank. | User is already logged in and is on New Easy Care Agreement page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to create a new Easy Care Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | Pass
TC_EasyCareSales_02 | To verify if the User is able to create new Easy Care Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | Pass
TC_EasyCareSales_03 | To verify if the User is able to create new Easy Care Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | Pass
TC_EasyCareSales_04 | To verify if the User is able to create new Easy Care Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required." |  |  | Pass
TC_EasyCareSales_05 | To verify if the User is able to create new Easy Care Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Priority of validation message coming for leaving GSTIN field blank for selecting yes on GSTIN applicable field is wrong its showing the validation after entering valid data in every mandatory field. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." | Low | low | Fail
TC_EasyCareSales_06 | To verify if the User is able to create new Easy Care Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | Pass
TC_EasyCareSales_07 | To verify if the User is able to create new Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required." |  |  | Pass
TC_EasyCareSales_08 | To verify if the User is able to create new Easy Care Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for city field as "City is required." |  |  | Pass
TC_EasyCareSales_09 | To verify if the User is able to create new Easy Care Agreement by leaving Vehicle Chasis No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Vehicle Chasis No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Vehicle Chasis No field as "Vehicle Chasis No is required." |  |  | Pass
TC_EasyCareSales_10 | To verify if the User is able to create new Easy Care Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | Pass
TC_EasyCareSales_11 | To verify if the User is able to create new Easy Care Agreement by leaving State field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave State field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for State field as "State is required." |  |  | Pass
TC_EasyCareSales_12 | To verify if the User is able to create new Easy Care Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required." |  |  | Pass
TC_EasyCareSales_13 | To verify if the User is able to create new Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | Pass
TC_EasyCareSales_14 | To verify if the User is able to create new Easy Care Agreement by leaving Executive Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Executive Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Executive Name field as "Executive Name is required." |  |  | Pass
TC_EasyCareSales_15 | To verify if the User is able to create new Easy Care Agreement by leaving Sales Manager Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Sales Manager Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Sales Manager Name field as "Sales Manager Name is required." |  |  | Pass
TC_EasyCareSales_16 | To verify if the User is able to create new Easy Care Agreement by leaving Registration No field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Registration No field as " Registration No is required." |  |  | Pass
TC_EasyCareSales_17 | To verify if the User is able to create new Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required." |  |  | Pass
TC_EasyCareSales_18 | To verify if the User is able to create new Easy Care Agreement by leaving Last Service Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for Last Service Odometer Reading field as " Last Service Odometer Reading is required." |  |  | Pass
TC_EasyCareSales_19 | To verify if the User is able to create new Easy Care Agreement by leaving the REC Plan field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave REC Plan field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for REC Plan field as "REC Plan is required." |  |  | Pass
TC_EasyCareSales_20 | To verify if the User is able to create new Easy Care Agreement by leaving REC Retail field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Leave REC Retail field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for REC Retail field as "REC Retail is required." |  |  | Pass
TC_EasyCareSales_21 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in First Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | @#@$221 | User is able to submit the agreement form by enterng invalid data in First Name field. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in First Name field as "Invalid First Name." | low | low | Fail
TC_EasyCareSales_22 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Last Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1223@# | User is able to submit the agreement form by enterng invalid data in Last Name field. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Name field as "Invalid Last Name." | low | low | Fail
TC_EasyCareSales_23 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in GSTIN and enter valid details in the remaining fields. (if YES selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in GSTIN field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in GSTIN No. field as "Invalid GSTIN No." |  |  | Pass
TC_EasyCareSales_24 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Mobile Phone No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1434 | User is able to submit the agreement form by enterng invalid data in Mobile Phone No. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Mobile Phone No. field as "Invalid Mobile Phone No." | High | High | Fail
TC_EasyCareSales_25 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "Invalid Primary Email No." |  |  | Pass
TC_EasyCareSales_26 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in City and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@# | User is able to submit the agreement form by enterng invalid data in city. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in City field as "Invalid City " | High | Low | Fail
TC_EasyCareSales_27 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Vehicle Chasis No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ | User is able to submit the agreement form by enterng invalid data in state. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Vehicle Chasis No. field as "Invalid Vehicle Chasis No. " | High | Low | Fail
TC_EasyCareSales_28 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Postal Code and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Postal Code. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123 | User is able to submit the agreement form by enterng invalid data in Postal Code. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in VPostal Code as "Invalid Postal Code" | High | high | Fail
TC_EasyCareSales_29 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in State and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in State. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ | User is able to submit the agreement form by enterng invalid data in STATE. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in State as "Invalid State." | Low | Low | Fail
TC_EasyCareSales_30 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Registration No. and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Registration No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@#!!rgsdds | User is able to submit the agreement form by enterng invalid data in Registration No. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Registration No. field as "Invalid Registration No." | High | High | Fail
TC_EasyCareSales_31 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Executive Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Executive field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !@!@121 | User is able to submit the agreement form by enterng invalid data in Executive Name. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Executive Name field as "Invalid Executive Name." | Mid | Mid | Fail
TC_EasyCareSales_32 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Sales Manager Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Sales Manager field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123@!# | User is able to submit the agreement form by enterng invalid data in Sales Manager Name. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Sales Manager Name field as "Invalid Sales Manager Name." | Mid | Mid | Fail
TC_EasyCareSales_33 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Service Odometer Reading:2001 Odometer Reading 2000 | User is able to create an agreement by entering odometer reading less than the Last Service Odometer Reading. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Odometer Reading field as "Invalid Odometer Reading." | High | High | Fail
TC_EasyCareSales_34 | To verify if the User is able to create new Easy Care Agreement by entering invalid data in Last Service Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter invalid data in Last Service Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Service Odometer Reading:2001 Odometer Reading 2000 | User is able to create an agreement by entering odometer reading less than the Last Service Odometer Reading. |  | User should not be able to create new Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Service Odometer Reading field as "Invalid Last Service Odometer Reading." | High | High | Fail
TC_EasyCareSales_35 | To verify if the User is able to create new Easy Care Agreement by entering valid data iin all the mandatory fields. | User is already logged in and is on New Easy Care Agreement page. | 1) Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | New Easy Care Agreement should get created followwing a confirmation message as "Easy Care Agreement Successfully Added." |  |  | Pass
TC_EasyCareSales_36 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on New Easy Care Agreement page. | 1)Click on Cancel Button. 2)Click on the Leave button appearing on the confirmation message. |  |  |  | User should move back to the previous screen. |  |  | Pass
TC_EasyCareSales_37 | To verify if the mandatory fields are * marked | User is already logged in and is on New Easy Care Agreement page. | 1) Check the * marked against each mandatory field. |  | fleet status (Does Vehicle belongs to Fleet?) should be * marked. |  | All the mandatory fields should be * marked. | High | Low | Fail
TC_EasyCareSales_38 | To verify if the data coming from middleware is non editable or not. | User is already logged in and is on New Easy Care Agreement page. | Observe the data coming from the middleware. |  | First Name, Last Name and Phone Number are editbale they should be freezed. |  | The data coming from middleware should be non editable. | High | High | Fail
TC_EasyCareSales_39 | REC Plan Details: To verify if the details under REC Plan are getting computed correctly or not. |  | Open the newly added agreement. |  | Customer Price is showing 14961 but if user calculate the customer price manually then total comes out as 14960. |  |  | High | High | Fail

## Test_Cases_EasyCareClaims
Project Name: Renault-EW
Created By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-21 |  | Review Date:-
Version: - |  |  | Module:- | Easy Care Claims |  | Power ID: | 10121
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_EasyCareClaims_01 | To verify if the User is able to get navigate to the Easy Care Claims page. | User is already logged in | 1)Click on the Easy Care Claims available at the menu section. 2)Click on the Add Easy Care Claims. | NA |  |  | Creating New Easy Care Claims page should get open having Easy Care Claim related fields and Save and Cancel button. |  |  | pass
TC_EasyCareClaims_02 | To verify if the User is able to create new Easy Care Claim by leaving all the mandatory fields blank. | User is already logged in and is on New Easy Care Claim page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to create a new Easy Care Claim and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | Pass
TC_EasyCareClaims_03 | To verify if the User is able to create new Easy Care Claim by leaving REC Sales Number field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave REC Sales Number fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for REC Sales Number field " REC Sales Number is required." Note: On the basis of REC sales number rest of the Easy Care Claims Details should get appear and they should be non editable |  |  | Pass
TC_EasyCareClaims_04 | To verify if the User is able to create new Easy Care Claim by leaving Warranty Admin Name field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Warranty Admin Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Warranty Admin Name field " Warranty Admin Name is required." |  |  | Pass
TC_EasyCareClaims_05 | To verify if the User is able to create new Easy Care Claim by leaving Dealer Email field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on New Easy Care Claim page. | 1) Leave Dealer Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Dealer Email field as "Dealer Email is required." |  |  | pass
TC_EasyCareClaims_06 | To verify if the User is able to create new Easy Care Claim by leaving Dealer Contact number field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Dealer Contact Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Dealer Contact field as " Dealer Contact Number is required." |  |  | pass
TC_EasyCareClaims_07 | To verify if the User is able to create new Easy Care Claim by leaving Job Card number field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Job Card Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Job Card field as " Job Card Number is required." |  |  | pass
TC_EasyCareClaims_08 | To verify if the User is able to create new Easy Care Claim by leaving Date of Job Card field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Date of Job Card field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | System shows a validation message but id does not get closed on clicking on OK button. |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Date of Job Card field as "Date of Job Card is required." | High | High | Fail
TC_EasyCareClaims_09 | To verify if the User is able to create new Easy Care Claim by leaving the Current PMS Visit field unselected and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Current PMS Visit field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Current PMS Visit field as " Current PMS Visit is required." |  |  | pass
TC_EasyCareClaims_10 | To verify if the User is able to create new Easy Care Claim by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required." |  |  | pass
TC_EasyCareClaims_11 | To verify if the User is able to create new Easy Care Claim by leaving Job Card Open Time field blank and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Leave Job Card Open Time field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for Job Card Open Time field as " Job Card Open Time is required." |  |  | pass
TC_EasyCareClaims_12 | To verify if the User is able to create new Easy Care Claim by entering invalid data in REC Sales Number and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in REC Sales Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in REC Sales Number field as "Invalid REC Sales Number." |  |  | Pass
TC_EasyCareClaims_13 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Warranty Admin Name and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Warranty Admin Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123456 | User is able to submit claim by entering invalid data in Warranty Admin Name. |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Warranty Admin Name field as "Invalid Warranty Admin Name." | Low | Low | Fail
TC_EasyCareClaims_14 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Dealer Email and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Dealer Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Dealer Email field as "Invalid Dealer Email." |  |  | pass
TC_EasyCareClaims_15 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Dealer Contact Number and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Dealer Contact Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 12 | User is able to submit claim by entering invalid data in Dealer Contact. |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Dealer Contact Number field as "Invalid Dealer Contact Number." | High | High | Fail
TC_EasyCareClaims_16 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Job Card Number and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Job Card Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Job Card Number field as "Invalid Job Card Number." |  |  | pass
TC_EasyCareClaims_17 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Date of Job Card and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Date of Job Card. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 2036-02-05 | User is able to submit claim by entering invalid data in Date of Job Card. |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Date of Job Card field as "Invalid Date of Job Card." | High | High | Fail
TC_EasyCareClaims_18 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Odometer Reading. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | -9 | User is able to submit claim by entering invalid data in Odometer Reading. |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Odometer Reading field as "Invalid Odometer Reading." | High | High | Fail
TC_EasyCareClaims_19 | To verify if the User is able to create new Easy Care Claim by entering invalid data in Job Card Open Time and enter valid details in the remaining fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter invalid data in Job Card Open Time. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Job Card Open Time field as "Invalid Job Card Open Time." |  |  | pass
TC_EasyCareClaims_20 | To verify if the user is able to create a new easy care claims by uploading invalid file in Invoice Document | User is already logged in and is on New Easy Care Claim page. | 1) Upload invalid file in Invoice document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for ethe same. |  |  | pass
TC_EasyCareClaims_21 | To verify if the user is able to create a new easy care claims by uploading invalid file in Job Card Document. | User is already logged in and is on New Easy Care Claim page. | 1) Upload invalid file in Job Card document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for ethe same. |  |  | pass
TC_EasyCareClaims_22 | To verify if the user is able to create a new easy care claims by uploading invalid file in Vehicle History Document | User is already logged in and is on New Easy Care Claim page. | 1) Upload invalid file in Vehicle History document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create new Easy Care Claim and the system must display a proper and specific validation message for ethe same. |  |  | pass
TC_EasyCareClaims_23 | To verify if the User is able to create new Easy Care Claim by entering valid data iin all the mandatory fields. | User is already logged in and is on New Easy Care Claim page. | 1) Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | New Easy Care Claim should get created followwing a confirmation message as "Easy Care Claim Successfully Added." |  |  | pass
TC_EasyCareClaims_24 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on New Easy Care Claim page. | 1)Click on Cancel Button. 2)Click on the Leave button appearing on the confirmation message. |  |  |  | User should move back to the previous screen. |  |  | pass
TC_EasyCareClaims_25 | To verify if the details coming through the REC sales number are non-editable or not. | User is already logged in and is on New Easy Care Claim page. | 1) Select REC SALES NUMBER 2) try to edit the fields of Easy Care Claims Details section. |  | REC Start Date, REC End Date and Vehicle Delivery Date are editable. |  | All the details of Easy Care Claims Details should be non-editable. | High | High
TC_Query_1 | Easy Care Claims Status is showing approved? | [8 empty] | fail

## Test_Cases_Update_EasyCareSales
Project Name: Renault-EW
Updated By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-21 |  | Review Date:-
Version: - |  |  | Module:- | Update Easy Care Sales |  | Power ID: | 10121
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_UpdateEasyCareClaims_01 | To verify if the Dealer is able to get navigate to the the Update page of selected Agreement. | User is already logged-in | 1)Click on Esy Care Sales link under menu item. 2)Click on agreement you wish to update. 3) Click on Amendment button. |  |  |  | An Amandment Message should get display having Amendment Type: Amendment , Cancel button, Reason select list , Close link and a submit button. |  |  | Pass
TC_UpdateEasyCareClaims_02 | To verify if the Dealer is able to get navigate to the the Update page by without selecting any reason for amendment. | User is on Amendment message. | 1) click on Submit button. | for amendment. |  |  | User should not be able to nevigate to the update page of selected agreement. |  |  | Pass
TC_UpdateEasyCareClaims_03 | To verify if the Dealer is able to get navigate to the the Update page by without selecting any reason for cancelling an agreement. | User is on Amendment message. | 1) click on Submit button. | for cancellation. |  |  | User should not be able to nevigate to the update page of selected agreement. |  |  | Pass
TC_UpdateEasyCareClaims_04 | To verify if the Dealer is able to get navigate to the the Update page by selecting a reason for amendment. | User is on Amendment message. | 1)Select any valid reasson from select list of reasons. 2) click on Submit button. | for amendment. |  |  | User should be able to nevigate to the update page of selected agreement. |  |  | Pass
TC_UpdateEasyCareClaims_05 | To verify if the Dealer is able to get navigate to the the Update page by selecting a reason for cancelling an agreement. | User is on Amendment message. | 1)Select any valid reasson from select list of reasons. 2) click on Submit button. | for cancellation. |  |  | User should be able to cancel the selected agreement. |  |  | Pass
TC_UpdateEasyCareClaims_06 | To verify if the Dealer is able to close the amendmnet message by clicking on close link. | User is on Amendment message. | 1)click on close link appearing at the right top corner of the message. | for cancellation. |  |  | amendmnet message should get close and user should get redirect to the previous page. |  |  | Pass
TC_UpdateEasyCareClaims_07 | To verify if the User is able to Update Easy Care Agreement by leaving all the mandatory fields blank. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to Update a Easy Care Agreement and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | Pass
TC_UpdateEasyCareClaims_08 | To verify if the User is able to Update Easy Care Agreement by leaving First Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave First Name fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for First Name field "First Name is required." |  |  | Pass
TC_UpdateEasyCareClaims_09 | To verify if the User is able to Update Easy Care Agreement by leaving Last Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Last Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Last Name field "Last Name is required." |  |  | Pass
TC_UpdateEasyCareClaims_10 | To verify if the User is able to Update Easy Care Agreement by leaving the GSTIN Applicable unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave GSTIN Applicable unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for GSTIN Applicable field as "GSTIN Applicable is required." |  |  | Pass
TC_UpdateEasyCareClaims_11 | To verify if the User is able to Update Easy Care Agreement by leaving GSTIN field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave GSTIN field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for GSTIN field as "GSTIN is required." |  |  | Pass
TC_UpdateEasyCareClaims_12 | To verify if the User is able to Update Easy Care Agreement by leaving Mobile Phone field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Mobile Phone field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Mobile Phone field as "Mobile Phone is required." |  |  | Pass
TC_UpdateEasyCareClaims_13 | To verify if the User is able to Update Easy Care Agreement by leaving Primary Email field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Primary Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Primary Email field as "Primary Email is required." |  |  | Pass
TC_UpdateEasyCareClaims_14 | To verify if the User is able to Update Easy Care Agreement by leaving the city field unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave city field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for city field as "City is required." |  |  | Pass
TC_UpdateEasyCareClaims_15 | To verify if the User is able to Update Easy Care Agreement by leaving Vehicle Chasis No field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Vehicle Chasis No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Vehicle Chasis No field as "Vehicle Chasis No is required." |  |  | Pass
TC_UpdateEasyCareClaims_16 | To verify if the User is able to Update Easy Care Agreement by leaving Postal Code field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Postal Code field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Postal Code field as "Postal Code is required." |  |  | Pass
TC_UpdateEasyCareClaims_17 | To verify if the User is able to Update Easy Care Agreement by leaving State field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave State field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for State field as "State is required." |  |  | Pass
TC_UpdateEasyCareClaims_18 | To verify if the User is able to Update Easy Care Agreement by leaving the Registration Type field unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Registration Type field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Registration Type field as "Registration Type is required." |  |  | Pass
TC_UpdateEasyCareClaims_19 | To verify if the User is able to Update Easy Care Agreement by leaving the Sales By field unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Sales By field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Sales By field as "Sales By is required." |  |  | Pass
TC_UpdateEasyCareClaims_20 | To verify if the User is able to Update Easy Care Agreement by leaving Executive Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Executive Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Executive Name field as "Executive Name is required." |  |  | Pass
TC_UpdateEasyCareClaims_21 | To verify if the User is able to Update Easy Care Agreement by leaving Sales Manager Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Sales Manager Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Sales Manager Name field as "Sales Manager Name is required." |  |  | Pass
TC_UpdateEasyCareClaims_22 | To verify if the User is able to Update Easy Care Agreement by leaving Registration No field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Registration No field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Registration No field as " Registration No is required." |  |  | Pass
TC_UpdateEasyCareClaims_23 | To verify if the User is able to Update Easy Care Agreement by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required." |  |  | Pass
TC_UpdateEasyCareClaims_24 | To verify if the User is able to Update Easy Care Agreement by leaving Last Service Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave Last Service Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for Last Service Odometer Reading field as " Last Service Odometer Reading is required." |  |  | Pass
TC_UpdateEasyCareClaims_25 | To verify if the User is able to Update Easy Care Agreement by leaving the REC Plan field unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave REC Plan field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for REC Plan field as "REC Plan is required." |  |  | Pass
TC_UpdateEasyCareClaims_26 | To verify if the User is able to Update Easy Care Agreement by leaving REC Retail field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and leave REC Retail field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for REC Retail field as "REC Retail is required." |  |  | Pass
TC_UpdateEasyCareClaims_27 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in First Name and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in First Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | @#@$221 | User is able to update the agreement form by enterng invalid data in First Name field. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in First Name field as "Invalid First Name." | Low | Low | Fail
TC_UpdateEasyCareClaims_28 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Last Name and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Last Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1223@# | User is able to update the agreement form by enterng invalid data in Last Name field. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Name field as "Invalid Last Name." |  |  | Fail
TC_UpdateEasyCareClaims_29 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in GSTIN and enter valid details in the remaining fields. (if YES selected for GSTIN Applicable) | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in GSTIN field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in GSTIN No. field as "Invalid GSTIN No." |  |  | Pass
TC_UpdateEasyCareClaims_30 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Mobile Phone No. and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Mobile Phone No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 143412 | User is able to update the agreement form by enterng invalid data in Mobile Phone No. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Mobile Phone No. field as "Invalid Mobile Phone No." | High | High | Fail
TC_UpdateEasyCareClaims_31 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Primary Email and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Primary Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Primary Email field as "Invalid Primary Email No." |  |  | Pass
TC_UpdateEasyCareClaims_32 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in City and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in City field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@# | User is able to update the agreement form by enterng invalid data in city. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in City field as "Invalid City " | low | low | fail
TC_UpdateEasyCareClaims_33 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Vehicle Chasis No. and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Vehicle Chasis No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Vehicle Chasis No. field as "Invalid Vehicle Chasis No. " |  |  | Pass
TC_UpdateEasyCareClaims_34 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Postal Code and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Postal Code. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 1234 | User is able to update the agreement form by enterng invalid data in Postal Code. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in VPostal Code as "Invalid Postal Code" | low | low | fail
TC_UpdateEasyCareClaims_35 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in State and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in State. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | #$@$@ | User is able to update the agreement form by enterng invalid data in STATE. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in State as "Invalid State." | low | low | fail
TC_UpdateEasyCareClaims_36 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Registration No. and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Registration No. field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !#@#!!rgsdds3235yu | User is able to update the agreement form by enterng invalid data in Registration No. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Registration No. field as "Invalid Registration No. " | low | low | fail
TC_UpdateEasyCareClaims_37 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Executive Name and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Executive field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | !@!@121 | User is able to update the agreement form by enterng invalid data in Executive Name. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Executive Name field as "Invalid Executive Name." | low | low | fail
TC_UpdateEasyCareClaims_38 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Sales Manager Name and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Sales Manager field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | 123@!# | User is able to update the agreement form by enterng invalid data in Sales Manager Name. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Sales Manager Name field as "Invalid Sales Manager Name." | low | low | fail
TC_UpdateEasyCareClaims_39 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Odometer Reading field as "Invalid Odometer Reading." |  |  | Pass
TC_UpdateEasyCareClaims_40 | To verify if the User is able to Update Easy Care Agreement by entering invalid data in Last Service Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Clear and enter invalid data in Last Service Odometer Reading field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Last Service Odometer Reading:2001 Odometer Reading 2000 | User is able to update an agreement by entering odometer reading less than the Last Service Odometer Reading. |  | User should not be able to Update Easy Care Agreement and the system must display a proper and specific validation message for entering invalid data in Last Service Odometer Reading field as "Invalid Last Service Odometer Reading." |  |  | Fail
TC_UpdateEasyCareClaims_41 | To verify if the User is able to Update Easy Care Agreement by entering valid data iin all the mandatory fields. | User is already logged in and is on Editing Easy Care Agreement page. | 1) Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Easy Care Agreement should get Updated followwing a confirmation message as "Easy Care Agreement Successfully Added." |  |  | Pass
TC_UpdateEasyCareClaims_42 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on Editing Easy Care Agreement page. | 1)Click on Cancel Button. 2)Click on the Clear and leave button appearing on the confirmation message. |  |  |  | User should move back to the previous screen. |  |  | pass

## Test_Cases_UpdateEasyCareClaims
Project Name: Renault-EW
Updated By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-21 |  | Review Date:-
Version: - |  |  | Module:- | Update EasyCareClaims |  | Power ID: | 10121
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_UpdateEasyCareClaims_01 | To verify if the User is able to get navigate to the Update Easy Care Claims page. | User is already logged in | 1)Click on the Easy Care Claims available at the menu section. 2)Click on the claim to be update. 3) Click on Edit button. | NA |  |  | Editing Easy Care Claims page should get open having previously filled Easy Care Claim related fields and Save and Cancel button.
TC_UpdateEasyCareClaims_02 | To verify if the User is able to Update Easy Care Claim by leaving all the mandatory fields blank. | User is already logged in and is on Editing Easy Care Claim page. | 1)Clear and Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to Update a Easy Care Claim and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required.
TC_UpdateEasyCareClaims_03 | To verify if the User is able to Update Easy Care Claim by leaving REC Sales Number field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave REC Sales Number fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for REC Sales Number field " REC Sales Number is required." Note: On the basis of REC sales number rest of the Easy Care Claims Details should get appear and they should be non editable
TC_UpdateEasyCareClaims_04 | To verify if the User is able to Update Easy Care Claim by leaving Warranty Admin Name field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Warranty Admin Name field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Warranty Admin Name field " Warranty Admin Name is required."
TC_UpdateEasyCareClaims_05 | To verify if the User is able to Update Easy Care Claim by leaving Dealer Email field blank and enter valid details in the remaining fields. (If Yes is selected for GSTIN Applicable) | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Dealer Email field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Dealer Email field as "Dealer Email is required."
TC_UpdateEasyCareClaims_06 | To verify if the User is able to Update Easy Care Claim by leaving Dealer Contact number field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Dealer Contact Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Dealer Contact field as " Dealer Contact Number is required."
TC_UpdateEasyCareClaims_07 | To verify if the User is able to Update Easy Care Claim by leaving Job Card number field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Job Card Number field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Job Card field as " Job Card Number is required."
TC_UpdateEasyCareClaims_08 | To verify if the User is able to Update Easy Care Claim by leaving Date of Job Card field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Date of Job Card field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Date of Job Card field as "Date of Job Card is required."
TC_UpdateEasyCareClaims_09 | To verify if the User is able to Update Easy Care Claim by leaving the Current PMS Visit field unselected and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Current PMS Visit field unselected. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Current PMS Visit field as " Current PMS Visit is required."
TC_UpdateEasyCareClaims_10 | To verify if the User is able to Update Easy Care Claim by leaving Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1)Clear and Leave Odometer Reading field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Odometer Reading field as "Odometer Reading is required."
TC_UpdateEasyCareClaims_11 | To verify if the User is able to Update Easy Care Claim by leaving Job Card Open Time field blank and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Leave Job Card Open Time field blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for Job Card Open Time field as " Job Card Open Time is required."
TC_UpdateEasyCareClaims_12 | To verify if the User is able to Update Easy Care Claim by entering invalid data in REC Sales Number and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in REC Sales Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in REC Sales Number field as "Invalid REC Sales Number."
TC_UpdateEasyCareClaims_13 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Warranty Admin Name and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Warranty Admin Name field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Warranty Admin Name field as "Invalid Warranty Admin Name."
TC_UpdateEasyCareClaims_14 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Dealer Email and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Dealer Email field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Dealer Email field as "Invalid Dealer Email."
TC_UpdateEasyCareClaims_15 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Dealer Contact Number and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Dealer Contact Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Dealer Contact Number field as "Invalid Dealer Contact Number."
TC_UpdateEasyCareClaims_16 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Job Card Number and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Job Card Number field. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Job Card Number field as "Invalid Job Card Number."
TC_UpdateEasyCareClaims_17 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Date of Job Card and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1)Clear and Enter invalid data in Date of Job Card. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Date of Job Card field as "Invalid Date of Job Card."
TC_UpdateEasyCareClaims_18 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Odometer Reading. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Odometer Reading field as "Invalid Odometer Reading."
TC_UpdateEasyCareClaims_19 | To verify if the User is able to Update Easy Care Claim by entering invalid data in Job Card Open Time and enter valid details in the remaining fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter invalid data in Job Card Open Time. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for entering invalid data in Job Card Open Time field as "Invalid Job Card Open Time."
TC_UpdateEasyCareClaims_20 | To verify if the user is able to Update a easy care claims by uploading invalid file in Invoice Document | User is already logged in and is on Editing Easy Care Claim page. | 1) Upload invalid file in Invoice document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for ethe same.
TC_UpdateEasyCareClaims_21 | To verify if the user is able to Update a easy care claims by uploading invalid file in Job Card Document. | User is already logged in and is on Editing Easy Care Claim page. | 1) Upload invalid file in Job Card document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for ethe same.
TC_UpdateEasyCareClaims_22 | To verify if the user is able to Update a easy care claims by uploading invalid file in Vehicle History Document | User is already logged in and is on Editing Easy Care Claim page. | 1) Upload invalid file in Vehicle History document. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to Update Easy Care Claim and the system must display a proper and specific validation message for ethe same.
TC_UpdateEasyCareClaims_23 | To verify if the User is able to Update Easy Care Claim by entering valid data iin all the mandatory fields. | User is already logged in and is on Editing Easy Care Claim page. | 1) Clear and Enter valid data in all the mandatory fields. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Easy Care Claim should get Updated followwing a confirmation message as "Easy Care Claim Successfully Added."
TC_UpdateEasyCareClaims_24 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on Editing Easy Care Claim page. | 1)Click on Cancel Button. 2)Click on the Leave button appearing on the confirmation message. |  |  |  | User should move back to the previous screen.

## Price_Logic_Change
Project Name: Renault-EW
Updated By:- | Jitendra |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-02-26 |  | Review Date:-
Version: - |  |  | Module:-Price_Logic_Change |  |  | Power ID: | 10175
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
Price_Logic_01 | To verify if the Price flag field is non-editable or freezed or not. | User is already on create agreement page. | 1) Validate the vin number for creatting new agreement. 2)Enter the valid data in all the mandatory fields. |  | Price Flag field is editable. |  | Price Flag field should be non editable and should come on the basisi of Selected Extended Warranty. | High | High | fail
Price_Logic_02 | To verify if the Total price of selected EW while creating an agreement is same as the total price available in EWS Retail Details. |  | 1)Create an agreement and select the best suitable plan. 2) now open the EWS Retail Details of the same selected plan. 3)Compare the details of both. | EWS Retal No EWS3025 | In the agreement details the price is "Customer Price 6240" and in EWS Retail Details of the same plan its "Final Price 6239" |  | details under both the pages should be same. | High | High | fail
Suggestion_Price_Logic_01 | There should be a history of flag changes on the admin portal. | [6 empty] | High | High
Suggestion_Price_Logic_02 | There should be an option tomanage flags on the front-end. | [6 empty] | High | High
Price_Logic_03 | To verify if the updated price is appearing in the new agreement. |  | 1) Edit the price of the ews plan. 2)Create a new agreement against which the same updated ews plan can be selected. 3) Compare the price both in create agreement page and ews details page. |  | Old price is appearing on create agreement page. |  | details under both the pages should be same. | High | High | fail
Price_Logic_04 | To verify if the price flag is getting change by updating the price in the EWS plan against the existing agreeement. |  | 1) Open any agreement. 2) Change the price of the EWS plan from the admin portal which was selected in the in the agreement. 3)Refresh the agreeement page and check tthe prrice flag. |  | Old Price Flag is appearing. |  | Price Flag should not get change. |  |  | Pass
Price_Logic_05 | To verify if the price flag is getting change by updating the the EWS plan against the existing agreeement. |  | 1) Open any agreement. 2) Update the EWS plan from the admin portal which was selected in the in the agreement. 3)Refresh the agreeement page and check tthe prrice flag. |  | Old Price Flag is appearing. |  | Price Flag should not get change. |  |  | Pass
Price_Logic_06 | To verify if the price flag is showing "Reno_OLDPRICE" in the previous agreements. |  | 1) Open any old agreement. 2) Check the Price Flag status. |  | Reno_OLDPRICE is appearing in the price flag. |  | Reno_OLDPRICE should get appear. |  |  | Pass

## Sheet3
MEEBBA00XG1325302
MEEHSRAWEKB029461
MEEHSRSGMKC005173

## Sheet1
http://13.127.10.134/renault_latest/index.php | AGJA-Agra | AM Central Dealer | Welcome@123
http://13.127.10.134/renault_latest/index.php | tvs-renault | TVS | Welcome@123