## Courier Details Update(Claim)
Project Name:-Bosch
Created By:- |  | Sakshi Tiwari |  | Re-Tested By:- |  |  |  | Pre-condition :-
Creation Date:- |  | 09.01.2021 |  | Re-Tested By:- |  |  |  | Developed By :- | Alok
Version: - |  |  |  | Module:- |  | Courier Details Update(Claim)
Module/Test Case ID | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Courier Details_01 | 13445 | 09.01.2021 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button without selecting any claim number. | NA | User was not get redirect to the Courier Details Update page and also there was a proper validation message for the same. |  | User should not get redirect to the Courier Details Update page and also there should be a proper validation message for the same. |  |  | Pass
TC_Courier Details_02 | 13445 | 09.01.2022 | To verify if the user is able to get navigate to the "courier details update" page without selecting any Claim Number having status other than approved. | User is already logged in and is on Add Claim page. | 1)Click on the Courier Details Update button by selecting any claim which is not approved. | NA | There was a proper validation message as "Claim is not approved." |  | there should be a proper validation message as "Claim is not approved." |  |  | Pass
TC_Courier Details_03 | 13445 | 09.01.2023 | To verify if the user is able to get navigate to the "courier details update" by selecting Claim Number. for which the courier details to be update. | User is already logged in and is on Add Claim page. | 1)Select the Claim Number no. for which thee courier details to be update. 2)Click on the Courier Details Update button. |  | User redirected to the concerned page with all the fields and buttons. |  | User should get redirect to the Courier Details Update page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) |  | Pass | Pass
TC_Courier Details_04 | 13445 | 09.01.2024 | To verify if the user is able to update courier details by leaving all the mandatory fields blank. | User is on the "courier details update" page. | 1)Click on the Save buton without entering any data in mandatory fields. | NA | System shows a validation message as "Please Enter Document Courier Date." but the message can revised to " All the mandatory fields marked with * are required so as to make it more appropriate and complete. |  | Courier details should not get update and system should display a proper validation message for leaving all the fields blank. |  |  | Pass
TC_Courier Details_05 | 13445 | 09.01.2025 | To verify if the user is able to update courier details by leaving "Document Send" field unchecked. | User is on the "courier details update" page. | 1)Leave the Document Send checkbox unchecked and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message(Please Select Dealer Document Sent ..) for leaving the Document Send field blank. |  |  | Pass
TC_Courier Details_06 | 13445 | 09.01.2026 | To verify if the user is able to update courier details by leaving the Document Courier Date field blank. | User is on the "courier details update" page. | 1)Leave the Document Courier Date field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message (Please Enter Document Courier Date.)for leaving the Document Courier Date field blank. |  |  | Pass
TC_Courier Details_07 | 13445 | 09.01.2027 | To verify if the user is able to update courier details by leaving the POD Number field blank. | User is on the "courier details update" page. | 1)Leave the POD Number field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for leaving the POD Number field blank. |  |  | Pass
TC_Courier Details_08 | 13445 | 09.01.2028 | To verify if the user is able to update courier details by leaving the Courier Company Name field blank. | User is on the "courier details update" page. | 1)Leave the Courier Company Name field blank and enter valid data in the remaining fields. 2)Click on the Save buton. | NA |  |  | Courier details should not get update and system should display a proper validation message for (Please Enter Courier Company Name.)leaving the Courier Company Name field blank. |  |  | Pass
TC_Courier Details_09 | 13445 | 09.01.2029 | to verify if user is able to Update Courier details by entering valid data in all the fields | User is on the "courier details update" page. | 1)select Document Send 2)select Document Courier Date 3)Enter POD Number 4)Enter Courier Company Name 5) click on save button | 1) date-2021/01/09 2)pod number-123455 3)Courier Company Name-DTDC |  |  | Courier deatails should get update and system should display a proper validation message "Record has been Successfully Submitted....." |  |  | Pass
TC_Courier Details_10 | 13445 | 09.01.2030 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is on the "courier details update" page. | 1)Click on Cancel Button. | NA |  |  | The page should get close. |  |  | Pass
TC_Courier Details_11 | 13445 | 09.01.2031 | To verify claim Details page | user is on the Claim Details page | 1)Click on the claim no |  |  |  | Status sholud change from approved to Post Approval Documents Sent |  |  | Pass
TC_Courier Details_12 | 13445 | 09.01.2032 | to verify Physical Document Tracking | user is on the Claim Details page | 1)Click on the claim no |  |  |  | updatde data should be visible on Physical Document Tracking |  |  | Pass
TC_Courier Details_13 | 13445 | 09.01.2033 | To verify Document Received by Assurant | user logged with manager credentials | 1)Enter url 2)Enter valid user name and pwd 2)click on Claim 3)click on courier details update |  |  |  | should display Document Tracking Panel page having following fields and buttons : 1)Document Send* (Checkbox) 2)Document Courier Date (yyyy-mm-dd).* (Field) 3)POD Number* (Field) 4)Courier Company Name *(Field) 5)Save (Button) 6)Cancel (Button) 7) Document Received*(Checkbox) 8)Document Received Date.*(yyyy-mm-dd).(field) |  |  | Pass
TC_Courier Details_14 | 13445 | 09.01.2034 | to verify Document Tracking Pannel page without selecting Document Received checkbox | user logged on Document Tracking Panel Page with manager credentials | 1)leave the Document Received box and enter the valid data in all the remaining fields 2)click on save |  |  |  | should ask for selecting for Document Received checkbox with proper validation msg "Please Select Document Received" |  |  | Pass
TC_Courier Details_15 | 13445 | 09.01.2035 | to verify if record has been uploaded successfully for claim number with entering with valid data in all the fields | user logged on Document Tracking Panel Page with manager credentials | select date for Document Received Date. And click on save button | Document Received Date-2020-11-19 |  |  | Record should be Successfully Submit and proper validation message should appear " Record has been Successfully Submitted....." |  |  | Pass
TC_Courier Details_16 | 13445 | 09.01.2036 | To verify if the User is able to navigate back to the previous screen by clicking on Cancel button. | User is already logged in and is on Add Claim page. | 1)Click on Cancel Button. | NA |  |  | The page should get close. |  |  | Pass

## SP-Claims
Project Name: BOSCH
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-12-22 |  | Review Date:-
Version: - |  |  | Module:- | SP-Service Request |  | Power ID: | 13445
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Retesting date | Power ID | Status
SP Claims_TC_01 | To verify if the User is able to get navigate to theSP Claims page. | User is already logged in and is on Creating New BOSCH - Claims page. | 1)Enter valid URL 2)Login with valid user name pwd 3)Click on SP-Service request module 4)Click on +Add Servvice request | 1)URL-http://13.126.69.89/bosch/index.php 2)User name-bhavya-123 and pwd-Welcome@1234567 |  |  | User should get navigate to the Creating New BOSCH - Claims |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_02 | To verify if the User is able to get navigate to theSP Claims page. | User is already logged in | 1)Click on theSP Claims available at the menu section. 2)Click on the claim to be update. |  |  |  | Creating New BOSCH - Claims page should get open having related fields and Save and Cancel button. |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_03 | To verify the Creating New BOSCH-Claims page | User is on Creating New BOSCH-Claims page |  |  | There is minor alignment for Previous Visit Date |  | all the mandatory fileds and alignment should be proper |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_04 | To verify if the User is able toCreating New BOSCH - Claims by leaving all the mandatory fields blank. | User is already logged in and is on Creating New BOSCH - Claims page. | 1)Leave all the mandatory fields blank. 2)Click On Save Button. |  |  |  | User should not be able to create a new New BOSCH - Claims and the system must display a proper and specific validation message for each mandatory field as required. " All the mandatory fields marked with * are required. |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_05 | To verify if the User is able to create New BOSCH - Claims by leaving Service Package number field blank and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1) Leave Service Package number fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create New BOSCH - Claims and the system must display a proper and specific validation message for REC Sales Number field " This field is required." Note: On the basis of REC sales number rest of the Easy Care Claims Details should get appear and they should be non editable |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_06 | To verify if dealer is able to select an agreement for claim to punch | User is already logged in and is on New BOSCH - Claims page. | 1)Select Service package number | Service Package number BSP207111 |  |  | Dealer should be able to Service package number for claim to punch |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_07 | To verify if All the agreement details will get auto populated in the respective fields. | User is already logged in and is on New BOSCH - Claims page. | 1)Select Service package number | Service Package number BSP207111 |  |  | All the agreement details should get auto populated in the respective fields. |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_08 | To verify if the User is able to create New BOSCH - Claims by leaving Job Card No field blank and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1) Leave Job Card No fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create New BOSCH - Claims and the system must display a proper and specific validation message for Service package Number field " This field is required." Note: On the basis of REC sales number rest of the Claims Details should get appear and they should be non editable |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_09 | To verify if the User is able to create New BOSCH - Claims by leaving Date of Job Card field blank and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1) Leave Date of Job Card fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Job card no-23232323232 |  |  | User should not be able to create New BOSCH - Claims and the system must display a proper and specific validation message for service package Number field " This field is required." Note: On the basis of Service package number rest of the Claims Details should get appear and they should be non editable |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_10 | To verify if the User is able to create New BOSCH - Claims by leaving Current Visit Odometer Reading field blank and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1) Leave Current Visit Odometer Reading fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | User should not be able to create New BOSCH - Claims and the system must display a proper and specific validation message for service package Number field " This field is required." Note: On the basis of Service package number rest of the Claims Details should get appear and they should be non editable |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_11 | To verify if Dealer is able to enter the Job Card Number and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1)Enter valid data in Job Card Number field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Job Card-FDGRTGI8RET |  |  | Dealer should be able to create New BOSCH-Claims |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_12 | To verify the by entering the data I job card number | User is already logged in and is on New BOSCH - Claims page. | Enter job card number 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Job Card-FDGRTGI8RET | Job card is accepting Alphanumeric and Caps |  | Job card no should be Min 7 Characters or max 11 alphanumeric and user is able to claim |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_13 | To verify if Dealer is able to enter the Date of Job Card and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1)Enter valid data in Date of Job Card field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job Card 06-11-2020 |  |  | Dealer should be able to create New BOSCH-Claims and there should be validation for Date of Job Card |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_14 | To verify by selecting the back date of job card no and enter valid details in all the fileds | User is already logged in and is on New BOSCH - Claims page. | 1)Enter valid data in Date of Job Card field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Date of Job Card 11.01.2021 | All the non editable fields are getting editable and also service part setion is getting hide |  | Date of Job card should be same as plan punched date or greater than that and usre is able to claim successfully |  |  | Fail | 2021-01-18 | 13622 | pass
SP Claims_TC_15 | To verify if Dealer is able to enter theCurrent Visit Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1)Enter valid data in Current Visit Odometer Reading field 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Dealer should be able to create New BOSCH-Claims |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_16 | To verify by entering the unlimited value in Current Visit Odometer Reading and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1)Enter unlimited data in Current Visit Odometer Reading field 2)Enter valid details in the remianing fields. 3)Click On Save Button. | Current Visit odometer Reading-50000 |  |  | Current odometer reading not be greater than the SP END KM and there should be a proper validation"Please Enter less than SP End KM" |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_17 | To verify if the User is able to create New BOSCH - Claims by leaving Service outlet Comment field blank and enter valid details in the remaining fields. | User is already logged in and is on New BOSCH - Claims page. | 1) Leave Service outlet Comment fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Dealer should not be able to create new BOSCH-Claims |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_18 | To verify if Data in fields like previous visit Odometer reading & Current visit will auto populate based on the plan taken by the customer | User is already logged in and is on New BOSCH - Claims page. |  |  |  |  | Data in fields like previous visit Odometer reading & Current visit should auto populate based on the plan taken by the customer |  |  | Fail | 2021-01-18 | 13622 | pass
SP Claims_TC_19 | To Verify if Dealer by checking the current PMS | User is already logged in and is on New BOSCH - Claims page. |  |  |  |  | Dealer should be able to check the current PMS Visit that needs to be carried out |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_20 | To verify the Service Part section | User is already logged in and is on New BOSCH - Claims page. | Checking the service part section Grid |  |  |  | Service part section should have the following column: 1.SI 2.select(CheckBox) 3.Part Code(Mandatory) 4.Part Description 5.HSN / SAC Code 6.Total Visit 7.Qty Per Occurrence 8.Cost 9.GST 10.IGST 11.Sgst 12.CGST 13.Actual Cost Per Unit Including Tax 14.Total cost |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_21 | To verify if by leaving Part Code Column for all part descriptions | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | 1) Leave Part Code fields blank. 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  | Dealer should not be able to create new BOSCH-Claims and There should be validation for Part value "This field is required." |  |  | pass | 2021-01-18 | 13622 | pass
SP Claims_TC_22 | To verify if dealer is able to save the claim by Uncheck for labour | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | 1.Uncheck the labour 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  | Claim is getting punched |  | Dealer should not be able to create new BOSCH-Claims and There should be validation message gor labour "This is mandatory Part.." |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_23 | To verify Grid section(Service part) -Check if dealer is able to create claim by uncheck the Engine oil part | User is already logged in and is on New BOSCH - Claims page and the service part grid | 1.Uncheck the Engine Oil part 2.Check all the part and save |  |  |  | dealer should be able to Save the claim successfully |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_24 | To verify Grid section(Service part) -Check if dealer is able to create claim by uncheck the oil Filter part | User is already logged in and is on New BOSCH - Claims page and the service part grid | 1.Uncheck the Oil Filter part 2.Check all the part and save |  |  |  | dealer should be able to Save the claim successfully |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_25 | To verify Grid section(Service part) -Check if dealer is able to create claim by uncheck the Air Filter part | User is already logged in and is on New BOSCH - Claims page and the service part grid | 1.Uncheck theAir Filter part 2.Check all the part and save |  |  |  | dealer should be able to Save the claim successfully |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_26 | To verify Grid section(Service part) -Check if dealer is able to create claim by Drain Plug Washer part | User is already logged in and is on New BOSCH - Claims page and the service part grid | 1.Uncheck the Drain Plug Washer part 2.Check all the part and save |  |  |  | dealer should be able to Save the claim successfully |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_27 | To verify Grid section(Service part) if Part Code for all part | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | Save the form with Entering data into the Part Code for all the part description(Engine Oil ,Oil Filter,Air Filter,Drain Plug Washer,Labour) | Engine Oil -EO12 Oil Filter-EO13 Air Filter-EO14 Drain Plug Washer-EO15 Labour-EO19 |  |  | Dealer should be able to create new BOSCH-Claims |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_28 | To verify Grid section(Service part)To Verify Ammount calculation-Check the total amount for the selected model and plan | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | Matching the cost with master against the model and plan type | Model-Vento fuel type-Petrol plan type-Maxcare Plus | Total cost is reflecting correct according to the master |  | Total cost should match with master against the claim |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_29 | To verify Grid section(Service part)To verify if the dealer is able to Edit the fields in the PMS grid | User is already logged in and is on New BOSCH - Claims page. | Changing the values of Qty Per Visit,Cost Greater than master values | Qty Per Visit-100,Cost-7000 |  |  | dealer should not be able to Enter the values of Qty Per Visit,Cost greater than as per the master and have a proper validation |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_30 | Grid section(Service part)To verfiy if Dealer is selecting the quantity and enter the amount corresponding against each line item flashing for the plan taken | User is already logged in and is on New BOSCH - Claims page. |  |  |  |  | Dealer should be able to select the quantity and also enter the amount corresponding against each line item flashing for the plan taken Note*(Based on which the grand total value will calculated) |  |  | master not updated | 2021-01-18 | 13622 | pass
SP Claims_TC_31 | To verify Grid section(Service part)Price logic-To verify the price logic by selecting the service package number BSP207130 | User is already logged in and is on New BOSCH - Claims page. |  |  |  |  | 1.Actual cost Including GST autopopulate 2.Part Description(Non editable) 3.Total Visit(Non editable) 4.Qty Per Occurrence(Editable but should not exceed with the master value ) |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_32 | Grid section(Service part)To verify the GST% with 18 and 28 is for oil filter, Air filter and Drain plug master | User is already logged in and is on New BOSCH - Claims page. | Comparing the data with the master | Engine Oil -18 Oil Filter-18 and 28 Air Filter-18 and 28 Drain Plug Washer-18 and 28 Labour-18 |  |  | GST% with 18 and 28 as per the requirement |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_33 | Grid section(Service part)To verify the value of drop down for Engine Oil | User is already logged in and is on New BOSCH - Claims page. | Click on drop down | Engine Oil -18 | Engine Oil -18 |  | Engine Oil -18 and should be freezed |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_34 | Grid section(Service part)To verify the value of drop down for Oil Filter | User is already logged in and is on New BOSCH - Claims page. | Click on drop down | Oil Filter -18 and 28 | Oil Filter -18 and 28 |  | Drop has both the value for Oil Filter-18 & 28 and should be freezed |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_35 | Grid section(Service part)To verify the value of drop down for Air Filter | User is already logged in and is on New BOSCH - Claims page. | Click on drop down | Air Filter -18 and 28 | Air Filter -18 and 28 |  | Drop has both the value for Air Filter-18 & 28 and should be freezed |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_36 | Grid section(Service part)To verify the value of drop down for Brain plug washer | User is already logged in and is on New BOSCH - Claims page. | Click on drop down | Drain Pluf Washer-18 & 28 | Drain Pluf Washer-18 & 28 |  | Drop has both the value for Drain Pluf Washer-18 & 28 and should be freezed |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_37 | Grid section(Service part)To verify the value of drop down for Labour | User is already logged in and is on New BOSCH - Claims page. | Click on drop down | Labour -18 | Labour -18 |  | Labour -18 and should be freezed |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_38 | Grid section(Service part) To verify if the Mrp for the selected plan | User is already logged in and is on New BOSCH - Claims page. | Matching the MRP with master against the model and plan type |  | MRP calculation is reflecting correct |  | MRP value should not Exceed with the value given in the master note:MRP Should not cross Actual cost. |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_39 | Grid section(Service part) To verify by entering the Part code for all the parts | User is already logged in and is on New BOSCH - Claims page. | Enter part code | Part code -!"££$ | Part code is accepting wrong data |  | There should be validation for Part code and accept alphanumeric ans caps Lk |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_40 | Grid section(Service part) -to verify by entering the HSN/SAC value for all the parts | User is already logged in and is on New BOSCH - Claims page. | Enter invalid value HSN/SAC field | HSN/SAC-!"££$$ | HSB/SAC code is Accepting wrong data |  | There should be validation for HSN?SAC code and accept alphanumeric ans caps Lk |  |  | Fail | 2021-01-18 | 13622 | pass
SP Claims_TC_41 | To verify by if the User is Able to Create Service Request by entering the valid data in all the mandatory fields | User is already logged in and is on New BOSCH - Claims page. | Enter valid data in all the fields |  |  |  | Daeler should be able create service requset successfully and Before saving the service request a pop should come “Ensure you have a selected the parts and unit value is entered correctly as per the Tax invoice” |  |  | Fail | 2021-01-18 | 13622 | pass
SP Claims_TC_42 | To verify if the Dealer is able to download the certificate | User is already logged in and is on Claims page BSP207121 | 1.Click on The link Print Claim From | Claim number-BSPC712 | Certificate generated and all the data are sh0wing according the requirement and service part section getting populating in the respective Grid |  | Dealer should able to print the certificate successfully |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_43 | To verify the certificate | User is already logged in and is on Certificate page for BSP207121 | Observing the Service part Grid |  | Certificate Tax break up HSN /SAC code is captured along with all the details |  | Certificate Tax break up HSN /SAC code should captured along with all the details |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_44 | To verify if HO is able to edit the Claim and also able to Edit Service part grid | TVS-HO is logged into the sysytem | 1.Login with valid User id and pwd 2.Select The BSP207121 3.Uncheck the Oil Filter | Claim number-BSPC712 |  |  | TVS-HO should be able to Edit the claim and save the claim |  |  | Pass | 2021-01-18 | 13622 | pass
SP Claims_TC_45 | To verify if all the data is autopopulating entered by dealer while editing by the claim manager | TVS-HO is logged into the sysytem | 1.Login with valid User id and pwd 2.Select The BSP207121 3.Uncheck the Oil Filter |  |  |  | All the entered data should refelect entered by the dealer and claim manager should be able to Edit the claim |  |  |  | 2021-01-18 | 13622 | pass
SP Claims_TC_46 | To verify by downloading the report for BSP207121 | TVS-HO is already logged in and on observing the data in the generated certificate | 1.Click on The link Print Claim From |  | Certificate generated and all the data are sh0wing according the requirement and service part section getting populating in the respective Grid |  | Changed certificate should get print after Changing the Claim by TVS HO |  |  | Pass | 2021-01-18 | 13622 | pass

## PolicyExpired
Project Name: BOSCH
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-12-22 |  | Review Date:-
Version: - |  |  | Module:- | SP-Service Request |  | Power ID: | 13445
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
Sp-ServiceRequest_TC1 | To verify the policy number by Taking all the pms | Dealer is logged into the system | 1.Avail all the pms and check the policy number |  | Policy is getting expired |  | User should not be able to Claim once all the PMS has been availed and Policy shouled get expired |  |  | pass
Sp-ServiceRequest_TC2 | To verify the Status of the policy number | Dealer is logged into the system | Click on SP-Sales and check the status of the same policy number next day |  | Policy is getting expired |  | Policy status should change Active to Expired |  |  | pass
Sp-ServiceRequest_TC3 | To verify the policy number by Taking all the Srvieces for Odometer reading | Dealer is logged into the system | check the policy number availed the Service based on odometer |  | Policy is not getting expired after |  | User should not be able to Claim Based on End Km Availed and Policy shouled get expired |  |  | pass
Sp-ServiceRequest_TC4 | To verify the Status of the policy number based on agreement Expire date | Dealer is logged into the system | Click on SP-Sales and check the status of the same policy number next day |  |  |  | Policy status should change Active to Expired |  |  | Pass

## UpdateOdometer
Project Name:->Renault EW
Created By:- | Sakshi Tiwari |  |  |  | Re-Tested By:- | Sakshi |  | Pre-condition :-
Creation Date:- | 2020-12-28 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Alok
Version: - |  |  |  |  | Module:- | Update Odometer
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
UpdateOdometer_TC1 | 13389 | 2020-12-28 | To verify if the able to update the currect odometer reading for the Existing policy | Dealer is logged | 1)Click on + Update Odometer |  |  |  | ask for Updating the odometer and pop-up should open the Do you want to current odometer reading and status |  |  | Pass
UpdateOdometer_TC2 | 13389 | 2020-12-28 | To verify the page | [5 empty] | pop[-Up having following fields 1.Agreement No 2.Chassis No 3.Current Odometer 4.Update and Close (Button) |  |  | Pass
UpdateOdometer_TC3 | 13389 | 2020-12-28 | To verfiy by clicking on Close button |  |  |  |  | Back to previous page | User should be able to close the pop up. |  |  | Pass
UpdateOdometer_TC4 | 13389 | 2020-12-28 | To verify if the User is able to Update the odometer by leaving all the mandatory fields blank. | User is already logged in and is on Creating New Service Package page. | 1)Leave all the mandatory fields blank. 2)Click On Update Button. |  |  | Valist | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC5 | 13389 | 2020-12-29 | To verify if the User is able to Update odometer by leaving Agreement number field blank and enter valid details in the remaining fields. | User is already logged in and is on Creating New Service Package page. | 1) Leave Agreement No fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MNC12334556778888 Current Odometer-70000 | As expected | MNC12334556778888 | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC6 | 13389 | 2020-12-30 | To verify if the User is able to Update odometer by leaving Chassis No field blank and enter valid details in the remaining fields. | User is already logged in and is on Creating New Service Package page. | 1) Leave Chessis No fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Agreement No-BSP207132 Current Odometer-70000 | Validation Message showing "Please Fill All Fields" |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC7 | 13389 | 2020-12-31 | To verify if the User is able to Update odometer by leaving Chassis No field blank and enter valid details in the remaining fields. | User is already logged in and is on Update odometer pop up page | 1) Leave Current Odometer fields blank. 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MNC12334556778888 Agreement number-BSP207132 | Validation Message showing "Please Fill All Fields" |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Please Fill All Fields" |  |  | Pass
UpdateOdometer_TC8 | 13389 | 2021-01-01 | To verify if the User is able to Update Current odometer by entering the Reading less than REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Less than SP end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MNC12334556778888 Agreement number-BSP207132 Current odometer -5000 | Validating message appear Current odometer reading should be greater than SP end km |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Current odometer reading should be greater than SP end km" |  |  | Fixed
UpdateOdometer_TC9 | 13389 | 2021-01-02 | To verify if the User is able to Update Current odometer by entering the Reading Equal to the REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Equal to the SP end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC003KA012501 Agreement number-BSP207132 Current odometer -10000 | Validating message appear Current odometer reading should be greater than SP end km |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Current odometer reading should be greater than SP end km" |  |  | Fixed
UpdateOdometer_TC10 | 13389 | 2021-01-03 | To verify if the user is able to Update Current Odometer by Enetring the data greater than REC end km | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Greater than the SP end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC003KA012501 Agreement number-BSP207132 Current odometer -99999999999999 |  |  | User should not be able to Update odometer Reading and the system must display a proper and specific validation message "Data Updated Successfully" |  |  | Pass
UpdateOdometer_TC11 | 13389 | 2021-01-03 | To verify if the data is updated when dealer is forcefully expired the policy | Admin and Cliam manager is logged into the system | 1.)Login with admin or Claim manager 2.Open the policy number which is expired by the Dealer 3.Check the Backend punching section |  | New Field is added on backend Puchind section(Odometer On Expiry ) and Expired reseon, Expiry Date only on Admin side |  | Updated data for Odometer On Expiry should be refelect on the Admin and Claim manager side |  |  | Fail
UpdateOdometer_TC12 | 13389 | 2021-01-04 | To verify if the user is able to expire the policy forcefully by updating the odometer reading | User is already logged in and is on Update odometer pop up page | 1) Enter Current Odometer fields Greater than the REC end km 2)Enter valid details in the remianing fields. 3)Click On Update Button. | Chassis No-MEERBC003KA012501 Agreement number-REC3459 Current odometer -70000(More than Rec end km) | Odometer is updated successfully |  | User should be able to expire the policy forcefully by entering the odometer reading more than the REC End KM and status to be changed Expired |  |  | Pass

## BugReport
Bug Report
Project :- |  | Bosch
Created_By :- |  | Sakshi Tiwari
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments
07.01.2021 | SP Claims_TC_03 | Bug ID_1 | 13445 | There is minor alignment for Previous Visit Date | User is on Creating New BOSCH-Claims page | [5 empty] | new | Alok
07.01.2021 | SP Claims_TC_04 | Bug ID_2 | 13445 | Service Package Plan reflecting incorrect data after claim saved | User is already logged in and is on New BOSCH - Claims page. | 1)Select Service package number | Service Package number BSP207111 |  |  |  | Fixed | Alok
07.01.2021 | SP Claims_TC_05 | Bug ID_3 | 13445 | Date of job card is accepting more than 15 days from the current date | User is already logged in and is on New BOSCH - Claims page. | 1)Enter valid data in Date of Job Card field 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  |  | Fixed | Alok
07.01.2021 | SP Claims_TC_06 | Bug ID_4 | 13445 | Dealer is able save the claim after entering the reading which is grater than SP END KM | User is already logged in and is on New BOSCH - Claims page. | 1)Enter unlimited data in Current Visit Odometer Reading field 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  |  | Fixed | Alok
07.01.2021 | SP Claims_TC_07 | Bug ID_5 | 13445 | Current visit fields is missing logic and aslo visiting multiple of time | User is already logged in and is on New BOSCH - Claims page. | [5 empty] | Fixed | Alok
07.01.2021 | SP Claims_TC_08 | Bug ID_6 | 13445 | There is no SAC/HSN column in the grid as the requirement | Checking the service part section Grid | [5 empty] | Fixed | Alok
07.01.2021 | SP Claims_TC_09 | Bug ID_7 | 13445 | Claim is getting punched without entering any data into the Part Code | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | 1.Uncheck the labour 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  |  | Fixed | Alok
07.01.2021 | SP Claims_TC_10 | Bug ID_8 | 13445 | Dealer is able to Exceed the qty and cost | User is already logged in and is on New BOSCH - Claims page and checking the service part grid | Changing the values of Qty Per Visit,Cost Greater than master values | Qty Per Visit-100,Cost-7000 |  |  |  | Fixed | Alok
14.01.2021 |  | Bug ID_9 |  | All the non editable fields are getting editable and also service part setion is getting hide | User is already logged in and is on New BOSCH - Claims page. | 1)Enter Bake date in in Date of Job Card from the privious vist date field 2)Enter valid details in the remianing fields. 3)Click On Save Button. |  |  |  |  | Fixed | Alok
14.01.2021 | SP Claims_TC_39 | Bug ID_10 |  | Part code is accepting wrong data | User is already logged in and is on New BOSCH - Claims page. | Enter part Incorrect part code | Part Code-1!"£$%^^& |  |  |  | Fixed | Alok
14.01.2021 | SP Claims_TC_40 | Bug ID_11 |  | HSB/SAC code is Accepting wrong data | User is already logged in and is on New BOSCH - Claims page. | [5 empty] | Fixed
14.01.2021 | SP Claims_TC_41 | Bug ID_12 |  | Grid is not proper as the requirement | User is already logged in and is on New BOSCH - Claims page. | Enetr valid data in all the mandatory fields |  |  |  |  | Fixed | Alok
| UpdateOdometer_TC11 | Bug ID_13 |  | New Field is added on backend Puchind section(Odometer On Expiry ) and Expired reseon, Expiry Date only on Admin side | Admin and Cliam manager is logged into the system | 1.)Login with admin or Claim manager 2.Open the policy number which is expired by the Dealer 3.Check the Backend punching section |  |  |  |  | Fixed | Alok
2021-01-30 | SP-Service Request Report_TC14 | Bug ID_14 | 13761 | Oil Filter and Labour details are missing in the Report | User is logged into the System | 1)Match all the Part / Labour details in the Generated SP-Service Request Report |  |  | High | High | New | Alok
2021-01-30 | SP-Service Request Report_TC15 | Bug ID_15 | 13761 | Plan Type is not there in the generated report | User is logged into the System | 1)Check the Plan type(Max care/Max care Plus) |  |  | High | High | New | Alok
2021-01-30 | SP-Service Request Details Report _TC1 | Bug ID_16 | 13761 | Dealer and Manager is not able to download the SP- service request Details report only Admin can be able to Download | User is logged into the System | 1)Click on the Reports available at the menu section. 2)Click on the SP- service request Details report 3)selecting valid date for start and end date | Start date=2021-01-30 End Date=2021-01-30 |  | High | High | New | Alok
|  | Bug ID_17 | 13761 | When User is Click on Save Button Without Entering any data into the mandatory Fields then System Directly showing the validation message"5) Before saving the service request a pop should come “Ensure you have a selected the parts and unit value is entered correctly as per the Tax invoice” Before Sowing the Validation message for to fill the Required field | User is logged into the System

## SP-ServiceRequestDetailsReports
Project Name: BOSCH
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-12-22 |  | Review Date:-
Version: - |  |  | Module:- | SP-Service Request Details Report |  | Power ID: | 13445
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Retesting date | Power ID | Status
SP-Service Request Details Report _TC1 | To verify if User(Dealer,Admin,Manager) is able to download the SP-Service Request Report | Dealer is logged into the System | 1)Click on the Reports available at the menu section. 2)Click on the SP- service request Details report 3)selecting valid date for start and end date | Start date=2021-01-30 End Date=2021-01-30 | Dealer and Manager is not able to download the SP- service request Details report only Admin can be able to Download | https://lh3.googleusercontent.com/-Hd9yDsQ2r3U/YBUH_CIPa7I/AAAAAAAAAWY/ywmDMLl9aVsevV0Ht9LAb3jio_4t8dffACK8BGAsYHg/s0/2021-01-29.png | System should allow to generate the report for SP- service request Details report | High | High | Fail

## SP-ServiceRequest Report
Project Name: BOSCH
Updated By:- | Sakshi Tiwari |  | Reviewed By:- |  |  | Developed By: | Alok Srivastava
Creation Date:- | 2020-12-22 |  | Review Date:-
Version: - |  |  | Module:- | SP-Service Request Report |  | Power ID: | 13761
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Retesting date | Power ID | Status
SP-Service Request Report_TC1 | To verify if User(Dealer,Manager,Admin) is able to download the SP-Service Request Report | Dealer is logged into the System | 1)Click on the Reports available at the menu section. 2)Click on the service request report 3)selecting valid date for start and end date | Start date=2021-01-30 End Date=2021-01-30 | User is downloading the SP-service request report |  | System should allow to generate the report for SP-service request report |  |  | Pass
SP-Service Request Report_TC2 | To verify the Generated Report | Dealer is logged into the System | 1)Match all the details of downloading Report with the Details page of Service Request |  |  |  | All the details should be simmilar to the Service request detail page |  |  | Pass
SP-Service Request Report_TC3 | To verify the Service Request number of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Service request number with Generated SP-Service Request Report |  | Service Request number is matching |  | the Service Request number of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC4 | To verify the Agreement Number of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Agreement Number with Generated SP-Service Request Report |  | Agreement Number is matching |  | the Agreement Number of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC5 | To verify the Customer name of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Customer name with Generated SP-Service Request Report |  | Customer name is matching |  | the Customer name of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC6 | To verify the Service Request Status of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Service Request Status of with Generated SP-Service Request Report |  | Service Request Status of is matching |  | the Service Request Status of of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC7 | To verify the Vehicle Brand of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Vehicle Brandwith Generated SP-Service Request Report |  | Vehicle Brand is matching |  | the Vehicle Brand of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC8 | To verify the Vehicle Model of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Vehicle Model with Generated SP-Service Request Report |  | Vehicle Model is matching |  | theVehicle Model of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC9 | To verify the Vehicle Chassis No of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Vehicle Chassis No with Generated SP-Service Request Report |  | Vehicle Chassis No is matching |  | the Vehicle Chassis No of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC10 | To verify the Service Package Start Date and End Date of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Service Package Start Date and End Date with Generated SP-Service Request Report |  | Service Package Start Date and End Date is matching |  | theService Package Start Date and End Date of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC11 | To verify the SP Start KM and End KM of Generated SP-Service Request Report | Dealer is logged into the System | 1)MatchSP Start KM and End KM with Generated SP-Service Request Report |  | SP Start KM and End KM is matching |  | the SP Start KM and End KM of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC12 | To verify the Job Card No and date od Job Card of Generated SP-Service Request Report | Dealer is logged into the System | 1)Match Job Card No and date od Job Card with Generated SP-Service Request Report |  | Job Card No and date od Job Card is matching |  | the Job Card No and date od Job Card of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC13 | To verify the Previous Visit Odometer Reading and Current Visit Odometer Reading of Generated SP-Service Request Report | Dealer is logged into the System | 1)MatchPrevious Visit Odometer Reading and Current Visit Odometer Reading with Generated SP-Service Request Report |  | Previous Visit Odometer Reading and Current Visit Odometer Reading is matching |  | the Previous Visit Odometer Reading and Current Visit Odometer Reading of Generated SP-Service Request Report should same as created Service request details page |  |  | Pass
SP-Service Request Report_TC14 | To verify the Part/Labour Details in Generated SP-Request Report | Dealer is logged into the System | 1)Match all the Part / Labour details in the Generated SP-Service Request Report | Service Package number BSP207138 | Oil Filter and Labour details are missing in the Report |  | In the generated Report all the Part /Labour Details should show which is Part/Labour taken by the Customer |  |  | Pass
SP-Service Request Report_TC15 | To verify by the Plan Type in the Generated Report | Dealer is logged into the System | 1)Check the Plan type(Max care/Max care Plus) |  | Plan Type is not there in the generated report |  | Plan Type should be there in the Generated Report |  |  | Fail

## Summary
BOSCH
Lead Dev: Alok Srivastava
Module | No. of test Written | No. of test executed | Pass | Fail | Suggestions
SP-Service Request | 46 | 46 | 45 | 0 | 1
Courier Details Update(Claim) | 16 | 16 | 16 | 0 | 0
SP-Service Request Details Report | 1 | 1 | 0 | 1 | 0
SP-Service Request Report | 15 | 15 | 13 | 1 | 1
Update Odometer | 12 | 12 | 12 | 0 | 0
Total | 90 | 90 | 86 | 2 | 1
[6 empty] | arranty | 1year
|  | d Warranty EW932/3 Year/ 50000 Kms |  |  | arranty ATW24/1year/20000 KM

## GeneratedReport
Sr.No. | Service Request | Agreement Number | Customer name | Service Request Status | Assigned To | Registration No | Vehicle Brand | Vehicle Model | Vehicle Category | Vehicle Chassis No | Service Package Start Date | Service Package End Date | SP Start KM | SP End KM | Job Card No | Date of Job Card | Previous Visit Odometer Reading | Current Visit Odometer Reading | Service Advisor Name | Service Outlet Comment | Engine oil | Cost Per Unit | Actual Cost Per Unit Including Tax | Qty Per Visit | Total Cost | Engine oil filter | Cost Per Unit | Actual Cost Per Unit Including Tax | Qty Per Visit | Total Cost | LABOR WITH GST | Cost Per Unit | Actual Cost Per Unit Including Tax | Qty Per Visit | Total Cost | AIR FILTER WITH GST | Cost Per Unit | Actual Cost Per Unit Including Tax | Qty Per Visit | Total Cost | FUEL FILTER WITH GST | Cost Per Unit | Actual Cost Per Unit Including Tax | Qty Per Visit | Total Cost | Final Invoice Amount | Approved Claim Amount as per Invoice | Created Date
1 | BSPC750 | BSP207138 | SSS DDD | Auto Approved | Test | EEEE | Hyundai | GETZ 1.1 L |  | DDDDD324443444444 | 2021-01-19 | 2025-01-18 | 40000 | 80000 | DD677667676 | 2021-01-23 | 69087 | 79000 | Test | hdhdh | Yes | 100 | 1085 | 3.1 | 365.8 | [10 empty] | Yes | 70 | 190 | 1 | 89.6 | [5 empty] | 1763.4 |  | 2021-01-30 11:32