## Digital Apk-Bugs
Bug Report
Project :- |  | MPartner-Digital APK |  |  |  |  | Lead_Devp. :- |  | Shalu
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 12567
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Status | Retesting Power ID | Retesting Date | Testers Comments | Open_Date | Close_Date
12567 | NA | 1 | App is getting crash when clicking on Add coupon symbol(+) with blank input. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2)Click on "+" icon without entering any input. |  | Video have been shared on hangout | High | High | Fixed | Shalu | done | 12598 | 13-10-2020
12567 | NA | 2 | App is getting crash when clicking on Add coupon symbol(+) with Invalid input. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter invalid data in coupn number field. 3) Click On "+" icon. | 1.5, Alphbets, special charecters etc | Video have been shared on hangout | High | High | Fixed | Shalu | done | 12598 | 13-10-2020
12567 | NA | 3 | Assigned coupons should get deducted from the total eligible coupons and should get added in the "Balance Coupons" bucket. As total eligible coupons before assigning was 50, and after assiging 5 from it. App should have dispyaed balance coupons but App still shows 0 balance coupons. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter valid data in coupn number field. 3) Click On "+" icon. 4) Check the total balance coupons. | 5 |  | High | High | Fixed | Shalu | Backend side (tested done) | 12598 | 13-10-2020
12567 | NA | 4 | Count of Assigned coupons should get Added in the "Used Coupons" bucket. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) Enter valid data in coupn number field. 3) Click On "+" icon. 4) Check the total eligible coupons. | 5 |  | High | High | Fixed | Shalu | Backend side (tested done) | 12598 | 13-10-2021
12567 | NA | 5 | App goes into forever "Please Wait" state when clicking on Resend OTP link under Terms and Conditions OTP verification. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  |  | High | High | Fixed | Shalu | done | 12598 | 13-10-2021
12567 | NA | 6 | App goes into forever "Please Wait" state when clicking on Resend OTP link under Terms and Conditions OTP verification. | User is logged in as a dealer. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  |  | High | High | Fixed | Shalu | done | 12598 | 13-10-2021
12567 | NA | 7 | There should be a maximum input character limit in the T&C otp, It should be same as the actual OTP length. | User is logged in as a dealer and distributor. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) click on Resend OTP link. |  | https://prnt.sc/uw2szk | High | High | Not Fixed | Shalu | please ask to rahul sir and jyoti ma'am, its should get change but , this aap is runing since 3 year , there is no any feedback from client side | 12598 | 13-10-2022 | You need to ask them and take action on it accordingly.
12567 | NA | 8 | At Gift Cards screen: There is a duplicacy of coupons appearing under Gift Cards when logged in as dealer. As there are two "Yesterday" headers under which coupns are available. | User is logged in as a dealer. | 1) Click on Super 7 menu option. 2) click on the check box and press continue. 3) check the gift cards screen. |  | Video have been shared on hangout | High | High | Not Fixed | Ravi | Backend side (tested done) | 12598 | 13-10-2022
12567 | NA | 9 | App is getting crash when dealer opens Super7 screen. | User is logged in as a dealer. | 1) Click on Super 7 menu option. |  | Video have been shared on hangout | High | High | Fixed | Shalu | done | 12598 | 13-10-2022
12567 | NA | 10 | App is getting crash when distributor opens Super7 screen. | User is logged in as a dealer. | 1) Click on Super 7 menu option. |  | Video have been shared on hangout | High | High | Fixed | Shalu | done | 12598 | 13-10-2023
12598 | NA | 11 | App does not show any error message for submitting blank coupons by the distributor in the Gift Cards section. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2)Click on submit button. |  |  | High | Low | New | Shalu |  | 12598 | 13-10-2023
12598 | NA | 12 | App does not show any error message for submitting coupons by leaving the “Dealer” field blank in the Gift Cards section. | User is logged in as a distributor | 1) Click on Super 7 menu option. 2)Leave dealer field blank and enter valid data in remaining fields. 3)Click on submit button. |  |  | High | Low | New | Shalu |  | 12598 | 13-10-2023
12598 | NA | 13 | App does not show any error message for submitting coupons without adding(+) coupons before submitting. | User is logged in as a dealer and distributor. | 1) Click on Super 7 menu option. 2)Do not click on + icon and enter valid data in remaining fields. 3)Click on submit button. |  |  | High | Low | New | Shalu |  | 12598 | 13-10-2024
12598 | NA | 14 | T&C OTP: after hitting the resend link, already entered OTP should get reset. | User is logged in as a dealer and distributor. |  |  |  | High | Low | New | Shalu |  | 12598 | 13-10-2024
12598 | NA | 15 | distributor should not be able to add coupons by entering 0 as the number of coupons. | User is logged in as a dealer and distributor. | 1) Click on Super 7 menu option. 2) Enter invalid data in coupn number field. 3) Click On "+" icon. | 0 | https://prnt.sc/uyapvs | High | Low | New | Shalu |  | 12598 | 13-10-2024
12598 | NA | 16 | There is a spelling mistake of “coupon” as coupn in the toast message appearing when entering more coupons than required, | User is logged in as a dealer and distributor. |  |  | https://prnt.sc/uyal40 | High | Low | New | Shalu |  | 12598 | 13-10-2025
12598 | NA | 17 | Toast Message appearing for entering coupons more than the available should be changed to “ Alloted coupon quantity should be less than or equal to Balance Coupons. | User is logged in as a dealer and distributor. |  |  | https://prnt.sc/uyal40 | High | High | New | Shalu |  | 12598 | 13-10-2025
12598 | NA | 18 | Distributor should not be able to add coupons more than the balance coupons. | User is logged in as a dealer and distributor. |  |  | https://prnt.sc/uyaopp | High | High | New | Shalu |  | 12598 | 13-10-2025
12598 | NA | 19 | Assigned coupons should get visible at the top of the Gift Cards section according to the date time. Latest should get visible first. |  |  |  |  | High | High | New | Shalu |  | 12598 | 13-10-2026

## OnGrid Apk-Bugs
Bug Report
Project :- |  | Mpartner-OnGrid APK |  |  |  |  | Lead_Devp. :- |  | Shalu
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :- |  | 12619
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severity | Status | Assigned to | Developers Status | Retesting Power ID | Retesting Date | Retesting Power ID | Retesting Date | Testers Comments | Open_Date | Close_Date
12619 | NA | 1 | Solar Load Calculator: No error appears for entering invalid pin number | User is already logged-in as distributor | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invlid data in Pin code and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 000000, 00,1235 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 2 | Solar Load Calculator: No error appears for entering invalid monthly bills. | User is already logged-in as distributor | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invalid data in Pin Monthly bill and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 0 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 3 | Solar Load Calculator: App does not calculate the load even with the valid data. That is nothing happens when clicking on calculate button with valid data. | User is already logged-in as distributor | s | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu | done showing dialog and server response will take time , and after then error message show | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 4 | Solar Load Calculator: No error appears for entering invalid pin number | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invlid data in Pin code and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 000000, 00,1235 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 5 | Solar Load Calculator: No error appears for entering invalid monthly bills. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 3) Enter invalid data in Pin Monthly bill and enter valid data in remaining mandatory fields. 4) Click on Calculate Button. | 0 |  | High | Mid | Fixed | Shalu | done | 12634 | 15-10-2020 | 12646 | 16-10-2020
12619 | NA | 6 | Solar Load Calculator: App does not calculate the load even with the valid data. That is nothing happens when clicking on calculate button with valid data. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu | done showing dialog and server response will take time , and after then error message show | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 7 | Side Menu: Duplicate Solar Calculator option is there under side menu options. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 8 | Solar Load Calculator: Server issues is coming when clicking on Calculate button. So therefore i am not able to verify the further process. | User is already logged-in as distributor. | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12634 | NA | 9 | Solar Load Calculator: Server issues is coming when clicking on Calculate button. So therefore i am not able to verify the further process. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=1500, 4500,5000 | Video shared on hangout | High | High | Fixed | Shalu |  | 12634 | 15-10-2020 | 12646 | 16-10-2020
12646 | NA | 10 | Solar Load Calculator: Server issues is coming when clicking on Calculate button by entering monthly bill of large amount (400000Rs or 500000Rs) | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=400000,500000 | Video shared on hangout | High | High | Deferred | Shalu | We can't add any limitation of the bill at our end. already discuss with Jyoti ma'am. |  |  | 12646 | 16-10-2020
12646 | NA | 11 | Solar Load Calculator: Server issues is coming when clicking on Calculate button by entering monthly bill of small amount (200rs or 150rs) | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | Video shared on hangout | High | High | Deferred | Shalu | We can't add any limitation of the bill at our end. already discuss with Jyoti ma'am. |  |  | 12646 | 16-10-2020
12646 | NA | 12 | On Grid System: Generate,Consume, Export and Save links are not working. That is they are not clickable. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | https://prnt.sc/v0c5pv | High | High | Deferred | Shalu | Generate, Consume, Export, and Save links are the static header there is no click, Its a non- linkable heading, UI is as per ios. |  |  | 12646 | 16-10-2020
12646 | NA | 13 | On Grid System: Click here link is not working under your estimate header. That is its not clickable. | User is already logged-in as dealer | 1) Go to the solar calculator under side menu. 2) Click on Solar (Gird On Solution) button. 3) click on Residential button. 4) enter valid data in all mandatory fields. 5) Click on Calculate Button. | PIN COde=110005,110096 Delhi, New Delhi, Monthly bills=200,150 | https://prnt.sc/v0c6yy | High | High | Fixed-Link removed | Shalu | done |  |  | 12646 | 16-10-2020
12646 | NA | 14 | Suggestion:On grid solar report:When sharing this file, there should be a some pre-written description about the report. |  |  |  | https://prnt.sc/v0c97q | High | High | Deferred | Shalu | Suggestion: we need to discuss it with the client. |  |  | 12646 | 16-10-2020
12646 | NA | 15 | On Grid System: After saving the results once report gets downloaded and then If user clicks on the share button then app again downloads the report which is wrong. App should only display the sharing option it does not download the report in such cases. |  |  |  |  | High | High | Deferred | Shalu | As per client requirement, we can share and download. |  |  | 12646 | 16-10-2020

## Summary
Mpartner-Solar Calculator
Lead Dev: Shalu
Module | No. of test Written | No. of test executed | Fixed | Not Fixed | New | Deffered
Solar Calculator | 23 | 23 | 12 | 5 | 1 | 5
Total | 23 | 23 | 12 | 9 | 1 | 5

## eWarranty- Pine lab Integration
Bug | Status
1) Cannot unblock dealer once it is blocked, pressing unblock button shows message “Blocked successfully”
2) Footer icons were again missing at the first time login
3) Received OTP from pinelabs page, but after submitting otp and clicking login button, it gets logged out | Fixed
4) Could not check the dealer id since I cannot unblock it from app

## Solar On Grid Calculator Proces
S. No | Feedback | Observation | Screenshot | Status
1 | When selecting state other than 7 listed states, cursor is just loading As discussed, other remaining states should be linked to output of DELHI NCR | 1) I have selected 799155 and 515001 as pincode but on selecting them system shows “Server Issue. Please try again later” toast msg. 2) When entering 510051 as pin code, it gets changed to 110043 and app goes into “Please wait” loop. | Video shared. | Not Fixed
2 | Added Tree Should be in number value, not percentage value |  |  | Fixed
3 | fields are not kept optional as discussed, form should have SKIP option |  |  | Fixed
4 | SAVE RESULTS button and SHARE icon have same functions, both asks for form filling and then provides sharing options SAVE RESULTS button should save the report directly in mobile once it is pressed | Customer Information pop up is not coming when clicking on Save Results button. |  | Not Fixed
5 | When sharing report, it is coming in a tabular format Report should be similar to output which comes in app along with Customer’s and Partner’s details along with product features and below disclaimer at the end of the report also- *Actual calculations and results for the site/location/application may vary from case to case depending on the actual ground conditions specific to the user. Users are advised to avail the facility of a site survey done by Luminous Channel Partners before undertaking actual solar installation. Report should also have Luminous logo in it | 1) Complete details are not coming in the PDF as that of the output of the app. Right side portions are cropped. 2) Customers/Partners details are overlapping with the output of the app result. 3) Not disclaimer is appearing in the PDF report. | 1)https://prnt.sc/vd63yq 2)https://prnt.sc/vd66xy | Not Fixed
6 | customer’s details filled in form are coming under partner’s details in report |  | 1)https://prnt.sc/vd66xy 2)https://prnt.sc/vd6tcf | Not Fixed
7 | partner’s details filled in form are coming under customer’s details in report |  | 1)https://prnt.sc/vd66xy 2)https://prnt.sc/vd6tcf | Not Fixed
8 |  | Not Validation comes for entering invalid Mobile number and Invalid email address in customer information form. | https://prnt.sc/vd99st | New
9
10