## Summary
Testing of Mercedes-Benz |  | Lead Dev. | Vikash Jha/ Ranjeet
Module | No. of test Written | No. of test executed | Pass | Fail
Claim | 63 | 63 | 44 | 19
Total | 63 | 63 | 44 | 19

## Bug_Report
Bug Report
Project :- |  | Luminious_Mpartner |  |  |  |  | Lead_Devp. :- |  | Vikash Jha/ Ranjeet
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10058
Date | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-19 | TC_03/Claim | 1 | There is allingment Issue in Static Button | Login cridential provided |  |  |  |  | Low | New
2020-02-19 | TC_05/Claim | 2 | There is allingment Issue in new Claim Form | Login cridential provided | Click on Add Claim |  |  |  | Low | New
2020-02-19 | TC_06/Claim | 3 | New Claim :-Two validation Msg. Appear and work order validation appears first which is not serial wise | Login cridential provided | Leave all field blank and click on submit |  |  |  | Low | New
2020-02-19 | TC_07/Claim | 4 | Service Request length is less than 16 char and validation of Work Order Length length is less than 16 char. Is displayed. | Login cridential provided | Fill data and check validation | Service Request :- 1234QW Work Order :- Service Request Date :- Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | New
2020-02-19 | TC_08/Claim | 5 | After submitting Wrong Information Creating New Claim page data Unable to reset Data. | Login cridential provided | Fill data and check validation |  |  |  | Low | New
2020-02-19 | TC_09/Claim | 6 | New Claim :-Validation msg. is not serial wise | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | High | New
2020-02-19 | TC_10/Claim | 7 | Validation msg. should be Please select Certificate No. instead of salesorder | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | New
2020-02-19 | TC_11/Claim | 8 | Validation :-Odometer reading should be in between warranty reading | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- |  |  | Low | New
2020-02-19 | TC_14/Claim | 9 | Add part information :- NAN is showing in Total Field. Field should be blank Also Quantity is accepting decimal value | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.2 MRP :- Part Location :- |  |  | High | New
2020-02-19 | TC_15/Claim | 10 | Add part information claim :- There is calculation mistake (Sugg. :- There should be GST on Total price of Part) | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.1 MRP :- 100 Total :- 110.00000000000001 Part Location :- |  |  | High | New
2020-02-19 | TC_22/Claim | 11 | Unable to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component of 5MB | Login cridential provided | Click on Add Document |  |  |  | Low | New
2020-02-19 | TC_24/Claim | 12 | Warranty Manager Name is accepting special character and numeric data | Login cridential provided | Click on Add Claim |  |  |  | Low | New
2020-02-19 | TC_33/Claim | 13 | Instead of created time it is searching with created date | Login cridential provided | Created Time |  |  |  | Low | New
2020-02-19 | TC_49/Claim | 14 | Unable To Delete Filter newly Created filter | Login cridential provided | 1) Click on Filter 2) Click on Delete Filter |  |  |  | High | New
2020-02-19 | TC_52/Claim | 15 | accepting Surveyor Contact No. less than 10 digit | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Contact No. :- 222 |  |  | High | New
2020-02-19 | TC_55/Claim | 16 | There is no option of Entering Claim Manager Name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty |  |  | High | New
2020-02-19 | TC_56/Claim | 17 | First Action Date and First Action Time automatically gets captured on adding Claim manager Details instead of Name | Login cridential provided |  |  |  |  | High | New
2020-02-19 | TC_62/Claim | 18 | Total record found in the report will be displayed on screen | Login cridential provided | 1) Login with manager ID 2) Open Report 3) Click on Claim Report | Start Date :- 2020-02-15 End Date :- 2020-02-19 |  |  | High | New
2020-02-19 | TC_63/Claim | 19 | Accepting special character and numeric data in surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- @##$123 |  |  | Low | New

## Claim
Project Name:-> Mercedes_Benz
Created By:- | Atyab Alam |  |  |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-17 |  |  |  | Review Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Claim
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to login to Mercedes-Benz | Login cridential provided | ID :- demo-dealer P.W. :- Welcome@123 |  |  |  | Will be able to login.
TC_02/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to go to Claim page | Login cridential provided | Click on Claim present on top left of the screen |  |  |  | Claim page will open
TC_03/Claim | 10058 | 2020-02-17 | To verify that all Static Buttons are allinged properly | Login cridential provided |  |  | There is allingment Issue |  | Static Buttons should be allinged properly |  | Low | Fail
TC_04/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Click on Add Claim |  |  |  | Creating New Claim form will open
TC_05/Claim | 10058 | 2020-02-17 | To Verify that Add New Claim form is Allinged properly | Login cridential provided | Click on Add Claim |  | There is allingment Issue |  | New Claim form should be Allinged properly |  | Low | Fail
TC_06/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Leave all field blank and click on submit |  | Two validation Msg. Appear and work order validation appears first which is not serial wise |  | This field is required msg will display on mandatory field |  | Low | Fail
TC_07/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW Work Order :- Service Request Date :- Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Work Order Length length is less than 16 char. |  | Service Request length is less than 16 char. |  | Low | Fail
TC_08/Claim | 10058 | 2020-02-17 | To verify that after submitting Wrong Information Creating New Claim page data will be reset | Login cridential provided | Fill data and check validation |  | Unable to reset Data |  | Data of All Fields Should be reset |  | Low | Fail
TC_09/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Validation msg. is not serial wise |  | Please select work order date |  | High | Fail
TC_10/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Validation msg. should be Please select Certificate No. |  | Please select salesorder first |  | Low | Fail
TC_11/Claim | 10058 | 2020-02-17 | To verify that Dealer is able to Add New Claim | Login cridential provided | Fill data and check validation | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- Service Request Time :- Work Order Open Time :- Current Odometer Reading :- Warranty Manager Name :- Dealer Email :- Warranty Manager Contact No :- Diagnosis done by Dealer :- Repair Cost :- Repair Estimation :- | Odometer reading should be less than or equal to warrnaty end kms |  | Odometer reading should be in between warranty reading |  | Low | Fail
TC_12/Claim | 10058 | 2020-02-17 |  | Login cridential provided |  | Service Request :- 1234QW789693FGBN Work Order :- 7895423TYUIOXCVB Service Request Date :- 16-02-2020 Work Order Date :- 13-02-2020 Service Request Time :- 01:30 Work Order Open Time :- 05:30 Current Odometer Reading :- 40000 Warranty Manager Name :- HOHOHO Dealer Email :- hoho@gogo.xyz Warranty Manager Contact No :- 9876543210 Diagnosis done by Dealer :- yes Repair Cost :- 50000 Repair Estimation :- 1.pdf
TC_13/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided | Click on Add Part Information Claim |  |  |  | Will be redirected to Creating New Part Information Claim page
TC_14/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.2 MRP :- Part Location :- | NAN is showing in Total Field. Field should be blank Also Quantity is accepting decimal value |  | Quantity Should not accept decimal value |  | High | Fail
TC_15/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 1.1 MRP :- 100 Total :- 110.00000000000001 Part Location :- | There is calculation mistake (Sugg. :- There should be GST on Total price of Part) |  | Total should be 110 |  | High | Fail
TC_16/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add part information claim | Login cridential provided |  | Part Code :- 12 Assigned To :- demo tvs Quantity :- 2 MRP :- 100 Total :- 200 Part Location :- Front Left |  |  | Part Information will be Added
TC_17/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Labour Information Claim | Login cridential provided | Click on Add Labour Information Claim |  |  |  | Will be redirected to Creating New Labour Information Claim page
TC_18/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Labour Information Claim | Login cridential provided | Fill details total will be calculated automatically | Labour Code :- 1 Rate per Hour :- 200 Operation Time in Hours :- 10 Amount :- 2000 GST% :- 10 GST Amount :- 200 Total Price :- 2200 |  |  | New Labour Information will be added
TC_19/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Miscellaneous Expenses | Login cridential provided | Click on Add Miscellaneous Expenses |  |  |  | Will be redirected to Creating New Miscellaneous Expenses
TC_20/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Miscellaneous Expenses | Login cridential provided | Fill details total will be calculated automatically | Amount :- 1000 GST % :- 100 |  |  | New Miscellaneous Expenses will be Added
TC_21/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Document | Login cridential provided | Click on Add Document |  |  |  | Will be redirected to Creating New Document
TC_22/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Add Document | Login cridential provided | Click on Add Document |  | Unable to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component of 5MB |  | Will be able to Add ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component |  | Low | Fail
TC_23/Claim | 10058 | 2020-02-17 | To verify that dealer is able to Edit Claim whose status is not Approved/Rejected | Login cridential provided | 1) Click on Claim 2) Click on Edit option present on top |  |  |  | Dealer should be able to Edit claim details
TC_24/Claim | 10058 | 2020-02-17 | To verify that dealer is able to create Claim | Login cridential provided | Click on Add Claim |  | Warranty Manager Name is accepting special character and numeric data |  | Warranty Manager Name should not accept special character and numeric data |  | Low | Fail
TC_25/Claim | 10058 | 2020-02-17 | To verify that manager can login to portal or not | Login cridential provided | ID :- demo-TVS P.W. :- Welcome@123 |  |  |  | Manager should be able to login to the portal
TC_26/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | 1) Click on Claim 2) Search claim by claim No. :- MBCAC115 |  |  |  | Claim of claim No. :- MBCAC115 Will appear on the screen
TC_27/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | 1) Click on Claim 2) Search claim by Customer Name :- GANGADHARA PAYYADE |  |  |  | Claim with customer name GANGADHARA PAYYADE will appear on the screen
TC_28/Claim | 10058 | 2020-02-17 | To verify that manager can search claim created by dealer | Login cridential provided | Search Claim by Vehicle VIN :- WDD2120346L047456 |  |  |  | Claim with Vehicle VIN :- WDD2120346L047456 will appear on the screen
TC_29/Claim | 10058 | 2020-02-17 | To verify that manager can search claim by model of vehicles | Login cridential provided | Model of vehicles :- 2 |  |  |  | No vehicle found
TC_30/Claim | 10058 | 2020-02-19 | To verify that manager can search claim by model of vehicles | Login cridential provided | Model of vehicles :- E |  |  |  | All claim on mercedes car with model contains E in it will filtered
TC_31/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Status :- Submitted |  |  |  | All claim with status submitted will appear
TC_32/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Assigned To :- Demo Dealer |  |  |  | All claim assinged to Demo Dealer will appear
TC_33/Claim | 10058 | 2020-02-19 | To verify that manager can search claim created by dealer | Login cridential provided | Created Time |  | Instead of created time it is searching with created date |  | Should be able search with created time |  | Low | Fail
TC_34/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Answered by Dealer | Login cridential provided | 1) Click on Filter 2) Click on Answered by Dealer |  |  |  | All claim that is answered by dealer will appear
TC_35/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Approved Claim | Login cridential provided | 1) Click on Filter 2) Click on Approved Claim |  |  |  | All claim whose status is approved will appear
TC_36/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Open Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Open Purchase Orders |  |  |  | All claim whose status is open purchase orders will appear
TC_37/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Payment Made | Login cridential provided | 1) Click on Filter 2) Click on Payment Made |  |  |  | All claim whose payment is made will appear
TC_38/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Pending with Surveyor | Login cridential provided | 1) Click on Filter 2) Click on Pending with Surveyor |  |  |  | All claim whose status is pending with surveyor will appear
TC_39/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Post Approval Documents Pending Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Pending Claim |  |  |  | All claim whose post Approval document is pending will appear
TC_40/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Post Approval Documents Received Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Recived Claim |  |  |  | All claim whose post Approval document is recived will appear
TC_41/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Query by Assurant | Login cridential provided | 1) Click on Filter 2) Click on Query by Assurant |  |  |  | All claim on which query is generated by assurant will appear
TC_42/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Received Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Received Purchase Orders |  |  |  | All claim whose purchased order is recived will appear
TC_43/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Rejected Claim | Login cridential provided | 1) Click on Filter 2) Click on Rejected Claim |  |  |  | All claim which is rejected will appear
TC_44/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Submitted Claim | Login cridential provided | 1) Click on Filter 2) Click on Submitted Claim |  |  |  | All claim whose status is submitted will appear
TC_45/Claim | 10058 | 2020-02-19 | To verify that Dealer is able to filter claim by Total Claim | Login cridential provided | 1) Click on Filter 2) Click on Total Claim |  |  |  | total claim registered from day 1 will appear
TC_46/Claim | 10058 | 2020-02-19 | To verify that dealer is able to create new Filter | Login cridential provided | 1) Click on Filter 2) Click on Create New Filter | View Name :- qwerty Choose columns and order :- Certificate No. |  |  | Please Select at-least one mandatory Field
TC_47/Claim | 10058 | 2020-02-19 | To verify that dealer is able to create new Filter | Login cridential provided | 1) Click on Filter 2) Click on Create New Filter | View Name :- qwerty Choose columns and order :- Certificate No., Current Odometer Reading |  |  | New Filter will be created
TC_48/Claim | 10058 | 2020-02-19 | To verify that dealer is able to edit Filter | Login cridential provided | 1) Click on Filter 2) Click on Edit New Filter | View Name :- qwerty Choose columns and order :- Certificate No., Current Odometer Reading, Modified Time |  |  | Modified Time filter option will be added
TC_49/Claim | 10058 | 2020-02-19 | To verify that dealer is able to Delete Filter | Login cridential provided | 1) Click on Filter 2) Click on Delete Filter |  | Unable To Delete Filter |  | Newly created filter will be deleted |  | High | Fail
TC_50/Claim | 10058 | 2020-02-19 | To verify that manager is able to change Status from Submitted to Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor |  |  | Status will change to Pending with Surveyor
TC_51/Claim | 10058 | 2020-02-19 | To verify that on changing status ​S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will automatically capture on changing status | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Change Status to pending with surveyor |  |  | S​urveyor ​A​ppointment​ Time and Request for ​S​urveyor ​A​ppointment​ Date will be automatically captured
TC_52/Claim | 10058 | 2020-02-19 | To verify that manager can insert Surveyor Contact No. | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Contact No. :- 222 | accepting Surveyor Contact No. less than 10 digit |  | Surveyor Contact No. should be of Atleast 10 digit |  | High | Fail
TC_53/Claim | 10058 | 2020-02-19 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- qwerty
TC_54/Claim | 10058 | 2020-02-19 | To verify that Surveyor Appointment Date and Surveyor Appointment Time will automatically capture on adding surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim |  |  |  | Surveyor Appointment Date and Surveyor Appointment Time will be automatically Added
TC_55/Claim | 10058 | 2020-02-19 | To verify that manager is able to Add Claim manager name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Claim Manager Name :- qwerty | There is No option of Entering Claim Manager Name |  | Claim Manager Name will be added |  | High | Fail
TC_56/Claim | 10058 | 2020-02-19 | To verify that First Action Date and First Action Time automatically gets captured on adding manager name | Login cridential provided |  |  | First Action Date and First Action Time automatically gets captured on adding Claim manager Details instead of Name |  | First Action Date and First Action Time will automatically get captured |  | High | Fail
TC_57/Claim | 10058 | 2020-02-19 | To verify that dealer is able to add comment on claim whose status :- Pending with surveyor | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Comment | Comment :- Hi |  |  | Comment will be added and status will be changed to Answered by dealer
TC_58/Claim | 10058 | 2020-02-19 | To verify that dealer is able to change status to Approved | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Status :- Approved |  |  | Status of Claim will Change to Approved
TC_59/Claim | 10058 | 2020-02-19 | To verify that dealer is able to change status to Rejected | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Status :- Rejected |  |  | Status of Claim will Change to Rejected
TC_60/Claim | 10058 | 2020-02-19 | To verify that Approved / Rejected Time and Approved / Rejected Date will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  |  |  |  | Approved / Rejected Time and Approved / Rejected Date will automatically gets updated
TC_61/Claim | 10058 | 2020-02-19 | To verify that Claim Matured Date andClaim Matured Time will automatically gets update on changing status to Approved / Rejected | Login cridential provided |  |  |  |  | Claim Matured Date and Claim Matured Time will be automatically updated
TC_62/Claim | 10058 | 2020-02-19 | To verify that manager is able to download report | Login cridential provided | 1) Login with manager ID 2) Open Report 3) Click on Claim Report | Start Date :- 2020-02-15 End Date :- 2020-02-19 | Total record found in the report will be displayed on screen |  | Should be able to download report and total record found in the report will be displayed on screen |  | High | Fail
TC_63/Claim | 10058 | 2020-02-19 | To verify that manager can enter surveyor name | Login cridential provided | 1) Login with manager ID 2) Open Claim 3) Click on Edit | Surveyor Name :- @##$123 | Accepting special character and numeric data in surveyor name |  | Invalid Dealer Name |  | Low | Fail