## Summary
|  | Testing of Ashok_Leyland |  | Lead Dev. | Vikash Jha/ Ranjeet
|  | Module | No. of test Written | No. of test executed | Pass | Fail
|  | Claim | 63 | 63 | 61 | 2
|  | Agreement | 28 | 28 | 21 | 7
|  | Total | 91 | 91 | 82 | 9
Note 1. :- | Date of job card should not be more than 2 days old from present date
Note 2. :- | Failure date should be of same date as that of job card date or 2 day before job card date
Link To Test :- |  | http://13.127.206.20/tvsalphp7/index.php

## Bug_Report
Bug Report
Project :- |  | Ashok_Leyland |  |  |  |  | Lead_Devp. :- |  | Vikash Jha
Created_By :- |  | Atyab Alam |  |  |  |  | Power_Task_I.D. :- |  | 10029
Date | Test Case ID | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Testers Comments | Open_Date | Close_Date
2020-02-15 | TC_06 | 1 | Please Select SalesOrder First Msg. is displayed. Instead of Agreement No. and Agreement No. should be mandatory field | Login cridential provided | Open Creating New Claim form | Job Card No :-1478523 Date of Job Card :- 14/02/2020 Failure Date :- Odometer Reading :- Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | https://drive.google.com/open?id=1IdKyKQvV9XyAWfk2pcd26f3FkCSPkOnM |  | Low | Fixed | Ranjeet | Done
2020-02-15 | TC_07 | 2 | Is not accepting Different Date of job card and Failure Date | Login cridential provided | Open Creating New Claim form | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 15-02-2015 Odometer Reading :- Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | https://drive.google.com/open?id=1bHtDKVyo7XP1BqdQboTxYCzZTB0amt6q |  | High | Fixed | Ranjeet | No need to change
2020-02-15 | TC_08 | 3 | Odometer reading should be in between Agreement Odometer Reading. | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 2000 Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | https://drive.google.com/open?id=11b2ZGNFHpHK_mQgvDEJYb4AUPtSiGVnn |  | Low | Fixed | Ranjeet | Done
2020-02-15 | TC_10 | 4 | Diagnosis Done by Dealer Accepting Numeric Value and special character | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 60000 Warranty Admin Name :- Bhola Dealer Email :- bhola@shola.com Dealer Contact No :- 7894561230 Diagnosis Done by Dealer :- 1223 | https://drive.google.com/open?id=1D7ym6hQgyGStidzOMGQsOAgw7shOt_79 |  | Low | Fixed | Ranjeet | No need to change
2020-02-15 | TC_11 | 5 | Warranty Admin Name is accepting special character and numeric data | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 60000 Warranty Admin Name :- @@ Dealer Email :- bhola@shola.com Dealer Contact No :- 7894561230 Diagnosis Done by Dealer :- 1223 | https://drive.google.com/open?id=1IiDBNmolj6XIDQEd-hXQJS7EVZQUKRTU |  | Low | Fixed | Ranjeet | Done
2020-02-15 |  | 6 | Dealer should have to use 2 slider one in top and other in bottom to reach search button | Login cridential provided | Click on Search Claim by Claim No | Claim No. :-DEASN17974 | https://drive.google.com/open?id=1Yc62ezVACb1NK0EZE-vFykKWgXPuYjZF |  | Low | Fixed | Ranjeet | No need to change
2020-02-15 | TC_20 | 7 | Instead of Create time it is searching claim by Create Date | Login cridential provided | Click on Search Claim by Create Time |  | https://drive.google.com/open?id=1EZzQvxSQFTKJfGcTG61Xi9qmGTf8hiDU |  | Low | Fixed | Ranjeet | No need to change
2020-02-15 | TC_33 | 8 | Treating -1.2 quantity as 12 (quantity can't be negative) | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (-1.2) | https://drive.google.com/open?id=1Qmsn1iYFRN-7qULz9oJi-gychtDED4Ka |  | High | Fixed | Ranjeet | Done
2020-02-15 | TC_34 | 9 | Treating 1.2 quantity as 12 and Upload Document should be Mandatory Field | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (1.2) Upload Document :- | https://drive.google.com/open?id=1Qmsn1iYFRN-7qULz9oJi-gychtDED4Ka |  | High | Fixed | Ranjeet | Done
2020-02-15 | TC_35 | 10 | When clicking on save notification appears that changes you made may not be saved | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (1) Upload Document :- | https://drive.google.com/open?id=1_87jguGbdjKkLN8ajaUTI83bEU8i3dPZ |  | High | Fixed | Ranjeet | No need to change
2020-02-15 | TC_36 | 11 | Remove selected part. Part removed but no field data is cleared (All field data should be reset) | Login cridential provided | Click on Add Part Information Claim | Remove part | https://drive.google.com/open?id=1Qmsn1iYFRN-7qULz9oJi-gychtDED4Ka |  | Low | Fixed | Ranjeet | No need to change
2020-02-15 | TC_37 | 12 | Dealer should be able to enter Rate, Operation Time | Login cridential provided | Click on Add Labour Information Claim | Select Labour Code | https://drive.google.com/open?id=1sy7z9V1M8GBhyWluYpOVG02h6WZoLNsd |  | High | Fixed | Ranjeet | No need to change
2020-02-15 | TC_38 | 13 | On Changing GST%age. GST amount remains same also there is no unit of operating time | Login cridential provided | Click on Add Labour Information Claim | Change GST %age | https://drive.google.com/open?id=1sy7z9V1M8GBhyWluYpOVG02h6WZoLNsd |  | High | Fixed | Ranjeet | Done
2020-02-15 | TC_39 | 14 | Unable to enter title hence unable to upload document | Login cridential provided | Click on Add Document | Enter Title | https://drive.google.com/open?id=1hutvSn-RPKdcXwecjQ3eSsG0h1EgwB6b |  | High | Fixed | Ranjeet | No need to change
2020-02-15 | TC_41 | 15 | Unable to upload file of 5MB and More in size | Login cridential provided | Click on Add Document | Upload file of ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component document varying from size (0MB to 10MB) | https://drive.google.com/open?id=1hutvSn-RPKdcXwecjQ3eSsG0h1EgwB6b |  | Low | New | Ranjeet | Server Issue
2020-02-15 | TC_48 | 16 | Sub-Status should by marked as mandatory field as manager is not able to approve claim without entering it. | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  | https://drive.google.com/open?id=1p0s4FwwwPTZubX4DRbDqJ68Ws5tNQh0g |  | Low | Fixed | Ranjeet | No need to change
2020-02-15 | TC_55 | 17 | EW Detail page is not allinged properly | Login cridential provided | 1) Login with manager/Dealer account 2) Select claim |  | https://drive.google.com/open?id=128rZrDqCBmqUXUaCk_Puy9xiJUYnxzGN |  | Low | New | Ranjeet | Done
2020-02-15 | TC_57 | 18 | Dealer is able to create claim by entering (2 year + old) date of job card | Login cridential provided | 1) Login with manager/Dealer account 2) Select Add claim |  | https://drive.google.com/open?id=19xinFeTGqyasHLei67R4R8QCp_JE-uTF |  | High | Fixed | Ranjeet | Done
2020-02-15 | TC_58 | 19 | Claim Manager: There is no validation for Surveyor contact number. User can enter invalid data in Surveyor contact number. (1234 as contact no.) | Login cridential provided | 1) Login with manager/Dealer account 2) Select claim 3) Click on Edit 4) Enter surveyor contact No. |  |  |  | High | Fixed | Ranjeet | Done
2020-02-15 | TC_59 | 20 | Create New part info. Claim there is no GST | Login cridential provided | 1) Login with manager/Dealer account 2) Select claim 3) Add Part info. |  | https://drive.google.com/open?id=1Qmsn1iYFRN-7qULz9oJi-gychtDED4Ka |  | High | Fixed | Ranjeet | Done
2020-02-20 | TC_04/ Agreement | 21 | Add Agreement :- There is no condition on First Name | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- Address :- Postal Code :- City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_06/ Agreement | 22 | Add Agreement :- There is no condition on Address | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_10/ Agreement | 23 | Add Agreement :- There is no condition on registration No. | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_11/ Agreement | 24 | Add Agreement :- There is no condition on Engine No. | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- 2000 Vehicle Delivery Date :- 22-07-2019 Engine No :- 1234567890ASDFGHJKL Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_13/ Agreement | 25 | Add Agreement :- Accepting Invalid Sales manager name and Executive Name | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- 2000 Vehicle Delivery Date :- 22-07-2019 Engine No :- 1234567890ASDFGHJKL Extended Warranty :- EW3 1Years / 50000 Kms EWS Retail :- EWS4674 Sales By :- Sales Sales Manager Name :- ## Executive Name :- #@ |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_20/ Agreement | 26 | Search Agreement :- Instead of Created Time it is searching with Created Date | Login cridential provided |  | Created Time :- 19-02-2020,20-02-2020 |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_28/ Agreement | 27 | Agreement Status :-Even when Ext. Warranty End Date is expired status remains active | Login cridential provided | 1) Click on agreement 2) open any agreement |  |  |  | Low | New | Ranjeet | on hold
2020-02-20 | TC_60 | 28 | Create New Claim :- Date of job card is accepting older date than Ext . Warranty Start Date | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | High | Fixed | Ranjeet | No need to change
2020-02-20 | TC_61 | 29 | Create New Claim :- Dealer E-mail ID is accepting wrong data | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | Low | Fixed | Ranjeet | possible validation already exist
2020-02-20 | TC_62 | 30 | Create New Claim :- Diagnosis done by dealer field is accepting special character | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | Low | Fixed | Ranjeet | No need to change
2020-02-20 | TC_63 | 31 | Creating New Miscellaneous Expenses Gst is not working | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | High | Fixed | Ranjeet | Done
2020-02-20 |  | 32 | Date of job card should not accept data more than 2 days old from present date | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | High | Fixed | Ranjeet | Done
2020-02-20 |  | 33 | Failure date should be of same date as that of job card date or 2 day before job card date | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | High | Fixed | Ranjeet | Done
2020-02-21 |  | 34 | Failure date :- validation msg. (Failure date should be same as job card date or maximum 2 days older than job card date) | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | Low | New | Ranjeet
2020-02-21 |  | 35 | Edit Document :- Unable to edit Uploaded document in claim | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  |  |  | High | New | Ranjeet

## Claim
Project Name: Ashok_Leyland
Created By:- | Atyab Alam |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-10 |  | Review Date:- |  |  | Developed By :- | Vikash Jha
Version: - |  |  | Module:- | Claim |  | Power_ID :- | 10029
Test Case ID | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01 | To verify that Dealer is able to login to Ashok Leyland EW | Login cridential provided | ID :- rainbow-salem P.W. :- Welcome@123 |  |  |  | Will be able to login.
TC_02 | To verify that Dealer is able to go to Claim page | Login cridential provided | Click on Claim present on top left of the screen |  |  |  | Claim page will open
TC_03 | To verify that Dealer is able to Add New Claim | Login cridential provided | Click on Add Claim |  |  |  | Creating New Claim form will open
TC_04 | To verify that Dealer is able to Add New Claim | Login cridential provided | Leave all field blank and click on submit |  |  |  | This field is required msg will display on mandatory field
TC_05 | To verify that Dealer is able to Add New Claim | Login cridential provided | Open Creating New Claim form | Job Card No :- 22 Date of Job Card :- Failure Date :- Odometer Reading :- Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- |  |  | Job Card No. can only be of 7 digit msg. will display
TC_06 | To verify that Dealer is able to Add New Claim | Login cridential provided | Open Creating New Claim form | Job Card No :-1478523 Date of Job Card :- 14/02/2020 Failure Date :- Odometer Reading :- Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | Please Select SalesOrder First Msg. is displayed. Instead of Agreement No. and Agreement No. should be mandatory field |  | Should Accept Date of job Card and msg. will be displayed to fill all remaining mandatory field. |  | Low | Fail
TC_07 | To verify that Dealer is able to Add New Claim | Login cridential provided | Open Creating New Claim form | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 15-02-2015 Odometer Reading :- Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | Is not accepting Different Date of job card and Failure Date |  | Should Accept Different Date of job card and Failure Date |  | High | Fail
TC_08 | To verify that Dealer is able to Add New Claim | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 2000 Warranty Admin Name :- Dealer Email :- Dealer Contact No :- Diagnosis Done by Dealer :- | Odometer reading should be less than or equal to Agreement Odometer Reading. |  | Odometer reading should be in between Aggrement Odometer reading |  | Low | Fail
TC_09 | To verify that Dealer is able to Add New Claim | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 60000 Warranty Admin Name :- Bhola Dealer Email :- bhola@shola.com Dealer Contact No :- 245 Diagnosis Done by Dealer :- |  |  | Dealer Contact No should be 10 digit number
TC_10 | To verify that Dealer is able to Add New Claim | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 60000 Warranty Admin Name :- Bhola Dealer Email :- bhola@shola.com Dealer Contact No :- 7894561230 Diagnosis Done by Dealer :- 1223 | Accepting Numeric Value and special character |  | Diagnosis Done by Dealer should accept only alphabet (yes or no) |  | Low | Fail
TC_11 | To verify that Dealer is able to Add New Claim | Login cridential provided |  | Job Card No :-1478523 Date of Job Card :- 20-02-2015 Failure Date :- 20-02-2015 Odometer Reading :- 60000 Warranty Admin Name :- @@ Dealer Email :- bhola@shola.com Dealer Contact No :- 7894561230 Diagnosis Done by Dealer :- 1223 | Warranty Admin Name is accepting special character and numeric data |  | Invalid Warranty Admin Name |  | Low | Fail
| To verify that dealer is able to search claim | Login cridential provided | Click on Search Claim by Claim No | Claim No. :-DEASN17974 | Dealer should have to use 2 slider one in top and other in bottom to reach search button |  | Related Claim Will Appear |  | Low | Fail
TC_12 | To Verify that Dealer is able to Search Claim by Claim No. | Login cridential provided | Click on Search Claim by Claim No | Claim No. :- @@## |  |  | No Claim found msg. is displayed
TC_13 | To Verify that Dealer is able to Search Claim by Claim No. | Login cridential provided | Click on Search Claim by Claim No | Claim No. :-DEASN17974 |  |  | Related Claim Will Appear
TC_14 | To Verify that Dealer is able to Search Claim by Customer Name | Login cridential provided | Click on Search Claim by Customer Name | Customer Name :- @@##12 |  |  | No Claim found msg. is displayed
TC_15 | To Verify that Dealer is able to Search Claim by Customer Name | Login cridential provided | Click on Search Claim by Customer Name | Customer Name :- SAJJAD SAMAD PATHAN |  |  | Related Claim Will Appear
TC_16 | To Verify that Dealer is able to Search Claim by Vehicle Chassis No. | Login cridential provided | Click on Search Claim by Vehicle Chassis No. | Vehicle Chassis No. :- 12345678901234567890 |  |  | No Claim found msg. is displayed
TC_17 | To Verify that Dealer is able to Search Claim by Vehicle Chassis No. | Login cridential provided | Click on Search Claim by Vehicle Chassis No. | Vehicle Chassis No. :- MB1AA22E9CRY07017 |  |  | Related Claim Will Appear
TC_18 | To Verify that Dealer is able to Search Claim by Vehicle Variant | Login cridential provided | Click on Search Claim by Vehicle Variant | Vehicle Variant :- #123 |  |  | No Claim found msg. is displayed
TC_19 | To Verify that Dealer is able to Search Claim by Vehicle Variant | Login cridential provided | Click on Search Claim by Vehicle Variant | Vehicle Variant :- LS(BS-III) |  |  | Claim on vehicle variant LS(BS-III) Will Appear
TC_20 | To Verify that Dealer is able to Search Claim by Create Time | Login cridential provided | Click on Search Claim by Create Time |  | Instead of Create time it is searching claim by Create Date |  | Should be able to Search Claim by Create Time |  | Low | Fail
TC_21 | To verify that Dealer is able to filter claim by Answered by Dealer | Login cridential provided | 1) Click on Filter 2) Click on Answered by Dealer |  |  |  | All claim that is answered by dealer will appear
TC_22 | To verify that Dealer is able to filter claim by Approved Claim | Login cridential provided | 1) Click on Filter 2) Click on Approved Claim |  |  |  | All claim whose status is approved will appear
TC_23 | To verify that Dealer is able to filter claim by Open Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Open Purchase Orders |  |  |  | All claim whose status is open purchase orders will appear
TC_24 | To verify that Dealer is able to filter claim by Payment Made | Login cridential provided | 1) Click on Filter 2) Click on Payment Made |  |  |  | All claim whose payment is made will appear
TC_25 | To verify that Dealer is able to filter claim by Pending with Surveyor | Login cridential provided | 1) Click on Filter 2) Click on Pending with Surveyor |  |  |  | All claim whose status is pending with surveyor will appear
TC_26 | To verify that Dealer is able to filter claim by Post Approval Documents Pending Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Pending Claim |  |  |  | All claim whose post Approval document is pending will appear
TC_27 | To verify that Dealer is able to filter claim by Post Approval Documents Received Claim | Login cridential provided | 1) Click on Filter 2) Click on Post Approval Documents Recived Claim |  |  |  | All claim whose post Approval document is recived will appear
TC_28 | To verify that Dealer is able to filter claim by Query by Assurant | Login cridential provided | 1) Click on Filter 2) Click on Query by Assurant |  |  |  | All claim on which query is generated by assurant will appear
TC_29 | To verify that Dealer is able to filter claim by Received Purchase Orders | Login cridential provided | 1) Click on Filter 2) Click on Received Purchase Orders |  |  |  | All claim whose purchased order is recived will appear
TC_30 | To verify that Dealer is able to filter claim by Rejected Claim | Login cridential provided | 1) Click on Filter 2) Click on Rejected Claim |  |  |  | All claim which is rejected will appear
TC_31 | To verify that Dealer is able to filter claim by Submitted Claim | Login cridential provided | 1) Click on Filter 2) Click on Submitted Claim |  |  |  | All claim whose status is submitted will appear
TC_32 | To verify that Dealer is able to filter claim by Total Claim | Login cridential provided | 1) Click on Filter 2) Click on Total Claim |  |  |  | total claim registered from day 1 will appear
TC_33 | To Verify that Dealer is able to Creating New Part Information Claim | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (-1.2) | Treating -1.2 quantity as 12 |  | Invalid Quantity |  | High | Fail
TC_34 | To Verify that Dealer is able to Creating New Part Information Claim | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (1.2) Upload Document :- | Treating 1.2 quantity as 12 and Upload Document should be Mandatory Field |  | Invalid Quantity |  | High | Fail
TC_35 | To Verify that Dealer is able to Creating New Part Information Claim | Login cridential provided | Click on Add Part Information Claim | Part Code :- F8P08950 Quantity :- (1) Upload Document :- | When clicking on save notification appears that changes you made may not be saved |  | New part information will be added |  | High | Fail
TC_36 | To Verify that Dealer is able to Creating New Part Information Claim | Login cridential provided | Click on Add Part Information Claim | Remove part | Part removed but no field data is cleared (All field data should be reset) |  | MRP field should be reset |  | Low | Fail
TC_37 | To Verify that Dealer is able to Creating New Labour Information Claim | Login cridential provided | Click on Add Labour Information Claim | Select Labour Code | All data is automatically filled |  | Should be able to fill operating time and rate |  | High | Fail
TC_38 | To Verify that Dealer is able to Creating New Labour Information Claim | Login cridential provided | Click on Add Labour Information Claim | Change GST %age | GST amount remains same also there is no unit of operating time |  | GST amount will be changed |  | High | Fail
TC_39 | To Verify that Dealer is able to Creating New Document | Login cridential provided | Click on Add Document | Enter Title | Unable to enter title hence unable to upload document |  | Should be able to enter Title |  | High | Fail
TC_40 | To Verify that Dealer is able to Creating New Document | Login cridential provided | Click on Add Document | Upload file name document varying from size (0MB to 5MB) |  |  | Document should be uploaded
TC_41 | To Verify that Dealer is able to Creating New Document | Login cridential provided | Click on Add Document | Upload file of ODO Meter Reading Photo, Vehicle History, Photo/Video Of Failed Component document varying from size (0MB to 10MB) | Unable to upload file of 5MB and More in size |  | All files of size upto 10MB will be uploaded |  | Low | Fail
TC_42 | To verify that EW Details capture first action date & time on entering Manager name | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Enter manager name | Manager name :- Babu bhai |  |  | First action date and time will automatically capture current date and time
TC_43 | To veri that manager is able to change status of claim to pending with surveior | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) change status to pending with surveior |  |  |  | Status will change to pending with surveior
TC_44 | To verify that dealer is able to add comment | Login cridential provided | 1) Filter claim with status (Pending with surveior) 2) open a filtered claim 3) Click on comment present on top right of the screen | Comment :- xyz |  |  | Comment will be added and status will changed to answered by dealer
TC_45 | To verify that request for surveyor appointment date & time is automatically updated | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) change status to pending with surveior |  |  |  | Request for surveyor appointment date & time will be automatically updated
TC_46 | To verify that surveyor appointment date & time is automatically updated | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Enter surveior name |  |  |  | surveyor appointment date & time will be automatically updated
TC_47 | To verify that manager can reject a claim | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to rejected |  |  |  | Selected claim will be rejected
TC_48 | To verify that manager can approve claim | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  | Sub-Status should by marked as mandatory field as manager is not able to approve claim without entering it. |  | Selected claim will be approved and no further change is possibe by dealer in that claim |  | Low | Fail
TC_49 | To verify that approval date is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | Approval date will be automatically captured
TC_50 | To verify that approval time is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | Approval time will be automatically captured
TC_51 | To verify that rejection date is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | rejection date will be automatically captured
TC_52 | To verify that rejection time is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | rejection time will be automatically captured
TC_53 | To verify that claim matured date is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | Date of last submitted document/last comment in portal will be captured
TC_54 | To verify that claim matured time is automatically captured | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on edit 4) Change status to Approved |  |  |  | Time of last submitted document/last comment in portal will be captured
TC_55 | To verify that allingment of EW Detail page correct | Login cridential provided | 1) Login with manager/Dealer account 2) Select claim |  | EW Detail page is not allinged properly |  | EW Detail page should be allinged properly |  | Low | Fail
TC_56 | To verify that all details present in EW detail page is on report | Login cridential provided | 1) Go to reports 2) Click on EW Claims dump 3) Select date |  |  |  | All task approved between selected date will be downloaded with all the details
TC_57 | To verify that dealer is able to create Claim of previous date of job card | Login cridential provided | 1) Login with manager/Dealer account 2) Select Add claim | Job Card No :-1478523 Date of Job Card :- 20-02-2012 Failure Date :- 20-02-2012 Odometer Reading :- 60000 Warranty Admin Name :- @@ Dealer Email :- bhola@shola.com Dealer Contact No :- 7894561230 Diagnosis Done by Dealer :- 1223 | Claim on previous date is generated |  | Can’t create calim on previous date |  | Low | Fail
TC_58 | To verify that Manager can enter Surveyor contact number | Login cridential provided | 1) Login with manager account 2) Select claim 3) Click on Edit | Surveyor contact numbe :- 123 | There is no validation |  | Surveyor contact numbe Should be of 10 digit |  | Low | Fail
TC_59 | To verify that Dealer can Add part Info. | Login cridential provided | 1) Login with dealer account 2) Select Add claim 3) Click on Add part info. |  | There is no GST on part price |  | There should be GST on part price |  | Low | Fail
TC_60 | To verify that Date of job card is accepting right Data | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | Date of job card is accepting older date than Ext . Warranty Start Date |  | Date of job card should not accept older date than Ext. Warranty Start Date |  | Low | Fail
TC_61 | To verify that Dealer E-mail ID is accepting right Data | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | Dealer E-mail ID is accepting wrong data |  | Invalid Dealer E-mail ID msg. will display |  | Low | Fail
TC_62 | To verify that Diagnosis done by Dealer is accepting right Data | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | Diagnosis done by dealer field is accepting special character |  | Diagnosis done by dealer field should not accept special character |  | Low | Fail
TC_63 | To verify that Dealer can create new Miscellaneous Expenses | Login cridential provided | 1) Login with manager/Dealer account 2) Add claim |  | Creating New Miscellaneous Expenses Gst is not working |  | Creating New Miscellaneous Expenses Gst should work |  | Low | Fail

## Agreement
Project Name: Ashok_Leyland
Created By:- | Atyab Alam |  |  |  | Reviewed By:- |  |  | Pre-condition :- | Login credential
Creation Date:- | 2020-02-20 |  |  |  | Review Date:- |  |  | Developed By :- | Vikash Jha
Version: - |  |  |  |  | Module:- | Agreement
Test Case ID/ Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_01/ Agreement | 10098 | 2020-02-20 | To verify that Dealer is able to login to Ashok Leyland EW | Login cridential provided | ID :- rainbow-salem P.W. :- Welcome@123 |  |  |  | Will be able to login.
TC_02/ Agreement | 10098 | 2020-02-20 | To verify that Dealer is able to Navigate to Agreement Page | Login cridential provided | Click on Agreement on top left of the screen |  |  |  | Will be navigated to Agreement Page
TC_03/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | Leave all field blank and click on Save |  |  | This field is mandatory msg. will be displayed on top of mandatory field
TC_04/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- Address :- Postal Code :- City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- | There is no condition on First Name |  | Invalid Name |  | Low | Fail
TC_05/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 987654321 Address :- Postal Code :- City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Mobile Phone No. should be of 10-digit
TC_06/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- | There is no condition on Address |  | Invalid Address |  | Low | Fail
TC_07/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123 City :- State :- Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Postal Code should be 6 digit number msg. will be displayed
TC_08/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Vehicle Invoice Date :- Make :- Registration Type :- Model :- Variant :- Fuel Type :- Vehicle Chassis No :- Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | This field is mandatory msg. will be displayed on top of all remaining mandatory field
TC_09/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH1234 Registration No :- Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- |  |  | Vehicle Chassis No. can only be of 17 digit validation msg. will appear
TC_10/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- Vehicle Delivery Date :- Engine No :- Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- | There is no condition on registration No. |  | Invalid Registration Number |  | Low | Fail
TC_11/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- 2000 Vehicle Delivery Date :- 22-07-2019 Engine No :- 1234567890ASDFGHJKL Extended Warranty :- EWS Retail :- Sales By :- Sales Manager Name :- Executive Name :- | There is no condition on Engine No. |  | Invalid Engine No. |  | Low | Fail
TC_12/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- 2000 Vehicle Delivery Date :- 22-07-2019 Engine No :- 1234567890ASDFGHJKL Extended Warranty :- EW3 1Years / 50000 Kms EWS Retail :- EWS4674 Sales By :- Sales Sales Manager Name :- Bhola Executive Name :- GOLU |  |  | New Agreement will be Added
TC_13/ Agreement | 10098 | 2020-02-20 | To Verify that Dealer is able to Add-Agreement | Login cridential provided | Click on Add-Agreement | First Name :- @#12 Mobile Phone :- 9876543210 Address :- @# Postal Code :- 123456 City :- Salem State :- Tamil Nadu Assigned To :- Rainbow Motors Commercial Division Vehicle Invoice Date :- 19-07-2019 Make :- Ashok Leyland Registration Type :- Commercial Fuel Type :- Diesel Vehicle Chassis No :- AB1CD23E4FGH12345 Registration No :- 1234567890QWERTYUIOP Odometer Reading :- 2000 Vehicle Delivery Date :- 22-07-2019 Engine No :- 1234567890ASDFGHJKL Extended Warranty :- EW3 1Years / 50000 Kms EWS Retail :- EWS4674 Sales By :- Sales Sales Manager Name :- ## Executive Name :- #@ | Accepting Invalid Sales manager name and Executive Name |  | Invalid Sales manager name and Executive Name |  | Low | Fail
TC_14/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Agreement Number | Login cridential provided | Click on search box below Agreement Number | Agreement Number :- SO95221 |  |  | Agreement with agreement No. SO95221 will display
TC_15/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by First Name | Login cridential provided | Click on search box below First Name | First Name :- #12 |  |  | All agreement with first name #12 will display
TC_16/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Last Name | Login cridential provided | Click on search box below Last Name | Last Name :- s |  |  | All agreement with Last Name :- S will be displayed
TC_17/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Variant | Login cridential provided | Click on search box below Variant | Variant :- Dost+ |  |  | All agreement with Variant :- Dost+ will display
TC_18/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Vehicle Chassis No | Login cridential provided |  | Vehicle Chassis No :- AB1CD23E4FGH12340 |  |  | Agreement with Vehicle Chassis No :- AB1CD23E4FGH12340 will be displayed
TC_19/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Assigned To | Login cridential provided |  | Assigned To :- Rainbow Motors Commercial Division |  |  | All agreement assinged ti Rainbow Motors Commercial Division will display
TC_20/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Created Time :- 19-02-2020,20-02-2020 | Login cridential provided |  | Created Time :- 19-02-2020,20-02-2020 | Instead of Created Time it is searching with Created Date |  | All agreement created between selected date will appear. |  | Low | Fail
TC_21/ Agreement | 10098 | 2020-02-20 | To verify that dealer is able to search agreement by Status | Login cridential provided |  | Status :- Active |  |  | All agreement whose status is active will be displayed
TC_22/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Active Agreement | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Active Agreement |  |  |  | All agreement whose status is active will be Filtered
TC_23/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Cancelled Agreements | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Cancelled Agreements |  |  |  | All agreement whose status is cancel will be Filtered
TC_24/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Pending for amendment | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Pending for amendment |  |  |  | All agreement whose status is Pending for amendment will be Filtered
TC_25/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Pending for cancellation | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Pending for cancellation |  |  |  | All agreement whose status is Pending for cancellation will be Filtered
TC_26/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Request for cancel Agreement | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Request for cancel Agreement |  |  |  | All agreement whose status is Request for cancel Agreement will be Filtered
TC_27/ Agreement | 10098 | 2020-02-20 | To verify that dealer can filter agreement by Total Agreement | Login cridential provided | 1) Click on filter on present on top center of screen 2) Click on Total Agreement |  |  |  | All agreement will display
TC_28/ Agreement | 10098 | 2020-02-20 | To verify that status of agreement changes when warranty end date expires | Login cridential provided | 1) Click on agreement 2) open any agreement |  | Even when Ext. Warranty End Date is expired status remains active |  | Status will change to expired when Ext. Warranty End Date is expired |  | Low | Fail