## Module wise plan
Module | overall Priority | Phase 1 | Phase 2 | To be shared by LPT |  | Completion date
Login | Phase 2 | Exiting feature | Entire module | Logo, SplashScreen text/Image , Login api's | P1 |  | logo new or old
Home Page POP UP | Phase 1 | Entire module | - | All Images, GIF, Video
Home Page | Phase 2 | Exiting feature | Entire module
Side Drawer | Phase 1 | Entire module | - | as per FSD
Catalog | Phase 1 | Entire module | -
Scheme | Phase 1 | Entire module | - | Thumbnail images, PDF
Price List | Phase 1 | Entire module | - | Thumbnail images, PDF
E Warranty Scanner-Android | Phase 1 | Entire module | - | LPT api's
Scheme Page Info | Phase 1 | Entire module |  | Image and T&C content
Check Serial Number warranty | Phase 2 | - | Entire module
Notification | Phase 2 | - | Entire module
Distributor Report | Phase 2 | - | Entire module
Dealer Management Report | Phase 2 | - | Entire module
E Warranty | Phase 1 | entire module time may vary as its depends on LPT API | - | LPT api's
Profile | Phase 2 | - | Entire module
Contact Us | Phase 2 | Existing Feature | Entire module
FAQ | Phase 2 | Existing Feature | Entire module
Partner Certificate | Phase 2 | - | Entire module
Product BIS Certificate | Phase 2 | - | Entire module
Multiple Contest | Phase 2 | - | Entire module
Digital Scheme Framework | Phase 2 | On Going- scheme specific as per latest scheme | -
Application frontend and Anaytics | Phase 1 | 1- entire module | -
Solar Calculator | On Going | On Going | -
Survey | Phase 2 | - | Entire module

## Time estimation
Module |  | Project manager | iOS | iOS-Buffer | Android | Android-Buffer | .net | .net-Buffer | QA | QA-Buffer | UI | UI-Buffer | Sub Total with buffer | Remarks
Login | Days |  | 9 | 13.5 | 9 | 13.5 | 7 | 10.5 | 1 | 1 | 4 | 4 | 42.5
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Sales and marketing | Days |  | 7 | 10.5 | 7 | 10.5 | 12 | 18 | 3 | 3 | 1 | 1
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Home Page POP UP | Days |  | 10 | 10 | 10 | 10 | 7 | 7 | 2 | 2 | 2 | 2 | 29
| Resource |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
Home Page | Days |  | 16 | 24 | 16 | 24 | 16 | 24 | 5 | 5 | 2 | 2 | 49
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Side Drawer | Days |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 8
| Resource |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
Catalog | Days |  | 30 | 45 | 30 | 45 | 7 | 10.5 | 6 | 6 | 3 | 3 | 109.5
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Scheme | Days |  | 12 | 18 | 12 | 18 | 5 | 7.5 | 3 | 3 | 2 | 2 | 48.5
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Price List | Days |  | 12 | 18 | 12 | 18 | 5 | 7.5 | 3 | 3 | 2 | 2 | 48.5
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
E Warranty Scanner-Android | Days |  | 1.5 | 2.25 | 1.5 | 2.25 | 1 | 1.5 | 1 | 1 | 1 | 1 | 8
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Scheme Page Info | Days |  | 5 | 7.5 | 5 | 7.5 | 1 | 1.5 | 2 | 2 | 2 | 2 | 20.5
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Check Serial Number warranty | Days |  | 3 | 4.5 | 3 | 4.5 | LPT Effort |  | 1 | 1 | 1 | 1 | 11
| Resource |  | 1.5 |  | 1.5 |  |  |  | 1 |  | 1
Notification | Days |  | 20 | 30 | 20 | 30 | 25 | 37.5 | 5 | 5 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Distributor Report | Days |  | 15 | 22.5 | 15 | 22.5 | 10 + LPT Effort | 15 | 5 | 5 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Dealer Management Report | Days |  | 15 | 22.5 | 15 | 22.5 | 10+LPT Effort | 15 | 5 | 5 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
E Warranty | Days |  | 10 | 15 | 10 | 15 | LPT Effort |  | 4 | 4 | 2 | 2 | 36
| Resource |  | 1.5 |  | 1.5 |  |  |  | 1 |  | 1
Profile | Days |  | 12 | 18 | 12 | 18 | 10 | 15 | 4 | 4 | 0 | 0
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Contact Us | Days |  | 1 | 1.5 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 0 | 0
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 0
FAQ | Days |  | 3 | 4.5 | 3 | 4.5 | 2 | 3 | 2 | 2 | 1 | 1
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Partner Certificate | Days |  | 7 | 10.5 | 7 | 10.5 | 5 | 7.5 | 2 | 2 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Product BIS Certificate | Days |  | 4 | 6 | 4 | 6 | 4 | 6 | 2 | 2 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Multiple Contest | Days |  |  | TBD |  | TBD |  | TBD |  | TBD |  | TBD |  | need discussion
Resource
Digital Scheme Framework | Days |  |  | TBD |  | TBD |  | TBD |  | TBD |  | TBD |  | On Going- scheme specific as per latest scheme
Resource
Application frontend and Anaytics | Days |  |  | TBD |  | TBD |  | TBD |  | TBD |  | TBD |  | need discussion
Resource
Solar Calculator | Days |  |  | TBD |  | TBD |  | TBD |  | TBD |  | TBD |  | On Going
Resource
Survey | Days |  | 7 | 10.5 | 7 | 10.5 | 12 | 18 | 4 | 4 | 2 | 2
| Resource |  | 1.5 |  | 1.5 |  | 1.5 |  | 1 |  | 1
Total effort |  |  |  | 296.25 |  | 296.25 |  | 208.5 |  | 62 |  | 36 | 416
|  |  |  | 13.4659 | [7 empty] | 899
|  |  |  | 875284.0909 | [7 empty] | 40.8636
4495

## internal priority
Client Priority | Module Name | Sub Module | Work prority | UAT Completion date | UI Status | UI Status | Api Status | Api Status | Status-android | Status-iOS | QA status | Remarks
[5 empty] | Planned | Actual | Planned | Actual
Priority 1 | Splash |  | 3 | 2020-06-10 | 2020-07-10 | Done | NA |  | Done | Done
| Login | Language selection | 3 | 2020-07-10 | 2020-07-10 | Done | Pending |  | Done | Done |  | We can go with the existing login feature if we are running out of time as per the plan- conffimed by client also
|  | Login |  |  | 2020-07-10 | Done | Pending |  | Done | Done
|  | Forgot Password | [6 empty] | Pending (password functionaliy)
|  | OTP |  |  | 2020-07-10 | Done | Pending |  | Pending (password functionaliy) | Pending (password functionaliy)
| Dashboard | Side drawer | 2 | 13-10-20 | 2020-08-10 | Done | Done |  | Done | Done
|  | Bottom bar |  | 13-10-20 | 2020-08-10 | Done | Done |  | Done | Done
|  | Notification Popup |  | 16-10-20 | 2020-08-10 | Done | Done |  | Done | Done
|  | Main screen |  | 20-10-20 | 2020-08-10 | Done | Pending |  | Pending(Product Search & Sub header UI and functionality) | Pending(Product Search & Sub header UI and functionality)
| Catelog |  | 4 | 27-10-20 | 2020-08-10 | Done | Pending |  | Done- Pending (Product Search functionality and UI Pending ) | Done- Pending (Product Search functionality and UI Pending )
| Scheme |  | 6 | 2020-10-11 | 2020-08-10 | Done | Pending |  | Done | Done
| PriceList |  | 7 | 14-11-20 | 2020-08-10 | Done | Pending |  | Done | Done
| Luminous youtube(Gallery) |  | 8 | 21-11-20 | 2020-09-10 |  | NA
| ContactUs |  | 9 | 18-11-20 | 2020-09-10 | Done | Pending |  | Done | Done
| Ewarranty | Main Page | 5 | 2020-03-11 | 2020-09-10 | Done | Pending |  | Done
|  | Mobile no. popup |  |  | 2020-09-10 | Done | Pending |  | Done
|  | Scanning |  |  | 2020-09-10 | Done | Pending |  | Done
|  | Otp popup |  |  | 2020-09-10 |  | Pending |  | Done
|  | Form |  |  | 2020-09-10 |  | Pending
Working
| Solar Calculator | OFF-GRID |  | NA | Done |  | Done |  |  | Done
|  | ON-GRID | 1 | Done | Done |  | Done |  |  | Done
|  |  |  | Last development date 18-11-20 | [6 empty] | End to end QA start from 19-11-20
| Home page- top menu | Top bar | 1 | 20-11-20
Priority 2 | Guest User Login |  | 1 | 24-11-20
| Survey |  |  | 28-11-20
| Product BIS Certificate |  |  | 2020-03-12
| FAQ |  |  | 2020-05-12
| Partner Certificate |  |  | 2020-08-12
| Profile |  |  | 2020-10-12
| Dealer Management Report |  |  | 25-12-20
| Distributor Report |  |  | 2021-08-01
| Notification |  |  | 16-1-2021
| Check Serial No. Warranty |  |  | 21-1-2021
Phase 2 UAT: 21-1-2021

## Login
| Requirement | Query | Effort | Effort | in days
| Once the app is installed, user will click on the app icon |  | App : 7 | Ios : | 9
| on click a splash screen should get displayed | this spalsh screen need to be dynamic - optional Need to provide image dimention to LPT | Backend : 7 | Android : | 9
|  | but incase there is some network issue the screen may take time to load as per the speed of the network or even may not load | UI : 2 | API | 7
| after the splash screen a welcome page should get displayed with option to select the langualge | list of language required ( currently will go with hindi and english but need an option where we can add other language in future) |  | QA | 4
| if user skips the page login page should get displayed |  |  | UI
Login will be done with registered mobile number with SAP
| OTP will be sent to that registered number | this parent user will have the option to add two child number in the profile section
|  | and if the user try to login with that number, system should allow. App should auto logout if user is removed Add user option will only be there in profile page |  | * Assume 1.5 resource for Ios, Android and API
| User can also skip the login process |  |  | * Assume 1QA for mobile and 1 for backend
| If the user skips the login , then only few modules will be available for the said user. | need the list of open modules
need to maintain user db for both primary and secondary user
| Updated Requirement | remark
Login | First login will be done by OTP, that will sent to registerd Phone no and email | OTP will be sent from LPT side
| after successful OTP submission, User can genarate new password | new pass will be stored at DB
User can login on one 1 device at a time, if he is already logged in on other device, it will logout automatically
Forgot Password | There will be an option for Forgot password link
| Clicking on it, will send OTP to Registerd Phone no and email | OTP will be sent from LPT side
| after successful OTP submission, User can genarate new password | new pass will be stored at DB
Skip | User can also skip the login process
| If the user skips the login , then only few modules will be available for the said user. | need the list of open modules

## UAT Tracker
Module | Type | Category | Point description | Reported Date | Resolved Date | Remarks | Android Status | Android QA | iOS status | iOS QA
Dashboard | Revamp | Enchancement | Home icon in footer is not needed as Luminous Logo is itself a home button | 27/11/20 | 2020-11-12 |  | done | backend side | done
Dashboard | Revamp | Enchancement | POP up holder will have no borders | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Catalog | Revamp | bug | Catalog-INBT and solar tabs are missing in level 2 and 3 | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Catalog | Revamp | Enchancement | Product pdf should open in full screen, currently it opens in mid of the screen with no data | 27/11/20 | 2020-11-12 |  | done | Fixed-Opening in full screen and also download and share buttons are coming on PDF viewer. | done
Catalog | Revamp | Enchancement | Product PDF Download, share and close options are not in proposal as these actions can be managed from inside the PDF viewer (functionality already available in PDF viewer) | 27/11/20 | 2020-11-12 |  | done with custome pdf viewer | Fixed-Opening in full screen and also download and share buttons are coming on PDF viewer. | done with custome pdf viewer
Catalog | Revamp | bug | What is message “Max length size 1” in catalog? | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Catalog | Revamp | Enchancement | PoP up loading screen is not good, hope it is just for testing and will be fixed in final cut | 27/11/20 | 2020-11-12 |  | done | NA | done
Catalog search | Revamp | Enchancement | Search and notification icons are not matching with with profile icon | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Catalog search | Revamp | Enchancement | search and notification icons are in bolds whereas profile icon looks normal | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Catalog search | Revamp | bug | cross button in search bar is not working | 27/11/20 | 2020-11-12 |  | done | Fixed | done
Contact Us | Revamp | bug | Contact us- E will be small in “Test address” | 2020-01-12 | 2020-11-13 |  | done | Fixed | done
Contact Us | Revamp | bug | Contact us-Email icon is in bolds whereas rest icons are not bold | 2020-01-12 | 2020-11-14 |  | done | Fixed | done
Price list | Revamp | bug | Pricelist-PDF is not opening as proposed | 2020-01-12 | 2020-11-15 |  | done | Opening in full screen and also download and share buttons are coming on PDF viewer. | done
Scheme | Revamp | bug | Scheme-PDF is not opening as proposed | 2020-01-12 | 2020-11-16 |  | done | Opening in full screen and also download and share buttons are coming on PDF viewer. | done
PDF viewer | Revamp | Enchancement | There should be a loader while loading the PDF file in PDF viewer. (Common for all the PDF sections). Please refer to the below video for more clarity: |  | 2020-11-16 | https://lh3.googleusercontent.com/U7w_AZtXI4vBe6OEoaMfeGF3xbX7pMInYIcWBp8YQuZMXUhS4ZMAP4M5GkoX5z00zMkvppHQSxgiVA=m37 | done | Fixed | done
catalog | Revamp | Enchancement | There should be a loader while switching from INBT to Solar and from Solar to INBT. Please refer to the video link below for more clarity: |  | 2020-11-16 | https://lh3.googleusercontent.com/D0M1nZvN422WhTPILplO99ql1OixgLuuRZCyQ51MOCrFriJOQG8opZg6APUF0-jAIFOHHXd0XHTR7Q=m18 | done | Fixed | done
contact us | Revamp | Bug | Contact Form is not getting submitted in android version 10. Getting http 400 error. |  |  | https://r3---sn-npoe7nl6.googlevideo.com/videoplayback?expire=1607414229&ei=tRXPX8vzIJmmlQSnpp7gBQ&ip=116.75.235.192&id=2f46b0ef4eed4d83&itag=18&source=picasa&begin=0&requiressl=yes&sc=yes&ttl=transient&susc=ph&app=fife&ic=473&eaua=EnEFQasTkGo&mime=video/mp4&dur=33.529&lmt=1607406924914014&sparams=expire,ei,ip,id,itag,source,requiressl,ttl,susc,app,ic,eaua,mime,dur,lmt&sig=AOq0QJ8wRgIhAIGTwhJN16t-GwW11fzMr4GekR142-Pjkv0mnU8XxptsAiEAqEyDhvJTj5-Cmq4CpzU1RivUaeJOc52MtqEdsCwpRkA=&redirect_counter=1&cm2rm=sn-qxak7s&req_id=fcc5c763f466a3ee&cms_redirect=yes&mh=Gw&mm=34&mn=sn-npoe7nl6&ms=ltu&mt=1607406991&mv=m&mvi=3&pl=22&lsparams=mh,mm,mn,ms,mv,mvi,pl,sc&lsig=AG3C_xAwRAIgdEvEInmshoK5_wP_-LQXU7gJhRxanLkbcXYbwqIiK8oCIClRgDMBPCm8mLc8JBd88gUAraycUOVqCW1o84_mBKoQ |  | not fixed
Login | Revamp | bug | First login-Shows wrong OTP | 15/12/20 | NA |  |  | Not Able to replicate this
Homepage | Revamp | bug | First login-footer icons were missing, refreshing the page did not work, have to login again for fixing it-video shared on whatsapp | 15/12/20 | NA | coming on Ankur's device only (android 10) |  | Not coming in my device
Forgot Pass | Revamp | Enchancement | Flow for forgot password event-Forgot password-directly share the OTP and open OTP submission screen, remove unnecessary clicks | 15/12/20 | 18/12/20 |  | done | Fixed
Forgot Pass | Revamp | Enchancement | Follow the password policy currently used in Luminous, except mandatory password change in 30-40 days | 15/12/20 | 18/12/20 | Minimum Password Length : 8 Characters (Alpha numeric with minimum 1 special character). | done | Fixed
Ad Creator | Existing | Enchancement | Language selection drop down will also be available on ad creator home page, currently it appears as a pop up when user opens the ad creator | 16/12/2020 | 21/12/20 |  |  | Fixed
Ad Creator | Existing | Enchancement | First attempt-Text type preview, text drag and drop placement, text font size options were not visible | 16/12/2020 |  | Not able to replicate
Ad Creator | Existing | Bug | All other attempts-no text is getting typed | 16/12/2020 |  | Not able to replicate
PDF viewer | Revamp | Bug | App will not have any inbuilt PDF viewer, most users have a 3rd party app to open/share/download the PDF | 28/12/2020 | 2021-11-01 | As discussed with client-Not an issue- ignore |  | Not an issue | Not an issue | Not an issue
Scheme | Revamp | Bug | No data in scheme and pricelist section-add data to test the same | 28/12/2020 | 2021-11-01 | Dummy data to be provided by LPT |  | Not an issue | Not an issue | Not an issue
Catalog | Revamp | Bug | Catalog-Sometime PDF in catalog section does not open-tested model (INBT>HUPS>Sine wave>Eco volt+ 850)-video shared on whatsapp | 28/12/2020 | 2021-11-01 | 1) add loader 2) if there is no PDF, dnt open frame, show alert msg |  | Fixed | Fixed
Popup | Revamp | Bug | POP up with purple buffering screen never loads completely (POP up loading time should be less than 1 second) | 28/12/2020 | 2021-11-01 |  | done gif is showing | Pending | Fixed
Popup | Revamp | Bug | POP ups still have borders | 28/12/2020 | 2021-11-01 |  | done | Fixed | Fixed
Login | Revamp | Change Request | Password is not case sensitive (Password policy-8 characters, alphanumeric, case sensitive, minimum 1 special character) | 28/12/2020 | 2021-11-01 | 1 Upper case-lower case | done | Fixed | Fixed
Login | Revamp | Enchancement | Password setting Hint is not complete-Include all conditions | 28/12/2020 | 2021-11-01 | 1)Add static text- Password should have 8-20 characters, alphanumeric, 1 Upper case, 1 lower case, minimum 1 special character 2) validation error should come- done 3)alert msg- Password should have 8-20 characters, alphanumeric, 1 Upper case, 1 lower case, minimum 1 special character | done | Fixed | Fixed
Side drawer | Revamp | Support | Side tray-Instead of mentioning “firm name” and “Sap code” display the details | 28/12/2020 | 2021-11-01 | https://prnt.sc/wcvkrl show by default profile icon | done from my side | Fixed | Fixed
profile | Revamp | Support | Dummy ID linked with my account is 9999982 but in profile section it is showing 9900000005 | 28/12/2020 | 2021-11-01 | coordinate with Ravi/rajesh |  | NA | comes from backed side (Luminous)
eWarranty | Revamp | Enchancement | remove Negative points & Final Points from the Table | 28/12/2020 | 2021-11-01 | https://prnt.sc/wbidam | done | Fixed | Fixed
Ewarranty | Revamp | Support | Majority dummy serial numbers are already scanned, please remove them from logs next time before sending | 28/12/2020 | 2021-11-01 | Not an issue, LPt side point | NA | Not an issue
Permission | Revamp | Bug | All the permissions (camera, storage etc.) should be taken at the time of login only in one go | 28/12/2020 | 2021-11-01 | allowed from ph setting, still asking everytime | done | Fixed
Permission | Revamp | Enchancement | After taking permissions directly proceed with the actions last tapped by user, don’t make him click and create the event again | 28/12/2020 | 2021-11-01 |  | done | Fixed
login | Revamp | Enchancement | Password-If user has reset his password, clear the previously filled password automatically, currently user has to delete the old wrong password manually | 28/12/2020 | 2021-11-01 |  | done | Fixed
Ewarranty | Revamp | Change Request | Ewarranty-As per the proposal after clicking the scanner icon first field will be of submitting user phone number to check how many serial numbers are already submitted with the entered mobile number, currently it ask to scan the QR codes and mobile number field is coming in next screen | 28/12/2020 | 2021-11-01 | we need to replace the currency logic with existing logic where only 10 serial can be scanned on a single customer no and Customer no will be inserted before serial no scanning procedure | Done | NA
Ewarranty | Revamp | Enchancement | Ewarranty-As per the proposal scanner layout will be horizontal and not vertical | 28/12/2020 | 2021-11-01 |  |  | Fixed
Ewarranty | Revamp | Enchancement | Ewarranty-Remove all the unnecessary messages like “scanned 8ghri7896j” & “wrs status ok, “scanned, primary billing with 1100808”, share the list of messages we are using, I will correct them as per the need of user | 28/12/2020 | 2021-11-01 | Toast for testing/UAT only not on prod LPT will share updated toast/error msg | done from my side showing backend split msg wrs status only | Fixed
Ewarranty | Revamp | Enchancement | Ewarranty-Don’t use term “OTP” anywhere use “warranty verification code” | 28/12/2020 | 2021-11-01 |  | done my side already given jitendra sheet | Fixed | fixed
Ewarranty | Revamp | bug | Ewarranty-If user scan same serial number twice in same attempt-in first attempt it showed message “error” while in next attempt it automatically removed the duplicate serial number | 28/12/2020 | 2021-11-01 | same serial no required from LPT more serila no required for QA |  | Not able to replicate
Ewarranty | Revamp | LPT Point | Ewarranty-SMS services are slow, user should receive the message within 3-5 seconds, keep it like banking standards (not received warranty verification code in last attempt) | 28/12/2020 | 2021-11-01 | LPT side point |  | NA
Ewarranty | Revamp | LPT Point | Ewarranty-Data is not getting saved in case of “without warranty verification code” | 28/12/2020 | 2021-11-01 | error in LPT api- TBD with ajay | done | NA
Ewarranty | Revamp | LPT Point | Ewarranty-Saved cards are not showing in report section, clicking PDF icon shows no data found | 28/12/2020 | 2021-11-01 | LPT side issue- 500 error | LPT side issue- 500 error | NA
Dashboard | Revamp | Support | All homepage banners were missing | 28/12/2020 | 2021-11-01 | need SS from LPT |  | NA
Toast msg | Revamp | Enchancement | Techfour will share all the toast msgs then LPT will share with us the modified content | 28/12/2020 | 2021-11-01 | pulkit will share |  | NA
Password | Revamp | Enchancement | Show eye icon to view the password | 28/12/2020 | 2021-11-01 | LPT approval received on Jitendra's suggest | done | Fixed | done
Ad Creator | Existing | bug | 1) Text size cannot be resized again if user has clicked done in font size slider, keep it open until image is saved by user | 29/12/2020 | 30/12/2020 |  | done | Fixed | its zoom in and zoom out
Ad Creator | Existing | Enchancement | 2) Entered text preview does not appear until the creative is touched again | 29/12/2020 | 30/12/2020 |  | done | Fixed | done
Ad Creator | Existing | Enchancement | 3) Text drag and drop is only working if text is dragged from its borders, user should be able to drag and drop text even from centre of the text box. | 29/12/2020 |  |  | done |  | done
Ad Creator | Existing | Enchancement | When there is no data available after selecting a partiular langauge then app must show a text message as "No data found". | 29/12/2020 | 30/12/2020 | https://lh3.googleusercontent.com/-RZoXiEOLA4M/X-rCg5rzVQI/AAAAAAAAEyE/Ggv91yRUv1wZzU6boPqhTRnIWSUxS-o-wCK8BGAsYHg/s0/2020-12-28.jpg | done |  | done
Ad Creator | Existing | Enchancement | Entered text should be freely resized. Currently added text stays horizontally. Please refer to the below screenshot for more details. | 29/12/2020 | 30/12/2020 | https://prnt.sc/vu2j1p https://lh3.googleusercontent.com/-Or254aTT0AY/X8csh7WYI1I/AAAAAAAADn8/aUC1OGDoWss4jAICIEZaL_2XrBRh95aWACK8BGAsYHg/s0/2020-12-01.jpg | discussed this points |  | fixed
Ad Creator | Existing | Bug | When changing the font size by extending/contracting the text, distorts the orientation of the text. | 30/12/2020 | NA |  | suggestion |  | suggestion
Home page | Revamp | Support | Homepage- Dummy Data Not Available | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | discussion
Catalogue | Revamp | Enchancement | Catalogue- We need a PDF download button under each category same briefed to Jyoti. | 20/1/21 | 28/1/21 |  | done | PDF is downloading but instead of file name URL is coming as title. | done
Pricelist | Revamp | Support | Pricelist- Dealer pricelist is also visible to Distributor. Dummy Data under dealer header not available | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | discussion
Pricelist | Revamp | Support | Pricelist – Should opened up Instantly, Currently it takes time to opened | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | Fixed | done
Pricelist | Revamp | Support | 5. Pricelist- In Pricelist pdf why refresh option is given | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | Fixed | done
Scheme | Revamp | Support | 6. Scheme- Dealer Scheme is also visible to Distributor. Dummy Data under dealer header not available | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | discussion
Scheme | Revamp | Support | 7. Scheme– Should opened up Instantly, Currently it takes time to opened | 20/1/21 | 28/1/21 | For testing purpose I am using Mobile Number : 8506040497. | done | Fixed | done
contact us | Revamp | Bug | 8. Contact us- Getting “HTTP 500 Internal Server Error “ when submitting the message and uploading the image (screenshot shared on Attached) | 20/1/21 | 28/1/21 | https://prnt.sc/x9zaja | done | Fixed | done
contact us | Revamp | Support | 9. Contact us- Luminous care details are wrong, it is for UAT purpose only ? | 20/1/21 | 28/1/21 | https://prnt.sc/x9zclw | done | Not Fixed: Tel, sales Support and EMail lables are coming twice in a single line. | done
Ewarranty | Revamp | Bug | 10. E-Warranty- We are able to entered more than 10 cards via one mobile number. | 20/1/21 | 28/1/21 |  | only 10 no is scanning from my side just i have checked, pls update the sceanrio if any so can check on this behalf | NA | same
Ewarranty | Revamp | bug | 11. E-Warranty- After Entered Date of Sale there is no “slots available” page has opened. | 20/1/21 | 28/1/21 |  | need to discuss | NA | discuss with LPT
Ewarranty | Revamp | bug | 12. E-Warranty- After Scanning one card page automatically back to the e-warranty page however it should continue scanning next card. | 20/1/21 | 28/1/21 |  | its as per flow | After scanning a qr code user gets move back to the Scan QR Code.
Ewarranty | Revamp | Enchancement | 13. E-Warranty- Please hide “Get Assist” tab | 20/1/21 | 28/1/21 |  | done | Fixed | done
Ewarranty | Revamp | bug | 14. E-Warranty- Scanned Serial numbers tab has been freezed not able to check out scanned serial numbers. | 20/1/21 | 28/1/21 |  | its not coming | NA | its not coming
Ewarranty | Revamp | bug | 15. E-Warranty- In report section, clicking PDF icon shows no details. | 20/1/21 | 28/1/21 |  | Done | "No data found" toast is coming. Either toast message should get changed to some meaningful nessage or add some data for testing. | done

## Alert msgs
Module | Condition | current Toast/Alert/Error/Validation msg | New Msgs by LPT
Login | Empty LPT Employe Code | Please enter Phone No or LPT Employee code.
| Wrong LPT Employe Code | Invalid Distributor/Dealer Code
| Status == "0" (error) | Invalid Distributor/Dealer Code
| Status == 200 (success) | Valid user
Password | Password Empty | Please enter password
| Password less than 8 digit | Password length should be 8 to 20 character
| Password Not In Combination | Password should be Alphanumeric with minimum 1 special character
| Password Does Not Match | NA
| Password Correct | Password verified successfully
| Status == 200 (success) | OTP verified successfully
| Status == 0 (error) | Invalid password
OTP | Empty OTP | Please enter OTP
| Wrong OTP | WRONG OTP
| OTP Correct | OTP verified successfully
| Status == 200 (success) | OTP verified successfully
| Status == 0 (error) | Invalid OTP
LoginCreatePassword | New Password Empty | Please enter new password
| Confirm Password Empty | Please enter confirm password
| New Password less than 8 digit | Password length should be 8 to 20 characters
| Confirm Password less than 8 digit | Password length should be 8 to 20 characters
| New Password Is Not Correct | Password should have 8-20 characters, alphanumeric, 1 Upper case, 1 lower case, minimum 1 special character
DashBoard | Status == 200 (success) | OTP verified successfully
| Status == 0 (error) | No Data Found
Survey Notification Alert | Status == 200 (success) | Data fetched successfully
| Status == 0 (error) | REPEATABLE NOTIFICATION
Profile | Status == 0 (error) | Unauthorized access
| Status == 200 | Data fetched successfully
| User Name == empty | Please Enter The User Name
| Business Name ==empty | Please Enter The Business Name
| Aniversary Date == empty | Please Enter The Aniversary Date
| Date Of Birth ==empty | Please Enter The Date Of Birth
| Email ID == empty | Please Enter The Email ID
| Email ID Enter Wrong Format | Please enter valid Email ID
| SAP Phone No == empty | Please Enter The SAP Phone No
| Address == empty | Please Enter The Address
| Password == empty | Please Enter The Password
| Secondary Device 1 == empty | Please Enter The Secondary Device 1
| Secondary Device 1 Enter Wrong Detail | Please Enter The Valid Secondary Device 1
| Secondary Device 2 == empty | Please Enter The Secondary Device 2
| Secondary Device 2 Enter Wrong Detail | Please Enter The Valid Secondary Device 2
Luminious YouTube | Status == 200 (success) | youtube#playlistItem
| Status == 0 (error) | Error while loading channel videos
SolarCalculator Solar Display | Status == 0 (error) | " No Data Available "
solar Calculation | RunningLoad == empty | Please enter Total Load"
| TotalLoad == empty | Please enter Average Running Load
| BackUpTime == empty | Please Select Backup Time
| totalLoad < 10 | Total Load must be a number between 100 and 10000
| totalLoad > 10000 | Total Load must be a number between 100 and 10000
solar> Appliance | if item Selected | You have selected the Appliances
| SelectedList == empty | Please Select Appliances
Location OnGrid | Pincode Limit | 6
| PinCode == empty | Please Enter Pincode
| if pincode is wrong entered | Please Enter Valid Pincode
| state == empty | Please Select State
| City == empty | Please Select City
| Bill2 == empty | Please Enter Monthly Bill
| bill! < 1 | Please Enter Valid Monthly Bill
Detail PopUp | Phone < 10 | Please enter a valid phone no
| SaleDate == empty | Please select a sale date
| OTP == 0 (error) | Please enter a valid OTP
EWarrenty PopUp | SaleDate == empty | Please select a sale date
| MobNo < 10 | Please Enter Valid MobileNo.
EWarranty Customer Detail | fullName == empty | Please Enter Full Name
| state == empty | Please Select State
| city == empty | Please Select City
| address == empty | Please Enter Address
Multiple Scan | if clicks on delete Btn on scan | Do you want to delete this item?
| Serial Number < 1 | Please scan Serial Number
| if all serial no is scanned by user | Entry Failed : 10 serial numbers are already registered with this number (given by LPT)
| if user enter Serial Number more than given count | Maximum limit to scan the code has reached
FAQ's | Status == 200 (success) | Data fetched successfully
| Status == 0 (error) | No Data Found
Contact Us | Status == 200 (success) | Data fetched successfully
| Status == 0 (error) | No Data Found
| if clicks on submit Btn | Thank you for your feedback
Scheme | Status == 200 (success) | Data fetched successfully
| Status == 0 (error) | No Data Found
PriceList | Status == 200 (success) | Data fetched successfully
| Status == 0 (error) | No Data Found

## Home page pop-ups
Requirement | Query | Effort | in days
Full page POP-UP capable of playing videos/GIFS/Image 1> type one permanent popup ( will be visible everytime the app opens ) 2> type two one time popup ( will be visible to user only once) | need clarity | Ios : | 10
|  | Android : | 10
|  | API | 7
|  | QA | 2
|  | UI | 2
* Assume 1 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Sales and Marketing team
Requirement | Query | Effort | in days
•Login based on employee code (8 digit) only numeric – Only One device login allowed for 1 Phone no. | will provide a link for emplyee on the login page | Ios : | 7
| need option inbackend to maintain emplyee code to add or remove LPT API will be called to validate the user and send the API | Android : | 7
need employee maping with disty | need to check if T4 have any API | API | 12
•Following Sections to be visible |  | QA | 3
•Catalog |  | UI | 1
•Pricelist
•Scheme
•Gallery |  | * Assume 1.5 resource for Ios, Android and API
•Home Page |  | * Assume 1QA for mobile and 1 for backend
•Profile (to be fetched from Luminous Portal app DB)
•FAQ
•Distributor Report - Addition of an extra drop down with distributor SAP codes (mapped to that sales team member) and then view report for that distributor
•Dealer Report – In case of digital schemes for mapped dealers in a way similar to Distributor
report, showing point achievements and other details in digital schemes and E-Warranty
guest login
catalog

## Home Page
Requirement | Query | Effort | in days
User permission based homepage (Different content for different users- hierarchy based) | will this include every image in the home page | Ios : | 16
Digital scheme launcher button in center of footer grid with dynamic icon (Like Swiggy pop button in size and will remain hidden in case no digital scheme is running) | digital scheme can be user specific in that case this button should be visible to only those users who are eligible for digital scheme | Android : | 16
|  | API | 16
|  | QA | 5
|  | UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Side Drawer
-1
| Requirement | Query | Effort | in days
| see profile option to be removed |  | Ios : | 2
| catalog, pricelist, scheme and e-warranty to be removed |  | Android : | 2
| rename gallery to "Luminous Youtube" and remove the option from side drawer |  | API | 2
| gallery, dealer management, report, service escalation to be removed from side drawer and need to create a scrollable header in home page | this sub header should be dunamic | QA | 1
| 1 tab for all service functionality | rename service escaltion to service | UI | 1
Winter maha festival tab to be removed
| Home tab to be part of header | not required in side drawer. Need to add home icon with Luminous header
| "check serial number warranty status " new tab to be added, this option will also be there in sub header |  | * Assume 1 resource for Ios, Android and API

## Catalog
| Requirement |  | Effort | in days
1 | This module will be visible to all users i.e (dealer, distributor, LPT employee and genral useres) | login autentication not required for this module | Query | 30
2 | Dynamic category Lable |  | Android : | 30
3 | Dynamic thumbnail for product category | this thumbnail will only have image or do we need text | API | 7
4 | Dynamic product list | this thumbnail will only have image or do we need text | QA | 6
|  | on click should we open the PDF in the app it self and have a download option | UI | 3
this pdf will also be dynamic
5 | The catalog in the bottom | on click should we open the PDF in the app in pdf viewer
|  | this pdf will also be dynamic | * Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Schemes
| Requirement | Query | Effort | in days
1 | this module will be restricted for User | can we have different scheemes with in the dealer --------there can be different schemes with in the dealer eg Scheme A and B for dealer 1 and Scheme Band c for dealer 2 in that case disty will see all three scheme i.e A,B,C | Ios : | 12
| Dealer can view his specific scheme |  | Android : | 12
| Distributor can view both i.e his specific scheme and the scheme running for his mapped delaers |  | API | 5
|  |  | QA | 3
2 | Distributor should have swipe and tap both option for this screen |  | UI | 2
3 | Dynamic scheme tiles with scheme thumbnail. Clicking tile will open PDF for view in PDF viewer (Download and share will be done from PDF viewer only)
4 | Switch of selecting dealer or distributor scheme (only for distributor, in dealer ID switch will not display)
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## PriceList
pricelisraccessScheem
| Requirement | Query | Effort | in days
1 | Swipe and tap enabled dealer and distributor page selection for distributor |  | Ios : | 12
2 | Switch of selecting dealer or distributor pricelist (only for distributor, in dealer ID switch will not display) |  | Android : | 12
3 | Dynamic Category tiles in same order with vector icons. Clicking category tile will open PDF for view in PDF viewer (Download and share will be done from PDF viewer only) |  | API | 5
| this module will be restricted for User | same as scheme | QA | 3
| Dealer can view his specific pricelist |  | UI | 2
Distributor can view both i.e his specific pricelist and the pricelist for his mapped delaers
4 | Disty price list should be visible based on the channel | dealer will able to see the price list based on the mapped disty
|  | if dealer is mapped with multiple disty , the price list of all the mapped disty will be visible to that dealer | * Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Ewarranty scanner
Requirement | Query | Effort | in days
Instead of bar code and QR code icons open scanner directly when user click scanner tab |  | Ios : | 1.5
Existing scanner open in a horizontal layout but it should be vertical and without any message | need to check if any licenced library available | Android : | 1.5
|  | API | 1
|  | QA | 1
|  | UI | 1
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Scheme info Page
Requirement | Query | Effort | in days
|  | Ios : | 5
only text and a thumbnail with an option to view in pdf viewer, also option to zoom in and zoom out the text |  | Android : | 5
|  | API | 1
|  | QA | 2
|  | UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Gallery
Requirement | Query | Effort - under discussion
To be Visible to Non- Login users as well
module name gallery to be changed to Luminous Youtube
When user clicks on Video option on sub header , youtube should get open (luminous channel) | need to check if we can open a specific channel
need to if we can play youtube in app

## Check serial number warranty
Requirement | Query | Effort | in days
New module to be created |  | Ios : | 3
user will enter the serial number | serial number will be entered manually or will be scanned | Android : | 3
on submit the detilas will get displayed | LPT will provide the API | API | LPT Effort
warranty expiry date to be removed |  | QA | 1
|  | UI | 1
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Notification
Requirement | Query | Effort | in days
on bell icon Count of unread notification should get displayed |  | Ios : | 20
latest entry should come first |  | Android : | 20
google and in app notification both to be manageged |  | QA | 5
need thumbnail view for text, video, GIF |  | API | 25
Video and GIF link can be visible in notification barm click on it will open video/gif sepratly |  | UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Distributor report
|  | S1,S2 will be in dropdown | Latest scheme will be on top
|  | Output- Summary and PDF option | No limit on description
If scheme is closed, remove from dropdown- not decided yet by LPT
Requirement | Query | Effort | in days
New module to be created - Distributor report |  | Ios : | 15
In this module only Primary billing and customer ledger report will be available |  | Android : | 15
other scheme live dashboard and complete dynamic report in PDF view format | based on the business requirement the report will be developed | API | 10+LPT Effort
| need LPT API for scheme | QA | 5
|  | UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Dealer Management Report
Tab name will be Dealer Report
Requirement | Query | Effort | in days
|  | Ios : | 15
Distributor can search dealer with dealer code, name and phone number in app |  | Android : | 15
Full dealer details in email report | need clarity | API | 10+LPT Effort
Dealer creation by distributor will be verified and approved by sales team (BM and Coordinator) | will be discussed later once the business confirms the process | QA | 5
Scheme related reports for dealers to be available, like Lucky 7 and E-Warranty | for disty there will be an option to select the dealer and based on the dealer list of reports will be displayed . Dealer will only see his reports on selecting any report the predefined summary will be displayed and a detail report should be availble for email | UI | 2
create dealer option to be hidden
search dealer to be renamed to dealer performance
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## E-warranty
| Requirement | Query | Effort | in days
| New tabs to be created : |  | Ios : | 10
| 1> Earned Points | need the API from the 3rd party to featch the value | Android : | 10
| 2> Redeemed Points | need the API from the 3rd party to featch the value | API | LPT Effort
| 3> Redeem Points > pinelab integration "redeem now" | need the url to where the user will be navigated to redeem points | QA | 4
|  |  | UI | 2
Condition | Distributor have right to block dealer > in that case, redeem now buttom will not visible to dealer
E-warranty new validation
user will click on E-warranty tab
| On click a pop will be displayed with an option to enter the mobile number | validation for mobile number 1> not less than 10 digit number 2> should start with only 6,7,8,9 3> only numberic value | * Assume 1.5 resource for Ios, Android and API
| on submitting the mobile number LPT API will be called | Case 1: | * Assume 1QA for mobile and 1 for backend
If count of serial number received from the API for the entered phone number is 0 then a toast will appear showing “Phone number not eligible for E- warranty as 10 serial numbers are already registered with this phone number”
Case 2:
if the count eceived from the API is greater than zero the user will navigate to next page
On scanning the Serial number the API will get hit to check the validation of the serial number, if in response "Ok" is received
next field will get displayed to scan the next serial number
Dustbin icons against previously scanned serial numbers to remove that entry if wrongly scanned
If serial number fails on any condition it will show the relative message in toast below the serial number and that particular serial number will not be listed and user will continue with other serial numbers
Till maximum numbers of serial numbers allowed with entered phone number are scanned or user click submit serial numbers
After scanning maximum serial numbers or clicking submit button a popup will appear, mobile number will autofill and its not editable. Scan date will be sale Date which will be auto filled and non editable. When click on submit button an API will call to generate OTP to entered mobile no
| Message in OTP field will be-Fill the OTP sent to customers phone number to start E-warranty of the products Case 1: user can enter the OTP and submit Case 2: user can continue without OTP. Page will direct to customer details | when serial number is submitted below fields to sent from LPT which will be displayed: 1> serial number 2> Status 3> normal points 4> bouns points 5> mapped distributor if bonus point is blank in that case that field will not be visible.
option to select disty and sale date to be removed

## Profile
need a detailed discussion on profile during the process
Requirement | Query | Effort | in days
•Edit profile icon (pencil) for primary user so as to change all the profile details, it will be updated in Mpartner instantly with a message “Detail change are subject to verification” against the changed detail | LPT to confirm the editable filed and if the filed is editable whct will be verification and approval process | Ios : | 12
•Detail fields which Luminous team needs to verify before approving it will have a mandatory field of attaching related document when user change the respective field detail (Mobile number, E-mail, address, city, state-OTP & link based verification. 2 fields for addresses (SAP & Mpartner) | need clarity | Android : | 12
•(Change allowed only in Mpartner address for distributor-all fields allowed for dealers) | need clarity | API | 10
•Primary device user can add secondary user by entering phone number or remove it |  | QA | 4
|  | UI | 0
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## FAQs
need collapse and expand view | Effort | in days
| Ios : | 3
| Android : | 3
| API | 2
| QA | 2
| UI | 1
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## contact Us
Effort | in days
Ios : | 1
Android : | 1
API | 1
QA | 1
UI | 0
* Assume 1.5 resource for Ios, Android and API

## Product BIS certificate
there will be multiple PDFs | Effort | in days
in app this module will have thumbnail and certificae name | Ios : | 4
| Android : | 4
| API | 4
| QA | 2
| UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Partner Certificate
this option will be in side drawer |  | Effort | in days
on click this will work similar to FSE agreement | Static content with dynamic parameters | Ios : | 7
|  | Android : | 7
Discussion required-greeshma, LPT |  | API | 5
|  | QA | 2
|  | UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend

## Multiple contest
multiple contest on one user | Effort - need discussion

## Digital scheme framework
Super 7 | Existing functionality to be moved on revamp

## Application frontend and Anayti
page wise click count | Need carity of requirement
E-warranty dealer points
need this feature in admin panel

## survey module
survey can be user specific | Effort | in days
also count specific i.e if we need only first 100 respnce after the survey should get closed | Ios : | 7
| Android : | 7
| API | 12
| QA | 4
| UI | 2
* Assume 1.5 resource for Ios, Android and API
* Assume 1QA for mobile and 1 for backend