## Cover
Functional Test Cases
Project: ServInsur Code Refactoring
Synopsis | Created the initial functional test case document for ServInsur
Author(s) | Jitendra
Current Version
Date | 2021-02-05
Reference : | https://docs.google.com/spreadsheets/d/1CjamtfieFOQTxKgvt8pn_qFumWhVQiIMAOjsIFg-pIs/edit#gid=854562134

## References
https://docs.google.com/spreadsheets/d/1CjamtfieFOQTxKgvt8pn_qFumWhVQiIMAOjsIFg-pIs/edit#gid=854562134

## Bug Report
Servinsur-UAT
Project :- | Servinsur-sit1 |  |  |  | Lead_Devp. :- | Ajay/Pawan/Deepak
Created_By :- | Jitendra |  |  |  | Power_Task_I.D. :- | 13976
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status | Assigned to | Developers Comments | Retesting Power ID | Status | Testers Comments | Open_Date | Close_Date
13859 | TC_Visit_Schedule_03 | 1 | Need to remove Reason for rescheduling" when appointment date does not get changed. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | https://prnt.sc/yslqhs |  |  | Existing |  |  |  | DEV-UAT Issue
13859 | TC_Visit_Schedule_ | 2 | Need to remove "Appointment Time Slot is Required" when holiday is selected. |  |  |  | https://prnt.sc/yi79l7 |  |  | Existing |  |  |  | DEV-UAT Issue
13859 | TC_Visit_Schedule_ | 3 | Need to remove Reason for rescheduling when holiday is selected. |  |  |  | https://prnt.sc/yslud3 |  |  | Existing |  |  |  | DEV-UAT Issue
13859 |  | 4 | Not able to schedule visit as m getting error for appointment date. https://sit1ui-serv-insur.innov.co.in/complaints/view/333 |  |  |  | https://lh3.googleusercontent.com/-AD6WdcLjkR0/YCIfWW2d44I/AAAAAAAAGko/br0RBczY530ynbrkril2BkCqW7OQjBsVQCK8BGAsYHg/s0/2021-02-08.png |  |  | Fixed
13859 |  | 5 | Not able to assign an engineer as m getting error as "Time Slot is not found in Engineer time slot master." https://sit1ui-serv-insur.innov.co.in/complaints/view/324 |  |  |  | https://lh3.googleusercontent.com/-E4d39yx-hkc/YCIhkIFRdEI/AAAAAAAAGk0/BzKWDVBon5k6ureg3OCDvr-DnWex3NLLACK8BGAsYHg/s0/2021-02-08.png |  |  | New |  | Done
13859 |  | 6 | Remarks entered by repairer should be visible to the CSR when updating the status to Customer Nnot Contactable. | User is at case status update pop up. | 1) Select Customer Not Contactable as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  |  | Existing |  |  |  | DEV-UAT Issue
13859 |  | 7 | There is no need for showing "Reason for status field" when marking customer available. | User is at case status update pop up. | 1) Select Customer available as the case status. 2) Select valid reason. 3) Click on submit button. |  | https://prnt.sc/yi5l94 |  |  | Existing | Pawan |  |  | DEV-UAT Issue
13859 |  | 8 | Remarks entered by repairer should be visible to the CSR when updating the status to Cancelled by Repairer. | User is at case status update pop up. | 1) Select Cancelled by CSR as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  |  | Existing
13859 |  | 9 | Option to mark "customer not available" should not come to CSR user. |  |  |  | https://prnt.sc/yi7rcx https://prnt.sc/yi7y7n |  |  | New |  | first check case sub status in case_sub_status_csr if not found then case status value is wrong else Case status Mapping Issue |  | DEV-UAT Issue
13859 |  | 10 | Error is coming for entering invalid visit completion date when valid date is selected by the user. instance: sit 1 case id 331 |  |  |  | https://prnt.sc/ysrsjv |  |  | Fixed
13859 |  | 11 | Wrong validation is coming when user submits the estimate without selecting an Approve Type. It should be " Please select Approve Type instead of Request method is not valid. |  |  |  | https://prnt.sc/yt048j |  |  | New |  | This error is also occur on dev because in method nothing is to be pass estimation model line 138 |  | DEV-UAT Issue
13859 |  | 12 | Estimate Submission API: "Repair_Action": null, It should be blank instead of null. |  |  |  | https://prnt.sc/yt1m5s |  |  | New |  | Done
13859 |  | 13 | Error is coming when user approves an estimation. | https://sit1ui-serv-insur.innov.co.in/complaints/view/326?module=estimate |  |  | https://prnt.sc/ynjko0 |  |  | New |  | Done
13859 |  | 14 | Invoice Submit: Remarks field should be mandatory. |  |  |  | https://prnt.sc/ynnv52 |  |  | New |  |  |  |  | DEV-UAT issue
13859 |  | 15 | Invoice Approve: CA is not able to approve the invoice. |  |  |  | https://prnt.sc/yno3ep |  |  | New |  | Done
13859 |  | 16 | Wrong validation is coming when user submits the estimate approval form without selecting an Approve Type. It should be " Please select Approve Type instead of Request method is not valid. |  |  |  | https://prnt.sc/yt3l26 |  |  | New |  | same as pt 15 |  |  | DEV-UAT issues
13859 |  | 17 | Client side validation is not coming for leaving approve unit price field blank due to which getting above error from server side. sit 1 |  |  |  | https://lh3.googleusercontent.com/--UY0r-WZXq4/YCI0n_xqRpI/AAAAAAAAGlY/Mf-aVJ0xkHcqcoEUTrw_rChtWaxkGPZBACK8BGAsYHg/s0/2021-02-08.png |  |  | New |  | Done
13859 |  | 18 | Success message after approving the estimate is wrong. |  |  |  | https://prnt.sc/yt4tx3 |  |  | New |  | done
13859 |  | 19 | Invoice Estimate Rejected: "Some error occurred while retrieving data." is coming when repairer saving an estimation or submitting for approval. |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/331?module=tasks | https://prnt.sc/z358w6 https://prnt.sc/z35lgd |  |  | New |  | Not Found Plz cross check
13859 |  | 20 | Getting " Error! You do not have permission." when NM is downloading an invoice. |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/326?module=invoice | https://prnt.sc/z36nce |  |  | New |  | done
13859 |  | 21 | Network Manager shoud not have rights to upload, view file and delete invoice actions. |  |  |  | https://prnt.sc/z374c7 |  |  | New |  |  |  | DEV-UAT issues
13859 |  | 22 | Bulk Invoice (NM): Instead of job ID system is showing "undefined" job ID. |  |  |  | https://prnt.sc/z3dp3s |  |  | New |  | Done
13859 |  | 23 | NM Login: "Error No Data Found." is coming when user is downloading the cases sent for bulk invoice approval. |  |  |  | https://prnt.sc/z3e617 |  |  | New |  | Done
13859 |  | 24 | Bulk Invoice (COO): Instead of job ID system is showing "undefined" job ID. |  |  |  | https://prnt.sc/z3fupw |  |  | New |  | Done
13859 |  | 25 | COO Login-"Error No Data Found." is coming when user is downloading the cases sent for bulk invoice approval. |  |  |  | https://prnt.sc/z3g0ju |  |  | New |  | Done
13859 |  | 26 | Bulk Invoice Approval : Only one case is going for bulk approval instead of all the selected cases. | [6 empty] | New |  | need to discuss with Ajay sir
13859 |  | 27 | Add Payment: There is no validation appears for leaving Payment Reference number blank. |  |  |  | https://prnt.sc/z3gnhu |  |  | New |  | Done
13859 |  | 28 | Add Payment: Wrong validation is coming for entering invalid amount. |  |  |  | https://prnt.sc/z3hcr3 |  |  | New |  |  |  | DEV-UAT issue
13859 |  | 29 | Add Payment:"Error Complaint not saved" is coming when user is adding the payment with valid data. |  |  |  | https://prnt.sc/z3hkfw |  |  |  |  | Done
13859 |  | 30 | Bulk Payment: "Exception happened." is coming on uploading cases for payment. |  |  |  | https://prnt.sc/z3i4dx |  |  | New |  | Done
13859 |  | 31 | Invoice Estimate Rejecte flow is not correctly working as after approving the estimate case should get assign for invoice generation but currently its going to the schedule visit flow. |  |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/326 |  |  | New
13859 |  | 32 | Newly created case should appear at the top | [6 empty] | New
13859 |  | 33 | Auto Approve: For auto approval cases, API should get triggered only when CA gives the final approval. |  |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/341 |  |  | New
13859 |  | 34 | Auto Approve: Discount going as null when auto approval is going. |  |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/341 |  |  | New
13859 |  | 35 | "Error happened while consuming API." when repairer is clicking on estimate history icon. |  |  |  | https://prnt.sc/z7lbim |  |  | New
13859 |  | 36 | "Error Write permission is not defined." is coming when marking the repair complete. |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/345 | https://prnt.sc/z7ly30 |  |  | New
13859 |  | 37 | Ack Case: When repairer is marking the repair complete then system shows permission error and then on refreshing the page, case moves back to its previous state. |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/345 | https://prnt.sc/z7mypj |  |  | New
13859 |  | 38 | Not able to submit Doc when clicking on upload button. |  |  |  | https://prnt.sc/z7px9w |  |  | New
13859 |  | 39 | 0 is coming in approved unit price for compressor. |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/346 | https://prnt.sc/z7r09r https://prnt.sc/z7r2b0 |  |  | New
13859 |  | 40 | No data is coming in estimation history of line items. |  |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/342 |  |  | New
13859 |  | 41 | "Error Something went wrong, please try again late" is coming when marking the payment bounce. manually |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/349?module=tasks | https://prnt.sc/z7zbb7 |  |  | new
13859 |  | 42 | "Error Something went wrong, please try again late" is coming when marking the payment paid. manually |  |  | https://sit1ui-serv-insur.innov.co.in/complaints/view/349?module=tasks | https://prnt.sc/z7zjwg |  |  | new

## Login
Project Name:-> Reassure
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- |  |  | Creation Date:- |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  | Version: - |  | Module:-TC_Login
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Login_01 | 13499 | 2021-02-05 | Entering in to the website. | Any particular browser is kept opened on the user's system and the internet connection in on and working. | 1)Type the website's address in the address bar. 2)Click on the "Go" button or press the Enter button of the keyboard. | https://sit1ui-serv-insur.innov.co.in/dashboard |  |  | The website should get opened having the option to login in to the website. The login form should be having the following fields and buttons displayed - 1)User name(Field) 2)Password(Field) 3)Login (Button) 4)Forgot Password(Link/option) |  |  | Pass
TC_Login_02 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by leaving all the mandatory fields blank. | User is on the website's landing page and is registered to the website. | 1)Leave the Username field blank. 2)Leave the Password field blank. 3)Click on the "Login" button. |  |  |  | Specific & proper Validation messages related to both the blank fields should get displayed. |  |  | Pass
TC_Login_03 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by leaving Username field blank. | User is on the website's landing page and is registered to the website. | 1)Leave the Username field blank. 2)Enter valid password in the Password field. 3)Click on the "Login" button. | Password: admin |  |  | Specific & proper Validationmessage related to the blank field i.e. the username field should get displayed. |  |  | Pass
TC_Login_04 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by leaving Password field blank. | User is on the website's landing page and is registered to the website. | 1)Enter the valid username in the field provided. 2)Leave the password field blank. 3)Click on the Login button. | Username: admin |  |  | Specific & proper Validation messagerelated to the blank field i.e. password field should get displayed. |  |  | Pass
TC_Login_05 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by entering invalid Username. | User is on the website's landing page and is registered to the website. | 1)Enter invalid username in the field provided 2)Enter valid password in the field provided. 3)Click on the Login button. | Username: #@@@ |  |  | Specific & proper Validation message related to the username field should get displayed. |  |  | Pass
TC_Login_06 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by entering invalid Password. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter invalid password in the field provided. 3)Click on the provided Login button. |  |  |  | Specific & proper Validation message related to the passwordfield should get displayed. |  |  | Pass
TC_Login_07 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by entering invalid Password and Username. | User is on the website's landing page and is registered to the website. | 1)Enter invalid username and password in the fields provided. 2)Click on the Login button. |  |  |  | Specific & proper Validation messages related to both the fields should get displayed. |  |  | Pass
TC_Login_08 | 13499 | 2021-02-05 | Verify that the registered user is able to login to the website by entering valid Password and Username. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Click on the Login button. |  |  |  | User should get logged in to his/her account |  |  | Pass
TC_Login_09 | 13499 | 2021-02-05 | To verify if the system remembers the login credentials if user checks the Remember Me check box. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Select the "Remember me" check box. 3)Click on the Login button. |  |  |  | User should get logged in to his/her account. Also , the next time when the same user tries to log in and enters his user name(email address) then automatically the password field should get filled the correct password of hisas he checked the Remember me check box when he logged for the first time. |  |  | NA
TC_Login_10 | 13499 | 2021-02-05 | Check if the password is masked on the screen i.e., password must be in bullets or asterisks | User is on the website's landing page and is registered to the website. | 1)Enter valid password in the field provided. | some password(can be a registered/unregistered) |  |  | The entered password should be masked/hidden. |  |  | Pass
TC_Login_11 | 13499 | 2021-02-05 | After logging in try to copy/cut the password and paste it on another screen(passwords are usually in * such that its not visible on the screen) | User is on the website's landing page and is registered to the website. | 1)Enter username and password in the respective fields. Copy the password field’s content(which is in *s) 3)paste the content on another screen | Registered user’s login id and password |  |  | The entered password shouldn't get copied. |  |  | Pass
TC_Login_12 | 13499 | 2021-02-05 | Verify the url without logging into to the site | User is on the website's landing page and is registered to the website. | 1) Login to the site using registered username and password 2)copy and save the url of the logged in page 3)logout of the site 4)now paste the copied url on the browser | Registered username and password |  |  | User should not get redirect o the home/login screen. |  |  | Pass
TC_Login_13 | 13499 | 2021-02-05 | Verify that the user's password is getting retrieved in case if he has forgotten his password. | Registered user is on the login page having the link of "Forgot Password" and has forgotten his/her password. | Click on the provided "Forgot password" link. |  |  |  | User should get navigated to the forgot password screen having the following options - 1) Username(Field) 2)Submit(Button)
TC_Login_14 | 13499 | 2021-02-05 |  |  | 1)Enter invalid username in the field provided(Invalid username can be categorized in to two type, first is the username which is not in correct format and the other one is that which is in correct format but does not exist in the application's data base) 2)Click on the "Submit" button. |  |  |  | Specific & proper validation message should get displayed related to the email address field.
TC_Login_15 | 13499 | 2021-02-05 |  |  | 1)Enter valid Username in the field provided. 2)Click on the "Submit" button. |  |  |  | System should reset the password and a mail should get sent to the user's email address having the Temp password along with the Log in Link. As Soon as the user enter the correct user name andPassword then he should get navigated to the "Change Password" screen under "My Account" section of the website.
TC_Login_16 | 13499 | 2021-02-05 | Verify that the user is able to get logout. | User is already logged in. | 1) Click on the logout button available underside menu otions. |  |  |  | User should get logged out of the system and should get rediret to the login/landing page. |  |  | Pass

## Change Password
Project Name:-> Re-assure
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Ajay Kumar
Version: - |  |  |  |  | Module:- Change Password
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Change Password_01 | 13191 | 2021-02-05 | To verify if the user is ableto get navigate to the Dashboards page after login. | User is on the website's landing page and is registered to the website. | 1)Enter valid username in the field provided. 2)Enter valid password in the field provided. 3)Click on the Login button. | https://sit1ui-serv-insur.innov.co.in/ |  |  | User should get logged in and Dashboards page should get appear after login to the website. |  |  | Pass
TC_Change Password_02 | 13191 | 2021-02-05 | To verify if the user is able get navigated to the change password screen by clicking on the link provided. | User is on the website's landing page and is registered to the website. | 1) Click on the profile icon. 2) Click on my profile. |  |  |  | User should get navigate to the change password pop up. And also there should be following fields and button. 1) Password field 2) New Password field 3)Confirm New Password field 4) Password Policy description |  |  | Pass
TC_Change Password_03 | 13191 | 2021-02-05 | To verify if the user is able to change the password by leaving all the mandatory fields blank. |  | 1) Leave all the mandatory fields blank. 2) Enter valid data in remaining fields. 3) Submit button. |  |  | https://prnt.sc/yd6zfy | User should not not be able to change the password and also there should be a proper and spacific validation message for the same. |  |  | Fail
TC_Change Password_04 | 13191 | 2021-02-05 | To verify if the user is able to change the password by leaving all the Password field blank. |  | 1) Leave Password field blank. 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same.
TC_Change Password_05 | 13191 | 2021-02-05 | To verify if the user is able to change the password by leaving all the New Password field blank. |  | 1) Leave New Password field blank. 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same. | p
TC_Change Password_06 | 13191 | 2021-02-05 | To verify if the user is able to change the password by leaving all the Confirm Password field blank. |  | 1) Leave Confirm Password field blank. 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same.
TC_Change Password_07 | 13191 | 2021-02-05 | To verify if the user is able to change the password by entering invalid data in Temp Password field.. |  | 1) Enter invalid data in Temp Password field . 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same.
TC_Change Password_08 | 13191 | 2021-02-05 | To verify if the user is able to change the password by entering invalid data in New Password field.. |  | 1) Enter invalid data in New Password field . 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same.
TC_Change Password_09 | 13191 | 2021-02-05 | To verify if the user is able to change the password by entering invalid data in Confirm Password field.. |  | 1) Enter invalid data in Confirm Password field . 2) Enter valid data in remaining fields. 3) Submit button. |  |  |  | User should not not be able to change the password and also there should be a proper and spacific validation message for the same.
TC_Change Password_10 | 13191 | 2021-02-05 | To verify if the user is able to change the password by entering valid data in Confirm Password field.. |  | 1) Enter valid data in all fields. 2) Submit button. |  |  |  | User should be able to change the password and also there should be a success message for the same and also user should get navigate to the login screen.
TC_Change Password_11 | 13191 | 2021-02-05 | Verify that the user is able to get logout. | User is already logged in. | 1) Click on the logout button available underside menu otions. |  |  |  | User should get logged out of the system and should get rediret to the login/landing page.
|  | 2021-02-05 | To verify if the password entered by user must not exceed 32 characters. |  | Enter password more than 32 characters |  |  |  | User should be able to enter less then or equal to 32 characters password

## Visit Schedule
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Visit_Schedule
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Visit_Schedule_01 | 13859 | 2021-02-06 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass
TC_Visit_Schedule_02 | 13859 | 2021-02-06 | To verify if the user is able to navigate to Repairer visit section by clicking on "Schedule Visit" quick link. | User is already on case requests page. | 1) Click on "Schedule Visit" link available under Quick Links section. |  |  |  | User should get navigate to the Repairer visit section. |  |  | Pass
TC_Visit_Schedule_03 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  | 1) When appointment date does not get change then there is no need for showing the reason for reschedule. | https://prnt.sc/yslqhs | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Fail
TC_Visit_Schedule_04 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by leaving the Appointment date field blank. | User is already on case requests page. | 1) Leave the Appointment date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Pass
TC_Visit_Schedule_05 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by leaving the Reason for Resecheduling field blank. | User is already on case requests page. | 1) Leave the Reason for Resecheduling field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Pass
TC_Visit_Schedule_06 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by leaving the Appointment Time Slot field blank. | User is already on case requests page. | 1) Leave the Appointment Time Slot field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Pass
TC_Visit_Schedule_07 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by leaving the Remark field blank. | User is already on case requests page. | 1) Leave the Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | The validation message coming for leaving the Remark field blank is wrong , As there is a punctuation error. The validation message should be as "Remark : Remark is Required & It can not be empty." |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | Low | Pass
TC_Visit_Schedule_08 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Appointment date field. | User is already on case requests page. | 1) Enter invalid data in Appointment date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. | 1)JHBHB 2)Current date : 02/05/2020 3) Appointment Date: 29/05/2020 | 1)The validation message coming for entering invalid data in Appointment date is wrong. 2) User should be able to select the Past date upto three days from current day but currenty this is not happeninig, |  | Repair Schedule form should not get submitted and there should be a proper validation message for the same. | High | High | Pass
TC_Visit_Schedule_09 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all the fields. 3)Click on submit button. |  | 1)After saving the Visit Schedule form the API should get triggeredand the same data should get sent to MetaCube portal but This is not happening currently. 2)[{"field":"aiz_claim_number","error":"invalid_value","description":"aiz_claim_number can not be null/empty."},{"field":"Rescheduled_Date","error":"invalid_date","description":"Invalid Rescheduled_Date"}] |  | Repair schedule form should get submitting. | High | High | Pass
[8 empty] | Need to remove "Appointment Time Slot is Required" when holiday is selected. | https://prnt.sc/yi79l7
[8 empty] | Need to remove Reason for rescheduling when holiday is selected. | https://prnt.sc/yslud3
[8 empty] | Not able to schedule visit as m getting error for appointment date. https://sit1ui-serv-insur.innov.co.in/complaints/view/333 | https://lh3.googleusercontent.com/-AD6WdcLjkR0/YCIfWW2d44I/AAAAAAAAGko/br0RBczY530ynbrkril2BkCqW7OQjBsVQCK8BGAsYHg/s0/2021-02-08.png
[8 empty] | Not able to assign an engineer as m getting error as "Time Slot is not found in Engineer time slot master." https://sit1ui-serv-insur.innov.co.in/complaints/view/324 | https://lh3.googleusercontent.com/-E4d39yx-hkc/YCIhkIFRdEI/AAAAAAAAGk0/BzKWDVBon5k6ureg3OCDvr-DnWex3NLLACK8BGAsYHg/s0/2021-02-08.png

## Case Status Update
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Case_Status_Update | [7 empty] | Retesting:2/5/2020
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Status | Date | Power ID | Status
TC_Case_Status_Update_01 | 13859 | 2021-02-06 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass | 10720 | Pass | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_02 | 13859 | 2021-02-06 | To verify if the user is able to navigate to case status update pop up by clicking on "Case Status Update" quicl link. | User is already on case requests page. | 1) Click on "Case Status Update" link available under Quick Links section. |  |  |  | Case Status Update pop up should get appear. |  |  | Pass | 10720 | Pass | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_03 | 13859 | 2021-02-06 | To verify if the user is able to submit the case status update form by leaving all the mandatory fields blank. | User is at case status update pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Pass | 10720 | Fail | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_04 | 13859 | 2021-02-06 | To verify if the user is able to submit the case status update form by leaving the Case Status field blank. | User is at case status update pop up. | 1) Leave Case Status field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Fail | 10720 | Fail | 2020-04-07 | 11428 | Fail
TC_Case_Status_Update_05 | 13859 | 2021-02-06 | To verify if the user is able to submit the case status update form by leaving the Reason for Cancellation field blank. | User is at case status update pop up. | 1) Leave Reason for Cancellation field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Pass | 10720 | Fail | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_06 | 13859 | 2021-02-06 | To verify if the user is able to submit the case status update form by leaving the Remarks field blank. | User is at case status update pop up. | 1) Leave Remarks field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Case status should not get update and also there should be a proper validation message for the same. | High | Low | Pass | 10720 | Pass | 2020-04-07 | 11428 | Fail
TC_Case_Status_Update_07 | 13859 | 2021-02-06 | To verify if the values of the dropdown is as per the master for Case Status Field. | User is at case status update pop up. | 1)Click on the Case Status Dropdown. 2) Check the values of the dropdown and match it with the data from the master. |  |  |  | The dropdown value should be as per the master. | High | Mid | Pass | 10720 | Pass | 2020-04-07 | 11428 | Fail
TC_Case_Status_Update_08 | 13859 | 2021-02-06 | To verify if the values of the dropdown is as per the master for Reason for cancellation Field. | User is at case status update pop up. | 1)Click on the Reason for cancellation Dropdown. 2) Check the values of the dropdown and match it with the data from the master. |  | 1)Duplicate dropdown value is appearing in the dropdown of the Reason for cancellation. 2) The dropdown values coming in Reason list when "Customer Not Available" selected in case status is not as per the Master. As Customer not Contactable should not be in the dropdown. |  | The dropdown value should be as per the master. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_09 | 13859 | 2021-02-06 | To verify if the user is able to submit the case status update form by entering valid data in all the mandatory fields. | User is at case status update pop up. | 1) Enter valid details in all fields. 2)Click on submit button. |  |  |  | Case status update should get submitted. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428
TC_Case_Status_Update_10 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Cancelled by repairer after selecting the case status as cancel. | User is at case status update pop up. | 1) Select Cancel as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the case status as cancel, the Case Sub Status should gvet changed to Cancelled by Repairer. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_11 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Customer Not Contactable after selecting the case status as Customer Not Contactable. | User is at case status update pop up. | 1) Select Customer Not Contactable as the case status. 2) Select valid reason. 3) Click on submit button. |  | Remarks entered by repairer should be visible to the CSR when updating the status to Customer Nnot Contactable. |  | After submitting the case status as Customer Not Contactable the Case Sub Status should get changed to Customer Not Contactable. | High | High | Fail | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_12 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Customer Not Available after selecting the case status as Customer Not Available. | User is at case status update pop up. | 1) Select Customer Not Available as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the case status as Customer Not Available the Case Sub Status should get changed to Customer Not Available. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_13 | 13859 | 2021-02-06 | To verify if the Cancel button at Case Status Update pop up is functional or not | User is at case status update pop up. | 1)Click on Cancel button. |  |  |  | Case status update should get close. |  |  | Pass | 10720 | Pass | 2020-04-07 | 11428 | Pass
TC_Case_Status_Update_14 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Customer available after selecting the case status as Customer available. | User is at case status update pop up. | 1) Select Customer available as the case status. 2) Select valid reason. 3) Click on submit button. |  | There is no need for showing "Reason for status field" when marking customer available. | https://prnt.sc/yi5l94 | After submitting the case status asCustomer available the Case Sub Status should get changed to Customer available. | High | High | Fail | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_15 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Customer available after selecting the case status as Customer available. | User is at case status update pop up. | 1) Select Customer available as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the case status asCustomer available the Case Sub Status should get changed to Customer available. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_16 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to part pending after selecting the case status as part pending. | User is at case status update pop up. | 1) Select part pending as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the case status as part pending the part pending should get changed to part pending. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_17 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to part Received after selecting the case status as part Received. | User is at case status update pop up. | 1) Select part Received as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the case status as part Receivedthe part Received should get changed to Customer available. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_18 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Stand by unit given after selecting the case status as Stand by unit given . | User is at case status update pop up. | 1) Select Stand by unit given as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the Stand by unit given as part Receivedthe part Received should get changed to Stand by unit given . | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_19 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Cancelled by CSR after selecting the case status as Cancelled by CSR. | User is at case status update pop up. | 1) Select Cancelled by CSR as the case status. 2) Select valid reason. 3) Click on submit button. |  |  |  | After submitting the Cancelled by CSR as part Receivedthe part Received should get changed to Cancelled by CSR. | High | High | Pass | 10720 | Fail | 2020-04-07 | 11428 | NA
TC_Case_Status_Update_20 | 13859 | 2021-02-06 | To verify if the Case Sub Status gets changed to Cancelled by Repairer after selecting the case status as Cancelled by CSR. | User is at case status update pop up. | 1) Select Cancelled by CSR as the case status. 2) Select valid reason. 3) Click on submit button. |  | Remarks entered by repairer should be visible to the CSR when updating the status to Cancelled by Repairer. |  | After submitting the Cancelled by CSR as part Receivedthe part Received should get changed to Cancelled by CSR. | Option to mark "customer not available" should not come to CSR user. | https://prnt.sc/yi7rcx https://prnt.sc/yi7y7n | Fail | 10720 | Fail | 2020-04-07 | 11428 | NA
[7 empty] | Option to mark "customer not available" should not come to CSR user. | https://prnt.sc/yi7rcx https://prnt.sc/yi7y7n |  | Option to mark "customer not available" should not come to CSR user. | https://prnt.sc/yi7rcx https://prnt.sc/yi7y7n

## Inspection
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add_Inspection
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Power ID | Status
TC_Add_Inspection_01 | 13859 | 2021-02-06 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Add_Inspection_02 | 13859 | 2021-02-06 | To verify if the user is able to navigate to Repairer visit section by clicking on "Inspection Details" quick link. | User is already on case requests page. | 1) Click on "Inspection Details" link available under Quick Links section. |  |  |  | User should get navigate to the Inspection Details section with having following fields and buttons: 1) Visit completion date 2)Visit Sub Status 3)Fault category by customer (Read Only) 4)3)Fault Sub category by customer (Read Only) 5)Fault diagnosed by engineer (Dropdown) 6)Problem diagnosed by engineer (Dropdown) 7)Problem Sub category by engineer (Dropdown) 8)Defect Type(Dropdown) 9)Part Selection (Dropdown) 10) Remarks 11) Defect Photos (Multiple) 12) Claim Form (Multiple) 13) Product Number Upload (Multiple) 14) Purchase Invoice(Multiple) 15) Job Sheet (Multiple) |  |  | pass
TC_Add_Inspection_03 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_04 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving the Visit Completion Date field blank. | User is already on case requests page. | 1) Leave the Visit Completion Date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_05 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Visit Sub Status field blank. | User is already on case requests page. | 1) Leave the Visit Sub Status field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_06 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving fault diagnosed by engineer field blank. | User is already on case requests page. | 1) Leave the Visit Sub Status field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | pass
TC_Add_Inspection_07 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Problem Diagnosed by Engineer field blank. | User is already on case requests page. | 1) Leave the Problem Diagnosed by Engineer field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_08 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Problem Sub-Category field blank. | User is already on case requests page. | 1) Leave the Problem Sub-Category field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_09 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Defect Type field blank. | User is already on case requests page. | 1) Leave the Defect Type field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_10 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_11 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_12 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Inspection Remark field blank. | User is already on case requests page. | 1) Leave the Inspection Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_13 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving defect photo field blank. | User is already on case requests page. | 1) Leave the defect photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_14 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving claim form photo field blank. | User is already on case requests page. | 1) Leave the claim form photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_15 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Product No. photo field blank. | User is already on case requests page. | 1) Leave the Product No. photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_16 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Purchase Invoice photo field blank. | User is already on case requests page. | 1) Leave the Purchase Invoice photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | Its a non mandatory field but syatm shows validation for it. |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_17 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Job Sheet photo field blank. | User is already on case requests page. | 1) Leave the Job Sheet photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_18 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Visit Completion date field. | User is already on case requests page. | 1) Enter invalid data in Visit Completion date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_19 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by uploading invalid files in the Documents section | User is already on case requests page. | 1) Upload invalid files/Oversize files in the documents section 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | 1)On uplaoding Over size Files(More than MB) system does not any validation message and keeps in uplaoding state. 2)After uplaoding a file is user deletes it even then View files option shows the count of it. 4) System shows error msg for deleting any uploaded file |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Fail
TC_Add_Inspection_20 | 13859 | 2021-02-06 | To verify if the Visit Sub Status, Fault diagnosed by engineer (Dropdown) ,Problem diagnosed by engineer (Dropdown) ,Problem Sub category by engineer (Dropdown), Defect Type(Dropdown) and Part Selection (Dropdown)values are as per the master. | User is already on case requests page. | 1) Click on the Visit Sub Status dropdown. 2)Now check the dropdown values with the values in status master. |  | Dropdown doe not show all the values from the case masters. Missing values 1)Visit Scheduled -Pending 2)Visit Scheduled Reassigned - Customer Available |  | dropdown values should be as per the master. |  |  | Pass
TC_Add_Inspection_21 | 13859 | 2021-02-06 | To verify if the user is able to Add Inspection by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all the fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | Error is coming for entering invalid visit completion date when valid date is selected by the user. instance: sit 1 case id 331 | https://prnt.sc/ysrsjv | Inspection details should get submitted and also the case status and sub status should get change to : Case Status:Visit Scheduled Case Sub Status:Completed |  |  | Fail
Same day repair
TC_Add_Inspection_22 | 13859 | 2021-02-06 | To verify if the user is able to navigate to Repairer visit section by clicking on "Inspection Details" quick link. | User is already on case requests page. | 1) Click on "Inspection Details" link available under Quick Links section. |  |  |  | User should get navigate to the Inspection Details section with having following fields and buttons: 1) Visit completion date 2)Visit Sub Status 3)Fault category by customer (Read Only) 4)3)Fault Sub category by customer (Read Only) 5)Fault diagnosed by engineer (Dropdown) 6)Problem diagnosed by engineer (Dropdown) 7)Problem Sub category by engineer (Dropdown) 8)Defect Type(Dropdown) 9)Part Selection (Dropdown) 10) Remarks 11) Defect Photos (Multiple) 12) Claim Form (Multiple) 13) Product Number Upload (Multiple) 14) Purchase Invoice(Multiple) 15) Job Sheet (Multiple) 16) "Is Repair Completed" check box 17) Resolution of issues (Dropdown) 18) Repair completion date 19) Repair Product Photos(Multiple) 20) Final Job Sheet(Multiple) 21) Defective Part Photos(Multiple) |  |  | Pass
TC_Add_Inspection_23 | 13859 | 2021-02-06 | To verify if the user is able to navigate to Repairer details section by clicking on "Is Repair Complete" checkbox | User is already on case requests page. | 1) Click on "Repair Details" link available under Quick Links section. 2) Click on "Is Repair Completed" check box. |  |  |  | Repair section should get open. |  |  | Pass
TC_Add_Inspection_24 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_25 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving the Visit Completion Date field blank. | User is already on case requests page. | 1) Leave the Visit Completion Date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_26 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Visit Sub Status field blank. | User is already on case requests page. | 1) Leave the Visit Sub Status field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_27 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving fault diagnosed by engineer field blank. | User is already on case requests page. | 1) Leave the Visit Sub Status field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_28 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Problem Diagnosed by Engineer field blank. | User is already on case requests page. | 1) Leave the Problem Diagnosed by Engineer field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_29 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Problem Sub-Category field blank. | User is already on case requests page. | 1) Leave the Problem Sub-Category field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_30 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Defect Type field blank. | User is already on case requests page. | 1) Leave the Defect Type field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_31 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_32 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Part Selection field blank. | User is already on case requests page. | 1) Leave the Part Selection field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_33 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Inspection Remark field blank. | User is already on case requests page. | 1) Leave the Inspection Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_34 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving defect photo field blank. | User is already on case requests page. | 1) Leave the defect photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_35 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving claim form photo field blank. | User is already on case requests page. | 1) Leave the claim form photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_36 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Product No. photo field blank. | User is already on case requests page. | 1) Leave the Product No. photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_37 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Purchase Invoice photo field blank. | User is already on case requests page. | 1) Leave the Purchase Invoice photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | Its a non mandatory field but syatm shows validation for it. |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_38 | 13859 | 2021-02-06 | To verify if the Inspection Details form is getting submitted by leaving Job Sheet photo field blank. | User is already on case requests page. | 1) Leave the Job Sheet photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_39 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Visit Completion date field. | User is already on case requests page. | 1) Enter invalid data in Visit Completion date field. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_40 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by uploading invalid files in the Documents section | User is already on case requests page. | 1) Upload invalid files/Oversize files in the documents section 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | 1)On uplaoding Over size Files(More than MB) system does not any validation message and keeps in uplaoding state. 2)After uplaoding a file is user deletes it even then View files option shows the count of it. 4) System shows error msg for deleting any uploaded file |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_41 | 13859 | 2021-02-06 | To verify if the Visit Sub Status, Fault diagnosed by engineer (Dropdown) ,Problem diagnosed by engineer (Dropdown) ,Problem Sub category by engineer (Dropdown), Defect Type(Dropdown) and Part Selection (Dropdown)values are as per the master. | User is already on case requests page. | 1) Click on the Visit Sub Status dropdown. 2)Now check the dropdown values with the values in status master. |  | Dropdown doe not show all the values from the case masters. Missing values 1)Visit Scheduled -Pending 2)Visit Scheduled Reassigned - Customer Available |  | dropdown values should be as per the master. |  |  | Pass
TC_Add_Inspection_42 | 13859 | 2021-02-06 | To verify if the Repair Details form is getting submitted by leaving the "Resolution od issue" field blank. | User is already on case requests page. | 1) Leave the Resolution od issue field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_43 | 13859 | 2021-02-06 | To verify if the Repair Details form is getting submitted by leaving the Repair Completion date field blank. | User is already on case requests page. | 1) Leave the Repair Completion date field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_44 | 13859 | 2021-02-06 | To verify if the Repair Details form is getting submitted by leaving Repair Prodcut photo field blank. | User is already on case requests page. | 1) Leave the Repair Prodcut photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_45 | 13859 | 2021-02-06 | To verify if the Repair Details form is getting submitted by leaving Final Job sheet photo field blank. | User is already on case requests page. | 1) Leave the Final Job sheet photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_46 | 13859 | 2021-02-06 | To verify if the Repair Details form is getting submitted by leaving Defective Part photo field blank. | User is already on case requests page. | 1) Leave the Defective Part photo field blank. 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_47 | 13859 | 2021-02-06 | To verify if the resolution of issue dropdown values are as per the case master. | User is already on case requests page. | 1) Click on the resolution of issue dropdown. 2)Now check the dropdown values with the values in status master. |  |  |  | resolution of issue dropdown values should be as per the Case master. |  |  | Pass
TC_Add_Inspection_48 | 13859 | 2021-02-06 | To verify ifthe user is able to submit repair details by entering invlid data in repair completion date | User is already on case requests page. | 1) Enter invalid data in repair completion date 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  |  |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_49 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by uploading invalid files in the Documents section | User is already on case requests page. | 1) Upload invalid files/Oversize files in the documents section 2) Enter valid data in all the remaining fields. 3)Click on submit button. |  | 1)On uplaoding Over size Files(More than MB) system does not any validation message and keeps in uplaoding state. 2)After uplaoding a file is user deletes it even then View files option shows the count of it. 3)Repair section should not be available to submit before visit reschedule. 4) System shows error msg for deleting any uploaded file |  | Repair Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Inspection_50 | 13859 | 2021-02-06 | To verify if the user is able to Add Repair by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all the fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Added Repair should get submitting for further actions. |  |  | Pass

## Add Estimation
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Add_Estimation
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Add_Estimation_01 | 13859 | 2021-02-06 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Add_Estimation_02 | 13859 | 2021-02-06 | To verify if the user is able to navigate to Add Estimation section by clicking on "Add Estimation" quick link. | User is already on case requests page. | 1) Click on "Add Estimation Details" link available under Quick Links section. |  |  |  | User should get navigate to the Estimation Details section. |  |  | pass
TC_Add_Estimation_03 | 13859 | 2021-02-06 | To verify if the Description section is showing all the "parts" added by the engineer at the time of adding inspection. | User is already on case requests page. | 1)Check the values under description tab and match them with the values entered at the time of adding inspection. |  |  |  | The description values should be same as the of parts/ |  |  | pass
TC_Add_Estimation_04 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving all the mandatory fields blank. | User is already on case requests page. | 1) Leave all the mandatory fields blank. 2) Click on Submit For Approval button. |  | There should be a proper validation message for leaving HSN/SAC No, Qty,Price,IGST,CGST,SGST fields blank. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | High | High | pass
TC_Add_Estimation_05 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the QTY field blank. | User is already on case requests page. | 1) Leave the QTY field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | There should be a proper validation message for leaving Qty field blank. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | Mid | pass
TC_Add_Estimation_06 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the Unit Price field blank. | User is already on case requests page. | 1) Leave the Unit Price field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | There should be a proper validation message for leaving Unit Price field blank. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | Mid | pass
TC_Add_Estimation_07 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the IGST or SGST+CGST field blank. | User is already on case requests page. | 1) Leave the IGST or SGST+CGST field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | There should be a proper validation message for leaving IGST or SGST+CGST field blank. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | Mid | pass
| 13859 | 2021-02-06 | Note: User can only add IGST or CGST+SGST.
TC_Add_Estimation_08 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the Expected Repair Completion Date field blank. | User is already on case requests page. | 1) Leave the Expected Repair Completion Date field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Estimation_09 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the Repair Type field blank. | User is already on case requests page. | 1) Leave the Repair Type field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Estimation_10 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the Remark field blank. | User is already on case requests page. | 1) Leave the Remark field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Estimation_11 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in QTY field. | User is already on case requests page. | 1) Enter invalid data in QTY field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. | Qty: -7 Qty: -0 | Estimation is getting submitted by entering invalid dat in QTY field. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | High | pass
TC_Add_Estimation_12 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in Unit Price field. | User is already on case requests page. | 1) Enter invalid data in Unit Price field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. | Unit Price: -9 Unit Price: 0 | Estimation is getting submitted by entering invalid dat in Unit Price field. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | High | pass
TC_Add_Estimation_13 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in IGST field. | User is already on case requests page. | 1) Enter invalid data in IGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. | IGST: -9 | Estimation is getting submitted by entering invalid dat in IGST field. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | High | pass
TC_Add_Estimation_14 | 13859 | 2021-02-06 | To verify if the Repair Schedule form is getting submitted by entering invalid data in SGST field. | User is already on case requests page. | 1) Enter invalid data in SGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. | SGST: -5 | Estimation is getting submitted by entering invalid dat in SGST field. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same.
TC_Add_Estimation_15 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by entering invalid data in CGST field. | User is already on case requests page. | 1) Enter invalid data in CGST field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. | CGST: -5 | Estimation is getting submitted by entering invalid dat in CGST field. |  | Estimation Details form should not get submitted and there should be a proper validation message for the same. | Mid | High | pass
| 13859 | 2021-02-06 | Note: User can only add IGST or CGST+SGST.
TC_Add_Estimation_16 | 13859 | 2021-02-06 | To verify if there is a validation for entering all three CGST,SGST AND IGST fields | User is already on case requests page. | 1) Enter data in all three fields. |  |  |  | There should be a proper validation msg for it. |  |  | Pass
TC_Add_Estimation_17 | 13859 | 2021-02-06 | To verify if the user is able to add any Part by clicking on + button. | User is already on case requests page. | 1) Click on + icon appearing on the Add estimation section. |  |  |  | User should be able to Add any missing part/description. |  |  | Pass
TC_Add_Estimation_18 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by entering invalid data in Expected Repair Completion date field. | User is already on case requests page. | 1) Enter invalid data in Expected Repair Completion date field. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Inspection Details form should not get submitted and there should be a proper validation message for the same. |  |  | Pass
TC_Add_Estimation_19 | 13859 | 2021-02-06 | To verify if the GST Amount of the each part is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in GST Amount fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The GST Amount of each part/description should be correct. |  |  | Pass
TC_Add_Estimation_20 | 13859 | 2021-02-06 | To verify if the Total of the each part is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in qty, unit price and tax related fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The total of each part/description should be correct. |  |  | Pass
TC_Add_Estimation_21 | 13859 | 2021-02-06 | To verify if the Sub-Total is showing the Sum of Total parts only. | User is already on case requests page. | 1) Enter valid data in qty, unit price and tax related fields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Sub total should only display the summation of parts only. |  |  | Pass
TC_Add_Estimation_22 | 13859 | 2021-02-06 | To verify if the Total of entire estimation is getting calculated correctly. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3) Change any parameter 3)Click on Submit For Approval button. |  | 1) Discount does not get added when user changes any line item after entering all the details. 2) Excess amount does not getted when user changes any line item after entering all the details. |  | The Total of entire Estiamtion should be mathematically correct. | High | High | pass
TC_Add_Estimation_24 | 13859 | 2021-02-06 | To verify if the user is able to save estimation as draft by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Save as Draft Button. |  |  |  | The Added submittion should get saved as draft for editing before submitting for approval. |  |  | Pass
TC_Add_Estimation_25 | 13859 | 2021-02-06 | To verify if the user is able to edit the estimation which was saved as draft. | User is already on case requests page. | 1) Add any part and its details. 2) Enter valid data in all the remaining |  | After adding new part,system calculated wrongly. |  | New part should get added and the calculation gets modified. | High | High | pass
TC_Add_Estimation_25 | 13859 | 2021-02-06 | To verify if the user is able to save estimation as draft by entering valid data in all the mandatory fields. | User is already on case requests page. | 1) Enter valid data in all thefields. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | After submitting the estimation , Transportaion amount and Labour charges shows 0 on UI. |  | The Added submittion should get submitting for Approval |  |  | pass
TC_Add_Estimation_26 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting submitted by leaving the Approve Type field blank. | User is already on case requests page. | 1) Leave the Approve Type field blank. 2) Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  | Wrong validation is coming when user submits the estimate without selecting an Approve Type. It should be " Please select Approve Type instead of Request method is not valid. | https://prnt.sc/yt048j | Estimation Details form should not get submitted and there should be a proper validation message for the same. |  |  | Fail
[7 empty] | "Repair_Action": null, It should be blank instead of null. | https://prnt.sc/yt1m5s

## Approve Estimation
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Approve_Estimation
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Approve_Estimation_01 | 13859 | 2021-02-06 | To verify if the Case Manager is able to get navigate to the Case Request Details page of selected Case Request. | Case Manager is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | pass
TC_Approve_Estimation_02 | 13859 | 2021-02-06 | To verify if the Case Manager is able to navigate to Approve Estimatio section by clicking on "Approve Estimation" quick link. | Case Manager is already on case requests page. | 1) Click on "Approve Estimation" link available under Quick Links section. |  |  |  | Case Manager should get navigate to the Approve Estimation section. |  |  | pass
TC_Approve_Estimation_03 | 13859 | 2021-02-06 | To verify if the a estimate section shows the details sent by the repairer are correct or not. | User is already on estimate approve section | 1)Check the details of the estimation and match them with the values entered at the time of adding inspection. |  |  |  | The estimation details should be same as that of entered by the repairer. |  |  | Pass
| 13859 | 2021-02-06 | Note: User can only add IGST or CGST+SGST. | User is already on estimate approve section
TC_Approve_Estimation_08 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting updated by leaving the Expected Repair Completion Date field blank. | User is already on estimate approve section | 1) Clear and Leave the Expected Repair Completion Date field blank. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get updated and there should be a proper validation message for the same. |  |  | Pass
TC_Approve_Estimation_09 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting updated by leaving the Repair Type field blank. | User is already on estimate approve section | 1) Clear and Leave the Repair Type field blank. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get updated and there should be a proper validation message for the same. |  |  | Pass
TC_Approve_Estimation_10 | 13859 | 2021-02-06 | To verify if the Estimation Details form is getting updated by leaving the Remark field blank. | User is already on estimate approve section | 1) Clear and Leave the Remark field blank. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | Estimation Details form should not get updated and there should be a proper validation message for the same. |  |  | Pass
| 13859 | 2021-02-06 | Note: User can only add IGST or CGST+SGST. | User is already on estimate approve section
TC_Approve_Estimation_16 | 13859 | 2021-02-06 | To verify if there is a validation for entering all three CGST,SGST AND IGST fields | User is already on estimate approve section | 1) Clear and Enter data in all three fields. |  |  |  | There should be a proper validation msg for it. |  |  | Pass
TC_Approve_Estimation_17 | 13859 | 2021-02-06 | To verify if the user is able to add any Part by clicking on + button. | User is already on estimate approve section | 1) Click on + icon appearing on the Add estimation section. |  |  |  | User should be able to Add any missing part/description. |  |  | Pass
TC_Approve_Estimation_19 | 13859 | 2021-02-06 | To verify if the GST Amount of the each part is getting calculated correctly. | User is already on estimate approve section | 1) Clear and Enter valid data in GST Amount fields. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The GST Amount of each part/description should be correct. |  |  | Pass
TC_Approve_Estimation_20 | 13859 | 2021-02-06 | To verify if the Total of the each part is getting calculated correctly. | User is already on estimate approve section | 1) Clear and Enter valid data in qty, unit price and tax related fields. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The total of each part/description should be correct. |  |  | Pass
TC_Approve_Estimation_21 | 13859 | 2021-02-06 | To verify if the Sub-Total is showing the Sum of Total parts only. | User is already on estimate approve section | 1) Clear and Enter valid data in qty, unit price and tax related fields. 2) Clear and Enter valid data in all the remaining fields. 3)Click on Submit For Approval button. |  |  |  | The Sub total should only display the summation of parts only. |  |  | Pass
TC_Approve_Estimation_24 | 13859 | 2021-02-06 | To verify if the case manager is able to Reject the estimation by clicking on Rejected button. | User is already on estimate approve section | 1) Click on the Rejected Button. |  |  |  | Estimation should get reject and get sent back to Repairer for re-submission. |  |  | Pass
TC_Approve_Estimation_25 | 13859 | 2021-02-06 | To verify if the case manager is able to put the estimation On Hold by clicking on On Hold button. | User is already on estimate approve section | 1) Click on the On Hold Button. |  |  |  | Estimation should get updated to On Hold.
TC_Approve_Estimation_26 | 13859 | 2021-02-06 | To verify if the case manager is able to Approve the estimation by clicking on Approved button. | User is already on estimate approve section | 1) Click on the Approved Button. | https://sit1ui-serv-insur.innov.co.in/complaints/view/326?module=estimate | Error is coming when user approves an estimation. | https://prnt.sc/ynjko0 | 1)Estimation should get directly Approve in case of CPP. 2)For Acko- Estimation should get sent to client for Approval. |  |  | Fail
TC_Approve_Estimation_27 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Rejected with service fee without selecting its reason field.. | User is already on estimate approve section | 1) Select Rejected with service fee option from the dropdown. 2) Click on submit button. |  | CA is able to mark rejected with service fee without selecting its reason dropdown which is a mandatory field. | https://prnt.sc/z6sogu | Case status should not get change and also there should be a proper validation message for the same/ |  |  | Fail
TC_Approve_Estimation_28 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Rejected with service fee with selecting its reason field.. | User is already on estimate approve section | 1) Select Rejected with service fee option from the dropdown. 2) Select suiable reason. 3)Click on submit button. |  |  |  | Case status should get change to Rejected with serive fee and case should get move to invoice section |  |  | Pass
TC_Approve_Estimation_29 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Rejected without service fee without selecting its reason field.. | User is already on estimate approve section | 1) Select Rejected without service fee option from the dropdown. 2) Click on submit button. |  | CA is able to mark rejected without service fee without selecting its reason dropdown which is a mandatory field. | https://prnt.sc/z6unjm | Case status should not get change and also there should be a proper validation message for the same/ |  |  | Fail
TC_Approve_Estimation_30 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Rejected without service fee with selecting its reason field.. | User is already on estimate approve section | 1) Select Rejected without service fee option from the dropdown. 2) Select suiable reason. 3)Click on submit button. |  |  |  | Case status should get change to Rejected with serive fee and case should get move to invoice section |  |  | PASS
TC_Approve_Estimation_31 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Total Loss. | User is already on estimate approve section | 1) Select Total Loss option from the dropdown. 2) Click on submit button. |  |  |  | Case status should get change to Total Loss. |  |  | PASS
TC_Approve_Estimation_32 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Reimbursement. | User is already on estimate approve section | 1) Select Reimbursement option from the dropdown. 2) Click on submit button. |  |  |  | Case status should get change to Reimbursement .
TC_Approve_Estimation_33 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Partial Settlement. | User is already on estimate approve section | 1) Select Partial Settlement option from the dropdown. 2) Click on submit button. |  |  |  | Case status should get change to Partial Settlement.
TC_Approve_Estimation_34 | 13859 | 2021-02-06 | To verify if the case manager is able to mark the case status as Invoice Rejected Approved. | User is already on estimate approve section | 1) Select Invoice Rejected Approved option from the dropdown. 2) Click on submit button. |  |  |  | Case status should get change to Invoice Rejected Approved.
| 13859 | 2021-02-06 | Auto Approve: For auto approval cases, API should get triggered only when CA gives the final approval. |  |  |  | Invoice Submit: Remarks field should be mandatory. | https://prnt.sc/ynnv52
| 13859 | 2021-02-06 |  |  |  |  | Invoice Approve: CA is not able to approve the invoice. | https://prnt.sc/yno3ep
| 13859 | 2021-02-06 |  |  |  |  | Wrong validation is coming when user submits the estimate approval form without selecting an Approve Type. It should be " Please select Approve Type instead of Request method is not valid. | https://prnt.sc/yt3l26
[7 empty] | Client side validation is not coming for leaving approve unit price field blank due to which getting above error from server side. sit 1 | https://lh3.googleusercontent.com/--UY0r-WZXq4/YCI0n_xqRpI/AAAAAAAAGlY/Mf-aVJ0xkHcqcoEUTrw_rChtWaxkGPZBACK8BGAsYHg/s0/2021-02-08.png
[7 empty] | Success message after approving the estimate is wrong. | https://prnt.sc/yt4tx3

## Invoice
Created By:- | Jitendra |  |  |  | Re-Tested By:- | Jitendra
Creation Date:- |  |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  |  |  | Module:-TC_Generate Invoice
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Date | Power ID | Status
TC_TC_Invoice_01 | 13859 | 2021-02-11 | To verify if the user is able to get navigate to the Case Request Details page of selected Case Request. | User is already on case requests page. | 1) Click on the View icon appearing against every Case Request. |  |  |  | user should be able to get navigate to the Case Request Details page of selected Case Request. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_02 | 13859 | 2021-02-11 | To verify if the user is able to navigate to Generate Invoice pop up by clicking on "Generate Invoice" quick link. | User is already on case requests page. | 1) Click on "Generate Invoice" link available under Quick Links section. |  |  |  | Generate Invoice Update pop up should get appear. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_03 | 13859 | 2021-02-11 | To verify if the user is able to submit the Generate Invoice form by leaving all the mandatory fields blank. | User is at Generate Invoice pop up. | 1) Leave all the mandatory fields blank. 2) Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_04 | 13859 | 2021-02-11 | To verify if the user is able to submit the Generate Invoice form by leaving the Invoice Number field blank. | User is at Generate Invoice pop up. | 1) Leave Invoice Number field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_05 | 13859 | 2021-02-11 | To verify if the user is able to submit the Generate Invoice form by leaving the Invoice Date field blank. | User is at Generate Invoice pop up. | 1) Invoice Date field blank. 2) Enter valid details in the remianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_06 | 13859 | 2021-02-11 | To verify if the user is able to generate invoice by entering invalid data in Invoice Number field. | User is at Generate Invoice pop up. | 1)Enter Invalid data in Invoice Number field blank. 2) Enter valid details in theremianing fields. 3)Click on submit button. | Blank spcases as characters, Special Characters. | Invoice getting generated by entering invalid data in Invice Number field. | https://prnt.sc/z2x8t8 | Invoice should not get generated and also there should be a proper validation message for the same. |  |  | Fail | 2020-08-07 | 11428 | Fail
TC_TC_Invoice_07 | 13859 | 2021-02-11 | To verify if the user is able to generate invoice by entering invalid data in Invoice Date field. | User is at Generate Invoice pop up. | 1)Enter Invalid data in Invoice Date field blank. 2) Enter valid details in theremianing fields. 3)Click on submit button. |  |  |  | Invoice should not get generated and also there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428 | Fail
TC_TC_Invoice_08 | 13859 | 2021-02-11 | To verify if the user is able to submit the Generate Invoice form by entering valid data in all the mandatory fields. | User is at Generate Invoice pop up. | 1) Enter valid details in all fields. 2)Click on submit button. |  |  |  | Invoice should get generated and get sent to Case Manager for approval. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_09 | 13859 | 2021-02-11 | To verify if the Cancel button at Generate Invoice pop up is functional or not | User is at Generate Invoice pop up. | 1)Click on Cancel button. |  |  |  | Generate Invoice should get close. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_10 | 13859 | 2021-02-11 | To verify if the user is able to navigate to Submit Invoice pop up by clicking on "Submit Invoice" quick link. | User is already on case requests page. | 1) Click on "Submit Invoice" link available under Quick Links section. |  |  |  | User should get navigate to Submit Invoice section. |  |  | Pass | 2020-08-07 | 11428 | Pass
TC_TC_Invoice_11 | 13859 | 2021-02-11 | To verify if the user is able to submit the invoice by leaving all the fields blank. | User is already on case requests page. | 1) Click on submit button. |  | Wrong validation message appears on directly submitting the Invoice without uploading invoice as "Something Went Wrong" |  | Invoice should not get submited and there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428
TC_TC_Invoice_12 | 13859 | 2021-02-11 | To verify if the user is able to submit the invoice by leaving invoice pdf blank.. | User is already on case requests page. | 1) Do not upload any file and enter remarks. 2) Click on Submit Button. |  |  |  | Invoice should not get submited and there should be a proper validation message for the same. |  |  | Pass | 2020-08-07 | 11428
TC_TC_Invoice_13 | 13859 | 2021-02-11 | To verify if the user is able to submit the invoice by leaving remarks blank.. | User is already on case requests page. | 1) Leave remarks blank and upload valid photo. 2) Click on Submit Button. |  | Remarks is a mandatory field but still there is no validation coming for the same. | https://prnt.sc/z2ziltt | Invoice should not get submited and there should be a proper validation message for the same. |  |  | Fail
TC_TC_Invoice_14 | 13859 | 2021-02-11 | To verify if the user is able to submit the Invoice by uploading invalid file as Invoice. | User is already on case requests page. | 1) Uploading invalid file (Over size/Incorrect file type) 2) Click on Submit Button. |  |  |  | Invoice should not get submited and there should be a proper validation message for the same. |  |  | Pass
TC_TC_Invoice_15 | 13859 | 2021-02-11 | To verify if the user is able to submit the Invoice by uploading valid file as Invoice. | User is already on case requests page. | 1) Uploading valid file. 2) Click on Submit Button. |  |  |  | Invoice should get submitted for approval. |  |  | Pass
TC_TC_Invoice_16 | 13859 | 2021-02-11 | To verify if the Cancel button at Submit Invoice is functional or not | User is already on case requests page. | 1)Click on Cancel button. |  |  |  | Invoice submission process should get abort. |  |  | NA
TC_TC_Invoice_17 | 13859 | 2021-02-11 | To verify if the Case Manager is able to get navigate to the Approve Invoice secion or not. | Case Manager is already on case requests page. | Click on Approve Invoice link under quick links. |  |  |  | Case Manager should get navigate to the Approve Invoice section. |  |  | Pass
TC_TC_Invoice_18 | 13859 | 2021-02-11 | To verify if the Case Manager is able to view the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the View Invoice button. |  |  |  | Case Manager should be able to view the Invoice. |  |  | Pass
TC_TC_Invoice_19 | 13859 | 2021-02-11 | To verify if the Case Manager is able to downloaded the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Download Invoice button. |  | System does not download the submitted invoice on clicking on Download Invoice button instead it shows a success msg as "Invoice Download link successfully has been found." |  | Case Manager should be able to download the Invoice. |  |  | Pass
TC_TC_Invoice_20 | 13859 | 2021-02-11 | To verify if the Case Manager is able to Approve the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Approve button. |  |  |  | Case Manager should be able to Approve the Invoice.
|  |  | To verify if the Case Manager is able to Reject the Uploaded Invoice . | Case Manager is already on case requests page. | 1)Click on the Reject button. |  | 1)Case Sub Status have been changed to On Rejected 2) There is no option to approve/On Hold the invoice after changing the status of the invoice to "On Hold". |  | Case Manager should be able to Reject the Invoice.
|  |  | To verify if the Case Manager is able to change the status of the invoice to On Hold. | Case Manager is already on case requests page. | 1)Click on the On Hold button. |  | 1)Case Sub Status have been changed to On Hold 2) There is no option to approve/reject the invoice after changing the status of the invoice to "On Hold". |  | Case Manager should be able to change the status to On Hold. |  |  | PASS
|  |  | To verify if the Case Manager is able to change the status of the invoice to Estimate Rejected. | Case Manager is already on case requests page. | 1)Click on the On Hold button. |  |  |  | Case Manager should be able to change the status to On Hold.
|  |  | To veriify if the claim manager is able to update the stsatus of the invoice by leaving the remarks field empty. | Case Manager is already on case requests page. | 1)Click on the On Hold button. |  | User is able to update the invoice status by leaving remarks field blank. | https://prnt.sc/z31hso | Invoice status should not get update and also there should be a proper validation message for the same. |  |  | Fail
|  |  | To veriify if the claim manager is able to update the stsatus of the invoice by entering invalid remarks. | Case Manager is already on case requests page. | 1)Enter remarks more than 2500 characters. 2)Click on the On Hold button. |  | User is able to update the invoice status by leaving remarks field blank. | https://prnt.sc/z31hso | Invoice status should not get update and also there should be a proper validation message for the same. |  |  | Fail

## Case Creation API
S. No | Bug Summary | Payload | Screenshot | Status
1 | As per the glow document, Brand and Product type can be left blank also but both the fields are mandatory for case creation at servinsur. |  | https://prnt.sc/yhrhr1 https://prnt.sc/yhrq80
2 | 1) Case got created when user entered invalid date format in purchase date. 2) Case created with this payload is not getting open on frontend. | { "policy_number": "2999201055509100000", "start_date": "01-01-2020", "end_date": "01-01-2022", "credit_available": "21300.2356897", "status": "active", "first_name": "Rakesh", "last_name": "", "email": "abc@gmail.com", "phone": "9716234003", "pincode": "110096", "address": "US Complex ", "city": "Delhi", "state": "Delhi", "country": "", "product_type": "Air Conditioner", "brand": "SAMSUNG", "model": "", "serial_number": "", "name": "", "price": "34499.008798", "properties": "", "purchase_date": "2021-01-01", "aiz_claim_number": "0637893640003", "client_claim_number": "CPP-C299919000301", "service_account_number": "IND068", "client_code": "cpp", "dealer_name": "Acko General Insurance Limited", "case_type": "Cashless", "loss_date": "01-01-2021", "reserve_amount": "5000", "caller_type": "NULL", "description": "ok", "nature_of_loss": "NULL", "problem_category": "Cooling Issue", "problem_sub_category": "Compressor problem", "priority": "high", "claim_status": "New", "claim_sub_status": "New", "claim_creation_date": "01-02-2020", "notes": "", "asset_care_number": "123456789", "earliest_start_permitted": "01-02-2020 15:22:22", "due_date": "01-02-2020", "expected_datetime_closure": "01-02-2020", "repeat_repair": "Yes" } | https://quip.com/c2avArmcrtgn/c#CDHACAB6iUT https://prnt.sc/yhsdao
3 | 1) Case got created when user entered invalid date format in Loss date. 2) Case created with this payload is not getting open on frontend. |  | https://prnt.sc/yhvhsj https://quip.com/c2avArmcrtgn/c#CDHACAB6iUT
4 | User is able to create case by entering inalid date format in all the date fields. | { "policy_number": "2999201055509100000", "start_date": "2020-01-01", "end_date": "2022-01-01", "credit_available": "21300.2356897", "status": "active", "first_name": "Rakesh", "last_name": "", "email": "abc@gmail.com", "phone": "9716234003", "pincode": "110096", "address": "US Complex ", "city": "Delhi", "state": "Delhi", "country": "", "product_type": "Air Conditioner", "brand": "SAMSUNG", "model": "", "serial_number": "", "name": "", "price": "34499.008798", "properties": "", "purchase_date": "2021-01-01", "aiz_claim_number": "0637893640007", "client_claim_number": "CPP-C299919000301", "service_account_number": "IND068", "client_code": "CPP", "dealer_name": "Acko General Insurance Limited", "case_type": "Reimbursement", "loss_date": "2021-01-01", "reserve_amount": "5000", "caller_type": "NULL", "description": "ok", "nature_of_loss": "NULL", "problem_category": "Cooling Issue", "problem_sub_category": "Compressor problem", "priority": "high", "claim_status": "New", "claim_sub_status": "New", "claim_creation_date": "2020-01-02", "notes": "", "asset_care_number": "123456789", "earliest_start_permitted": "2020-01-02 15:22:22", "due_date": "2020-01-02", "expected_datetime_closure": "2020-01-02", "repeat_repair": "Yes" } | https://prnt.sc/yhwepy https://quip.com/c2avArmcrtgn/c#CDHACAB6iUT
5 | Case Got created with blank reserve amount. | { "policy_number": "2999201055509100000", "start_date": "01-01-2020", "end_date": "01-01-2022", "credit_available": "21300.2356897", "status": "active", "first_name": "Rakesh", "last_name": "", "email": "abc@gmail.com", "phone": "9716234003", "pincode": "110096", "address": "US Complex ", "city": "Delhi", "state": "Delhi", "country": "", "product_type": "Air Conditioner", "brand": "SAMSUNG", "model": "", "serial_number": "", "name": "", "price": "34499.008798", "properties": "", "purchase_date": "01-01-2021", "aiz_claim_number": "063789364", "client_claim_number": "CPP-063789364", "service_account_number": "IND068", "client_code": "CPP", "dealer_name": "Acko General Insurance Limited", "case_type": "Reimbursement", "loss_date": "01-01-2021", "reserve_amount": "", "caller_type": "NULL", "description": "ok", "nature_of_loss": "NULL", "problem_category": "Cooling Issue", "problem_sub_category": "Compressor problem", "priority": "high", "claim_status": "New", "claim_sub_status": "New", "claim_creation_date": "01-02-2020", "notes": "", "asset_care_number": "123456789", "earliest_start_permitted": "01-02-2020 15:22:22", "due_date": "01-02-2020", "expected_datetime_closure": "01-02-2020", "repeat_repair": "Yes" } | https://prnt.sc/yhwr1b
6 |  | { "policy_number": "2999201055509100000", "start_date": "01-01-2020", "end_date": "01-01-2022", "credit_available": "21300.2356897", "status": "active", "first_name": "Rakesh", "last_name": "", "email": "abc@gmail.com", "phone": "9716234003", "pincode": "110096", "address": "US Complex ", "city": "Delhi", "state": "Delhi", "country": "", "product_type": "Air Conditioner", "brand": "SAMSUNG", "model": "", "serial_number": "", "name": "", "price": "34499.008798", "properties": "", "purchase_date": "01-01-2021", "aiz_claim_number": "063789366", "client_claim_number": "CPP-063789366", "service_account_number": "IND068", "client_code": "CPP", "case_type": "Reimbursement", "loss_date": "01-01-2021", "reserve_amount": "", "caller_type": "", "description": "", "nature_of_loss": "Others", "problem_category": "Cooling Issue", "problem_sub_category": "Compressor problem", "priority": "", "claim_status": "", "claim_sub_status": "", "claim_creation_date": "01-02-2020 15:22:22", "notes": "", "asset_care_number": "123456789", "earliest_start_permitted": "01-02-2020 15:22:22", "due_date": "01-02-2020", "expected_datetime_closure": "01-02-2020", "repeat_repair": "Yes" }
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41