## Summary
Mercedes Benz
Lead Dev: Ranjeet/Vikash Jha
Module | No. of test Written | No. of test executed | Pass | Fail
Restrict URL access - correction | 13 | 13 | 13 | 0
Approved_Claim_Amt-Dev | 14 | 14 | 8 | 6
Re-purchase Functionality | 43 | 32 | 8 | 3
Total | 70 | 59 | 29 | 9

## Bug Report
Bug Report
Project :- |  | Mercedes Benz
Created_By :- |  | Jitendra
Date | Test Case ID | Bug ID | Task ID | Bug Summary | Pre - Conditions | Steps to Reproduce | Test Data | Attachments/link | Priority | Severaity | Status | Assigned To | Developers Comments | Testers Comments | Status on 21-02-2020 | Task ID- Retesting | Open | Close
2020-02-07 | NA | 1 | 11386 | Certificate Request: On uploading a PFD file of more than 5 mb in Final quick test loader keeps on loading and file does not get upload. |  |  |  |  | High | High | New | Apurwa
2020-02-07 | NA | 2 | 11386 | Agreement: User is able to validate the vin against a Vin number : WDC1569086L0009 which is having a certificate request status as Submitted. |  |  |  |  | High | High | New | Apurwa
2020-02-07 | NA | 3 | 11386 | Agreement: On selecting the * Certified Assurance Plan, its dependent fields like Certified Assurance Start Date Certified Assurance End Date Certified Assurance Start Kms Certified Assurance End Kms and Pricing Information should get auto populate. |  |  |  | https://prnt.sc/tadl32 | High | High | New | Apurwa
2020-03-07 | NA | 4 | 11417 | Claim: Dealer is able to create claim by selecting Service Request Date and Work Order Date less than the standard warranty start date and also less than the Certified Assurance Start Date. |  |  |  | https://prnt.sc/tb5q7q | High | High | New | Ranjeet
2020-03-07 | NA | 5 | 11417 | Claim:Dealer is able to create a claim by entering Service Requestnumber and Work Order # of an existing claim. |  |  |  | https://prnt.sc/tb6dsh Existing claim:https://prnt.sc/tb6epr | High | High | New | Ranjeet
2020-03-07 | NA | 6 | 11417 | Claim: Dealer is able to create a claim by entering a Repair Cost as "0" it should be greater than 0 |  |  |  | https://prnt.sc/tb6him | Low | Low | New | Ranjeet
2020-03-07 | NA | 7 | 11417 | Part Information :Dealer is able to add Part Information by entering "0" in MRP and Quantity field. |  |  |  |  | High | High | New | Ranjeet
2020-03-07 | NA | 8 | 11417 | Labour Information :Dealer is able to add Part Information by entering "0" in Operation Time in Minutes and Rate per Hour field. |  |  |  |  | High | High | New | Ranjeet
2020-03-07 | NA | 9 | 11417 | Miscellaneous Information :Dealer is able to add Part Information by entering "0" in Amount field. |  |  |  |  | High | High | New | Ranjeet
2020-04-07 | NA | 10 | 11417 | Certificate Requeest: Dealer is able to create an agreement against a vin number having status as "Reject". (I have changed the status as approve and then changed it to Reject) |  |  | WDC1569086L001235 |  | High | High | New | Apurwa
2020-04-07 |  | 11 | 11417 | "User is able to validate the vin for a vin number having Certification request status: Submitted and Agreement Status: Expired." |  |  | WDD2050026L011379 |  | High | High | New | Apurwa
2020-04-07 |  | 12 | 11417 | Create Agreement: Price List of classes other than A,B,C,E,,SCLA,GLA,GLC,GLE,GLS,ML and GL is not available due to which dealer is not able to create an agreement. |  |  |  |  | High | High | New | Apurwa
2020-04-07 | NA | 13 | 11417 | Not able to test for agreement status Cancelled as there is no data available to test that. |  |  |  |  | High | High | New | Apurwa
2020-04-07 |  | 14 | 11417
2020-04-07 |  | 15 | 11417
2020-04-07 | NA | 16 | 11417
2020-04-07 |  | 17 | 11417
2020-04-07 |  | 18 | 11417
2020-04-07 | NA | 19 | 11417
2020-04-07 |  | 20 | 11417
2020-04-07 |  | 21 | 11417
2020-04-07 | NA | 22 | 11417
2020-04-07 |  | 23 | 11417
2020-04-07 |  | 24 | 11417
2020-04-07 | NA | 25 | 11417
2020-04-07 |  | 26 | 11417
2020-04-07 |  | 27 | 11417

## Restrict URL access - correctio
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Restrict URL access - correction
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_URLCorrection_01 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name:CA Expired Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=38 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_02 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: CA Active Report | Dealer is already logged on. | 1) Pate the URL of restricted reports one by one in your browsers address bar. 2)Hit enter. | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=39 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_03 | 11384 | 2020-01-07 | To verify if dealer is able to view CA Sales Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=26 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_04 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=29 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_05 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Part Information Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=34 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_06 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Labour Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=30 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_07 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=35 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_08 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: User Detail Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=36 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_09 | 11384 | 2020-01-07 | To verify if dealer is able to view Claim Miscellaneous Report | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=40 |  |  | dealer should be able to view report. | High | High | Pass
TC_URLCorrection_10 | 11384 | 2020-01-07 | To verify if the dealer is able to view restricted reports (Reports which are not visible to dealer) by entering URL of restricted reports. Report Name: Undelivered Vehicles Details | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Reports&view=Detail&record=37 |  |  | Report page should not get open instead "Access Denied" message should get appear on the opened page. | High | High | Pass
TC_URLCorrection_11 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the Certificate Request made by other dealer B by entering URL of the Certificate Request made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Detail&record=249643 http://13.127.10.134/mercedes_dev/index.php?module=Faq&view=Edit&record=249643 |  |  | Certificate Request should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_12 | 11384 | 2020-01-07 | To verify if the dealer A is able to view/edit the claim made by other dealer B by entering URL of the claim made by dealer B. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Detail&record=249659 http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249659 |  |  | Claim should not get visible to dealer A. | High | High | Pass
TC_URLCorrection_13 | 11384 | 2020-01-07 | To verify if the dealer is able to edit the claim by entering the "Edit URL" of the claim having status as Payment Made. | Dealer is already logged on. |  | http://13.127.10.134/mercedes_dev/index.php?module=PurchaseOrder&view=Edit&record=249454 |  |  | Dealer who punched the claim an view it but NO edit button should be available to him and other dealer should not be able to view the claim. | High | High | Pass

## Re-purchase Functionality
Project Name:->Renault
Created By:- | Jitendra |  |  |  | Re-Tested By:- |  |  | Pre-condition :-
Creation Date:- | 2020-01-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Vikash Jha/ Ranjeet
Version: - |  |  |  |  | Module:- | Re-purchase Functionality
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status
TC_Re-purchase_Functionality_01 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Submitted. |  |  | Pass
TC_Re-purchase_Functionality_02 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Answer By Dealer. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Answer By Dealer.. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Query By Assurant. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request Query By Assurant. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Reject. | Dealer is already logged-in |  | WDC1569086L098655 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should not be able to create a new certificate request with a vin number having a certificate request status Reject. |  |  | Pass
TC_Re-purchase_Functionality_03 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approve. | Dealer is already logged-in |  | WDC1569086L001235 | Syatem shows validation message as "Entered VIN No. is not Available..' |  | User should be able to create a new certificate request. |  |  | Pass
TC_Re-purchase_Functionality_04 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Rejected. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Rejected.
TC_Re-purchase_Functionality_05 | 11386 | 2020-01-07 | To verify if the user is able to create certificate request when the certification request for a vin nmber having status is Approved. Note: Agreement for the same Vin number should have status either Approved or expired. | Dealer is already logged-in |  |  |  |  | User should be able to create a new certificate request with a vin number for which there is already a certificate request with Approved.
TC_Re-purchase_Functionality_06 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_07 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_08 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_09 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_10 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Expired. | Dealer is already logged-in |  | WDD2050026L011379 | User is able to validate the vin for a vin number having Certification request status: Submitted and Agreement Status: Expired. |  | Dealer should not be able to create an agreement. |  |  | Fail
TC_Re-purchase_Functionality_11 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Submitted and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_12 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_13 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_14 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_15 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_16 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_17 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Answer By Dealer and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_18 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_19 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_20 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_21 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_22 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_23 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Query By Assurant and Agreement Status: Submitted. | Dealer is already logged-in |  | WDD2120036L056714 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_24 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_25 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_26 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_27 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_28 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Expired. | Dealer is already logged-in |  | WDC1569086L002075 MBCA926 |  |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_29 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Approve and Agreement Status: Submitted. | Dealer is already logged-in |  | WDC1569086L001235 | Alert close Agreement already created. |  | Dealer should not be able to create an agreement. |  |  | Pass
TC_Re-purchase_Functionality_30 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_31 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_32 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_33 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_34 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement.
TC_Re-purchase_Functionality_35 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: Reject and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement.
TC_Re-purchase_Functionality_36 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for amendment. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_37 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Pending for cancellation. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_38 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Active. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_39 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Cancelled. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_40 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Expired. | Dealer is already logged-in |  |  |  |  | Dealer should be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select
TC_Re-purchase_Functionality_41 | 11386 | 2020-01-07 | To Verify if the dealer is able to renew an agreement with an existing vin number having Certification request status: No Data and Agreement Status: Submitted. | Dealer is already logged-in |  |  |  |  | Dealer should not be able to create an agreement. |  |  | Not able to validate as the required statusn "No Data" is not available to be select

## Approved_Claim_Amt-Dev
Project Name:-> MB
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- | 2020-03-07 |  |  |  | Re-Testing Date:- |  |  | Developed By :- | Ranjeet
Version: - |  |  | Version: - |  | Module:- | Rejected amount is showing in approved amount
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Date | Status | Power ID | Date | Status
TC_ApprovedClaimAMT_01 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Part Information. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 | 134852.23 |  | The rejected part amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_02 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Labour Information. | User is already logged in | 1)mark the checkbox against the Labour to be reject, 2)Click on Update Labour Rejection | MBCAC198 |  |  | The rejected Labour amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_03 | 11417 | 2020-03-07 | To verify if the Rejected amount is getting correctly populat under Rejected Amount header for Miscellaneous Information. | User is already logged in | 1)mark the checkbox against the Miscellaneous to be reject, 2)Click on Update Miscellaneous Rejection | MBCAC198 |  |  | The rejected Miscellaneous amount should get appear under the Rejection Amount header in Summary. |  |  | Pass
TC_ApprovedClaimAMT_04 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Part Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_05 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for Labour information by selecting check box against Rejection check in Labour information. | User is already logged in | 1)mark the checkbox against the Rejection check for Labour Information. | MBCAC198 |  |  | All Labour should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_06 | 11417 | 2020-03-07 | To verify if the claim manager is able to select All parts to reject for part information by selecting check box against Rejection check in Part information. | User is already logged in | 1)mark the checkbox against the Rejection check for Miscellaneous Information. | MBCAC198 |  |  | All parts should get rejected and should appar in the Rejection Amount in sammary. |  |  | Pass
TC_ApprovedClaimAMT_07 | 11417 | 2020-03-07 | To verify if the Net Approval amount is showing the amount equal to Total Amt-Rejected Amount | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection | MBCAC198 |  |  | Net approval amount should be equal to total amt-rejected amount. |  |  | Pass
TC_ApprovedClaimAMT_08 | 11417 | 2020-03-07 | To verify if the Grand Total Calculation is correct or not. | User is already logged in | 1)mark the checkbox against the part to be reject, 2)Click on Update Part Rejection 3)Check the summary of all the parts and calculate manually | MBCAC198 |  |  | Grand total of all the fields should be correct. |  |  | Pass
30-06-2020