## Summary
Ashok Leyland
Lead Dev: Vikash/Apurwa
Module | No. of test Written | No. of test executed | Pass | Fail | NA
AL PDF Modification | 7 | 7 | 5 | 0 | 0
Total | 7 | 7 | 5 | 0 | 0

## Bug Report
Bug Report
Project :- |  | Ashok Leland |  |  |  |  | Lead_Devp. :- |  | Vikash / Apurwa
Created_By :- |  | Jitendra |  |  |  |  | Power_Task_I.D. :-
Power ID | Test Case ID/Module | Bug ID | Bug Summary | Pre - Conditions | Test Case Steps | Test Data | Attachments/Links | Priority | Severaity | Status
11316 | TC_Al_PDF_Modification_01 | 1 | PDF file for created Agreement is not getting generated as on clicking on "Generate Agreement Certificate " new page gets open where "Not Found-The requested URL was not found on this server." appears. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO89859 | https://prnt.sc/t53kf1 | High | High | Fixed
11316 | TC_Al_PDF_Modification_02 | 2 |  | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO171 |  | High | High | Fixed
11316 | TC_Al_PDF_Modification_03 | 3 | PDF file for created Agreement is not getting generated as on clicking on "Generate Agreement Certificate " new page gets open where "Not Found-The requested URL was not found on this server." appears. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO95229, SO95220 | https://prnt.sc/t53sqq | High | High | Fixed
11316 | TC_Al_PDF_Modification_05 | 4 | Certificate details in the downloaded PDF file is not properly aligned. It should be properly aligned. Please refer to the screenshot for more details. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | SO95237 | https://prnt.sc/t64wnl | High | Low | Fixed
11316 | TC_Al_PDF_Modification_07 | 5 | Option for selecting MITRA as model while creating an agreement should get removed/hide as agreement for MITRA created only from backend. | user is already logged in | 1) Create a new agreement or open existing/created agreement by selecting model as MITRA |  |  | High | High | Fixed

## TC_Al pdf modification
Project Name:-> Ashok Leland
Created By:- | Jitendra |  | Created By:-Jitendra |  | Re-Tested By:-
Creation Date:- | 23-06-2020 |  |  |  | Re-Testing Date:- |  |  | Developed By :-
Version: - |  |  | Version: - |  | Module:- | TC_Al pdf modification
Test Case ID/Module | Power_ID :- | Date :- | Test Case Summary | Pre - Conditions | Test Case Steps | Test Data | Actual Result | Attachments/Links | Expected Result | Priority | Severaity | Status | Power ID | Date | Status | Power ID | Date | Status
TC_Al_PDF_Modification_01 | 11316 | 23-06-2020 | To verify if the user is able to generate the agreement certificate for modal Dost+. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO89859 Agreement_SO95237 | PDF file for created Agreement is not getting generated as on clicking on "Generate Agreement Certificate " new page gets open where "Not Found-The requested URL was not found on this server." appears. | https://prnt.sc/t53kf1 | PDF file should get generate. | High | High | Fail | 11324 | 24-06-2020 | Pass-Agreement_SO95234 Agreement_SO99233 | NA | 26-06-2020 | Pass
TC_Al_PDF_Modification_02 | 11316 | 23-06-2020 | To verify if the user is able to generate the agreement certificate for modal Dost. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO171 | Link to Generate Agreement Certificate is not functional that is nothing happens when user clicks on the "Generate Agreement Certificate " link |  | PDF file should get generate. | High | High | Fail | 11324 | 24-06-2020 | Pass-SO151,SO172 | NA | 26-06-2020
TC_Al_PDF_Modification_03 | 11316 | 23-06-2020 | To verify if the user is able to generate the agreement certificate for modal DOST(IFS RFS Smart Strong Xpress). | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | dealer : Rainbow Motors Commercial Division Agreement No.:SO95229, SO95220 | PDF file for created Agreement is not getting generated as on clicking on "Generate Agreement Certificate " new page gets open where "Not Found-The requested URL was not found on this server." appears. | https://prnt.sc/t53sqq | PDF file should get generate. | High | High | Fail | 11324 | 24-06-2020 | Pass-SO95233 Agreement_SO101826 | NA | 26-06-2020 | Pass
TC_Al_PDF_Modification_04 | 11316 | 23-06-2020 | To verify if the user is able to generate the agreement certificate for modal DOST+ 3rd year E-warranty | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | Agreement_SO95238 | PDF file for created Agreement is not getting generated as on clicking on "Generate Agreement Certificate " new page gets open where "Not Found-The requested URL was not found on this server." appears. |  | PDF file should get generate. | High | High | NA | 11324 | 24-06-2020 | Pass-Agreement_SO94604 Agreement_SO95236 | NA | 26-06-2020
TC_Al_PDF_Modification_05 | 11316 | 23-06-2020 | To verify if the downloaded agreement is as per the template provided or not. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. | Agreement_SO95237 | Certificate details in the downloaded PDF file is not properly aligned. It should be properly aligned. Please refer to the screenshot for more details. | https://prnt.sc/t64wnl | Downloaded PDF of the created agreement should be as per the template provided and also the details of the PDF should be correct (same as that of the agreement) | High | Low | Fail | 11324 | 24-06-2020 | Fail | NA | 26-06-2020 | Pass
TC_Al_PDF_Modification_06 | 11316 | 23-06-2020 | To verify if the details of downloaded agreement are same as that of the agreement for which the pdf has generated. | user is already logged in | 1) Create a new agreement or open existing/created agreement. 2)Click on the "Generate Agreement Certificate" link. 3) Save the generated PDF file. |  |  |  | Downloaded PDF of the created agreement should be correct (same as that of the agreement) |  |  | NA | 11324 | 24-06-2020 | Pass | NA | 26-06-2020 | Pass
TC_Al_PDF_Modification_07 | 11324 | 25-06-2020 | To verify if the user is able to create an agreement for Mitra model. | user is already logged in | 1) Create a new agreement or open existing/created agreement by selecting model as MITRA |  | Option for selecting MITRA as model while creating an agreement should get removed/hide as agreement for MITRA created only from backend. |  | User should be able to create agreement for Mitra model. | High | Hugh | Fail | 11324 | 24-06-2020 | Fail | NA | 26-06-2020 | Pass

## Bug Report old
Bug Tracker
|  | Project | TVSAL
|  | Created By | Jitendra
|  | Module | Reports
Date | Bug ID | Bug Description | Steps to Reproduce | Severity | Priority | Status | URL/Attachments | Assigned to | Developers Comments | Developers Status | Developers URL | Testers Comments | Open | Close
2020-01-27 | 1 | EW Sales Master Dump Report: Policy Status coming in downloaded excel report is incorrect. That is Policy status column is showing EW issue/creation date instead of showing the status. | 1)Download the EW sales master dump report by clicking on Reports button. 2)Click on EW sales master dump report link. 3)Enter the valid dates in Start Date and End Date. 4)Click on Generate Now button. 5)Open the downloaded excel file. 7)Check the Policy Status column in excel file. | Mid | Mid | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtbue7 | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 2 | EW Sales Master Dump Report: Customer Name is coming without any space in first name and last name. (If both First and Last name have been added) | 1) Open any agreement having First Name and Last Name added in the agreement. 2)Open the downloaded excel file and check the customer name colum of the same agreement which you have opened in portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtbyni and https://prnt.sc/qtbz4q | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 3 | EW Sales Master Dump Report: There is mismatch in the Extended warranty field that is in the downloaded excel file Selected EW plan is appearing for a particular agreement but the same plan field is appearing blank in the portal. (E.G:Agreement Number : SO94318,SO94400,SO94394 ) | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtcb67 and https://prnt.sc/qtcbhs | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 4 | EW Sales Master Dump Report:Mobile number in the downloaded record is different from the mobile number appearing on the portal for the same agreement number. E.G: Take SO94385 agreement number. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtdiu6 and https://prnt.sc/qtdk3d | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 5 | EW Sales Master Dump Report: There is a speclling mistake in Agreement List as "W out" It should be Without. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Low | Low | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtelck | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 6 | Claim Dump For Assurant: In the downloaded excel fil of claim dump for assurant document number is missing. | 1)Download the excel file of Claim Dump For Assurant available under reports and check it with the entries on the portal. | High | High | Fixed- Report is deleted/hidden for dealer | https://prnt.sc/qtes12 and https://prnt.sc/qtesk3 | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 7 | Extended Warranty Report: Fuel Type for Product Number PRO1371 and PRO1370 is incorrct in the extended warranty excel file as DIESEL but it should be CNG. | 1)Download the excel file of Extended Warranty Report available under reports and check it with the entries on the portal. | High | High | Fixed | https://prnt.sc/qtffs5 and https://prnt.sc/qtfg98 https://prnt.sc/qtfgm3
2020-01-27 | 8 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is EWS RetaIl No is " Assests No." in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 9 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Dealer Margin is " Distribution_Commissions" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 10 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is AL Royalty is " Manufacturer Royalty" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 11 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Program Fees is " Program Price" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 12 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Roadside Assistance Fees is " Total Sales Excu Incentive" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 13 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Add: Service Tax (GST) is " Service Tax" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 14 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Basic Price (Excluding GST) is "Final Price W`out Tax" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 15 | EWS Retail Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Final Price (Including GST) is "Final Price" in excel. | 1)Download the excel file of EWS Retail Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-27 | 16 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Created Time is "EW Issue Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 17 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty is "EW Plan Selected" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 18 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty Start Period is "EW Start Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 19 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty End Period is "EW End Date" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 20 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty Start Kms is "EW Start Km" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 21 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Extended Warranty End Kms is "EW End Km" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 22 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Status is "Policy Status" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 23 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Address is "Address 1" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 24 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Postal Code is "Pin Code" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 25 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Mobile Phone is "Customer Contact No. 1" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 26 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Office Phone / Home Phone is "Customer Contact No. 2" in excel. | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 27 | EW Sales Master Dump Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Primary Email is "Customer Email ID" in excel. 2)Executive Name is Sales Person Name 3)Final Price W out Tax is Sub Total 4)Customer Price is Customer Charge 5)CGST Amount is CGST Amount % 6)Dealer Margin is Dealer Commision 7)Final Price Without Tax is Dealer to pay TVS (incl Tax) 8)AL Royalty is Royalty | 1)Download the excel file of EW Sales Master Dump Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed- Report is deleted/hidden for dealer |  | Ranjeet | changes not required. now this report is showing only to admin & this will be delete.
2020-01-27 | 28 | EW cancellation report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Assigned To is "Dealer name" in excel. 2)Agreement Number is Policy No. 3)Vehicle Chassis No is Chassis# 4)Created Time is EW Policy issue date 5) | 1)Download the excel file of EW cancellation report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Done
2020-01-28 | 29 | Part Information Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is Vehicle Model is "Remark" in excel. 2)Part Description is Description 3)Unit Price No is Price 4)Created Time is EW Policy issue date 5)Status is Approved by TVS | 1)Download the excel file of Part Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Not clear.
2020-01-28 | 30 | Labour Information Report: Name of entities/column(S) are different in downloaded excel file from the Names available on portal for the same entity. That is "Status" is "Approved by TVS" in excel file. 2)GST Amount is "Tax." | 1)Download the excel file of Labour Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed |  | Ranjeet | Not clear.
2020-01-28 | 31 | Labour Information Report: Rejection status of Labour Information Claim is not coming in the downloaded excel file for the same. | 1)Download the excel file of Labour Information Report available under reports and check it with the entries on the portal. | Mid | Mid | Fixed | https://prnt.sc/qttrbd and https://prnt.sc/qttsr0 | Ranjeet | Not clear.
2020-01-28 | 32 | Claims : Labour code appearing in the Labour Information Claim section is wrong. It is showing as 26028 instead of RS200VA | 1)Download the excel file of EW cancellation report available under reports and check it with the entries on the portal. | High | High | Not Fixed | https://prnt.sc/qttt9s and https://prnt.sc/qtttuk | Ranjeet | Not required to change. It is showing RS200VA.