## User Organisation
Bug Tracker
|  | Project | Greenlam CSRP
|  | Created By | Jitendra
|  | Module | User Organisation
|  | Task ID | 9970
Date | Bug ID | Bug Description | Severity | Priority | Status | URL/Attachments | Steps To Reproduce | Test Data | Assigned to | Developers Status | Developers Comments | Developers URL | Testers Comments | Open | Close
2020-02-10 | 1 | Creating New User Mapping Master: User is able to create new user without selecting his/her role. That is user role should be mandatory in order to add new User. | High | High | New | https://prnt.sc/r02zds | 1) Click on Add Record button. 2) Enter valid data in Username field. 3)Click Save button without selecting any role. | Test
2020-02-10 | 2 | Creating New User Mapping Master: User Name field is taking spaces as "jitendra k". Username should not take spaces. | High | High | New | https://prnt.sc/r033gy | 1) Click on Add Record button. 2) Enter invalid data in Username field. 3)Click Save button without selecting any role. | Jitendra k
2020-02-10 | 3 | Creating New User Mapping Master: Usernamee field is taking special characters. | Low | Low | New | https://prnt.sc/r0353l | 1) Click on Add Record button. 2) Enter invalid data in Username field. 3)Click Save button without selecting any role. | 1@#$%#%
2020-02-10 | 4 | Creating New User Mapping Master: User is able to add a same username more than one time. Username should be unique and there should not be any duplicacy of username. | High | High | New | https://prnt.sc/r03pi6
2020-02-10 | 5 | User Mapping Master Information: User is able to add user mapping by leaving all the fields blank as its taking first value from the dropdowns of User Business Vertical and User Country. And also its selecting all by default if user submits the form with blank enteries. Note: There should be a proper validation message for each mandatory fields. | High | High | New | https://prnt.sc/r036q7 | 1. Click on Add button without entering any data in the mandatory fields.
2020-02-10 | 6 | User Mapping Master Information: User is able to add user mapping by leaving User Business Vertical blank and also there should be proper validation message for the same. By default its taking AFX as the Business Vertical. | High | High | New |  | 1. Leave the User Business Vertical field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 7 | User Mapping Master Information: User is able to add user mapping by leaving User Country blank and also there should be proper validation message for the same. By default its taking Andorra as the User Country. | High | High | New |  | 1. Leave the User Country field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 8 | User Mapping Master Information: User is able to add user mapping by leaving User Country blank and also there should be proper validation message for the same. By default its taking Andorra as the User Country. | High | High | New |  | 1. Leave the User Country field blank. 2) Enter valid data in the remaining fields. 3)Click on Add button.
2020-02-10 | 9 | User Mapping Master Information: On clicking on "View All button" new page gets open with details of user which are not present in the user list. | High | High | New | https://prnt.sc/r03r8n https://prnt.sc/r03rot
2020-02-10 | 10 | User Mapping Master Information: Is user is able to map the duplicate entry that is sae user is getting mapped under the same business verticle and same user territory. | High | High | New | https://prnt.sc/r03trx
2020-02-10 | 11 | Suggestion: User Mapping Master Information: View All button should get hide as its showing the same data which is already present on the User Mapping Master Information page. | High | High | New | https://prnt.sc/r03xwy
2020-02-10 | 12 | User Mapping Master Information: If there is only one listing in User territory then there is no point of having "ALL" in the list as both the things are same. For Example: Delhi-Delhi and All | High | High | New | https://prnt.sc/r0427y
2020-02-10 | 13 | User Mapping Master Information: User can map More than one sales executive under same Business verticle and same Territory. | High | High | New | https://prnt.sc/r04c7o https://prnt.sc/r04cdu
2020-02-10 | 14 | Update User Mapping Master: User is able to update with the duplicate data (Already added mapping under the same user) | High | High | New
2020-02-10 | 15 | Update User Mapping Master: When user tries to update the User Territory provided User Country,User Zone and User Region are same then the territory dropdown is showing the territories of different regions. | High | High | New | https://prnt.sc/r04f99
2020-02-10 | 16 | Update User Mapping Master: User is able to update the role by selecting the territory of different region. | High | High | New | https://prnt.sc/r04ler
2020-02-10 | 17 | Update User Mapping Master: User is able to update the role by selecting the Region of different User Zone. | High | High | New | https://prnt.sc/r04o72
2020-02-10 | 18 | Update User Mapping Master: User is able to update the user mapping with blank User Zone, User Region and User Territory details. | High | High | New
2020-02-10 | 19 | Update User Mapping Master: User is able to update the details by clicking on "X" button. | High | High | New
2020-02-10 | 20